## Settings (hidden)
Prior | Version: | 1
Post | Last changed: | 2009-04-13
| Revised by: | Andrew Alexander Jacobs
Firm
Individual
Yes
No
Goods
Works
Non-Consulting Services

## General revised
Sample Procurement Plan
I. General
1. | Project Information
| Project Name: | Rain fed Agriculture and Livestock Project (RALP)
| Country: | YEMEN
| Project ID: | P089259
| Credit Number : | IDA Cr.#4220/Yem
2. | Bank's approval date of Procurement Plan | Original: January 2008
Revision 1: July 15, 2009
Revision 2: January 18, 2010
Revision 3: November 20,2010
Revision 4: April 19, 2011
Revision 5: March 10,2012
Revision 6: July 9 , 2012
Revision 7: October 16 , 2012 Bank's approval date : November 19,2012
Revision 8: April 14 , 2013 Bank's approval date April 22 , 2013
Revision 9: June 3,2013 Bank's approval date June 21 , 2013
Revision 10 : October 21 ,2013 Bank's approval date October 31, 2013
Revision 11: April 22, 2014
3. | Date of General Procurement Notice: | 30,September, 2009 issue No. 759
latest update ; UNDB print Edition : issue No .781 , 31-8-2010
Posted online : 3 August 2010
II. Goods, Work and Non-Consulting Services Thresholds
1. Prior Review Threshold. Procurement Decisions subject to Prior Review by the Bank as stated in Appendix 1 to the Guidelines for Procurement: [Thresholds for applicable procurement methods (not limited to the list below) will be determined by the Procurement Specialist /Procurement Accredited Staff based on the assessment of the implementing agency’s capacity.]
1a. | Procurement Category | Prior Review Threshold (USD) | Comments
| Goods | ≥300000
| Works | ≥500000
1b. | Procurement Method | Procurement Method Threshold (USD) | Comments
| ICB and LIB (Goods) | ≥ 300000
| NCB (Goods) | < 300,000
| NS/IS( minimum of three quotations)(Goods) | < 25000 | <50,000 for contracts under Part C
| ICB (Works) | ≥ 500,000
| NCB (Works) | < 500,000
| (N S) (three quotations)(work) | < 25000 | <50,000 for contracts under Part C
2. | Prequalification. Bidders for Works shall be prequlified in accordance with the provisions of paragraphs 2.9 and 2.10 of the Guidelines.
3. | Proposed Procedures for CDD Components (as per paragraph 3.17 of the Guidelines): <30,000
4. | Reference to (if any) Project Operational/Procurement Manual: Not Prepared
5. | Any Other Special Procurement Arrangements: NA
6. | Procurement Packages with Methods and Time Schedule: See attached "Goods and Works" sheet
III. Selection of Consultants
1. | Prior Review Threshold: Selection decisions subject to Prior Review by Bank as stated in Appendix 1 to the Guidelines Selection and Employment of Consultants:
1a. | Procurement Category | Prior Review Threshold (USD) | Comments
| Consulting Firms (Competitive) | >200000
Consulting Firms(CQ) and Least Cost Selection (LCS)
| Consulting Firms (Single Source) | ALL CONTRACTS
| Individual Consultants (Competitive) | >50000
| Individual Consultants (Single Source) | ALL CONTRACTS
1b. | Procurement Method | Procurement Method Threshold (USD) | Comments
| QCBS | NA
| QBS | NA
| FBS | NA
| LCS | NA
| CQS | <100,000
| Single Source (Firms) | < 50,000 | To be used if it meets with the requirements of paragraph 3.10 of the Consultant Guidelines for Single Source Selection, with the provisions of paragraphs 3.9 through 3.13 of the Consultant Guidelines.
| Individual Consultants (Competitive) |  | To be used if it meets with the requirements set forth in paragraphs 5.1 through 5.3 of the Consultant Guidelines.
| Individual Consultants (Single Source) |  | To be used if it meets with the requirements set forth in paragraph 5.4 of the Consultant Guidelines.
to individual consultants on a sole-source basis.
2. | Short list comprising entirely of national consultants: Short list of consultants for services, estimated to cost less than $<=100000 equivalent per contract, may comprise entirely of national consultants in accordance with the provisions of paragraph 2.7 of the Consultant Guidelines.
Note: OPCPR list of ceilings can be found here http://go.worldbank.org/MKXO98RY40
3. | Any Other Special Selection Arrangements: NA
4. | Consultancy Assignments with Selection Methods and Time Schedule: See attached "Consulting Services" sheet
IV. Implementing Agency Capacity Building Activities with Time Schedule: See attached "Capacity Building" sheet

## Goods & Works
Procurement Plan for Goods/Works/Non-Consulting Services
YEMEN P089259 : Rainfed Agriculture and Livestock Project (RALP) IDA Cr.#4220/Yem
** Applicable in case of Bank's prior review | [9 empty] | Prequalification
| SL No. | Package/ Reference No. | Description of Goods/ Works | Goods/ Works/ NCS | Estimated Cost and Date of Estimate | Currency of Estimated Cost | Review by Bank (Prior/ Post) | Procurement Method | Domestic Preference (yes/no) | Prequalification (yes/no) | No Objection from Bank for Draft Prequalification documents (Date)** | No Objection from Bank for Evaluation of Prequalification Application (Date)** | Preparation of Bid Document (Date) | Bank’s No Objection to Bidding Document (Date)** | Bid Invitation (Date) | Bid Closing (Date) | Bid Opening (Date) | Contract Award Decision (Date) | Bank’s No Objection to Bid Evaulation Report and Contract Award (Date)** | Contract Signed (Date) | Contract Value | Contract Currency | Contract No. | Name, City, and Country of Contractor (incl. Zip Code if US) | Completion of Contract (Date) | Expenditure incurred to Date | Comments
Planned | 1 | RALP/ PSU /G/NS /1 /2007 | Supply Stationary for Project support Unit (PSU ) . | Goods |  | USD | Prior | NS | No | No |  |  | NA | NA | NA | NA | NA | NA | NA | NA | 621625 | YER | RALP/G/1/2007 | AL-Maktaba Office Supplies Sana,a -Republic of Yemen | 2007-11-11 | 621625 | Completed
Revised | [8 empty] | No | No |  |  | NA | NA | NA | NA | NA | NA | NA | NA |  |  |  |  | NA
Actual | [8 empty] | No | No |  |  | 2007-07-23 | NA | 2007-07-30 | NA | 2007-08-14 | 2007-10-01 | 2007-10-29 | 2007-11-04 |  |  |  |  | 2007-11-25
Planned | 2 | RALP/G/NCB/02/2007 | Procurement of (Computers and office appliances for (23) Regional agricultural offices in ( 5) Governorates . (SANA,A, LAHJ, AL-Mhweet ,Hodeida ,Hajja,a) | Goods |  | USD | Prior | NCB | No | No |  |  | 2007-11-03 | 2007-11-11 | 2007-11-12 | 2007-12-12 | 2007-12-12 | 2007-12-26 | 2008-01-02 | 2008-01-09 | 80270 | USD | RALP/G/1/2008 | ALGWDAH For Trading Co. Sana,a -Republic of Yemen | 2008-03-20 | 80270 | Completed
Revised | [8 empty] | No | No |  |  | NA | NA | NA | NA | NA | NA | NA | NA |  |  |  |  | NA
Actual | [8 empty] | No | No |  |  | 2007-11-01 | 2007-11-06 | 2007-11-11 | 2007-12-12 | 2007-12-12 | 2008-01-26 | 2008-02-17 | 2008-02-19 |  |  |  |  | 2008-03-24
Planned | 3 | RALP/G/NCB/03/2007 | Procurement of Transportation vehicle for Project support Unit (PSU ) . /Sana’a | Goods |  | USD | Prior | NCB | No | No |  |  | 2007-11-18 | 2007-12-01 | 2007-12-07 | 2008-01-06 | 2008-01-06 | 2008-01-20 | 2008-01-27 | 2008-02-03 | 28500 | USD | RALP/G/2/2008 | TEHAMA TRADING COMPANY Shmsan street .- HODEIDAH- Republic of Yemen | 2008-05-24 | 28500 | Completed
Revised | [8 empty] | No | No | [14 empty] | NA | bar: 2007-11-01 to 2008-02-19
Actual | [8 empty] | No | No |  |  | 2007-11-05 | 2007-12-01 | 2007-12-07 | 2008-01-15 | 2008-01-15 | 2008-01-30 | 2008-02-17 | 2008-02-24 |  |  |  |  | 2008-10-18
Planned | 4 | RALP/G-NS/O1/2008 | Office furniture Project support Unit (PSU ) . sana,a | Goods |  | USD | Prior | NS | No | No |  |  | 2008-02-28 | 2008-03-15 | 2008-03-16 | 2008-03-30 | 2008-03-30 | 2008-04-06 | 2008-04-13 | 2008-04-20 | 4835 | USD | RALP/G/3/2008 | Ard Hemier Trading for office ,house ,school Furnture sale Sana,a -Republic of Yemen | 2008-04-12 | 4835 | Completed
Revised | [8 empty] | No | No | [14 empty] | NA | bar: 2007-11-05 to 2008-02-24
Actual | [8 empty] | No | No |  |  | 2008-03-01 | NA | 2008-03-01 | 2008-03-18 | 2010-03-18 | 2008-03-24 | 2008-04-01 | 2008-04-05 |  |  |  |  | 2008-04-10
Planned | 5 | RALP/ W/NCB/01/2008 | REHABILITATION OF REGIONAL AGRICULTURAL OFFICES in (10) districts ( 3) Governorates ( Sana’a -Lahej-Almhweet) | Works |  | USD | Prior | NCB | No | No |  |  | 2008-02-28 | 2008-03-13 | 2008-03-16 | 2008-04-15 | 2008-04-15 | 2008-04-29 | 2008-05-13 | 2008-05-20 | 242995 | USD | RALP/W/4/2008Adden.contract 1--2009 Amend. contract 2--2008 | Mohammed Hassan Hajib, For Trading & Contracting Sana,a -Republic of Yemen | 2009-02-10 | 231791 | Completed
Revised | [8 empty] | No | No | [14 empty] | 2009-08-14 | bar: 2007-12-01 to 2008-02-24
Actual | [8 empty] | No | No |  |  | 2008-06-25 | 2008-06-28 | 2008-07-01 | 2008-07-30 | 2008-07-30 | 2008-08-12 | 2008-09-07 | 2008-09-20 |  |  |  |  | 2009-08-01
Planned | 6 | RALP/ W/NCB/ 02/2008 | Rehabilitation of GDAR Head office Maintenance /SANA,A | Works |  | USD | Prior | NCB | No | No |  |  | 2008-03-30 | 2008-04-10 | 2008-04-15 | 2008-05-15 | 2008-05-15 | 2008-05-29 | 2008-06-05 | 2008-06-12 | 7562443 | YER | RALP/W/5/2008/ With Adden. Contract 1-2008 | Mohammed Gayed Al-Waghdi for Trading &General contracting Sana,a -Republic of Yemen | 2008-12-11 | 7562443 | Completed
Revised | [8 empty] | No | No | [14 empty] | 2009-01-09 | bar: 2008-06-25 to 2008-09-20
Actual | [8 empty] | No | No |  |  | 2008-06-25 | 2008-06-28 | 2008-07-01 | 2008-07-30 | 2008-07-30 | 2008-09-09 | 2008-10-08 | 2008-10-11 |  |  |  |  | 2008-12-01
Planned | 7 | RALP/ W/NS//03/2008 | Rehabilitation & Decoration of library and Hall Central Veterinary Laboratory ( CVL) Sana’a | Works |  | USD | Prior | NS | No | No |  |  | 2008-03-28 | 2008-04-15 | 2008-04-16 | 2008-04-30 | 2008-04-30 | 2008-05-10 | 2008-05-25 | 2008-06-08 | 4744686 | YER | RALP/W/1/2009/ With Adden. contract2-2009 | Mohammed Gayed Al-Waghdi for Trading &General contracting Sana,a -Republic of Yemen | 2009-02-24 | 4744686 | Completed
Revised | [8 empty] | No | No | [14 empty] | 2009-05-24 | bar: 2008-06-25 to 2008-10-11
Actual | [8 empty] | No | No |  |  | 2008-03-28 | NA | 2008-12-06 | 2008-12-24 | 2008-12-24 | 2008-12-28 | 2009-01-19 | 2009-01-24 |  |  |  |  | 2009-04-28
Planned | 8 | RALP/ GDAR / G/NCB/4/ 2008 | Procurement of (5) vehicles 4WD) for public private partnership for veterinary services | Goods |  | USD | Post | NCB | No | No |  |  | 2008-11-05 | 2008-11-15 | 2008-11-22 | 2008-12-22 | 2008-12-22 | 2009-01-01 | 2009-01-08 | 2009-01-15 | 82500 | USD | RALP/G/2/2009 | Sabeha Trading Co. Zubiri street SANA,A Republic of Yemen | 2009-05-02 | 82500 | Completed
Revised | [8 empty] | No | No | [14 empty] | 2009-09-05 | bar: 2008-06-25 to 2008-10-11
Actual | [8 empty] | No | No |  |  | 2008-11-06 | NA | 2008-12-23 | 2009-01-14 | 2009-01-14 | 2009-01-22 | NA | 2009-02-01 |  |  |  |  | 2009-08-25
Planned | 9 | RALP/ GDAR/G /NCB/3/2009 | Procurement of ( VAN & pick up 4*4 double cabin for (Central Veterinary laboratory (CVL). | Goods |  | USD | Post | NCB | No | No |  |  | 2008-12-15 | NA | 2009-02-03 | 2009-03-05 | 2009-03-05 | 2009-03-11 | NA | 2009-03-23 | 37100 | USD | RALP/G/3/2009 with addend.contract on ( 4/10/2010) | TEHAMA TRADING COMPANY Shmsan street .- HODEIDAH Republic of Yemen | 2009-05-22 | 37100 | Completed
Revised | [8 empty] | No | No | [14 empty] | 2010-11-04 | bar: 2008-06-25 to 2008-10-11
Actual | [8 empty] | No | No |  |  | 2008-12-31 | NA | 2009-02-03 | 2009-02-21 | 2009-02-21 | 2009-03-06 | NA | 2009-03-23 |  |  |  |  | 2010-10-17
Planned | 10 | RALP/ GDAR/ CVL/G/NCB/ 04/2009 | Supply and install furniture and equipments for library and conference hall) in Central Veterinary Laboratory (CVL ) SANA,A | Goods |  | USD | Post | NCB | No | No |  |  | 2009-01-05 | NA | 2009-02-04 | 2009-03-07 | 2009-03-07 | 2009-03-21 | NA | 2009-03-28 | 48060 | USD | RALP/G/4/2009 / with /Adden.contract3-2009 | Leaders Technology,, Maqadisho street Sana'a - Republic of Yemen | 2009-07-31 | 48060 | Completed
Revised | [8 empty] | No | No | [14 empty] | 2009-08-31 | bar: 2008-06-25 to 2008-10-11
Actual | [8 empty] | No | No |  |  | 2008-02-07 | NA | 2009-02-14 | 2009-03-14 | 2009-03-14 | 2009-05-13 | NA | 2009-06-01 |  |  |  |  | 2009-09-02
Planned | 11 | RALP/ GDAH/G/NCB/ 07/2009 | Supply and install Incinerator for the Central Veterinary Laboratory (CVL ) Sana’a | Goods |  | USD | Post | NCB | No | No |  |  | 2009-05-25 | 2009-05-30 | 2009-05-31 | 2009-07-15 | 2009-07-15 | 2009-07-30 | 2009-08-06 | 2009-08-13 | 41990 | USD | RALP/G/5/2009 with addend.cont. no 2/ 2010 extend period | Brothers INT,L.Co.LTD - S .Ring.RD SANA,A Republic of Yemen | 2009-12-26 | 41738 | Completed - with Deducted Liquidated Damages
Revised | [8 empty] | No | No | [14 empty] | 2010-02-24 | bar: 2008-06-25 to 2008-10-11
Actual | [8 empty] | No | No |  |  | 2009-05-25 | NA | 2009-05-31 | 2009-06-30 | 2009-06-30 | 2009-07-27 | NA | 2009-09-27 |  |  |  |  | 2010-03-20
Planned | 12 | RALP /G/NCB/ 06/2009 | Supply office Furniture for agricultural offices 5 Governorates (sana,a,lahj,hodedah.almhweet,hajja) | Goods |  | USD | Post | NCB | No | No |  |  | 2009-05-12 | NA | 2009-05-31 | 2009-06-30 | 2009-06-30 | 2009-07-15 | 2009-07-25 | 2009-08-02 | 27320 | USD | RALP/G/6 /2009 | Al-Hadha Furnuture &Carpets co. (HADFUR) Hadda street SANA,A Republic of Yemen | 2009-11-27 | 27320 | Completed
Revised | [8 empty] | No | No | [14 empty] | 2010-01-11 | bar: 2008-06-25 to 2008-10-11
Actual | [8 empty] | No | No |  |  | 2009-05-12 | NA | 2009-05-31 | 2009-07-01 | 2009-07-01 | 2009-08-12 | NA | 2009-10-13 |  |  |  |  | 2009-12-29
Planned | 13 | RALP/CVL/G/NCB/11/2009 | Supply and Install Generator for the Central Veterinary Laboratory (CVL ) | Goods |  | USD | Post | NCB | No | No |  |  | 2009-10-15 | NA | 2009-10-25 | 2009-11-24 | 2009-11-24 | 2009-12-08 | NA | 2009-12-15 | 85850 | USD | RALP/G/7 /2009 | Jumaan Trading &Investment Co.(YJSC) AL-Zubairy street SANA,A Republic of Yemen | 2010-03-28 | 85850 | Completed
Revised | [8 empty] | No | No | bar: 2008-06-25 to 2008-10-11
Actual | [8 empty] | No | No |  |  | 2009-08-28 | NA | 2009-09-06 | 2009-10-12 | 2009-10-12 | 2009-11-10 | NA | 2009-12-28 |  |  |  |  | 2010-03-27
Planned | 14 | RALP/ PSU /G/NS /1 /2009 | Supply Stationary for Project support Unit (PSU ) . | Goods |  | USD | Post | NS | No | No |  |  | 2009-09-05 | NA | 2009-09-19 | 2009-10-03 | 2009-10-03 | 2009-10-10 | NA | 2009-10-17 | 4322.63 | USD | RALP/G/8 /2009 | Maktabati Stationery Hadda street SANA,A Republic of Yemen | 2009-12-14 | 4322.63 | Completed
Revised | [8 empty] | No | No | [14 empty] | NA | bar: 2008-06-25 to 2008-10-11
Actual | [8 empty] | No | No |  |  | 2009-10-05 | NA | 2009-10-17 | 2009-10-31 | 2009-10-31 | 2009-11-04 | NA | 2009-11-14 |  |  |  |  | 2009-11-21
Planned | 15 | RALP/ GDAH/G/ICB/05/2009 | Supply and Install Laboratory Benching Equipments for ( Central Veterinary laboratory (CVL) SANA,A | Goods |  | USD | Prior | ICB | No | No |  |  | 17. Feb. 09 | 2009-03-01 | 2009-03-08 | 2009-04-22 | 2009-04-22 | 2009-05-06 | 2009-05-20 | 2009-05-27 | 169936 | USD | RALP/G/1 /2010 with addend.contract no 1/2010 | Engineering Technologies for Consultant Services &Supplies Bait BOS ,50 Sothern SANAA-Republic of Yemen | 2010-06-03 | 169936 | Completed
Revised | [8 empty] | No | No |  |  | 2009-06-28 | 2009-07-12 | 2009-08-15 | 2009-09-29 | 2009-09-29 | 2009-10-13 | 2009-10-20 | 2009-10-27 |  |  |  |  | NA
Actual | [8 empty] | No | No |  |  | 2009-07-19 | 2009-08-03 | 2009-09-15 | 2009-11-01 | 2009-11-01 | 2010-01-04 | 2010-01-06 | 2010-02-03 |  |  |  |  | 2010-05-31
Planned | 16 | RALP/RVL/G/NCB/2/2010 | Purchase of ( 2) vehicles (Pick up 4*4 double cabins) for Regional Veterinary laboratories.(RVL) | Goods |  | USD | Post | NCB | No | NO |  |  | 2010-11-01 | NA | 2010-11-08 | 2010-12-08 | 2010-12-08 | 2010-12-23 | NA | 2011-01-07 | 46400 | USD | RALP/ RVL/G/2/2010 | TEHAMA TRADING COMPANY Shmsan street . HODEIDAH Republic of Yemen | 2011-02-26 | 46400 | Completed
Revised | [8 empty] | No | NO |  |  | 2010-07-12 | NA | 2010-07-24 | 2010-08-24 | 2010-08-24 | 2010-08-24 | NA | 2010-09-08 |  |  |  |  | NA
Actual | [8 empty] | No | No |  |  | 2010-07-12 | NA | 2010-07-24 | 2010-08-24 | 2010-08-24 | 2010-10-24 | NA | 2010-11-28 |  |  |  |  | 2010-12-15
Planned | 17 | RALP/ RVL/G/NCB/1 /2011 | Supply and install Complementary equipment for Regional lab in (Abs ) HAJJA Gov. | Goods |  | USD | Post | NCB | No | NO |  |  | 2010-09-15 | NA | 2010-09-22 | 2010-10-22 | 2010-10-22 | 2010-11-06 | NA | 2010-11-13 | 56198 | USD | RALP/G/ 1 /2011 | Inter Tek Supply AL-Zubairy street Sana'a - Republic of Yemen | 2011-08-15 | 56198 | Completed
Revised | [8 empty] | No | No |  |  | 2011-04-05 | NA | 2011-04-12 | 2011-05-12 | 2011-05-12 | 2011-05-27 | NA | 2011-06-03 |  |  |  |  | NA
Actual | [8 empty] | No | No |  |  | 2011-01-05 | NA | 2011-01-22 | 2011-02-22 | 2011-02-22 | 2011-04-09 | NA | 2011-05-15 |  |  |  |  | 2011-08-17
Planned | 18 | RALP/CVL/G/ICB/1 /2010 | Supply and Install Autoclave and waste water treatment plant the system) for Central Veterinary laboratory (CVL) SANA,A | Goods |  | USD | Prior | ICB | No | NO |  |  | 2009-10-15 | 2009-10-22 | 2009-10-29 | 2009-12-13 | 2009-12-13 | 2009-12-27 | 2010-01-03 | 2010-01-10 | 106893.23 | EUR | RALP/G/2 /2011 | AGMIN ITALY s r I Vicolo,Trave4 -37121Verona Italy | 2011-10-18 | on going | Amendment : (Modify the Method and Conditions of Payment the WB NO objection Letter dated (May 16, 2011)Prior signed the original contract on (May 21,2011 ). Addendum: (change the Brand &country of origin for tow items included the original contract the WB NO objection Letter to the Addendum dated (October 17, 2011) the Addendum signed on (October 18, 2011). | on going
Revised | [8 empty] | No | NO |  |  | 2010-10-25 | 2010-11-08 | 2010-11-28 | 2011-01-12 | 2011-01-12 | 2011-01-27 | 2011-02-03 | 2011-02-10 |  |  |  |  | 2014-05-30
Actual | [8 empty] | No | No |  |  | 2010-10-25 | 2010-11-08 | 2010-11-28 | 2011-01-12 | 2011-01-12 | 2011-03-06 | 2011-04-05 | 2011-05-21
Planned | 19 | RALP/GDAH/G/NS/1 /2011 | Supply and install office furniture for central epidemiological unit in (Directorate General of Animal Health and Veterinary Quarantine (DGAH&VQ). | Goods |  | USD | Post | NS | No | No |  |  | 2010-11-27 | NA | 2010-12-10 | 2010-12-24 | 2010-12-24 | 2011-01-07 | NA | 2011-01-14 | 851000 | YER | RALP /G/3/2011 | SAM FOR IND.& TRADING Aldairi street Sana'a - Republic of Yemen | 2011-07-12 | 851000 | Completed
Revised | [8 empty] | No | No |  |  | 2011-04-02 | NA | 2011-04-10 | 2011-04-24 | 2011-04-24 | 2011-05-01 | NA | 2011-05-08 |  |  |  |  | NA
Actual | [8 empty] | No | No |  |  | 2011-04-27 | NA | 2011-05-07 | 2011-05-21 | 2011-05-21 | 2011-05-30 | NA | 2011-06-12 |  |  |  |  | 2011-06-26
Planned | 20 | RALP/GDAD/G/NS/2/2011 | Procurement of (5)computer sets (including one designed for data management ) &office appliances for (Directorate General of Animal Development (DGAD). | Goods |  | USD | Post | NS | No | No |  |  | 2011-07-09 | NA | 2011-07-19 | 2011-08-03 | 2011-08-03 | 2011-08-13 | NA | 2011-08-28 | 8148 | USD | RALP /G/4 /2011 | Leaders Technology,, Maqadisho street Sana'a - Republic of Yemen | 2011-07-19 | 8148 | Completed
Revised | [8 empty] | No | No | [14 empty] | NA | bar: 2010-10-25 to 2011-05-21
Actual | [8 empty] | No | No |  |  | 2011-05-07 | NA | 2011-05-09 | 2011-05-23 | 2011-05-23 | 2011-05-30 | NA | 2011-06-19 |  |  |  |  | 2011-07-10
Planned | 21 | AI /W/NCB/ 01/2010 | Reform and Improvement AI lab in new building central Veterinary Laboratory (CVL) | Works |  | USD | Prior | NCB | No | No | NA | NA | 2009-09-30 | 2009-10-15 | 2009-10-20 | 2009-11-20 | 2009-11-20 | 2009-12-20 | 2009-12-30 | 2010-01-14 | 107548.05 | USD | AI/W/1/2011 | M/ S .C STYRCOOL for Industry, A/C &Contracting SANA,A YEMEN | 2011-06-30 | 88532 | The contract awarded through avian influenza Prevention &Control Project (AIPCP) , The orginal contract Value is ( USD 250464 ) only (USD 142915.95 paid from the influenza Prevention &Control Project (AIPCP). . The remaining amount of contract ( USD 107548.05 ) will be paid from RALP due to the closing date of AI Project in addition to the delay happened to complete this contract due to unpaid the direct payments .as agreed during cairo mission march 2012 . | Completed
Revised | [8 empty] | No | No | NA | NA | 2010-11-01 | 2010-11-20 | 2010-11-27 | 2010-12-27 | 2010-12-27 | 2011-01-03 | 2011-02-07 | 2011-02-12 |  |  |  |  | 2012-12-31
Actual | [8 empty] | No | No | NA | NA | 2010-11-01 | 2010-11-20 | 2010-11-27 | 2010-12-27 | 2010-12-27 | 2011-01-25 | 2011-02-07 | 2011-02-19 |  |  |  |  | 2012-12-31
Planned | 22 | AI/ G/NS / 2/2011 | Procurement of Mobile GIS units for professional GIS mapping applications unit (2) for monitoring in (DGAHVQ) | Goods |  | USD | Post | NS | No | No | NA | NA | 2009-08-30 | NA | 2009-06-30 | 2009-08-14 | 2009-08-14 | 2009-11-01 | 2009-10-28 | 2009-11-12 | 6800 | USD | AI/G/4/2011 | Leaders Technology,, Maqadisho street Sana'a - Republic of Yemen | 2011-05-24 | 6800 | The contract awarded through avian influenza Prevention &Control Project (AIPCP) but unpaid due to the closing date of AI project, so ALL the contract Value paid from RALP Project.as agreed during cairo mission march 2012 | Completed
Revised | [8 empty] | No | No | NA | NA | 2011-03-15 | NA | 2011-03-19 | 2011-04-02 | 2011-04-02 | 2011-04-07 | NA | 2011-04-14 |  |  |  |  | NA
Actual | [8 empty] | No | No | NA | NA | 2011-03-15 | NA | 2011-03-19 | 2011-04-02 | 2011-04-02 | 2011-04-05 | NA | 2011-04-24 |  |  |  |  | 2011-05-29
Planned | 23 | AI/ G/NS / 3/2011 | Procurement of equipments for improvement surveillance network & training regional centers (staff) in CVL | Goods |  | USD | Post | NS | No | No | NA | NA | 2009-01-30 | 2009-03-03 | 2009-08-30 | 2009-10-14 | 2009-10-14 | 2009-12-30 | 2009-12-28 | 2010-01-12 | 18540 | USD | AI/G/3/2011 | Leaders Technology,, Maqadisho street Sana'a - Republic of Yemen | 2011-05-11 | 18540 | The contract awarded financed through avian influenza Prevention &Control Project (AIPCP) but unpaid due to the closing date of AI project, so ALL the contract Value paid from RALP Project.as agreed during cairo mission march 2012 | Completed
Revised | [8 empty] | No | No | NA | NA | 2011-02-09 | NA | 2011-02-16 | 2011-03-02 | 2011-03-02 | 2011-03-07 | 2011-03-14 | 2011-03-14 |  |  |  |  | NA
Actual | [8 empty] | No | No | NA | NA | 2011-02-09 | NA | 2011-02-16 | 2011-03-02 | 2011-03-02 | 2011-03-21 | NA | 2011-04-11 |  |  |  |  | 2011-05-14
Planned | 24 | RALP/AQF/PW/ICB/01/2012 | Construction works of AL- Mocha quarantine at Al -mocha district in Taiz Governorate. | Works |  | USD | Prior | ICB | No | No |  |  | 2009-07-29 | 2009-08-15 | 2009-08-22 | 2009-10-06 | 2009-10-06 | 2009-11-05 | 2009-12-15 | 2010-01-12 | 4481783 | USD | RALP/AQF/PW/ICB/01/2012 | Mr. 'Ali Moh'd Hamood Al-Wadei for Architectural and Construction Contracting - Sana,a YEMEN | 2014-02-22 | 3,703,901 | Addendum 1 : The contract amount increased from USD 3,7979,69 to USD 4,481,783 The addendum amount is US$ 683,814 and the contract period extended from 450 days to 540days NOL dated on (21/9/2013 - 1/10/2013 ). | on going
Revised 1 | [8 empty] | No | No |  |  | 2010-04-01 | 2010-04-20 | 2010-05-02 | 2010-06-16 | 2010-06-16 | 2010-07-31 | 2010-08-30 | 2010-09-29 |  |  |  |  | 2014-05-23
Revised 2 | [8 empty] | Yes | Yes | 2010-11-20 | 2011-01-09 | 2011-01-15 | 2011-01-22 | 2011-01-29 | 2011-03-12 | 2011-03-12 | 2011-04-26 | 2011-05-26 | 2011-06-02
Revised 3 | [8 empty] | Yes | No |  |  | 2011-03-31 | 2011-04-20 | 2011-05-07 | 2011-06-22 | 2011-06-22 | 2011-07-16 | 2011-07-23 | 2011-07-30
Revised 4 | [8 empty] | Yes | No |  |  | 2012-06-20 | 2012-07-09 | 2012-07-16 | 2012-08-27 | 2012-08-27 | 2012-10-10 | 2012-11-10 | 2012-11-15
Actual | [8 empty] | Yes | No |  |  | 2012-06-14 | 2012-06-24 | 2012-06-30 | 2012-08-14 | 2012-08-14 | 2012-09-29 | 2012-10-08 | 2012-11-14
Planned | 25 | RALP/AQF/G/NCB/01/2013 | Supply and install Incinerator for AL- Mocha quarantine at Al -mocha district in Taiz Governorate. | Goods |  | USD | Post | NCB | No | No |  |  | 2013-11-03 | NA | 2013-11-17 | 2013-12-17 | 2013-12-17 | 2013-12-31 | NA | 2014-01-14 | 229250 | USD | RALP/AQF/G/NCB/01/2013 | Brothers INT,L.Co.LTD - SANA,A Republic of Yemen | 2014-06-10 |  | on going | on going
Revised | [8 empty] | No | No | bar: 2012-06-14 to 2012-11-14
Actual | [8 empty] | No | No |  |  | 2013-11-12 | NA | 2013-11-16 | 2013-11-16 | 2013-12-17 | 2014-01-16 | NA | 2014-02-10
Planned | 26 | RALP/ CVL/G/NCB/1 /2014 | Supply Furniture & offices equipment and Complementary equipment for Central Veterinary laboratory (CVL) | Goods |  | USD | Post | NCB | No |  |  |  | 2014-04-01 | NA | 2014-04-04 | 2014-05-04 | 2014-05-04 | 2014-05-11 | NA | 2014-05-15 |  |  |  |  | 2014-08-13
Revised | [8 empty] | No
Actual | [8 empty] | No |  |  |  | 2012-06-14: 2014-03-31; 2012-06-24: NA; 2012-06-30: 2014-04-06; 2012-08-14: 2014-05-06
Formulas:
Completion of Contract (Date) = [Contract Signed (Date), row below]+216
Completion of Contract (Date) = [Contract Signed (Date)]+90
Preparation of Bid Document (Date) = [Bid Invitation (Date)]-7
Bid Closing (Date) = [Bid Invitation (Date)]+30
Bid Opening (Date) = [Bid Closing (Date)]
Contract Award Decision (Date) = [Bid Opening (Date)]+14
NA = [Contract Award Decision (Date)]+7
Contract Signed (Date) = [NA]+7

## Consulting Services
Procurement Plan for Consultant Services
YEMEN P089259 : Rainfed Agriculture and Livestock Project (RALP) IDA Cr.#4220/Yem
** Applicable in case of Bank's prior review | [11 empty] | In some contracts, one or more of these approvals may be contained in one Bank communication.
| SL No. | Package/ Reference No. | Description of Services | Estimated Cost | Currency of Estimated Cost | Review by Bank (Prior/ Post) | Type of Consultant (Firm/ Individual) | Method of Selection | Advertising for Short listing (Date) | TOR/Shortlist to be Finalised (Date) | RFP Final Draft to be forwarded to the Bank (Date) | No Objection from Bank for TOR (Date)** | No Objection from Bank for Shortlist (Date)** | No Objection from Bank for Final RFP (Date)** | RFP Issued (Date) | Proposal Submission Deadline (Date) | No Objection by the Bank to the Technical Evaluation Report (Date)** | No Objection by the Bank (Technical/ #Combined/ Draft Contract/ Final Contract) (Date)** | Contract Signed (Date) | Contract Value | Contract Currency | Contract No. | Name, City, and Country of Contractor (incl. Zip Code if US) | Services Completion (Date) | Expenses Incurred to Date | Comments
Planned | 1 | RALP/CS/1/2008 | Coordinate, communicate, Follow-up identification/collection of priority crops and land races. | 30000 | USD | Prior | Firm | SSS | NA | NA | NA | NA | NA | NA | NA | NA | NA | 2008-06-28 | 2008-01-01 |  | USD | RALP/CS/1/2008 | GENERAL SEEDS MULTIPLICATION CORPORATION (GSMC) West of Gym stadium Dhammar Governorate . Yemen Republic of | 2008-12-31 | 30000 | Completed
Revised | [9 empty] | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  |  |  |  | NA
Actual | [9 empty] | NA | NA | NA | NA | NA | NA | 2008-01-01 | NA | 2008-06-28 | 2008-01-01 |  |  |  |  | 2009-03-27
Planned | 2 | RALP/CS/ 2/2008 | Civil Engineer for (Rehabilitation and maintenance) of agriculture offices) (11 districts )and Designing & supervision for additional works of agriculture extension offices | 11000 | USD | Prior | Individual | IC | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  | USD | RALP/CS/2/ 2008 | SALAH ADDIN NASSIR (MR.)Sana'a - Yemen Republic of | 2008-04-30 | 3800 | Completed
Revised | [9 empty] | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  |  |  |  | NA
Actual | [9 empty] | NA | NA | NA | 2007-09-30 | NA | NA | NA | 2007-12-17 | 2007-12-17 | 2008-01-05 |  |  |  |  | 2009-06-09
Planned | 3 | RALP/CS/3/2008 | Civil engineer for GDAR Head office Maintenance (designing ) and supervision | 1500 | USD | Prior | Individual | IC | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  | USD | RALP/CS/3/2008 | Eng Ahmed S. Al-Hammadi Sana'a - Yemen Republic of | 2008-05-10 | 1600 | Completed
Revised | [9 empty] | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  |  |  |  | 2009-02-15
Actual | [9 empty] | NA | NA | NA | NA | NA | NA | NA | 2008-04-16 | 2008-04-27 | 2008-04-20 |  |  |  |  | 2008-12-01
Planned | 4 | RALP/CS/4/2008 | Laboratory equipment specialist ( international ). | 20000 | USD | Post | Individual | IC | 2008-03-22 | 2008-04-30 | NA | 2008-05-10 | NA | NA | NA | NA |  | 2008-08-10 | 2008-08-30 |  | USD | RALP/CS/4/2008 | Dr.Unger Herman, w - Lebsaftgasses 3 A-3400 Klosterneuburg Germany | 2008-02-23 | 14837 | Completed
Revised | [8 empty] | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  |  |  |  | NA
Actual | [8 empty] | 2008-03-22 | 2008-01-08 | NA | 2008-01-08 | NA | NA | NA | NA | NA | NA | 2008-02-09 |  |  |  |  | 2009-07-20
Planned | 5 | RALP/PT/002/2007 | MONITORING AND EVALUATION OFFICER | 9300 | USD | Prior | Individual | IC | 2007-09-06 | 2007-09-20 | NA | NA | NA | NA | NA | NA | NA | 2007-09-27 | 2007-10-04 |  | USD | RALP/CS/5/2008 | Dr.Mustafa H.Abdul Sattar Crater Aden Yemen Republic of | 2009-06-15 | 10000 | Completed | The contract extended the WB NO objection Letter to extend the contract dated on (December 27,2009 ) the extension contract signed on ( December 27,2009) the period extended to ( June 15,2010 ) and the amount of extension contract (USD 5000 ) .
Revised | [8 empty] | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  |  |  |  | 2010-06-15
Actual | [8 empty] | 2007-09-06 | 2008-01-13 | NA | NA | NA | NA | NA | NA | 2008-01-16 | 2008-05-24 | 2008-06-15 |  |  |  |  | 2010-10-21
Planned | 6 | RALP/CS/ 6/2008 | Enhancement of Seeds Production and Maintenance of varieties. | 50000 | USD | Prior | Firm | SSS | NA | NA | NA | NA | NA | NA | NA | NA | NA | 2008-07-25 | 2008-07-01 |  | USD | RALP/CS/6/2008 | GENERAL SEEDS MULTIPLICATION CORPORATION (GSMC) West of Gym stadium Dhammar Governorate . Yemen Republic of | 2009-06-30 | 50000 | Completed
Revised | [9 empty] | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  |  |  |  | NA
Actual | [9 empty] | NA | NA | NA | NA | NA | NA | NA | NA | 2008-07-29 | 2008-07-01 |  |  |  |  | 2009-09-10
Planned | 7 | RALP/CS/7/2008 | Training of CAHWs &Veterinary Technicians and Assistants - (1) | 168000 | USD | Prior | Firm | SSS | NA | NA | NA | NA | NA | 2008-05-25 | 2008-04-17 | 2008-05-15 | 2008-07-10 | 2008-07-25 | 2008-07-30 |  | YER | RALP/CS/7/2008 | Yemeni Veterinary Medicine Association (YVMA), Almithaq Street, Sana'a - Yemen Republic of | 2009-06-30 | 36462500 | Completed
Revised | [9 empty] | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  |  |  |  | NA
Actual | [9 empty] | NA | NA | NA | NA | NA | NA | NA | NA | 2008-11-04 | 2008-07-01 |  |  |  |  | 2010-02-03
Planned | 8 | RALP/CS/8/2008 | Collection, characterization, evaluation, participatory improvement and conservation of landraces (Lahej governorate) 2008-2009 | 20000 | USD | Prior | Firm | SSS | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 2008-08-01 |  | USD | RALP/CS/8/2008 | ADEN UNIVERSITY - NASSER FACULTY OF AGRICULTURAL SCIENCES Alhwta Lahi Yemen Republic of | 2009-07-31 | 24000 | Completed
Revised | [9 empty] | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  |  |  |  | NA
Actual | [9 empty] | NA | NA | NA | NA | NA | NA | NA | NA | 2008-11-29 | 2008-08-01 |  |  |  |  | 2009-12-07
Planned | 9 | RALP/CS /9/2008 | Collection, characterization, evaluation, participatory improvement and conservation of landraces ( SANAA governorate ) 2008-2009 | 20000 | USD | Prior | Firm | SSS | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 2008-08-01 |  | USD | RALP/CS/9/2008 | SANA'A UNIVERSITY - FACULTY OF AGRICULTURE Ring Road]. Street P.o Sana'a - Yemen Republic of | 2009-07-31 | 24000 | Completed
Revised | [9 empty] | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
Actual | [9 empty] | NA | NA | NA | NA | NA | NA | NA | NA | 2008-11-29 | 2008-08-01 |  |  |  |  | 2009-12-08
Planned | 10 | RALP/CS/10/2008 | Collection, characterization, evaluation, participatory improvement and conservation of landraces ( Hodeidah governorate). 2008-2009 | 20000 | USD | Prior | Firm | SSS | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 2008-08-01 |  | USD | RALP/CS/10/2008 | AGRICULTURAL RESEARCH AND EXTENSION AUTHORITY (AREA) Sana'a Road, Dammar Governorate . Yemen Republic of | 2009-07-31 | 24000 | Completed
Revised | [9 empty] | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  |  |  |  | 2009-12-30
Actual | [9 empty] | NA | NA | NA | NA | NA | NA | NA | NA | 2008-12-17 | 2008-08-01 |  |  |  |  | 2010-05-15
Planned | 11 | RALP/CS/11/2008 | Collection, characterization, evaluation, participatory improvement and conservation of landraces ( HAJJA GOV.) 2008-2009 | 20000 | USD | Prior | Firm | SSS | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 2008-08-01 |  | USD | RALP/CS/11/2008 | AGRICULTURAL RESEARCH AND EXTENSION AUTHORITY (AREA) Sana'a Road, Dammar Governorate . Yemen Republic of | 2009-07-31 | 24000 | Completed
Revised | [9 empty] | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  |  |  |  | 2009-12-30
Actual | [9 empty] | NA | NA | NA | NA | NA | NA | NA | NA | 2008-12-17 | 2008-08-01 |  |  |  |  | 2010-05-15
Planned | 12 | RALP/CS/12/2008 | Collection, characterization, evaluation, participatory improvement and conservation of landraces ( AL-Mahweet governorate ) . 2008-2009 | 20000 | USD | Prior | Firm | SSS | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 2008-08-01 |  | USD | RALP/CS/12/2008 | AGRICULTURAL RESEARCH AND EXTENSION AUTHORITY (AREA) Sana'a Road, Dammar Governorate . Yemen Republic of | 2009-07-31 | 24000 | Completed
Revised | [9 empty] | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  |  |  |  | 2009-12-30
Actual | [9 empty] | NA | NA | NA | NA | NA | NA | NA | NA | 2008-12-17 | 2008-08-01 |  |  |  |  | 2010-05-15
Planned | 13 | RALP/CS/ 13/2008 | Consultancy Services on Capacity Building and Technical Backstopping for the Following Project First comp. (Sub-Components: (1.1) Landrace Improvement and Maintenance; (1.2) Promotion of Seed Producer Groups; - (2) | 336000 | USD | Prior | Firm | SSS | NA | NA | NA | 2007-08-07 | NA | NA | NA | NA | NA | 2007-08-22 | 2007-08-29 |  | USD | RALP/CS/13/2008 | International Centre for Agriculture Research in the Dry Areas (ICARDA) Aleppo- Syria | 2012-12-30 | 330012 | Completed | The contract expired on 31 December 2012 and the remaining and some new activities shifted to the new contract in 2013.
Revised | [9 empty] | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  |  |  |  | NA
Actual | [9 empty] | NA | NA | 2007-08-29 | NA | NA | NA | NA | NA | 2008-08-03 | 2008-08-25 |  |  |  |  | 2012-12-31
Planned | 14 | RALP/CS/ QCBS/ 2/ 2008 | INTERNATIONAL CONSULTANCY SERVICES FOR CENTRAL VETERINARY LABORATOYR (CVL), SANA'A ( 3 Experts) | 120000 | USD | Prior | Firm | QCBS | 2008-02-10 | 2008-02-24 | 2008-03-02 | NA | NA | 2008-03-16 | 2008-03-23 | 2008-04-22 | 2008-05-06 | 2008-05-14 | 2008-05-28 |  | USD | RALP/CS/14/2008 | International Projects Partnership (IPP) Consultants 30 bis rue du Vieil Abruvoir 78100 St Germain-en-Laye France | 2011-11-04 | 217850 | Completed | Amendment : ( Staffing ,terms of payments and Reports NOL dated on ( May 24 ,2010 ) and amendment (1) signed on ( May 30,2010 ) addendum (1) : (The contract amount of the Original contract increased from US$189000 US$ to US$ 222352 due to the addition of local taxes estimated US$ 33352 The NOL dated on ( December28,2010) and the amendment signed on (January 3 , 2011).
Revised | [8 empty] | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  |  |  |  | NA
Actual | [8 empty] | 2008-02-01 | 2008-04-01 | 2008-04-26 | NA | 2008-04-23 | 2008-05-07 | 2008-05-10 | 2008-06-11 | 2008-07-07 | 2008-09-02 | 2008-09-20 |  |  |  |  | 2012-09-05
Planned | 15 | RALP/CS/ 14/2008 | Civil engineer for Designing & Redesigning and supervision of the avian influenza laboratory within the new building of the new CVL. | 12500 | USD | Post | Individual | IC | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  | USD | RALP/CS/15/2008 | Anwar Ahmed Alhaboob Sana'a - Yemen Republic of | NA | 12500 | Completed | Amendment contract no (4/2011) dated on ( 15/ 2/ 2011 ) the orginal contract amount increased from US$ 7500 toUS$ 12500 due to Redesigning and supervision
Revised | [9 empty] | 2011-01-07 | NA | NA | NA | NA | NA | NA | NA | NA | NA |  |  |  |  | 2011-06-30
Actual | [9 empty] | NA | NA | NA | NA | NA | NA | NA | NA | NA | 2008-11-24 |  |  |  |  | 2012-12-29
Planned | 16 | RALP/CS/ QCBS /1/ 2008 | INTERNATIONAL EXPERTISE SERVICES FOR GENERAL DIRECTORATE OF ANIMAL RESOURCES (GDAR) (5 Experts ). | 250000 | USD | Prior | Firm | QCBS | 2007-12-31 | 2008-01-14 | 2008-01-14 | NA | NA | 2008-01-16 | 2008-01-25 | 2008-05-07 | 2008-06-07 | 2008-06-25 | 2008-06-30 |  | EUR | RALP/CS/1/2009 | ICON INSTITUT PUBLIC SECTOR GMBH- Von – Groote – Strasse 28, 50968 – Cologne, Germany | 2014-02-06 | 351 610 | Completed | Addendum(1) : ( (The contract amount increased from Euro268860 to Euro 302860 due to Append activity (local legal expert) for 12 months estimated (34000Euro ) & period of contract reduced from (60 months )to (39 months ) NOL dated on ( July 25.2010 ) the addendum signed on( August 1,2010) - Amendment : ( substitute key staff ) on (October 16,2010) and the NOL dated on ( November 6,2010 ). Addendum(2) : ( The contract amount increased from (302860 Euro ) to ( 356305 Euro ) due to the addition of local taxes estimated ( 53445 Euro) NOL dated on ( December 28,2010 )and the addendum(2) signed on (January 3 , 2011).
Revised | [8 empty] | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  |  |  |  | 2012-04-30
Actual | [8 empty] | 2008-02-01 | NA | 2008-05-07 | NA | NA | 2008-05-19 | 2008-05-24 | 2008-07-09 | 2008-09-01 | 2009-01-26 | 2009-02-07 |  |  |  |  | 2013-03-18
Planned | 17 | RALP /CS/2/2009 | Technical expertise for quarantines development.(AL-MoKha -Taiz)-Al-mukla -hadrmot) International expert | 24064.25 | USD | Prior | Individual | IC | NA | 2008-05-15 | NA | NA | NA | NA | NA | NA | NA | 28 Jan. 09 | 10 Feb. 09 |  | USD | RALP/CS/2/2009 | David Fleming, DVM Locust Grove, OK 74352 | 2010-02-20 | 31660 | Completed | The contract terminated NOL recived from WB on (July 26,2012)
Revised | [9 empty] | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
Actual | [9 empty] | NA | NA | NA | NA | NA | NA | NA | 2009-01-27 | NA | 2009-02-21 |  |  |  |  | 2012-07-26
Planned | 18 | RALP /CS/2009 | Technical expertise for quarantines development (AL-MoKha -Taiz)-Al-mukla -hadrmot) national expert | 5400 | USD | Prior | Individual | IC | NA | NA | NA | NA | NA | NA | NA | 2008-05-15 | 2008-06-07 | 2008-06-25 | 2008-06-30 |  | USD | RALP/CS/3/-2009 | Dr Khalid Mohammed saeed HODEIDAH - Yemen Republic of | 2010-02-20 | 3750 | Completed
Revised | [9 empty] | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  |  |  |  | NA
Actual | [9 empty] | NA | NA | NA | NA | NA | NA | NA | NA | 2009-04-05 | 2009-04-11 |  |  |  |  | 2010-09-18
Planned | 19 | RALP /CS/4/2009 | Yemen Veterinary Association Support expert(International expert) | 25000 | USD | Post | Individual | IC | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  | USD | RALP/CS /4/2009 | Haleem hasnain/ House 13 Street:6, Sector :F-8/3 Islamabad 44000 Pa kistan | 2009-05-29 | 25411 | Completed
Revised | [9 empty] | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  |  |  |  | NA
Actual | [9 empty] | NA |  | NA | NA | NA | NA | NA | NA | NA | 2009-04-14 |  |  |  |  | 2009-06-18
Planned | 20 | RALP /PSU/1/2009 | Procurement Officer | 18000 | USD | Prior | Individual | IC | 2009-03-25 | 2009-04-24 | NA | NA | NA | NA | NA | NA | NA | 2009-06-27 | 2009-06-28 |  | USD | RALP/CS /5/2009 | ALI MOHAMMED ASHAISH Sana'a - Yemen Republic of | 2011-12-31 | 72092 | On going | The contract extended by MAI and Amendment to the orginal contract increased salary by MOPIC
Revised | [8 empty] | 2009-03-25 | 2009-04-24 | NA | NA | NA | NA | NA | NA | NA | NA | NA |  |  |  |  | 2014-05-31
Actual | [8 empty] | NA | NA | NA | NA | NA | NA | NA | NA | NA | 2009-06-27 | 2009-06-28
Planned | 21 | RALP /PSU/1/2009 | Procurement Assistant | 12000 | USD | Post | Individual | IC | 2009-03-25 | 2009-04-24 | NA | NA | NA | NA | NA | NA | NA | 2009-06-27 | 2009-06-28 |  | USD | RALP/CS /6/2009 | NAGEEB ABDULLAH AL-HASHEDI Sana'a - Yemen Republic of | 2011-12-31 | 59539 | On going | The contract extended by MAI and Amendment to the orginal contract increased salary by MOPIC
Revised | [8 empty] | 2009-03-25 | 2009-04-24 | NA | NA | NA | NA | NA | NA | NA | NA | NA |  |  |  |  | 2014-12-31
Actual | [8 empty] | NA | NA | NA | NA | NA | NA | NA | NA | NA | 2009-06-27 | 2009-06-28
Planned | 22 | RALP /CS/ 5/2009 | Coordinate, communicate, Follow-up identification/collection of priority crops and land races | 30000 | USD | Prior | Firm | SS | NA | 2009-05-11 | NA | 2009-05-17 | NA | NA | NA | NA | NA | 2009-05-20 | 2009-06-01 |  | USD | RALP/CS/7/2009 | GENERAL SEEDS MULTIPLICATION CORPORATION (GSMC) West of Gym stadiumDhammar Governorate . Yemen Republic of | 2009-12-31 | 34000 | Completed
Revised | [9 empty] | NA | NA | NA | NA | NA | NA | NA | NA
Actual | [9 empty] | NA | NA | NA | NA | NA | NA | NA | NA | 2009-05-17 | 2009-07-06 |  |  |  |  | 2010-04-06
Planned | 23 | RALP /CS/ 3/2009 | Consultant Services for Design of Al-Mokha Quarantine Building in TAIZ gov. | 20000 | USD | Prior | Individual | IC | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  | USD | RALP/CS/ 8/2009 | YAHIYA MOHAMMED NO'MAN HAMIM Sana'a - Yemen Republic of | 2010-03-23 | 20000 | Completed | The contract amended (the contract amount increased from ($12500) to( $20000) and extend the end period from (March 23,2010) to (July 31,2010) NOL dated on( July 25,2010 ) the Addendum signed on ( July 27,2010).
Revised | [9 empty] | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  |  |  |  | 2010-07-31
Actual | [9 empty] | NA | NA | NA | NA | NA | NA | NA | 2009-06-10 | 2009-12-14 | 2009-12-15 |  |  |  |  | 2010-08-08
Planned | 24 | RALP /CS/1/2010 | Establishment of Seed Producers Groups and Sites and Communities Selection | 50000 | USD | Prior | Firm | SSS | NA | 2009-10-12 | NA | 2009-10-25 | NA | NA | NA | NA | NA | 2009-11-10 | 2009-11-15 |  | USD | RALP/CS/1/2010 - | GENERAL SEEDS MULTIPLICATION CORPORATION (GSMC) West of Gym stadium Dhammar Governorate Yemen Republic of | 2010-06-13 | 36562 | Completed | First Amendment : ( Amended TOR ) amendment signed on (June 5,2010 ) NOL dated on (June 2,2010 ) Second amendment : ( Extend Completion (Date) from (June 13,2010 ) to (August 31,2010 ) NOL dated on ( August 2,2010 ) Deducted Liquidated Damages
Revised | [9 empty] | 2010-03-20 | NA | NA | NA | NA | NA | NA | NA | [6 empty] | 2010-08-31
Actual | [9 empty] | 2010-03-06 | NA | NA | NA | NA | NA | NA | NA | 2010-03-15 | 2010-03-15 |  |  |  |  | 2010-10-18
Planned | 25 | RALP /CS/ 2/2010 | Enhancing on farm - seed production | 50000 | USD | Prior | Firm | SSS | NA | 2009-07-20 | NA | 2009-08-01 | NA | NA | NA | NA | NA | 2009-08-10 | 2009-08-20 |  | USD | RALP/CS/2/2010 | GENERAL SEEDS MULTIPLICATION CORPORATION (GSMC) West of Gym stadium Dhammar Governorate Yemen Republic of | 2010-12-31 | 49170 | Completed
Revised | [9 empty] | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  |  |  |  | NA
Actual | [9 empty] | 2010-03-06 | NA | NA | NA | NA | NA | NA | NA | 2010-03-15 | 2010-03-15 |  |  |  |  | 2011-02-21
Planned | 26 | RALP /PSU/1 /2010 | Recruiting a Secretary for RALP &Avian Flue project | 6000 | USD | Post | Individual | IC | NA | 2010-02-02 | NA | NA | NA | NA | NA | NA | NA | 2010-02-16 | 2010-02-23 |  | USD | RALP/PSU/1/-2010 | Ms.Dunya Mohammed AL-Dubai Sana'a - Yemen Republic of | 2011-12-31 | 26170 | On going
Revised | [9 empty] | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  |  |  |  | 2014-12-31
Actual | [9 empty] | 2010-03-03 | NA | NA | NA | NA | NA | NA | NA | 2010-03-24 | 2010-04-03
Planned | 27 | RALP /CS/ 3/2010 | Veterinary Institute training program (Vet. Technicians training program &Vet. Assistants training program) (11) students .) 2010 | 50000 | USD | Prior | Firm | SSS | NA | 2010-01-02 | NA | NA | NA | NA | NA | NA | NA | 2010-02-01 | 2010-02-16 |  | USD | RALP/CS/3/2010 | Yemeni Veterinary Medicine Association (YVMA), Almithaq Street, Sana'a - Yemen Republic of | 2011-04-04 | 11912605 | Completed
Revised | [9 empty] | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  |  |  |  | NA
Actual | [9 empty] | 2010-02-17 | NA | NA | NA | NA | NA | NA | NA | 2010-03-30 | 2010-04-04 |  |  |  |  | 2011-04-19
Planned | 28 | RALP /CS/4/2010 | Research Contract in Animal Fodders | 41433 | USD | Prior | Individual | IC | 2009-09-09 | 2009-09-02 | NA | 2009-09-16 | NA | NA | NA | NA | NA | 2009-10-17 | 2009-10-20 |  | USD | RALP/CS/4/2010 | ABDO BAKRI AHMED FAKIRA (DR.) Sana'a - Yemen Republic of | 2011-02-28 | 37342.51 | Completed | First amendment :The period of contract extended up to 30-4-2011 (NOL dated on ( February 1,2011) and the amendment signed on ( February 2,2011 ) -The addendum (1) (increase the contract amount from (48340US$ ) TO (49340 US$ ) and the completion period of contract extended to (May 31,2011) instead of (April30,2011) NOL dated on (June19,2011 ) and the addendum signed on(June20,2011 )
Revised | [8 empty] | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 2010-01-01 |  |  |  |  | 2011-05-31
Actual | [8 empty] | NA | 2009-09-13 | NA | 2009-10-07 | NA | NA | NA | NA | NA | 2010-04-11 | 2010-04-12 |  |  |  |  | 2011-07-04
Planned | 29 | RALP /CS/5/2010 | National Coordinator for RALP to implement farmer based system of seed improvement and management | 12000 | USD | Prior | Individual | IC | NA | 2010-02-28 | NA | 2010-03-07 | NA | NA | NA | NA | NA | 2010-03-15 | 2010-03-22 |  | USD | RALP/CS/5/2010 | Dr. Mohamed Ali Hassan Farea Dhamar - Yemen Republic of | 2010-11-10 | 12000 | Completed | First mission (6 months ).
Revised | [9 empty] | NA | NA | NA | NA | NA | NA | NA | NA | N A | NA |  |  |  |  | NA
Actual | [9 empty] | 2010-03-05 | NA | 2010-03-30 | NA | NA | NA | NA | NA | 2010-05-08 | 2010-05-10 |  |  |  |  | 2010-11-10
Planned | 30 | RALP /CS/ 6/2010 | Collection, characterization, evaluation, participatory improvement and conservation of landraces ( SANAA governorate (Renew) 2010 | 24000 | USD | Prior | Firm | SSS | NA | 2009-08-10 | NA | 2009-08-15 | NA | NA | NA | NA | NA | 2009-08-25 | 2009-09-02 |  | USD | RALP/CS/6/2010 | SANA'A UNIVERSITY - FACULTY OF AGRICULTURE Ring Road]. Street Sana'a - Yemen Republic of | 2010-12-31 | 30000 | Completed
Revised | [9 empty] | 2010-01-01 | NA | NA | NA | NA | NA | NA | NA | 2010-01-16 | 2010-01-30 |  |  |  |  | NA
Actual | [9 empty] | 2010-04-24 | NA | NA | NA | NA | NA | NA | NA | 2010-05-22 | 2010-05-29 |  |  |  |  | 2011-01-27
Planned | 31 | RALP /CS/ 7/2010 | Collection, characterization, evaluation, participatory improvement and conservation of landraces ( Lahej governorate (Renew) 2010 | 24000 | USD | Prior | Firm | SSS | NA | 2009-08-10 | NA | 2009-08-15 | NA | NA | NA | NA | NA | 2009-08-25 | 2009-09-02 |  | USD | RALP/CS/7/2010 | ADEN UNIVERSITY - NASSER FACULTY OF AGRICULTURAL SCIENCES Alhwta Lahi Yemen Republic of | 2010-12-31 | 30000 | Completed
Revised | [9 empty] | 2010-01-01 | NA | NA | NA | NA | NA | NA | NA | 2010-01-16 | 2010-01-30 |  |  |  |  | NA
Actual | [9 empty] | 2010-04-24 | NA |  | NA | NA | NA | NA | NA | 2010-05-22 | 2010-05-29 |  |  |  |  | 2011-01-03
Planned | 32 | RALP /CS/ 8/2010 | variety maintenance | 50000 | USD | Prior | Firm | SSS | NA | 2009-07-20 | NA | 2009-07-30 | NA | NA | NA | NA | NA | 2009-08-10 | 2009-08-20 |  | USD | RALP/CS/8/2010 | GENERAL SEEDS MULTIPLICATION CORPORATION (GSMC) West of Gym stadium Dhammar Governorate . Yemen Republic of | 2010-12-31 | 49924 | Completed
Revised | [9 empty] | 2010-01-01 | NA | NA | NA | NA | NA | NA | NA | 2010-01-16 | 2010-01-30 |  |  |  |  | NA
Actual | [9 empty] | 2010-05-24 | NA | NA | NA | NA | NA | NA | NA | 2010-06-08 | 2010-06-09 |  |  |  |  | 2011-02-21
Planned | 33 | RALP /CS/9 /2010 | Seed quality control | 25000 | USD | Prior | Firm | SSS | NA | 2009-07-20 | NA | 2009-08-01 | NA | NA | NA | NA | NA | 2009-08-10 | 2009-10-15 |  | USD | RALP/CS/ 9 /2010 | GENERAL SEEDS MULTIPLICATION CORPORATION (GSMC) West of Gym stadium Dhammar Governorate Yemen Republic of | 2010-12-31 | 0 | The contract terminated the Project notified GSMC on (Jan31,2011) that the contract should terminate as WB Mission suggested (January3-18,2011) and GSMC should return the advance payment (paid ) . The GSMC agreed and returned the advance paid on ( April 18,2011) . the no objection to Terminate the contract received on (June 19,2011).
Revised | [9 empty] | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  |  |  |  | NA
Actual | [9 empty] | 2010-05-18 | NA | NA | NA | NA | NA | NA | NA | 2010-06-20 | 2010-06-22 |  |  |  |  | 2011-01-31
Planned | 34 | RALP /CS/10 /2010 | Collection, characterization, evaluation, participatory improvement and conservation of landraces (Hodeidah governorate ) (Renew) 2010 | 24000 | USD | Prior | Firm | SSS | NA | 2009-08-10 | NA | 2009-08-15 | NA | NA | NA | NA | NA | 2009-08-25 | 2009-09-02 |  | USD | RALP/CS/ 10/2010 | AGRICULTURAL RESEARCH AND EXTENSION AUTHORITY (AREA) Sana'a Road, Dammar Governorate . Yemen Republic of | 2011-06-15 | 30000 | Completed
Revised | [9 empty] | 2010-01-01 | NA | NA | NA | NA | NA | NA | NA | 2010-01-16 | 2010-01-30 |  |  |  |  | NA
Actual | [9 empty] | 2010-04-15 | NA | NA | NA | NA | NA | NA | NA | 2010-06-23 | 2010-06-26 |  |  |  |  | 2012-07-09
Planned | 35 | RALP /CS/11/2010 | Collection, characterization, evaluation, participatory improvement and conservation of landraces (HAJJA governorate (Renew) 2010 | 24000 | USD | Prior | Firm | SSS | NA | 2009-08-10 | NA | 2009-08-15 | NA | NA | NA | NA | NA | 2009-08-25 | 2009-09-02 |  | USD | RALP/CS/ 11 /2010 | AGRICULTURAL RESEARCH AND EXTENSION AUTHORITY (AREA) Sana'a Road, Dammar Governorate . Yemen Republic of | 2011-06-15 | 30000 | Completed
Revised | [9 empty] | 2010-01-01 | NA | NA | NA | NA | NA | NA | NA | 2010-01-16 | 2010-01-30 |  |  |  |  | NA
Actual | [9 empty] | 2010-04-15 | NA | NA | NA | NA | NA | NA | NA | 2010-06-23 | 2010-06-26 |  |  |  |  | 2012-07-09
Planned | 36 | RALP /CS/12 /2010 | Collection, characterization, evaluation, participatory improvement and conservation of landraces ( AL-Mahweet governorate .(Renew) 2010 | 24000 | USD | Prior | Firm | SSS | NA | 2009-08-10 | NA | 2009-08-15 | NA | NA | NA | NA | NA | 2009-08-25 | 2009-09-02 |  | USD | RALP/CS/ 12 /2010 | AGRICULTURAL RESEARCH AND EXTENSION AUTHORITY (AREA) Sana'a Road, Dammar Governorate . Yemen Republic of | 2011-06-15 | 30000 | Completed
Revised | [9 empty] | 2010-01-01 | NA | NA | NA | NA | NA | NA | NA | 2010-01-16 | 2010-01-30 |  |  |  |  | NA
Actual | [9 empty] | 2010-04-15 | NA | NA | NA | NA | NA | NA | NA | 2010-06-23 | 2010-06-26 |  |  |  |  | 2012-07-09
Planned | 37 | RALP /CS/2010 | National Coordinator to Implement Farmer-Based System of Seed Improvement and Management (FBSSIM) - 2nd contract | 14000 | USD | Prior | Individual | SS | NA | NA | NA | NA | NA | NA | NA | NA | NA | 2010-11-01 | 2010-11-12 |  | USD | RALP/CS/13 /2010 | Dr. Mohamed Ali Hassan Farea Dhamar - Yemen Republic of | 2011-05-10 | 25099 | Completed | The Value of the orginal contract was (USD14000) the contract extended during 2011 the NOL dated on ( May16,2011) the Addendum (1) signed on (June 1,2011) the amount of addendum(1) is USD(12000). The Value of contract increased to USD (26000 ).
Revised | [8 empty] | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  |  |  |  | 2011-11-30
Actual | [8 empty] | NA | NA | NA | NA | NA | NA | NA | NA | NA | 2010-11-06 | 2010-11-10 |  |  |  |  | 2011-11-30
Planned | 38 | RALP/ PSU/CS/WB | Recruiting MONITORING AND EVALUATION OFFICER | 14400 | USD | Post | Individual | IC | 2010-09-18 | 2010-10-02 | NA | NA | NA | NA | NA | NA | NA | NA | 2010-12-01 |  | USD | RALP/CS/ 14 /2010 | Eng. Jamil A. Al baddani Sana'a - Republic of Yemen | 2011-11-30 | 12000 | The contract terminated
Revised | [8 empty] | 2010-11-30 | 2010-12-14 | NA | NA | NA | NA | NA | NA | NA | NA | NA |  |  |  |  | NA
Actual | [8 empty] | 2010-08-31 | 2010-10-04 | NA | NA | NA | NA | NA | NA | NA | NA | 2010-12-01 |  |  |  |  | 2011-09-30
Planned | 39 | RALP /CS/WB | Consultant Services for Redesigning of Al-Mokha Quarantine Building - 2nd contract . - ( 3 ) | 15000 | USD | Prior | Individual | SS | NA | 2010-11-25 | NA | NA | NA | NA | NA | NA | NA | 2010-12-18 | 2010-12-25 |  | USD | RALP/CS/ 15 /2010 | YAHIYA MOHAMMED NO'MAN HAMIM Sana'a - Yemen Republic of | 2011-01-24 | 15000 | Completed
Revised | [9 empty] | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  |  |  |  | NA
Actual | [9 empty] | 2010-09-04 | NA | NA | NA | NA | 2010-10-04 | 2010-12-12 | NA | 2010-12-25 | 2010-12-25 |  |  |  |  | 2011-10-01
Planned | 40 | RALP/CS/1/2011 | Survey of Seed Demand and Market Analysis | 50000 | USD | Prior | Individual | IC | NA | 2009-09-10 | NA | 2009-09-15 | NA | NA | NA | NA | NA | 2009-09-27 | 2009-10-03 |  | USD | RALP/CS/ 1 /2011 | Eng. ABDUL HAFEZ AL-HAKIMI Sana'a - Yemen Republic of | 2011-11-17 | 53700 | Completed | The period of contract extended up to February 28, 2012 NOL dated on (March 26,2012 ) the amendment signed on (March 26,2012)
Revised | [9 empty] | 2010-11-20 | NA | 2010-12-10 | NA | NA | 2010-12-28 | 2011-01-04 | 2011-01-14 | 2011-01-21 | 2011-01-28 |  |  |  |  | 2012-02-28
Actual | [9 empty] | 2010-07-07 | NA | 2010-07-13 | NA | NA | 2011-02-13 | 2011-02-27 | 2010-12-26 | 2011-05-09 | 2011-05-10 |  |  |  |  | 2012-07-14
Planned | 41 | RALP/CS/2/2011 | Collection, characterization, participatory improvement of landraces in (Lahej governorate) 2011 | 30000 | USD | Prior | Firm | SSS | NA | 2011-03-20 | NA | 2011-03-27 | NA | NA | 2011-04-01 | 2011-04-11 | NA | 2011-04-18 | 2011-05-06 |  | USD | RALP/CS/ 2 /2011 | ADEN UNIVERSITY - NASSER FACULTY OF AGRICULTURAL SCIENCES Alhwta Lahi Yemen Republic of | 2012-05-17 | 30000 | Completed
Revised | [8 empty] | NA | 2011-03-05 | NA | NA | NA | NA | 2011-05-07 | 2011-05-14 | NA | 2011-05-19 | 2011-05-20 |  |  |  |  | NA
Actual | [8 empty] | NA | 2011-03-05 | NA | NA | NA | NA | 2011-05-07 | 2011-05-08 | NA | 2011-05-19 | 2011-05-19 |  |  |  |  | 2012-06-04
Planned | 42 | RALP/CS/3/2011 | Collection, characterization, participatory improvement of landraces in ( SANAA governorate)(Renew) 2011 | 30000 | USD | Prior | Firm | SSS | NA | 2011-03-20 | NA | 2011-03-27 | NA | NA | 2011-04-01 | 2011-04-11 | NA | 2011-04-18 | 2011-05-06 |  | USD | RALP/CS/ 3 /2011 | SANA'A UNIVERSITY - FACULTY OF AGRICULTURE Ring Road]. Street Sana'a - Yemen Republic of | 2012-05-17 | 34475 | Completed
Revised | [8 empty] | NA | 2011-03-05 | NA | NA | NA | NA | 2011-05-07 | 2011-05-14 | NA | 2011-05-19 | 2011-05-20 |  |  |  |  | NA
Actual | [8 empty] | NA | 2011-03-05 | NA | NA | NA | NA | 2011-05-07 | 2011-05-08 | NA | 2011-05-19 | 2011-05-19 |  |  |  |  | 2012-07-23
Planned | 43 | RALP/CS/4/2011 | Veterinary Institute training program (Technicians &Vocational students) (14) students .) 2011 /2012 | 60000 | USD | Prior | Firm | SSS | NA | 2011-03-20 | NA | 2011-03-27 | NA | NA | 2011-04-01 | 2011-04-15 | NA | 2011-04-20 | 2011-04-27 |  | YER | RALP/CS/ 4 /2011 | Yemeni Veterinary Medicine Association (YVMA), Almithaq Street, , Sana'a - Yemen Republic of | 2012-06-01 | 12990594 | Completed
Revised | [9 empty] | 2011-03-20 | NA | NA | NA | NA | 2011-04-03 | 2011-04-17 | NA | 2011-04-24 | 2011-05-01 |  |  |  |  | NA
Actual | [9 empty] | 2011-03-10 | NA | NA | NA | NA | 2011-03-16 | 2011-05-13 | NA | 2011-06-14 | 2011-06-14 |  |  |  |  | 2012-11-06
Planned | 44 | RALP/CS/44 | Updating the EA/EMP of the Al-Mokha Quarantine | 5000 | USD | Post | Individual | IC | NA | 2012-03-08 | NA | 2012-03-12 | NA | NA | NA | NA | NA | NA | 2012-03-18 |  | USD | RALP/CS/44 | Dr. Khalid Ibrahim Hariri SANA,A Yemen Republic of | 2012-03-31 | 5431 | Completed
Revised | [8 empty] | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  |  |  |  | NA
Actual | [8 empty] | NA | 2012-03-07 | NA | 2012-03-10 | NA | NA | NA | NA | NA | NA | 2012-03-21 |  |  |  |  | 2012-04-23
Planned | 45 | RALP/CS/45 | Seed maintenance and stocks Security of the improved landraces from the SPGs( 2011/2012 ). | 50000 | USD | Prior | Firm | SSS | NA | 2011-05-16 | NA | 2011-05-21 | NA | NA | 2011-05-26 | 2011-06-09 | NA | 2011-06-19 | 2011-07-03 |  | USD | RALP/CS/45 | GENERAL SEEDS MULTIPLICATION CORPORATION (GSMC) West of Gym stadium Dhammar Governorate . Yemen Republic of | 2012-04-30 | 50000 | Completed | IDA's no-objection to the retroactive signing and processing of payment of the contract in reference.
Revised | [8 empty] | NA | 2012-03-28 | NA | NA | NA | NA | 2012-04-04 | 2012-04-18 | NA | 2012-04-28 | 2012-05-05 |  |  |  |  | NA
Actual | [8 empty] | NA | 2011-05-21 | NA | NA | NA | NA | 2011-05-22 | 2011-06-19 | NA | 2012-08-30 | 2011-04-30 |  |  |  |  | 2012-04-30
Planned | 46 | RALP/CS/46 | Preparing drafting legislation & regulations of Seed Quality Control . (national consultant) | 11266 | USD | Post | Individual | IC | NA | 2011-05-16 | NA | NA | NA | NA | 2011-05-23 | 2011-06-06 | NA | NA | 2011-06-13 |  | USD | RALP/CS/46 | Dr. Abbas Ahmed Abdlrahman Bawazir Having it is principal office located at: Khormaksar, Aden Yemen Republic of | 2013-05-18 | 15760 | Completed
Revised 1 | [8 empty] | NA | 2012-03-28 | NA | NA | NA | NA | NA | NA | NA | NA | 2012-04-14 |  |  |  |  | NA
Revised 2 | [8 empty] | NA | 2012-06-30 | NA | NA | NA | NA | NA | NA | NA | NA | 2012-07-16 |  |  |  |  | NA
Actual | [8 empty] | NA | 2012-07-18 | NA | NA | NA | NA | NA | NA | NA | NA | 2013-02-09 |  |  |  |  | 2013-06-11
Planned | 47 | RALP/CS/47 | Recruitment of a MONITORING AND EVALUATION OFFICER(New ) | 5600 | USD | Post | Individual | IC | NA | 2012-03-14 | NA | NA | NA | NA | NA | NA | NA | NA | 2012-03-31 |  |  |  |  | 2012-07-29 |  | shifted to ACAP Project
Revised | [8 empty] | NA | 2012-06-30 | NA | NA | NA | NA | NA | NA | NA | NA | 2012-07-16 |  |  |  |  | 2014-06-30
Actual | [8 empty] | NA | 2012-08-01 | NA | NA | NA | NA | NA | NA | NA | NA
Planned | 48 | RALP/CS/48 | Collection, characterization, evaluation, participatory improvement and conservation of landraces ( Hodeidah governorate (Renew) 2012/2013 | 30000 | USD | Prior | Firm | SSS | NA | 2011-05-16 | NA | 2011-05-21 | NA | NA | 2011-05-26 | 2011-06-09 | NA | 2011-06-19 | 2011-07-03 |  | USD | RALP/CS/48 | AGRICULTURAL RESEARCH AND EXTENSION AUTHORITY (AREA) Sana'a Road, Dammar Governorate . Yemen Republic of | 2013-09-01 | 21000 | Completed | The completion date extended from Sep 1, 2013 to December 31, 2013 NOL on 22/8/2013 and the amendment of the contract signed on 25/8/2013
Revised | [8 empty] | NA | 2012-06-30 | NA | NA | NA | NA | 2012-07-07 | 2012-07-14 | NA | 2012-07-23 | 2012-07-30 |  |  |  |  | 2013-12-31
Actual | [8 empty] | NA | 2012-07-15 | NA | NA | NA | NA | 2012-07-16 | 2012-08-01 | NA | 2012-08-27 | 2012-09-01
Planned | 49 | RALP/CS/49 | Collection, characterization, evaluation, participatory improvement and conservation of landraces (Hajja governorate )(Renew) 2012/2013 | 30000 | USD | Prior | Firm | SSS | NA | 2011-05-16 | NA | 2011-05-21 | NA | NA | 2011-05-26 | 2011-06-09 | NA | 2011-06-19 | 2011-07-03 |  | USD | RALP/CS/49 | AGRICULTURAL RESEARCH AND EXTENSION AUTHORITY (AREA) Sana'a Road, Dammar Governorate . Yemen Republic of | 2013-09-01 | 21000 | Completed | The completion date extended from Sep 1, 2013 to December 31, 2013 NOL on 22/8/2013 and the amendment of the contract signed on 25/8/2013
Revised | [8 empty] | NA | 2012-06-30 | NA | NA | NA | NA | 2012-07-07 | 2012-07-14 | NA | 2012-07-23 | 2012-07-30 |  |  |  |  | 2013-12-31
Actual | [8 empty] | NA | 2012-07-15 | NA | NA | NA | NA | 2012-07-16 | 2012-08-01 | NA | 2012-08-27 | 2012-09-01
Planned | 50 | RALP/CS/50 | Landraces Participatory improvement in (AL-Mahweet governorate ( 2012/2013 ). | 20000 | USD | Prior | Firm | SSS | NA | 2011-05-16 | NA | 2011-05-21 | NA | NA | 2011-05-26 | 2011-06-09 | NA | 2011-06-19 | 2011-07-03 |  | USD | RALP/CS/50 | AGRICULTURAL RESEARCH AND EXTENSION AUTHORITY (AREA) Sana'a Road, Dammar Governorate . Yemen Republic of | 2013-09-01 | 14000 | Completed | The completion date extended from Sep 1, 2013 to December 31, 2013 NOL on 22/8/2013 and the amendment of the contract signed on 25/8/2013
Revised | [8 empty] | NA | 2012-06-30 | NA | NA | NA | NA | 2012-07-07 | 2012-07-14 | NA | 2012-07-23 | 2012-07-30 |  |  |  |  | 2013-12-31
Actual | [8 empty] | NA | 2012-07-15 | NA | NA | NA | NA | 2012-07-16 | 2012-08-01 | NA | 2012-08-27 | 2012-09-01
Planned | 51 | RALP/CS/51 | Collection, characterization, evaluation, participatory improvement and conservation of landraces (Lahej governorate).( 2012/2013 ). | 35000 | USD | Prior | Firm | SSS | NA | 2012-06-30 | NA | NA | NA | NA | 2012-07-07 | 2012-07-14 | NA | 2012-07-23 | 2012-07-30 |  | USD | RALP/CS/51 | ADEN UNIVERSITY - NASSER FACULTY OF AGRICULTURAL SCIENCES Alhwta P.O. BOX: 10044 Lahi - Yemen Republic of | 2013-07-30 | 35000 | Completed
Revised | [8 empty] | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  |  |  |  | NA
Actual | [8 empty] | NA | 2012-07-08 | NA | NA | NA | NA | 2012-07-09 | 2012-07-16 | NA | 2012-07-26 | 2012-07-28 |  |  |  |  | 2013-06-24
Planned | 52 | RALP/CS/52 | Landraces participatory improvement SANA, A Governorate (2012 /2013) | 35000 | USD | Prior | Firm | SSS | NA | 2012-06-30 | NA | NA | NA | NA | 2012-07-07 | 2012-07-14 | NA | 2012-07-23 | 2012-07-30 |  | USD | RALP/CS/52 | SANA'A UNIVERSITY - FACULTY OF AGRICULTURE Ring Road]. Street Sana'a - Yemen Republic of | 2013-07-30 | 34025 | Completed
Revised | [8 empty] | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  |  |  |  | NA
Actual | [8 empty] | NA | 2012-07-08 | NA | NA | NA | NA | 2012-07-09 | 2012-07-25 | NA | 2012-07-29 | 2012-07-30 |  |  |  |  | 2013-12-05
Planned | 53 | RALP/CS/53 | Seed maintenance and stocks Security of the improved landraces from the SPGs.( 2012/2013 ). | 50000 | USD | Prior | Firm | SSS | NA | 2012-06-30 | NA | NA | NA | NA | 2012-07-07 | 2012-07-14 | NA | 2012-07-23 | 2012-07-30 |  | USD | RALP/CS/53 | GENERAL SEEDS MULTIPLICATION CORPORATION (GSMC) West of Gym stadium Dhammar Governorate . Yemen Republic of | 2013-07-30 | 50000 | Completed
Revised | [8 empty] | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  |  |  |  | NA
Actual | [8 empty] | NA | 2012-07-08 | NA | NA | NA | NA | 2012-07-09 | 2012-07-18 | NA | 2012-07-28 | 2012-07-29 |  |  |  |  | 2013-07-23
Planned | 54 | RALP/CS/54 | Construction Supervision of AL- Mocha quarantine at Al -mocha district in Taiz Governorate | 140000 | USD | Prior | Firm | QCBS | NA | 2009-03-20 | NA | NA | NA | NA | 2009-04-03 | 2009-04-17 | NA | NA | 2009-05-01 |  | USD | RALP/CS/54 | Al-Amidah Consult (AMICON) Al -Qiadeh Street Sana'a - Yemen Republic of | 2014-03-31 | 165718.25 | On going | Addendum(1) : The contract amount increased from (USD 122,065) to (USD140,271.7) due to Append activity (Doing and Implementing Survey & Design works for the new Site Project General Location)) for estimated ( 18,206.7) Including Local Tax, NOL dated on Feb 28,2013 ) the amendment signed on (March 2,2013) . Addendum 2: The contract amount increased from USD140,271.7 to USD 185012 , The NOL dated on November 22,2013 ) the amendment signed on ( November 26,2013 ).Due to Prepared the designs for Roads , irrigation network and new sheep Pens .and Extended the Period from 15 Months to 18 Months.
Revised 1 | [8 empty] | 2011-02-22 | 2011-03-08 | 2011-03-15 | NA | NA | 2011-03-29 | 2011-04-05 | 2011-05-20 | 2011-05-25 | 2011-05-30 | 2011-06-06 |  |  |  |  | 2014-06-30
Revised 2 | [8 empty] | 2011-03-15 | 2011-03-29 | 2011-04-05 | NA | NA | 2011-04-19 | 2011-04-26 | 2011-06-10 | 2011-06-20 | 2011-06-25 | 2011-07-30
Revised 3 | [8 empty] | 2012-08-14 | 2012-08-28 | 2012-09-08 | NA | NA | 2012-09-22 | 2012-09-29 | 2012-10-31 | 2012-11-07 | 2012-11-26 | 2012-12-10
Revised 4 |  |  |  | 113940 | USD |  |  | CQS | NA | 2012-10-16 | NA | NA | NA | NA | NA | NA | 2012-11-15 | 2012-11-22 | 2012-11-29
Actual | [8 empty] | NA | 2012-10-17 | NA | 2012-10-21 | NA | NA | 2012-11-19 | 2012-11-20 | 2012-11-18 | 2012-12-03 | 2012-12-04
Planned | 55 | RALP/CS/55 | National coordinator to implement RALP, S First component (Farmer - based system of seed improvement and management) 2012/2013 | 34000 | USD | Prior | Individual | SSS | NA | 2012-01-01 | NA | NA | NA | NA | NA | NA | NA | 2012-01-15 | 2012-01-22 |  | USD | RALP/CS/55 | Dr. Mohamed Ali Hassan Farea Dhamar - Yemen Republic of | 2013-10-01 | 24000 | Completed
Revised | [8 empty] | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  |  |  |  | NA
Actual | [8 empty] | NA | 2012-07-18 | NA | NA | NA | NA | NA | NA | NA | 2012-09-27 | 2012-10-01 |  |  |  |  | 2013-10-01
Planned | 56 | RALP/CS/56 | Communication Officer | 22500 | USD | Post | Individual | IC | NA | 2012-12-01 | NA | NA | NA | NA | NA | NA | NA | NA | 2012-12-31 |  | USD | RALP/CS/56 | Mr. Salah Ahmed Ali Almashraqi Rada Street Dhamar - Yemen Republic of | 2014-04-06 | 10800 | On going
Revised | [7 empty] | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 2013-12-31 |  |  |  |  | 2014-04-30
Actual | [7 empty] | IC | NA | 2012-11-25 | NA | NA | NA | NA | 2014-01-06 | 2014-01-18 | NA | NA | 2014-02-02
Planned | 57 | RALP/CS/57 | Technical Expertise for Preparation of Operation and Management Arrangements for New Al-Mukha Quarantine for Live Animals | 27084 | USD | Post | Individual | IC | NA | 2014-02-20 | NA | 2014-03-06 | NA | NA | NA | NA | NA | NA | 2014-04-21 |  | USD | RALP/CS/57 | David Fleming, DVM Locust Grove, OK 74352 | 2013-10-10 | 29730 | Completed
Revised | [8 empty] | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  |  |  |  | NA
Actual | [8 empty] | NA | 2013-05-25 | NA | 2013-05-29 | NA | NA | 2013-06-18 | 2013-07-27 | NA | NA | 2013-08-14 |  |  |  |  | 2013-09-30
Planned | 58 | RALP/CS/58 | Consultancy Services on Capacity Building and Technical Backstopping for the Following Project First comp. (Sub-Components: (1.1) Landrace Improvement and Maintenance; (1.2) Promotion of Seed Producer Groups; - (2) (2013) | 58824 | USD | Prior | Firm | SSS | NA | NA | NA | NA | NA | NA | NA | 2013-01-05 | NA | 2013-01-30 | 2013-02-03 |  | USD | RALP/CS/58 | International Centre for Agriculture Research in the Dry Areas (ICARDA) Aleppo- Syria | 2013-12-31 | 58824 | Completed
Revised | [8 empty] | NA | NA | NN | NA | NA | NA | NA | NA | NA | NA | NA |  |  |  |  | NA
Actual | [8 empty] | NA | NA | NA | NA | NA | NA | NA | 2013-03-04 | NA | 2013-04-16 | 2013-04-20 |  |  |  |  | 2014-02-03
Planned | 59 | RALP/CS/59 | Consultancy Services on Technical Assistance to MAI - Preparation of a proposal for the Global Agriculture and Food Security Program (GAFSP) | 17400 | USD | Prior | Individual | SSS | NA | 2013-03-15 | NA | NA | NA | NA | NA | NA | NA | 2013-04-01 | 2013-04-05 |  | USD | RALP/CS/592013 | Mr. Christopher Ward The Old Vicarage Hennock Devon TQ13 9QD England | 2013-06-30 | 18913 | Completed
Revised | [8 empty] | NA | NA | NN | NA | NA | NA | NA | NA | NA | NA | NA |  |  |  |  | NA
Actual | [8 empty] | NA | 2013-03-29 | NA | NA | NA | NA | NA | NA | NA | 2013-04-17 | 2013-04-17 |  |  |  |  | 2013-06-10
Planned | 60 | RALP/CS/60 | International Consultant support to stakeholder consultations on Yemen’s agriculture and food security strategy and associated investment plan on Yemen’s 2013 project proposal for GAFSP financing | 26235 | USD | Prior | Individual | SSS | NA | 2013-04-25 | NA | 2013-04-26 | NA | NA | NA | NA | NA | 2013-04-26 | 2013-04-26 |  | USD | RALP/CS/61/2013 | Mrs. Helen Lackner 42 Marston Street, Oxford OX4 1JU, UK | 2013-05-17 | 26235 | Completed
Revised | [8 empty] | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  |  |  |  | NA
Actual | [8 empty] | NA | 2013-04-25 | NA | 2013-04-26 | NA | NA | NA | NA | NA | 2013-04-26 | 2013-04-27 |  |  |  |  | 2013-05-29
Planned | 61 | RALP/CS/61 | National Consultant support to stakeholder consultations on Yemen’s agriculture and food security strategy and associated investment plan on Yemen’s 2013 project proposal for GAFSP financing | 6900 | USD | Prior | Individual | SSS | NA | 2013-04-25 | NA | 2013-04-26 | NA | NA | NA | NA | NA | 2013-04-26 | 2013-04-26 |  | USD | RALP/CS/62/2013 | Prof. Dr. Eng. Omar Hassan Al-Sakaf Sana'a, Yemen Republic of | 2013-05-27 | 6900 | Completed
Revised | [8 empty] | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  |  |  |  | NA
Actual | [8 empty] | NA | 2013-04-25 | NA | 2013-04-26 | NA | NA | NA | NA | NA | 2013-04-26 | 2013-04-27 |  |  |  |  | 2013-05-25
Planned | 62 | RALP/CS/62 | Beneficiary Assessment Survey (BAS) | 65000 | USD | Post | Firm | CQS | 2014-08-01 | 2014-07-25 | NA | 2014-07-30 | NA | NA | 2014-08-04 | 2014-08-11 | NA | NA | 2014-08-16 |  |  |  |  | 2014-09-30
Revised
Actual
Planned | 63 | RALP/CS/63 | Preparing the Implementation Completion Report (ICR ) from Borrower Perspective. | 70000 | USD | Post | Firm | CQS | 2014-09-01 | 2014-08-25 | NA | 2014-08-30 | NA | NA | 2014-10-11 | 2014-10-16 | NA | NA | 2014-12-20 |  |  |  |  | 2015-02-18
Revised
Actual
Exceptional cases :
| N# | Description
| -1 | YVMA AGREEMENT was even mentioned in project (PAD)
| -2 | ICARDA IS the only research center specialized on such activities Moreover this agreement was even mentioned in pad project (PAD)
| -3 | Tasks are continuation of previous work that consultant has carried out and the consultant was selected competitively
NOTE: All SSS shall be initiated only after specific clearance from the Bank
Formulas:
TOR/Shortlist to be Finalised (Date) = [Advertising for Short listing (Date)]+14
TOR/Shortlist to be Finalised (Date) = [Advertising for Short listing (Date)]-7
NA = [TOR/Shortlist to be Finalised (Date)]+7
NA = [No Objection from Bank for TOR (Date)**]+15
Contract Signed (Date) = [NA]+7
Contract Signed (Date) = [TOR/Shortlist to be Finalised (Date)]+30
Services Completion (Date) = [Contract Signed (Date)]+30
RFP Issued (Date) = [NA]+7
RFP Issued (Date) = [No Objection from Bank for TOR (Date)**]+18
Proposal Submission Deadline (Date) = [RFP Issued (Date)]+30
Advertising for Short listing (Date) = [NA]-14
Advertising for Short listing (Date) = [TOR/Shortlist to be Finalised (Date)]+7
No Objection from Bank for TOR (Date)** = [TOR/Shortlist to be Finalised (Date)]+7

## Capacity Building
Procurement Plan for Capacity Building Activities
| YEMEN P089259 : Rainfed Agricuture and Livestock Project (RALP) IDA Cr.#4220/Yem |  | YEMEN P089259 : Rainfed Agricuture and Livestock Project (RALP) IDA Cr.#4220/Yem
component/SUBCOMBONENT | kind of training | SL No. | Expected Outcome/ Activity Description | Estimated Cost | Currency of Estimated Cost | Estimated Duration | Start Date | Completion Date | actual cost | Actual Duration | Actual Start Date | ActualCompletion Date | Comments
livestock husbandry and health servies(strenthingthe GDAR Core Function) | Participation to international veterinary events | 1 | Annual Conference for Animal Genetic Resources |  | USD | 5days | 2009-01-26 | 2009-01-30 | 1100 | 6 | 2009-01-26 | 2009-01-30 | Romme-Italy | done
|  | 2 | 77th General Session international committee of the OIE ( 2009) |  | USD | 7 days | 2009-05-24 | 2009-05-29 | 1880 | 8 | 2009-05-24 | 2009-05-29 | Paris -France | done
|  | 3 | 78 General Session of the OIE -( 2010) |  | USD | 7 days | 2010-05-23 | 2010-05-28 | 1761 | 7 | 2010-05-23 | 2010-05-28 | Paris -France | done
|  | 4 | Codex Alimentations ( Committee in contaminants in foods )-2010 (1 person ). |  | USD | 7days | 2010-04-26 | 2010-04-30 | 2026 | 7 | 2010-04-26 | 2010-04-30 | Azmir -Turkey | done
|  | 5 | Workshop on policies and regulations |  | USD | 3 day | 2009-02-15 | 2009-02-18 | 17075 | 1 day | 2009-04-07 | 2009-04-08 | Sanaa | done
|  | 6 | Workshop on animal production(trainer trainsPRA ) Taiz |  | USD | 3days | 2009-05-17 | 2009-05-20 | 5286 | 3days | 2009-05-17 | 2009-05-20 | TAIZ-Hodiedah-Hajjah GOV. | done
|  | 7 | Workshop on epidemiosurveillance PADZI - TAIZ |  | USD | 2 days | 2009-04-21 | 2009-04-22 | 799 | 2days | 2009-04-21 | 2009-04-22 | TAIZ | done
|  | 8 | Workshop on animal production(trainer trainsPRA ) |  | USD | 3days | 2010-07-19 | 2010-07-22 | 5261 | 3days | 2010-07-19 | 2010-07-22 | (sanaa,amran,dhmar,mareb) | done
|  | 9 | Workshop on epidemiosurveillance |  | USD | 3days | 2011-07-17 | 2011-07-19 |  |  |  |  | Sanaa | done
|  | 10 | Workshop on policies and regulations |  | USD | 2days | 2010-12-07 | 2010-12-08 | 19700 | 2 days | 2010-12-11 | 2010-12-12 | Sanaa | done
|  | 11 | English courses for technical staff for CVL 10 Persons |  | USD | 12 months | 2010-02-20 | 2011-02-20 |  |  |  |  | Exceed language centre / Sana,a | done
|  | 12 | English training ( 2)Techical staff at AL-Mocha Quarantine Dr.derhim shmsan &Dr.mohammed AL-mohamadi |  | USD | 12 months | 2010-12-01 | 2011-12-01 |  |  |  |  | Modern American Language institute (MALI ) Taiz | done
|  | 13 | Training Program for (procurement assistant) on (Works Procurement Management Course ) |  | USD | 18 DAYS | 2010-07-05 | 2010-07-23 |  |  |  |  | GHANA INSTITUTE OF MANAGEMENT AND PUPLIC ADMINISTRATION (GIMPA)) | done
|  | 14 | Training Program for (procurement specialist) on (Selection and Recruitment of Consultants in World Bank -Funded Projects |  | USD | 7 days | 2010-11-15 | 2010-11-19 |  |  |  |  | International Training Centre of the ILO Turin - Italy | done
|  | 15 | Stockholder consultation & workshops in support of the updating Yemen's agriculture &food security, associated investment plans & preparation of 2013 GAFSP proposal |  | USD | 10 days | 2013-05-08 | 2013-05-18 |  |  |  |  | several workshops | done
|  | 16 | 81 General Session of the OIE 2013 |  | USD | 7 days | 2013-05-26 | 2013-05-31 |  |  |  |  | Paris -France | done
|  | 17 | Study tour to Visit Djibouti quarantine |  | YER | 5 Days | 2013-04-30 | 2013-05-04 |  |  |  |  | The Minister & Yasser | done
Formulas:
Completion Date = [Start Date]+4
ActualCompletion Date = [Actual Start Date]+4