Procurement Plan for

Shanxi Coal Bed Methane (CBM) Development and Utilization Project

(2014.1.14)

## I. I.Contracts Funded by World Bank

### 1) Goods

| Contract No. | Description | Estimated Cost (10,000 US$) | Contract value (10,000 US$) | Procurement metho | Review Method by Bank | Expected Date for Bidding Document Review by the Bank | Expected Bid Opening Time | Expected Contract Signing Date | Actual Contract Signing Date | Progress |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Liquefaction project |
| GL1 | Nitrogen compressor unit | 123.7 | 186.03 | ICB | Prior | 2010.06 | 2010.11 |  | 2011.4 | Contract signed |
| GL2 | Expander compressor unit | 190.0 | 256.83 | ICB | Prior | 2010.06 | 2010.11 |  | 2011.4 | Contract signed |
| GL3 | Cold box | 48.9 | 24.13 | NCB | Prior | 2010.06 | 2010.11 |  | 2011.4 | Contract signed |
| GL4 | LCBM storage tank | 164.4 | 267.46 | ICB | Prior | 2010.11 | 2011.01 |  | 2011.05 | Contract signed |
| GL5 | Control valves | 19.1 | 12.74 | ICB | Prior | 2010.11 | 2011.01 |  | 2011.05 | Contract signed |
| GL6 | Switch valves | 22.2 | 16.67 | ICB | Prior | 2010.11 | 2011.01 |  | 2011.05 | Contract signed |
| GL7 | Molecular sieve switch valves | 36.0 | 36.19 | ICB | Prior | 2010.11 | 2011.01 |  | 2011.05 | Contract signed |
| GL8 | LCBM loading pump | 12.9 | 23.47 | ICB | Prior | 2010.11 | 2011.01 |  | 2011.05 | Contract signed |
| GL9 | China-made control valves | 47.5 | 6.22 | ICB | Post |  | 2011.06 |  | 2011.08 | Contract signed |
| GL10 | Air compressor unit | 13.5 | 3.94 | NCB | Post |  | 2011.06 |  | 2011.08 | Contract signed |
| GL11 | Re-heater | 15.6 | 2.67 | NCB | Post |  | 2011.06 |  | 2011.08 | Contract signed |
| GL12 | Co2 removal system pump | 10.4 | 10.40 | NCB | Post |  | 2011.06 |  | 2011.08 | Contract signed |
| GL13 | Flare system | 37.4 | 18.89 | NCB | Post |  | 2011.06 |  | 2011.08 | Contract signed |
| GL14 | Fire-fighting pump | 16.5 | 23.51 | NCB | Post |  | 2011.06 |  | 2011.08 | Contract signed |
| GL15 | Cold/Warm water unit | 12.2 | 18.04 | NCB | Post |  | 2011.06 |  | 2011.08 | Contract signed |
| GL16 | Filters | 7.3 | 22.07 | Shopping | Prior | 2011.05 | 2011.07 |  | 2011.10 | Contract signed |
| GL18 | PSA nitrogen unit | 7.9 | 2.50 | Shopping | Post |  | 2011.07 |  | 2011.10 | Contract signed |
| GL19 | Recycled gas heater | 7.9 | 10.00 | Shopping | Post |  | 2011.07 |  | 2011.10 | Contract signed |
| GL20 | Rich/Lean amine heat exchanger | 0.7 | 0.48 | Shopping | Post |  | 2011.07 |  | 2011.10 | Contract signed |
| GL21 | Turbo flow meters | 5.4 | 2.50 | Shopping | Post |  | 2011.07 |  | 2011.10 | Contract signed |
| GL22 | Recycled gas pressure booster | 8.6 | 6.75 | Shopping | Post |  | 2011.07 |  | 2011.10 | Contract signed |
| GL24 | Liquid nitrogen storage tank | 3.5 | 4.37 | Shopping | Post |  | 2011.07 |  | 2011.10 | Contract signed |
| GL25 | Non-standard pressure vessels | 28.4 | 39.65 | NCB | Post |  | 2011.06 |  | 2011.08 | Contract signed |
| GL26 | Meters | 13.9 | 14.84 | NCB | Post |  | 2011.06 |  | 2011.08 | Contract signed |
| GL27 | DCS system | 30 | 28.05 | Shopping | Post |  | 2011.07 |  | 2012.02 | Contract signed |
| GL29 | Stainless pipelines | 37.62 | 25.56 | NCB | Post |  | 2012.02 |  | 2012.03 | Contract signed |
| GL30 | Carbon steel pipelines | 90.32 | 64.13 | NCB | Post |  | 2012.02 |  | 2012.03 | Contract signed |
| GL31 | Power cables | 87.3 | 129.59 | NCB | Prior | 2012.04 | 2012.05 |  | 2012.06 | Contract signed |
| GL32 | Bridges | 18.41 | 9.22 | NCB | Post |  | 2012.05 |  | 2012.05 | Contract signed |
| GL33 | Coolers | 3.8 | 16.79 | Shopping | Post |  | 2011.07 |  | 2011.10 | Contract signed |
| GL34 | Circulating water cooling system | 9.2 | 10.25 | Shopping | Post |  | 2011.07 |  | 2011.10 | Contract signed |
| GL35 | Water treatment unit | 4.2 | 4.69 | Shopping | Post |  | 2011.07 |  | 2011.10 | Contract signed |
| GL36 | Air conditioning system | 1.0 | 2.46 | Shopping | Post |  | 2011.07 |  | 2011.10 | Contract signed |
| GL37 | Power distribution rack | 20.63 | 18.33 | NCB | Post |  | 2012.05 |  | 2012.06 | Contract signed |
| GL38 | Power generator unit | 8.6 | 12.01 | Shopping | Post |  | 2012.11 |  | 2012.12 | Contract signed |
| GL39 | Valves | 47.62 | 95.08 | NCB | Post |  | 2012.02 |  | 2012.03 | Contract signed |
| GL40 | Fire fighting devices | 2.38 | 4.4 | Shopping | Post |  | 2012.11 |  | 2012.12 | Contract signed |
| GL41 | Online analysis instruments | 9.52 | 4.2 | Shopping | Post |  | 2012.11 |  | 2012.12 | Contract signed |
| GL42 | Lab analysis instruments | 4.76 | 4.13 | Shopping | Post |  | 2012.11 |  | 2012.12 | Contract signed |
| GL43 | Monitoring devices | 9 | 9.43 | Shopping | Post |  | 2012.11 |  | 2012.12 | Contract signed |
| GL45 | Loading arm | 15.87 | 13.33 | NCB | Post |  | 2012.05 |  | 2012.06 | Contract signed |
| GL46 | Meter wires | 71.43 | 79.1 | NCB | Prior | 2012.04 | 2012.05 |  | 2012.06 | Contract signed |
| Development project |
| GD01 | Pumping unit | 605.14 |  | ICB | Prior | 2014.04 | 2014.06 | 2014.06 |  | Bidding document still in preparation |
| GD02 | oil pipe | 397.09 |  | ICB | Prior | 2014.03 | 2014.05 | 2014.05 |  | Bidding document still in preparation |
| GD03 | Compressor unit for station | 278.1 |  | Direct Contracting | Prior |  |  | 2014.02 |  |  |
| GD04 | Gas flow line | 235.50 |  | NCB | Post |  | 2014.06 | 2014.06 |  | Bidding document still in preparation |
| GD05 | Automatic system for well site | 233.53 |  | NCB | Post |  | 2014.07 | 2014.07 |  | Bidding document still in preparation |

### 2) Works

| Contract No. | Description | Estimated Cost (US$ 10,000) | Actual Contract Value (US$ 10,000) | Procurement Method | Prequalification (Yes/No) | Review Method by Bank | Expected Date for Bidding Document Review by the Bank | Expected Bid Opening Time | Expected Contract Signing Date | Progress |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| WL1 | Installation contract for NO.1 LNG Plant | 349.21 | 140.97 | NCB | No | Post |  | 2012.02 | 2012.03 | Contract signed |
| WL2 | EPC contract for the second process plant | 4428.57 |  | ICB | No | Prior | 2014.01 | 2014.03 | 2014.04 | Bidding document still in preparation |

## II. Procurement plan with counterpart fund

| No. | Description | Cost (10,000 CNY) | Time | Procurement Method | Progress |
| --- | --- | --- | --- | --- | --- |
| liquefaction project |
| YH01 | Design of first process train | 360 | 2008.04 | Open bidding | Contract signed |
| YH02 | Site survey of plant | 51.56 | 2008.12 | Open bidding | Contract signed |
| YH03 | Technical support | 400 | 2009.04 | No bidding | Contract signed |
| YH04 | Design of road and bridges | 12.66 | 2010.01 | Selective bidding | Contract signed |
| YH05 | Design of anti-flood dam and flood discharge trench | 33.06 | 2010.01 | Selective bidding | Contract signed |
| YH06 | Soil and water conservation resolution for the plant | 19 | 2010.01 | Selective bidding | Contract signed |
| YH07 | Civil works of plant | 4298.138 | 2010.09 | Open bidding | Contract signed |
| YH08 | Supervision fee for the civil works of first process train | 84 | 2010.09 | Open bidding | Contract signed |
| YH09 | Installation supervision fee for the first process train | 54.38 | 2011.06 | Open bidding | Contract signed |
| YH10 | Review of safe system design | 60 | 2011.06 | Open bidding | Contract signed |
| YH11 | Design of network power supply | 145.9 | 2011.06 | Open bidding | Contract signed |
| YH12 | Anti-flood dam, road and bridges, and process train foundation | 2893.63 | 2011.10 | Open bidding | Contract signed |
| YH13 | Color coated steel for the plant and Steel construction | 1239.63 | 2012.05 | Open bidding | Contract signed |
| YH14 | 35 KV Power Transmission and Distribution Engineering | 3025 | 2013.12 | Open bidding | Bidding document still in preparation |
| YH15 | Pump | 13.9 | 2011.07 | Open bidding | Contract signed |
| YH16 | PMC contract for the second process train of Shanxi CBM Pro | 887.5418 | 2013.04 | Open bidding | Contract signed |
| YH17 | supervision for 35 KV Power Transmission and Distribution Engineering | 66.84 | 2014.01 | Open bidding | Bidding document still in preparation |
| Development project (construction ) |
| KF01 | Phase ⅰ Biddings for pre-drilling of 20 trial wells | 41.09 | 2012.09 | Open bidding | Contract signed |
| KF02 | Phase ⅱBiddings for pre-drilling of 20 trial wells | 39.15 | 2012.09 | Open bidding | Contract signed |
| KF03 | Phase ⅲBiddings for pre-drilling of 20 trial wells | 41.76 | 2012.09 | Open bidding | Contract signed |
| KF04 | Phase ⅰ Biddings for drilling of 20 trial wells | 278.16 | 2012.10 | Open bidding | Contract signed |
| KF05 | Phase ⅱBiddings for drilling of 20 trial wells | 241.50 | 2012.10 | Open bidding | Contract signed |
| KF06 | Phase ⅲBiddings for drilling of 20 trial wells | 283.02 | 2012.10 | Open bidding | Contract signed |
| KF07 | Drilling supervision of 20 trial wells | 15.70 | 2012.10 | Open bidding | Contract signed |
| KF08 | Well logging engineering of 20 trial wells | 60.00 | 2012.10 | Open bidding | Contract signed |
| KF09 | Phase ⅰ Biddings for cementing engineering of 20 trial wells | 50.00 | 2012.10 | Open bidding | Contract signed |
| KF10 | Phase ⅱ Biddings for cementing engineering of 20 trial wells | 50.00 | 2012.10 | Open bidding | Contract signed |
| KF11 | Underground engineering of 20 trial wells | 57.22 | 2012.10 | Open bidding | Contract signed |
| KF12 | Mud curing of 20 trial wells | 26.00 | 2012.10 | Open bidding | Contract signed |
| KF13 | Fracturing engineering of 20 trial wells | 563.35 | 2012.10 | Open bidding | Contract signed |
| KF14 | Phase ⅰ Biddings for pumping engineering of 20 trial wells | 72.26 | 2012.10 | Open bidding | Contract signed |
| KF15 | Phase ⅱ Biddings for pumping engineering of 20 trial wells | 72.53 | 2012.10 | Open bidding | Contract signed |
| KF16 | Engineering supervision of 20 trial wells | 24.39 | 2012.10 | Open bidding | Contract signed |
| KF17 | Perforation engineering of 20 trial wells | 33.58 | 2012.10 | Open bidding | Contract signed |
| KF18 | surface engineering design | 448.00 | 2013.10 | Open bidding | contract negotiation |
| KF19 | Stage I for pre-drilling | 233.80 | 2013.10 | Open bidding | contract negotiation |
| KF20 | Stage II for pre-drilling | 278.27 | 2013.10 | Open bidding | contract negotiation |
| KF21 | Stage III for pre-drilling | 285.18 | 2013.10 | Open bidding | contract negotiation |
| KF22 | drilling supervisor | 518.00 | 2013.10 | Open bidding | contract negotiation |
| KF23 | Stage I for drilling | 2058.76 | 2013.11 | Open bidding | Bidding in progress |
| KF24 | Stage II for drilling | 1759.07 | 2013.11 | Open bidding | Bidding in progress |
| KF25 | Stage III for drilling | 2230.03 | 2013.11 | Open bidding | Bidding in progress |
| KF26 | Stage IV for drilling | 2210.26 | 2013.11 | Open bidding | Bidding in progress |
| KF27 | Stage V for drilling | 1915.23 | 2013.11 | Open bidding | Bidding in progress |
| KF28 | Stage VI for drilling | 1990.58 | 2013.11 | Open bidding | Bidding in progress |
| KF29 | Stage I of cementing | 620 | 2013.11 | Open bidding | Completion of the tender |
| KF30 | Stage II of cementing | 661.25 | 2013.11 | Open bidding | Completion of the tender |
| KF31 | Stage I of Underground Engineering | 232.4 | 2013.11 | Open bidding | Bidding in progress |
| KF32 | Stage II of Underground Engineering | 232.4 | 2013.11 | Open bidding | Bidding in progress |
| KF33 | Stage III of Underground Engineering | 232.4 | 2013.11 | Open bidding | Bidding in progress |
| KF34 | Engineering supervision | 224.54 | 2013.11 | Open bidding | Bidding in progress |
| KF35 | Logging cost | 861.3 | 2013.11 | Open bidding | Completion of the tender |
| KF36 | Stage I of Perforation | 212.2 | 2013.11 | Open bidding | Completion of the tender |
| KF37 | Stage II of Perforation | 227.48 | 2013.11 | Open bidding | Completion of the tender |
| KF38 | Stage I of fracturing | 2318.74 | 2013.11 | Open bidding | Completion of the tender |
| KF39 | Stage II of fracturing | 2319.44 | 2013.11 | Open bidding | Completion of the tender |
| KF40 | Stage III of fracturing | 2141.4 | 2013.11 | Open bidding | Bidding in progress |
| KF41 | Horizontal well drilling and extraction outsourcing | 15450 | 2013.11 | Open bidding | Bidding in progress |
| KF42 | mud cementing | 136 | 2014.06 | Open bidding | Bidding document still in preparation |
| KF43 | installation of pumping unit | 1088 | 2014.06 | Open bidding | Bidding document still in preparation |
| KF44 | Station civil works | 429.67 | 2014.06 | Open bidding | Bidding document still in preparation |
| KF45 | Station Installation works | 362.99 | 2014.06 | Open bidding | Bidding document still in preparation |
| KF46 | Flow-line engineering | 3166 | 2014.06 | Open bidding | Bidding document still in preparation |
| KF47 | Power supply | 1640.36 | 2014.06 | Open bidding | Bidding document still in preparation |
| KF48 | Communication system | 281.8 | 2014.06 | Open bidding | Bidding document still in preparation |
| KF49 | Automation and control engineering | 412.85 | 2014.06 | Open bidding | Bidding document still in preparation |
| KF50 | Road works | 383.07 | 2014.06 | Open bidding | Bidding document still in preparation |
| Development project(Goods) |
| KG01 | Pumping unit of 20 trial wells | 277.765 | 2012.10 | Open bidding | Contract signed |
| KG02 | Oil pipe of 20 trial wells and Sucking rod | 199.8924 | 2012.10 | Open bidding | Contract signed |
| KG03 | Casing of 20 trial wells | 331.9187 | 2012.10 | Open bidding | Contract signed |
| KG04 | Casing | 4332.011 | 2013.10 | Open bidding | contract negotiation |
| KG05 | Power cables | 374.1 | 2014.06 | Open bidding | Bidding document still in preparation |
| KG06 | Transmitter | 104.2 | 2014.06 | Open bidding | Bidding document still in preparation |
| KG07 | Swirl Flowmeter | 192 | 2014.06 | Open bidding | Bidding document still in preparation |
| KG08 | Separator | 134 | 2014.06 | Open bidding | Bidding document still in preparation |
| KG09 | Transformer | 289.23 | 2014.06 | Open bidding | Bidding document still in preparation |
| KG10 | Communications equipment, materials | 379.32 | 2014.06 | Open bidding | Bidding document still in preparation |

## III Consulting Services with Bank Loan

| NO | Contract Description | Cost Estimate($10，000) | Selection method | Review by Bank(Prior/Post) | Expected Date for Bank Review of RFP and Shortlist | Expected Proposal Submission Date | Expected time of signing contract | Actual Contract Value RMB10000 | Actual Contract Signing Date t | progress |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| C2 | CBM wells drainage effect and its improvement methods study of Libi Block in the South of Qinshui | 16.96 | CQS | Post |  | 2013.07 | 2013.07 | 16.96 | 2013.08 | Completion of the tender |
| C3 | Institutional capacity building of the Company | 13.63 | CQS | Prior | 2013.04 | 2013.06 | 2013.06 | 13.63 | 2013.06 | Completion of the tender |
| C4 | Hire individual experts(teaching) | 3 | IC | Post |  | 2014.05 | 2014.06 |  |  | TOR still in preparation |
| C6 | Safe work standarization | 4.13 | CQS | Post |  | 2014.01 | 2014.02 |  |  | TOR still in preparation |
| C7 | simulation project for Safe work | 15 | CQS | Post |  | 2014.02 | 2014.03 |  |  | TOR still in preparation |

## III Consulting Services with counterpart fund

| NO | Contract Description | Cost Estimate($10，000) | Selection method | Expected Proposal Submission Date | Expected time of signing contract | Actual Contract Value RMB10000 | Actual Contract Signing Date t | progress |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| C1 | Coal reservoir conditions and capacity study of Libi Block in the South of Qinshui | 17.37 | CQS | 2014.06 | 2013.07 |  |  | Completion of TOR |