## Thresholds
Sample Procurement Plan
I. General
1. | Project Information
| Project Name: | PCB management in the Power Sector project
| Country: | Lebanon
| Project ID: | P122540
| Loan/Credit Numbers: | TF018030
2. | Bank's approval date of Procurement Plan | Original: | 2014-06-05
|  | Revision 1: | 2015-04-23
Add new revisions
3. | Date of General Procurement Notice
II. Goods, Work and Non-Consulting Services Thresholds
1. | Prior Review Threshold. Procurement Decisions subject to Prior Review by the Bank as stated in Appendix 1 to the Guidelines for Procurement: [Thresholds for applicable procurement methods (not limited to the list below) will be determined by the Procurement Specialist /Procurement Accredited Staff based on the assessment of the implementing agency’s capacity.]
1a. | Procurement Category | Prior Review Threshold (USD) | Comments
| Goods | >1 Million | Technical aspects may be reviewed but not from procurement perspective
| Works | >10 Million
| Non-Consultant Services | >10 Million
Include all categories authorized by the loan agreement
1b. | Procurement Method | Procurement Method Threshold (USD) | Comments
| ICB and LIB (Goods) | No threhsold
| NCB (Goods) | <1 Million
| Shopping (Goods) | <200,000
| ICB (Works) | No threhsold
| NCB (Works) | <10 Million
| Shopping (Works) | <300,000
| ICB (Non-Consultant Services) | No threhsold
Include all methods authorized by the loan agreement
2. | Prequalification. Bidders for _________ shall be prequlified in accordance with the provisions of paragraphs 2.9 and 2.10 of the Guidelines.
3. | Proposed Procedures for CDD Components (as per paragraph 3.17 of the Guidelines): Refer to the relevant CDD project implementation document approved by the Bank
4. | Reference to (if any) Project Operational/Procurement Manual:
5. | Any Other Special Procurement Arrangements: [including advance procurement and retroactive financing, if applicable
6. | Procurement Packages with Methods and Time Schedule: See attached "Goods and Works" sheet
III. Selection of Consultants
1. | Prior Review Threshold: Selection decisions subject to Prior Review by Bank as stated in Appendix 1 to the Guidelines Selection and Employment of Consultants:
1a. | Procurement Category | Prior Review Threshold (USD) | Comments
| Consulting Firms (Competitive) | >500,000 | Technical aspects may be reviewed but not from procurement perspective
| Consulting Firms (Sole Source) | All
| Individual Consultants (Competitive) | >200,000
| Individual Consultants (Sole Source) | All
Include all categories authorized by the loan agreement
1b. | Procurement Method | Procurement Method Threshold (USD) | Comments
| QCBS | No threshold
| QBS | <300,000
| FBS | <300,000
| LCS | <300,000
| CQS | <300,000
| Consulting Firms (Sole Source) | No threshold
| Individual Consultants (Competitive) | No threshold
| Individual Consultants (Sole Source) | No threshold
Include all methods authorized by the loan agreement
2. | Short list comprising entirely of national consultants: Short list of consultants for services, estimated to cost less than $300,000 equivalent per contract, may comprise entirely of national consultants in accordance with the provisions of paragraph 2.7 of the Consultant Guidelines.
| Note: OPCPR list of ceilings can be found here: | http://go.worldbank.org/MKXO98RY40
3. | Any Other Special Selection Arrangements: [including advance procurement and retroactive financing, if applicable]
4. | Consultancy Assignments with Selection Methods and Time Schedule: See attached "Consulting Services" sheet
IV. Implementing Agency Capacity Building Activities with Time Schedule: See attached "Capacity Building" sheet

## PRthresh_20090114
Estimated Contract Cost (in USD)
Type of Procurement |  | High Risk Implementing Agency | Substantial Risk Implementing Agency | Moderate Risk Implementing Agency | Low Risk Implementing Agency
Works, Turnkey and S&I of Plant and Equipment |  | $ 5 million | $ 10 million | $ 15 million | $ 20 million
Goods |  | $ 0.5 million | $ 1 million | $ 3 million | $ 5 million
IT Systems, and Non-consulting Services |  | $ 0.5 million | $ 1 million | $ 3 million | $ 5 million
Consulting Services | Firms | $ 0.2 million | $ 0.5 million | $ 1 million | $ 2 million
| Individuals | $ 0.1 million | $ 0.2 million | $ 0.3 million | $ 0.5 million

## Training
PLANNING FOR TRAINING
as at 23 Apr 2015
Plan vs. Actual | Proc. System Ref. # | Comp | Location/ Description of Assignment | Selection Method | Bank Rev. | TOR Start Date | Interval | TOR end Date | Interval | NOL Date | Interval | Training preparation | Interval | Training Start Date | Execution in days | Execution in months | Completion Date (original) | Completion Date (last revision) | Participants | REFERENCE DATE FOR PAD | Comments
P | TR001 | C3 | PMU Training | NA | PR | 2015-07-15 | 14 | 2015-07-29 | 14 | 2015-08-12 | 14 | 2015-08-26 | 2 | 2015-08-28 | 1464 | 48 | 2019-08-31 | NA
R | [5 empty] | 2015-11-01 | 14 | 2015-11-15 | 14 | 2015-11-29 | 14 | 2015-12-13 | 2 | 2015-12-15 | 1464 | 48 | 2019-12-18 | NA
A | [6 empty] | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 | 0
Formulas:
TOR end Date = [TOR Start Date]+[Interval]
NOL Date = [TOR end Date]+[Interval]
Training preparation = [NOL Date]+[Interval]
Training Start Date = [Training preparation]+[Interval]
Completion Date (original) = [Training Start Date]+[Execution in days]

## Works & Goods
PROCUREMENT PLAN FOR GOODS AND WORKS
as at 23 Apr 2015
Plan vs. Actual | Proc. System Ref. # | Comp | Location/ Description of Assignment | Revised Estimated Cost (US$) | Selection Method | Bank Rev. | Pre-qualification prep. doc. start Date | Interval | Pre-qualification prep. doc. end Date | Interval | NOL Date | Interval | Adv. for pre-qualification | Interval | Pre-qualification evaluation | Interval | NOL Date | Interval | Bid. Doc/Specs prep. Start Date | Interval | Bid. Doc/Specs prep. End Date | Interval | NOL Date | Interval | Invitation Date | Interval | Bid Opening Date | Interval | Evaluation & Recomm. | Interval | NOL Date | Interval | Contract Signature Date | Interval | Start Date | Execution in days | Execution in months | Completion Date (original) | Completion Date (last revision) | Contractor Name | REFERENCE DATE FOR PAD | Comments
P | PW001 | C1 | Inventory of PCB contaminated transformers at Bauchrieh and remianing locations (including contingencies of 10%) | 788700 | NCB | PR | 2015-04-15 | 14 | 2015-04-29 | 14 | 2015-05-13 | 14 | 2015-05-27 | 7 | 2015-06-03 | 14 | 2015-06-17 | 14 | 2015-07-01 | 30 | 2015-08-17 | 14 | 2015-08-31 | 1 | 2015-09-01 | 28 | 2015-10-04 | 28 | 2015-11-01 | 14 | 2015-06-28 | 3 | 2015-07-01 | 14 | 2016-01-01 | 240 | 7.8689 | 2016-08-28 | NA
R | [7 empty] | 14 | 1900-01-13 | 14 | 1900-01-27 | 14 | 1900-02-10 | 7 | 1900-02-17 | 14 | 1900-03-03 | 14 | 2015-09-14 | 30 | 2015-10-14 | 14 | 2015-10-28 | 1 | 2015-10-29 | 28 | 2015-11-26 | 28 | 2015-12-24 | 14 | 2016-01-07 | 3 | 2016-01-10 | 14 | 2016-01-24 | 240 | 7.8689 | 2016-09-20 | NA
A | [7 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 | 0 | 0
P | PW002 | C2 | Disposal of out of service high content PCB equipment+ disposal capacitors from private sector (including 15% contingencies) | 235750 | ICB | PR | 2015-02-27 | 14 | 2015-03-13 | 14 | 2015-03-27 | 14 | 2015-04-10 | 7 | 2015-04-17 | 14 | 2015-05-01 | 14 | 2015-05-15 | 30 | 2015-05-31 | 14 | 2015-06-14 | 1 | 2015-06-15 | 42 | 2015-07-18 | 28 | 2015-08-15 | 14 | 2015-08-12 | 3 | 2015-08-15 | 14 | 2015-10-01 | 366 | 12 | 2016-10-01 | NA
R | [7 empty] | 14 | 1900-01-13 | 14 | 1900-01-27 | 14 | 1900-02-10 | 7 | 1900-02-17 | 14 | 1900-03-03 | 14 | 2015-09-01 | 30 | 2015-10-01 | 14 | 2015-10-15 | 1 | 2015-10-16 | 42 | 2015-11-27 | 28 | 2015-12-25 | 14 | 2016-01-08 | 3 | 2016-01-11 | 14 | 2016-01-25 | 366 | 12 | 2017-01-25 | NA
A | [7 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 | 0 | 0
P | PW003 | C2 | Disposal of in service high content PCB equipment and contaminated oil+ PCB contaminated oil from Bauchrieh (from contaminated transformers + well) (including 15% contingencies) | 865950 | ICB | PR | 2016-07-16 | 14 | 2016-07-30 | 14 | 2016-08-13 | 14 | 2016-08-27 | 7 | 2016-09-03 | 14 | 2016-09-17 | 14 | 2016-10-01 | 30 | 2016-12-17 | 14 | 2016-12-31 | 1 | 2017-01-01 | 42 | 2017-02-01 | 28 | 2017-03-01 | 14 | 2016-08-12 | 3 | 2016-08-15 | 14 | 2017-05-01 | 240 | 7.8689 | 2017-12-27 | NA
R | [7 empty] | 14 | 1900-01-13 | 14 | 1900-01-27 | 14 | 1900-02-10 | 7 | 1900-02-17 | 14 | 1900-03-03 | 14 | 1900-03-17 | 30 | 1900-04-16 | 14 | 1900-04-30 | 1 | 1900-05-01 | 42 | 1900-06-12 | 28 | 1900-07-10 | 14 | 1900-07-24 | 3 | 1900-07-27 | 14 | 1900-08-10 | 240 | 7.8689 | 1901-04-07 | NA
A | [7 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 | 0 | 0
Formulas:
Pre-qualification prep. doc. start Date = [Pre-qualification prep. doc. end Date]-[Interval]
Pre-qualification prep. doc. end Date = [NOL Date]-[Interval]
Pre-qualification prep. doc. end Date = [Pre-qualification prep. doc. start Date]+[Interval]
NOL Date = [Adv. for pre-qualification]-[Interval]
NOL Date = [Bid. Doc/Specs prep. Start Date]-[Interval]
Adv. for pre-qualification = [Pre-qualification evaluation]-[Interval]
Adv. for pre-qualification = [NOL Date]+[Interval]
Pre-qualification evaluation = [NOL Date]-[Interval]
Pre-qualification evaluation = [Adv. for pre-qualification]+[Interval]
Bid. Doc/Specs prep. End Date = [NOL Date]-[Interval]
Bid. Doc/Specs prep. End Date = [Bid. Doc/Specs prep. Start Date]+[Interval]
Bid Opening Date = [Evaluation & Recomm.]-[Interval]
Bid Opening Date = [Invitation Date]+[Interval]
Completion Date (original) = [Start Date]+[Execution in days]
Invitation Date = [NOL Date]+[Interval]
Evaluation & Recomm. = [Bid Opening Date]+[Interval]
Contract Signature Date = [NOL Date]+[Interval]
Start Date = [Contract Signature Date]+[Interval]
Interval = [Adv. for pre-qualification]-[NOL Date]
Interval = [Pre-qualification evaluation]-[Adv. for pre-qualification]
Completion Date (last revision) = [Execution in days]+[Execution in months]
Bid. Doc/Specs prep. Start Date = [NOL Date]+[Interval]

## Shopping
PROCUREMENT PLAN FOR GOODS AND WORKS (Shopping)
as at 23 Apr 2015
Plan vs. Actual | Proc. System Ref. # | Comp | Location/ Description of Assignment | Revised Estimated Cost (US$) | Selection Method | Bank Rev. | Specs prep. Start Date | Interval | Specs prep. End Date | Interval | Quotations Submission Date | Interval | Comparaison of Quotations | Interval | Contract Draft | Interval | NOL Date | Interval | Contract Signature Date | Interval | Contract Start Date | Execution in days | Execution in months | Completion Date (original) | Completion Date (last revision) | Consultant Name | REFERENCE DATE FOR PAD | Comments
P | PG001 | C3 | Minor equipment as needed | 40000 | SH | PR | 2015-05-01 | 14 | 2015-05-10 | 14 | 2015-05-20 | 7 | 2015-06-01 | 3 | 2015-02-26 | 14 | 2015-03-12 | 3 | 2015-03-15 | 14 | 2015-06-10 | 1537.2 | 50.4 | 2019-08-25 04:48 | NA
R | [6 empty] | 2015-09-20 | 14 | 2015-10-04 | 14 | 2015-10-18 | 7 | 2015-10-25 | 3 | 2015-10-28 | 14 | 2015-11-11 | 3 | 2015-11-14 | 14 | 2015-11-28 | 1537.2 | 50.4 | 2020-02-12 04:48
A | [7 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 | 0
P | NA | C3 | Operating cost | 80800 | NA | NA | 2015-05-01 | 14 | 2015-05-10 | 14 | 2015-05-20 | 7 | 2015-06-01 | 3 | 2014-12-28 |  | 2014-12-28 | 3 | 2014-12-31 | 14 | 2015-06-10 | 1537.2 | 50.4 | 2019-08-25 04:48 | NA
R | [6 empty] | 2015-07-01 | 14 | 2015-07-15 | 14 | 2015-07-29 | 7 | 2015-08-05 | 3 | 2015-08-08 |  | 2015-08-08 | 3 | 2015-08-11 | 14 | 2015-08-25 | 1537.2 | 50.4 | 2019-11-09 04:48
A | [7 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 | 0
Formulas:
Contract Draft = [NOL Date]-[Interval]
Contract Draft = [Comparaison of Quotations]+[Interval]
NOL Date = [Contract Signature Date]-[Interval]
NOL Date = [Contract Draft]+[Interval]
Completion Date (original) = [Contract Start Date]+[Execution in days]
Specs prep. End Date = [Specs prep. Start Date]+[Interval]
Quotations Submission Date = [Specs prep. End Date]+[Interval]
Comparaison of Quotations = [Quotations Submission Date]+[Interval]
Contract Signature Date = [NOL Date]+[Interval]
Contract Start Date = [Contract Signature Date]+[Interval]

## Firms Cons.
PROCUREMENT PLAN FOR CONSULTANCY SERVICES - CONSULTING FIRMS
as at 23 Apr 2015
Plan vs. Actual | Proc. System Ref. # | Comp | Location/ Description of Assignment | Revised Estimated Cost (US$) | Selection Method | Bank Rev. | TOR Start Date | Interval | TOR end Date | Interval | NOL Date | Interval | Adv. EOI end Date | Interval | Short Listing Report Date | Interval | NOL Date | Interval | RFP prep. | Interval | NOL Date | Interval | RFP Submission Date | Interval | Technical Evaluation Report Date | Interval | NOL Date | Interval | Finan. Public openg Date | Interval | Final Evaluation Report Date | Interval | Contract negotiation/Award- Draft | Interval | NOL Date | Interval | Contract signature Date | Interval | Contract Start Date | Execution in days | Execution in months | Completion Date (original) | Completion Date (last revision) | Consultant Name | REFERENCE DATE FOR PAD | Comments
P | FC001 | C3 | Project external audit | 20000 | LCS | PR | 2015-07-01 | 14 | 2015-07-15 | 14 | 2015-07-29 | 14 | 2015-08-12 | 7 | 2015-08-19 | 14 | 2015-09-02 | 7 | 2015-09-09 | 14 | 2015-09-23 | 35 | 2015-10-28 | 7 | 2015-11-04 | 14 | 2015-11-18 | 14 | 2015-12-02 | 5 | 2015-12-07 | 7 | 2015-12-14 | 14 | 2015-12-28 | 2 | 2015-12-30 | 2 | 2016-01-01 | 1573.8 | 51.6 | 2020-04-22 19:12 | NA |  |  | To cover grace period
R | [6 empty] | 2015-07-14 | 14 | 2015-07-28 | 14 | 2015-08-11 | 14 | 2015-08-25 | 7 | 2015-09-01 | 14 | 2015-09-15 | 7 | 2015-09-22 | 14 | 2015-10-06 | 35 | 2015-11-10 | 7 | 2015-11-17 | 14 | 2015-12-01 | 14 | 2015-12-15 | 5 | 2015-12-20 | 7 | 2015-12-27 | 14 | 2016-01-10 | 2 | 2016-01-12 | 2 | 2016-01-14 | 1573.8 | 51.6 | 2020-05-05 19:12 | NA
A | [6 empty] | 2015-07-14 | -42199 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 | 0
Formulas:
TOR Start Date = [TOR end Date]-[Interval]
TOR end Date = [NOL Date]-[Interval]
TOR end Date = [TOR Start Date]+[Interval]
NOL Date = [Adv. EOI end Date]-[Interval]
NOL Date = [RFP prep.]-[Interval]
Adv. EOI end Date = [Short Listing Report Date]-[Interval]
Adv. EOI end Date = [NOL Date]+[Interval]
Short Listing Report Date = [NOL Date]-[Interval]
Short Listing Report Date = [Adv. EOI end Date]+[Interval]
RFP prep. = [NOL Date]-[Interval]
RFP prep. = [NOL Date]+[Interval]
RFP Submission Date = [Technical Evaluation Report Date]-[Interval]
RFP Submission Date = [NOL Date]+[Interval]
Technical Evaluation Report Date = [NOL Date]-[Interval]
Technical Evaluation Report Date = [RFP Submission Date]+[Interval]
Finan. Public openg Date = [Final Evaluation Report Date]-[Interval]
Finan. Public openg Date = [NOL Date]+[Interval]
Final Evaluation Report Date = [Contract negotiation/Award- Draft]-[Interval]
Final Evaluation Report Date = [Finan. Public openg Date]+[Interval]
Contract negotiation/Award- Draft = [NOL Date]-[Interval]
Contract negotiation/Award- Draft = [Final Evaluation Report Date]+[Interval]
Contract Start Date = [Contract signature Date]+[Interval]
Completion Date (original) = [Contract Start Date]+[Execution in days]
Contract signature Date = [NOL Date]+[Interval]

## Ind. Cons.
PROCUREMENT PLAN FOR CONSULTANCY SERVICES - INDIVIDUAL CONSULTANTS
as at 23 Apr 2015
Plan vs. Actual | Proc. System Ref. # | Comp | Location/ Description of Assignment | Revised Estimated Cost (US$) | Selection Method | Bank Rev. | TOR Start Date | Interval | TOR end Date | Interval | NOL Date | Interval | Adv. EOI end Date | Interval | Short Listing Report Date | Interval | NOL Date | Interval | Contract negotiation/Award- Draft | Interval | NOL Date | Interval | Contract signature Date | Interval | Contract Start Date | Execution in days | Execution in months | Completion Date (original) | Completion Date (last revision) | Consultant Name | REFERENCE DATE FOR PAD | Comments
P | IC001 | C3 | Project Manager | 226800 | IC | PR | 2015-10-01 | 14 | 2015-10-11 | 14 | 2015-10-25 | 14 | 2015-11-08 | 7 | 2015-11-15 | 14 | 2015-04-01 | 7 | 2015-04-08 | 14 | 2014-12-24 | 7 | 2014-12-31 | 2 | 2015-05-01 | 1537.2 | 54 | 2019-11-01 | NA |  |  | level of effort is x mths;
R | [7 empty] | 14 | 1900-01-13 | 14 | 1900-01-27 | 14 | 1900-02-10 | 7 | 1900-02-17 | 14 | 1900-03-03 | 7 | 1900-03-10 | 14 | 1900-03-24 | 7 | 1900-03-31 | 2 | 1900-04-02 | 1537.2 | 50.4 | 1904-06-17 04:48 | NA
A | [7 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 | 0
P | IC002 | C3 | Assistant PM | 75600 | IC | PR | 2015-10-01 | 14 | 2015-10-11 | 14 | 2015-10-25 | 14 | 2015-11-08 | 7 | 2015-11-15 | 14 | 2015-04-01 | 7 | 2015-04-08 | 14 | 2014-12-24 | 7 | 2014-12-31 | 2 | 2015-05-01 | 1537.2 | 51 | 2019-07-01 | NA |  |  | level of effort is x mths;
R | [7 empty] | 14 | 1900-01-13 | 14 | 1900-01-27 | 14 | 1900-02-10 | 7 | 1900-02-17 | 14 | 1900-03-03 | 7 | 1900-03-10 | 14 | 1900-03-24 | 7 | 1900-03-31 | 2 | 1900-04-02 | 1537.2 | 50.4 | 1904-06-17 04:48 | NA
A | [7 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 | 0
P | IC003 | C3 | Consultant services (multiple) | 130000 | IC | PO | 2015-07-01 | 14 | 2015-07-11 |  | 2015-07-11 | 14 | 2015-07-25 | 7 | 2015-08-01 |  | 2015-08-08 | 7 | 2015-08-15 |  | 2015-05-24 | 7 | 2015-05-31 | 2 | 2015-09-01 | 1537.2 | 50.4 | 2019-11-16 04:48 | NA |  |  | level of effort is x mths;
R | [6 empty] | 2015-07-30 | 14 | 2015-08-13 |  | 2015-08-13 | 14 | 2015-08-27 | 7 | 2015-09-03 |  | 2015-09-03 | 7 | 2015-09-10 |  | 2015-09-10 | 7 | 2015-09-17 | 2 | 2015-09-19 | 1537.2 | 50.4 | 2019-12-04 04:48 | NA
A | [7 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 | 0
Formulas:
TOR end Date = [NOL Date]-[Interval]
TOR end Date = [TOR Start Date]+[Interval]
NOL Date = [Adv. EOI end Date]-[Interval]
NOL Date = [Contract negotiation/Award- Draft]-[Interval]
Adv. EOI end Date = [Short Listing Report Date]-[Interval]
Adv. EOI end Date = [NOL Date]+[Interval]
Short Listing Report Date = [Adv. EOI end Date]+[Interval]
Contract negotiation/Award- Draft = [NOL Date]+[Interval]
Contract signature Date = [NOL Date]+[Interval]
Contract Start Date = [Contract signature Date]+[Interval]
Completion Date (original) = [Contract Start Date]+[Execution in days]