## Threshold
Procurement Plan
I. General
1. | Project Information
| Project Name: | EDP II
| Country: | Lebanon
| Project ID: | P118187
| Loan/Credit Numbers: | 7966
2. | Bank's approval date of Procurement Plan | Original: November 10, 2010
Revision 3: 27 August 2013
Revision 4: 4 December 2013
Revision 5: 4 June 2014
3. | Date of General Procurement Notice
II. Goods, Work and Non-Consulting Services Thresholds
1. | Prior Review Threshold. Procurement Decisions subject to Prior Review by the Bank as stated in Appendix 1 to the Guidelines for Procurement: [Thresholds for applicable procurement methods (not limited to the list below) will be determined by the Procurement Specialist /Procurement Accredited Staff based on the assessment of the implementing agency’s capacity.]
1a. | Procurement Category | Prior Review Threshold (USD) | Comments
| Goods (ICB) | > = 3,000,000 | and First Contract regardless the amount
| Works (ICB) | not applicable
| Goods, Works (NCB) | First Contract regardless the amount
| Goods, Works (Shopping) | First Contract
| Goods, Works (Direct Contracting) | All
| IT Systems and Non-Consultant Services | > = 3,000,000 | maintenance and upgraded services for equipment, including hardware and software
| School Fund |  | As defined by the operational manual thresholds
| Operating Costs |  | using ESDS administrative procedures found acceptable to the Bank.
1b. | Procurement Method | Procurement Method Threshold (USD) | Comments
| ICB and LIB (Goods) | No threshlod
| NCB (Goods) | <= USD 1,000,000 | Upgraded June 4, 2014
| ICB (Works) | not applicable | Works Bids are expected to be launched under NCB procedure due to the nature (rehabilitation works, location/disbursement/scattering of the Sites, and local context.) and timing of the Implementation (limited to almost 3 months). This will be requested for WB clearance.
| NCB (Works) | <= 10,000,000 | Upgraded June 4, 2014
| Shopping (Works, Goods) | <= 200,0000
| Direct Contracting | No threshold
ICB (Non-Consultant Services)
| Procurement of Operation Costs (Direct) | <= 2,000 | Direct purchase by payment against invoice
| School Fund |  | As defined by the operational manual thresholds
2. | Prequalification. Bidders for _________ shall be prequlified in accordance with the provisions of paragraphs 2.9 and 2.10 of the Guidelines.
3. | Proposed Procedures for CDD Components (as per paragraph 3.17 of the Guidelines): Refer to the relevant CDD project implementation document approved by the Bank
4. | Reference to (if any) Project Operational/Procurement Manual:
5. | Any Other Special Procurement Arrangements: [ncluding advance procurement and retroactive financing, if applicable
6. | Procurement Packages with Methods and Time Schedule: See attached "Goods and Works" sheet
III. Selection of Consultants
1. | Prior Review Threshold: Selection decisions subject to Prior Review by Bank as stated in Appendix 1 to the Guidelines Selection and Employment of Consultants:
1a. | Selection Category | Prior Review Threshold (USD) | Comments
| Consulting Firms (Competitive) | >= 1,000,000 | and First Contract regardless of contract value
| Consulting Firms (Single Source) | All
| Individual Consultants (Competitive) | >= 300,000 | and First Contract regardless of contract value
| Individual Consultants (Sole Source) | All
| School Fund |  | As defined by the operational manual thresholds
1b. | Selection Method | Selection Method Threshold (USD) | Comments
| QCBS (Firms) | No Threshold
| CQS, FBS, LCS | < 300,000
| Consulting Firms (Single Source) | No Threshold
| Individual Consultants (Competitive) | No Threshold
| Individual Consultants (Sole Source) | No Threshold
| Procurement of Operation Costs (Direct) | <= 2,000 | Direct purchase by payment against invoice
| School Fund |  | As defined by the operational manual thresholds
2. | Short list comprising entirely of national consultants: Short list of consultants for services, estimated to cost less than $300,000 equivalent per contract, may comprise entirely of national consultants in accordance with the provisions of paragraph 2.7 of the Consultant Guidelines. (POM-3.3.2.1)
| Note: OPCPR list of ceilings can be found here: | http://go.worldbank.org/MKXO98RY40
3. | Any Other Special Selection Arrangements: [including advance procurement and retroactive financing, if applicable]
4. | Consultancy Assignments with Selection Methods and Time Schedule: See attached "Consulting Services" sheet
5. | The advertisement should be published in two national newspapers or in a freely accessible electronic portal for at least two days. Contracts expected to cost more than US$ 200,000 shall be advertised in UNDB online and in dgMarket. (EOI: min. 14 days from UNDB posting)
6. | The Bank’s Standard Request for Proposal (SRFP) is the mandatory format for the preparation and issuance of the actual RFP for contracts exceeding US$ 200,000, and is the recommended format for smaller contracts.
7. | The Procurement Plan will be updated in agreement with the Project Team annually or as required to reflect the actual project implementation needs and improvements in institutional capacity.
IV. Implementing Agency Capacity Building Activities with Time Schedule: See attached "Capacity Building" sheet

## PRthresh_20090114
Estimated Contract Cost (in USD)
Type of Procurement |  | High Risk Implementing Agency | Substantial Risk Implementing Agency | Moderate Risk Implementing Agency | Low Risk Implementing Agency
Works, Turnkey and S&I of Plant and Equipment |  | $ 5 million | $ 10 million | $ 15 million | $ 20 million
Goods |  | $ 0.5 million | $ 1 million | $ 3 million | $ 5 million
IT Systems, and Non-consulting Services |  | $ 0.5 million | $ 1 million | $ 3 million | $ 5 million
Consulting Services | Firms | $ 0.2 million | $ 0.5 million | $ 1 million | $ 2 million
| Individuals | $ 0.1 million | $ 0.2 million | $ 0.3 million | $ 0.5 million

## Training
PLANNING FOR TRAINING
as of January 25, 2016
Costab ref | Plan vs. Actual | Proc. System Ref. # | SN. # | Comp | Sub-Comp | Location/ Description of Assignment | Unit (Mth/ Yr/ Study[Sty], Lumpsum [LS], Workshop [Wsh]) | Selection Method | Bank Rev. (by TTL only ) | TOR Start Date | Interval | TOR end Date | Interval | NOL Date | Interval | Training preparation | Interval | Training Start Date | Execution in days | Execution in months | Completion Date (original) | Completion Date (last revision) | Activity amount US$ (original) | Activity amount US$ (last revised) | Participants | Comments
t1 | P | TR001 | TR001 | 1 | 1.6 | 3 training program 3 trips |  | NA | PR | 2011-11-20 | 14 | 2011-12-04 | 14 | 2011-12-18 | 14 | 2012-01-01 | 2 | 2012-01-03 | 15 | 0.4918 | 2012-01-18 | NA | NA | NA
| R | [5 empty] | 0 |  |  | 2014-09-20 | 14 | 2014-10-04 | 14 | 2014-10-18 | 14 | 2014-11-01 | 2 | 2014-11-03 | 15 | 0.49 | 2014-11-18 | NA | NA | NA
| A | [9 empty] | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 | 0
t2 | P | TR002 | TR002 | 2 | 2.1 | Training of 30 facilitators |  | NA | PR | 2011-11-21 | 14 | 2011-12-05 | 14 | 2011-12-19 | 14 | 2012-01-02 | 2 | 2012-01-04 | 1464 | 48 | 2016-01-07 | NA | NA | NA
| R | [8 empty] | 2013-11-21 | 14 | 2013-12-05 | 14 | 2013-12-19 | 14 | 2014-01-02 | 2 | 2014-01-04 | 1464 | 48 | 2018-01-07 | NA | NA | NA
| A | [9 empty] | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 | 0
t3 | P | TR003 | TR003 | 3 | 3.3 | Workshops, Training , & Study Tours |  | NA | PR | 2013-06-18 | 14 | 2013-07-02 | 14 | 2013-07-16 | 14 | 2013-07-30 | 2 | 2013-08-01 | 1830 | 60 | 2018-08-05 | NA | NA | NA |  | Ongoing
| R | [5 empty] | 0 |  |  | 2013-04-27 | 14 | 2013-05-11 | 14 | 2013-05-25 | 14 | 2013-06-08 | 2 | 2013-06-10 | 1647 | 54 | 2017-12-13 | NA | NA | NA
| A | [9 empty] | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 | 0
| P | TR003 | TR003 | 3 | 3.3 | Study tours of TIMSS and PIZA |  | NA | PR | 2013-06-18 | 14 | 2013-07-02 | 14 | 2013-07-16 | 14 | 2013-07-30 | 2 | 2013-08-01 | 1830 | 60 | 2018-08-05 | NA | NA | NA |  | Ongoing
| R | [5 empty] | 0 |  |  | 2013-04-27 | 14 | 2013-05-11 | 14 | 2013-05-25 | 14 | 2013-06-08 | 2 | 2013-06-10 | 1647 | 54 | 2017-12-13 | NA | NA | NA
| A | [8 empty] | 2013-04-27 |  |  | 0 |  | 0 |  |  | 2014-10-24 | 799.1 | 26.2 | 2016-12-31 02:24
| P | TR003 | TR003 | 3 | 3.3 | Procurement Audit |  |  |  | 2013-04-27 | 14 | 2013-05-11 | 14 | 2013-05-25 | 14 | 2013-06-08 | 2 | 2013-06-10 | 4.88 | 0.16 | 2013-06-14 21:07 | NA | TBA | NA |  | Completed
| R | [8 empty] | 2013-04-27 | 14 | 2013-05-11 | 14 | 2013-05-25 | 14 | 2013-06-08 | 2 | 2013-06-10 | 4.88 | 0.16 | 2013-06-14 21:07 | NA | TBA | NA
| A | [8 empty] | 2013-04-27 | 14 | 2013-05-11 | 14 | 2013-05-25 | 14 | 2013-06-08 | 2 | 2013-06-10 | 4.88 | 0.16 | 2013-06-14 21:07 | NA | TBA | NA | 1-Bilal Nasser: Proc.Audit
| P | TR003 | TR003 | 3 | 3.3 | Procurement Works | [14 empty] | 2013-06-14 21:07 | NA | TBA | NA |  | Completed
| R | [19 empty] | 2013-06-14 21:07 | NA | TBA | NA
| A | [16 empty] | 2015-11-30 | 4 |  | 2015-12-04 | NA | TBA | NA | Riwa & Maya
Formulas:
TOR Start Date = [TOR end Date]-[Interval]
TOR end Date = [NOL Date]-[Interval]
TOR end Date = [TOR Start Date]+[Interval]
NOL Date = [Training preparation]-[Interval]
NOL Date = [TOR end Date]+[Interval]
Training Start Date = +[Training preparation]+[Interval]
Training Start Date = [Training preparation]+[Interval]
Completion Date (original) = +[Training Start Date]+[Execution in days]
Completion Date (original) = [Training Start Date]+[Execution in days]
Training preparation = [NOL Date]+[Interval]
Training preparation = +[Training Start Date]-[Interval]
Interval = [TOR end Date]-[TOR Start Date]
Interval = [NOL Date]-[TOR end Date]
Execution in months = [Execution in days]/30.5

## Works & Goods
PROCUREMENT PLAN FOR GOODS AND WORKS
as of January 25, 2016
Costab ref | Plan vs. Actual | Proc. System Ref. # | SN. # | Comp | Sub-Comp | Location/ Description of Assignment | Selection Method | Bank Rev. | Bid. Doc/Specs prep. Start Date | Interval | Bid. Doc/Specs prep. End Date | Interval | NOL Date | Interval | Invitation Date | Interval | Bid Opening Date | Interval | Evaluation & Recomm. | Interval | NOL Date | Interval | Contract Signature Date | Interval | Start Date | Execution in days | Execution in months | Completion Date (original) | Completion Date (last revision) | Consultant Name | Comments
| A | B | C |  |  | D | F | G | T | U | T | U | V | W | X | Y | Z | AA | AB | AC | AD | AE | AF | AG | AH | AI | AJ | AK | AL | AO | AP
| P | W1 | PW001 | 1 | 1.1 | Rehabilitation of 72 KG schools | NCB | PR | 2012-03-19 | 30 | 2012-04-18 | 14 | 2012-04-18 | 1 | 2012-04-19 | 28 | 2012-05-17 | 28 | 2012-06-14 | 14 | 2012-06-28 | 3 | 2012-07-01 | 14 | 2012-07-15 | 122 | 4 | 2012-11-14 | NA
| R | [7 empty] | 2016-01-20 | 45 | 2016-03-05 | 14 | 2016-03-19 | 14 | 2016-04-02 | 45 | 2016-05-17 | 30 | 2016-06-16 | 14 | 2016-06-30 | 14 | 2016-07-14 | 14 | 2016-07-28 | 122 | 4 | 2016-11-27 | NA
| A |  |  |  |  | W: 0; Y: 0; AA: 0; AC: 0; AE: 0; AG: 0; AJ: 0; AK: 0; AL: 0 | 2014-10-20 | 4 | 2014-10-24
| P | W2 | PW002 | 1 | 1.1 | Rehabilitation of 72 KG schools | NCB | PR | 2013-04-02 | 30 | 2013-05-02 |  | 2013-05-02 | 1 | 2013-05-03 | 28 | 2013-05-31 | 28 | 2013-06-28 |  | 2013-06-28 | 3 | 2013-07-01 | 14 | 2013-07-15 | 122 | 4 | 2013-11-14 | NA
| R | [7 empty] | 2016-01-20 | 45 | 2016-03-05 | 14 | 2016-03-19 | 14 | 2016-04-02 | 45 | 2016-05-17 | 30 | 2016-06-16 | 14 | 2016-06-30 | 14 | 2016-07-14 | 14 | 2016-07-28 | 122 | 4 | 2016-11-27 | NA
| A |  |  |  |  | U: 0; W: 0; Y: 0; AA: 0; AC: 0; AE: 0; AG: 0; AJ: 0; AK: 0; AL: 0
| P | W3 | PW003 | 1 | 1.1 | Rehabilitation of KG schools | NCB | PO | 2014-04-02 | 30 | 2014-05-02 |  | 2014-05-02 | 1 | 2014-05-03 | 28 | 2014-05-31 | 28 | 2014-06-28 |  | 2014-06-28 | 3 | 2014-07-01 | 14 | 2014-07-15 | 122 | 4 | 2014-11-14 | NA
R | bar: AL
| A |  |  |  |  | U: 0; W: 0; Y: 0; AA: 0; AC: 0; AE: 0; AG: 0; AJ: 0; AK: 0; AL: 0 |  | 8 | 8
| P | GG1 | PG001 | 1 | 1.1 | Equipment for 103Schools 17 additional schools KG sections | ICB | PR | 2012-02-04 | 30 | 2012-03-05 | 14 | 2012-03-05 | 1 | 2012-03-06 | 42 | 2012-04-17 | 28 | 2012-05-15 | 14 | 2012-05-29 | 3 | 2012-06-01 | 14 | 2012-06-15 | 1464 | 36 | 2016-06-18 | NA | Al Diyar International Co SARL | Contract Completed and Paid
| R | [7 empty] | 2013-11-13 | 30 | 2013-12-26 | 14 | 2014-01-17 | 11 | 2014-01-28 | 72 | 2014-05-08 | 50 | 2014-06-27 | 14 | 2014-07-11 | 14 | 2014-07-25 | 14 | 2014-08-08 | 213.5 | 7 | 2015-03-09 12:00 | NA
| A | [7 empty] | 2013-11-13 | 43 | 2013-12-26 | 22 | 2014-01-17 | 11 | 2014-01-28 | 72 | 2014-05-08 | 21 | 2014-05-29 | 68 | 2014-08-05 | 29 | 2014-09-04 | 14 | 2014-09-04 | 122 | 4 | 2015-01-04 | 2015-03-04
| P | GG1 | PG001 | 1 | 1.1 | Furniture for 103Schools and 17 additional schools KG sections | ICB | PR | 2012-02-04 | 30 | 2012-03-05 | 14 | 2012-03-05 | 1 | 2012-03-06 | 42 | 2012-04-17 | 28 | 2012-05-15 | 14 | 2012-05-29 | 3 | 2012-06-01 | 14 | 2012-06-15 | 1464 | 36 | 2016-06-18 | NA | Fleifel IND. CO. S.A.R.L | Contract Completed and Paid
| R | [7 empty] | 2013-11-13 | 30 | 2013-12-26 | 14 | 2014-01-17 | 11 | 2014-01-28 | 72 | 2014-05-08 | 50 | 2014-06-27 | 14 | 2014-07-11 | 14 | 2014-07-25 | 14 | 2014-08-08 | 213.5 | 7 | 2015-03-09 12:00 | NA
| A | [7 empty] | 2013-11-13 | 43 | 2013-12-26 | 22 | 2014-01-17 | 11 | 2014-01-28 | 72 | 2014-05-08 | 21 | 2014-05-29 | 68 | 2014-08-05 | 29 | 2014-09-04 | 14 | 2014-09-04 | 122 | 4 | 2015-01-04 | 2015-03-04
| P | GG2 | PG002 | 1 | 1.1 | Equipment &Furniture for 153 Schools - KG sections- to be rehabilitated under EDP-II | ICB | PR | 2012-02-04 | 30 | 2012-03-05 | 14 | 2012-03-05 | 1 | 2012-03-06 | 42 | 2012-04-17 | 28 | 2012-05-15 | 14 | 2012-05-29 | 3 | 2012-06-01 | 14 | 2012-06-15 | 1464 | 36 | 2016-06-18 | NA
| R | [7 empty] | 2016-01-20 | 30 | 2016-02-19 | 14 | 2016-03-04 | 14 | 2016-03-18 | 49 | 2016-05-06 | 28 | 2016-06-03 | 0 | 2016-06-03 | 14 | 2016-06-17 | 7 | 2016-06-24 | 152.5 | 5 | 2016-11-23 12:00 | NA
| A |  |  |  |  | U: 0; W: 0; Y: 0; AA: 0; AC: 0; AE: 0; AG: 0; AJ: 0; AK: 0; AL: 0
| P | GG3 | PG003 | 1 | 1.1 | Furniture for 110 KG schools | ICB | PO | 2012-02-04 | 30 | 2012-03-05 |  | 2012-03-05 | 1 | 2012-03-06 | 28 | 2012-04-03 | 28 | 2012-05-01 | 14 | 2012-05-15 | 3 | 2012-05-18 | 14 | 2012-06-01 | 1464 | 48 | 2016-06-04 | NA
| R | [7 empty] | 2014-03-24 | 30 | 2014-04-23 |  | 2014-04-23 | 14 | 2014-05-07 | 49 | 2014-06-25 | 35 | 2014-07-30 |  | 2014-07-30 | 21 | 2014-08-20 | 14 | 2014-09-03 | 366 | 12 | 2015-09-04 | NA
| A |  |  |  |  | U: 0; W: 0; Y: 0; AA: 0; AC: 0; AE: 0; AG: 0; AJ: 0; AK: 0; AL: 0
| P | GG4 | PG004 | 1 | 1.1 | Replacement Equipment for KG schools | NCB (SS) | PR | 2015-05-03 | 30 | 2015-06-02 | 14 | 2015-06-02 | 1 | 2015-06-03 | 28 | 2015-07-01 | 28 | 2015-07-29 |  | 2015-07-29 | 3 | 2015-08-01 | 14 | 2015-08-15 | 122 | 5 | 2015-12-15 | NA
| R | [7 empty] | 2015-12-24 | 7 | 2015-12-31 | 14 | 2016-01-14 | 3 | 2016-01-17 | 28 | 2016-02-14 | 7 | 2016-02-21 | 14 | 2016-03-06 | 14 | 2016-03-20 | 14 | 2016-04-03 | 152.5 | 5 | 2016-09-02 12:00 | NA
| A |  |  |  |  | U: 0; W: 0; Y: 0; AA: 0; AC: 0; AE: 0; AG: 0; AJ: 0; AK: 0; AL: 0
| P | GG5 | PG005 | 1 | 1.1 | Replacement Equipment for KG schools | SS | PR | 2015-05-03 | 30 | 2015-06-02 |  | 2015-06-02 | 1 | 2015-06-03 | 28 | 2015-07-01 | 28 | 2015-07-29 |  | 2015-07-29 | 3 | 2015-08-01 | 14 | 2015-08-15 | 122 | 4 | 2015-12-15 | NA
| R | [7 empty] | 2015-12-24 | 7 | 2015-12-31 | 14 | 2016-01-14 | 3 | 2016-01-17 | 28 | 2016-02-14 | 7 | 2016-02-21 | 14 | 2016-03-06 | 14 | 2016-03-20 | 14 | 2016-04-03 | 152.5 | 5 | 2016-09-02 12:00 | NA
| A |  |  |  |  | U: 0; W: 0; Y: 0; AA: 0; AC: 0; AE: 0; AG: 0; AJ: 0; AK: 0; AL: 0
| P | GG6 | PG006 | 3 | 3.1 | Development /implementation of document management system, workflow and archiving needs | NCB | PR | 2012-04-05 | 30 | 2012-05-05 | 14 | 2012-05-05 | 1 | 2012-05-06 | 42 | 2012-06-17 | 28 | 2012-07-15 | 14 | 2012-07-29 | 3 | 2012-08-01 | 14 | 2012-08-15 | 488 | 16 | 2013-12-16 | NA
| R | [7 empty] | 2016-04-03 | 30 | 2016-05-03 |  | 2016-05-03 | 14 | 2016-05-17 | 42 | 2016-06-28 | 28 | 2016-07-26 | 14 | 2016-08-09 | 7 | 2016-08-16 | 14 | 2016-08-30 | 366 | 12 | 2017-08-31 | NA
| A |  |  |  |  | W: 0; Y: 0; AA: 0; AE: 0; AG: 0; AJ: 0; AK: 0; AL: 0
1 ICB | P | GG7 | PG007 | 3 | 3.2 | Provision, Installation and Upgrade of Servers (Lot 1) | ICB | PR | 2012-05-03 | 30 | 2012-06-02 | 14 | 2012-06-02 | 1 | 2012-06-03 | 28 | 2012-07-01 | 28 | 2012-07-29 |  | 2012-07-29 | 3 | 2012-08-01 | 14 | 2012-08-15 | 488 | 16 | 2013-12-16 | NA |  | Procurement Process Ongoing
| R | [7 empty] | 2014-08-01 | 417 | 2015-09-22 | 8 | 2015-09-30 | 21 | 2015-10-21 | 78 | 2016-01-07 | 40 | 2016-02-16 | 14 | 2016-03-01 | 7 | 2016-03-08 | 14 | 2016-03-22 | 91.5 | 3 | 2016-06-21 12:00 | NA
| A |  |  |  |  | T: 2015-01-21; U: 244; T: 2015-09-22; U: 8; V: 2015-09-30; W: 21; X: 2015-10-21; Y: 78; Z: 2016-01-07
| P | GG7 | PG007 | 3 | 3.2 | Provision and Installation of Servers and Power Lot (Lot 2) | ICB | PR | 2012-05-03 | 30 | 2012-06-02 | 14 | 2012-06-02 | 1 | 2012-06-03 | 28 | 2012-07-01 | 28 | 2012-07-29 |  | 2012-07-29 | 3 | 2012-08-01 | 14 | 2012-08-15 | 488 | 16 | 2013-12-16 | NA
| R | [7 empty] | 2014-08-01 | 417 | 2015-09-22 | 8 | 2015-09-30 | 21 | 2015-10-21 | 78 | 2016-01-07 | 40 | 2016-02-16 | 14 | 2016-03-01 | 7 | 2016-03-08 | 14 | 2016-03-22 | 91.5 | 3 | 2016-06-21 12:00 | NA
| A |  |  |  |  | T: 2015-01-21; U: 244; T: 2015-09-22; U: 8; V: 2015-09-30; W: 21; X: 2015-10-21; Y: 78; Z: 2016-01-07; AJ: 0; AK: 0; AL: 0
| P | GG7 | PG007 | 3 | 3.2 | Provision and Installation of Storage(Lot 3) | ICB | PR | 2012-05-03 | 30 | 2012-06-02 |  | 2012-06-02 | 1 | 2012-06-03 | 28 | 2012-07-01 | 28 | 2012-07-29 |  | 2012-07-29 | 3 | 2012-08-01 | 14 | 2012-08-15 | 488 | 16 | 2013-12-16 | NA
| R | [7 empty] | 2014-08-01 | 417 | 2015-09-22 | 8 | 2015-09-30 | 21 | 2015-10-21 | 78 | 2016-01-07 | 40 | 2016-02-16 | 14 | 2016-03-01 | 7 | 2016-03-08 | 14 | 2016-03-22 | 91.5 | 3 | 2016-06-21 12:00 | NA
| A |  |  |  |  | T: 2015-01-21; U: 244; T: 2015-09-22; U: 8; V: 2015-09-30; W: 21; X: 2015-10-21; Y: 78; Z: 2016-01-07; AE: 0; AG: 0; AJ: 0; AK: 0; AL: 0
| P | GG7 | PG007 | 3 | 3.2 | Provision and Installation of Network and Security (Lot 4) | ICB | PR | 2012-05-03 | 30 | 2012-06-02 |  | 2012-06-02 | 1 | 2012-06-03 | 28 | 2012-07-01 | 28 | 2012-07-29 |  | 2012-07-29 | 3 | 2012-08-01 | 14 | 2012-08-15 | 488 | 16 | 2013-12-16 | NA
| R | [7 empty] | 2014-08-01 | 417 | 2015-09-22 | 8 | 2015-09-30 | 21 | 2015-10-21 | 78 | 2016-01-07 | 40 | 2016-02-16 | 14 | 2016-03-01 | 7 | 2016-03-08 | 14 | 2016-03-22 | 152.5 | 5 | 2016-08-21 12:00 | NA
| A |  |  |  |  | T: 2015-01-21; U: 244; T: 2015-09-22; U: 8; V: 2015-09-30; W: 21; X: 2015-10-21; Y: 78; Z: 2016-01-07; AE: 0; AG: 0; AJ: 0; AK: 0; AL: 0
| P | GG7 | PG007 | 3 | 3.2 | MEHE Data Center (HQ,DR/BU)Servers Provision, Upgrade and Maintenance | ICB | PR | 2012-05-03 | 30 | 2012-06-02 | 14 | 2012-06-02 | 1 | 2012-06-03 | 28 | 2012-07-01 | 28 | 2012-07-29 |  | 2012-07-29 | 3 | 2012-08-01 | 14 | 2012-08-15 | 488 | 16 | 2013-12-16 | NA
| R | [7 empty] | 2014-08-01 | 95 | 2014-11-04 | 14 | 2014-11-18 | 14 | 2014-12-02 | 60 | 2015-01-31 | 30 | 2015-03-02 | 14 | 2015-03-16 | 7 | 2015-03-23 | 14 | 2015-04-06 | 366 | 12 | 2016-04-06 | NA
| A |  |  |  |  | T: 2014-08-01; W: 0; Y: 0; AA: 0; AJ: 0; AK: 0; AL: 0
| P | GG8 | PG008 | 3 | 3.2 | MEHE HQ and DR/BU SAN Storages | ICB | PR | 2012-05-03 | 30 | 2012-06-02 |  | 2012-06-02 | 1 | 2012-06-03 | 28 | 2012-07-01 | 28 | 2012-07-29 |  | 2012-07-29 | 3 | 2012-08-01 | 14 | 2012-08-15 | 488 | 16 | 2013-12-16 | NA
| R | [7 empty] | 2014-08-01 | 95 | 2014-11-04 | 14 | 2014-11-18 | 14 | 2014-12-02 | 28 | 2014-12-30 | 28 | 2015-01-27 |  | 2015-01-27 | 7 | 2015-02-03 | 14 | 2015-02-17 | 366 | 12 | 2016-02-18 | NA
| A |  |  |  |  | T: 2014-08-01; W: 0; Y: 0; AA: 0; AE: 0; AG: 0; AJ: 0; AK: 0; AL: 0
| P | GG9 | PG009 | 3 | 3.2 | MEHE Data Center Network | ICB | PR | 2012-05-03 | 30 | 2012-06-02 |  | 2012-06-02 | 1 | 2012-06-03 | 28 | 2012-07-01 | 28 | 2012-07-29 |  | 2012-07-29 | 3 | 2012-08-01 | 14 | 2012-08-15 | 488 | 16 | 2013-12-16 | NA
| R | [7 empty] | 2014-08-01 | 95 | 2014-11-04 | 14 | 2014-11-18 | 14 | 2014-12-02 | 28 | 2014-12-30 | 28 | 2015-01-27 |  | 2015-01-27 | 7 | 2015-02-03 | 14 | 2015-02-17 | 366 | 12 | 2016-02-18 | NA
| A |  |  |  |  | T: 2014-08-01; W: 0; Y: 0; AA: 0; AE: 0; AG: 0; AJ: 0; AK: 0; AL: 0
| P | GG7 | PG007 | 3 | 3.2 | Provision and Installation of Public Schools Connectivity (Lot 5) | ICB | PR | 2012-05-03 | 30 | 2012-06-02 |  | 2012-06-02 | 1 | 2012-06-03 | 28 | 2012-07-01 | 28 | 2012-07-29 |  | 2012-07-29 | 3 | 2012-08-01 | 14 | 2012-08-15 | 488 | 16 | 2013-12-16 | NA
| R | [7 empty] | 2014-08-01 | 417 | 2015-09-22 | 8 | 2015-09-30 | 21 | 2015-10-21 | 78 | 2016-01-07 | 40 | 2016-02-16 | 14 | 2016-03-01 | 7 | 2016-03-08 | 14 | 2016-03-22 | 152.5 | 5 | 2016-08-21 12:00 | NA
| A |  |  |  |  | T: 2015-01-21; U: 244; T: 2015-09-22; U: 8; V: 2015-09-30; W: 21; X: 2015-10-21; Y: 78; Z: 2016-01-07; AE: 0; AG: 0; AJ: 0; AK: 0; AL: 0
Note on G8: Fadi Barakat: W1 and W2 In one package (to be implemented together at same time). Supervision cannot wait for another year to supervise a second batch) This is NCB (view the timing, nature, and scattering of the related works)
Note on S9: Fadi Barakat: Lots
Note on AA9: Riwa ElKhoury: a 12 month Defect Notification Period should be taken into consideration
Note on AC9: Riwa ElKhoury: a 12 month Defect Notification Period should be taken into consideration
Note on AA12: Riwa ElKhoury: a 12 month Defect Notification Period should be taken into consideration
Note on AC12: Riwa ElKhoury: a 12 month Defect Notification Period should be taken into consideration
Note on G14: Fadi Barakat: Distributed over W1 and W2
Note on I17: Fadi Barakat: First Bid in Goods
Note on I20: Fadi Barakat: First Bid in Goods
Note on G26: Fadi Barakat: Shifted to PG002
Note on G29: Fadi Barakat: Shifted to PG001
Note on D38: Riwa ElKhoury: PG007, PG008, PG009 were merged in One ICB PG007-3.2 (4 Lots)
Note on D41: Riwa ElKhoury: PG007, PG008, PG009 were merged in One ICB PG007-3.2 (4 Lots)
Note on D44: Riwa ElKhoury: PG007, PG008, PG009 were merged in One ICB PG007-3.2 (4 Lots) USED TO BE pg008
Note on D47: Riwa ElKhoury: PG007, PG008, PG009 were merged in One ICB PG007-3.2 (4 Lots) used to be PG009
Note on G50: Riwa ElKhoury: replaced by PG007 LOT 1 & 2
Note on C53: Riwa ElKhoury: replaced by PG007
Note on G53: Riwa ElKhoury: replaced by PG007 (LOT 3)
Note on C56: Riwa ElKhoury: Replaced by PG007
Note on G56: Riwa ElKhoury: Replaced by PG007 (Lot 4)
Note on D59: Riwa ElKhoury: PG007, PG008, PG009 were merged in One ICB PG007-3.2 (4 Lots) used to be PG009

## Shopping
PROCUREMENT PLAN FOR GOODS AND WORKS (Shopping)
as of January 25, 2016
Costab ref | Plan vs. Actual | SN # | Proc. System Ref. # | Comp | Sub-Comp | Location/ Description of Assignment | Selection Method | Bank Rev. | Specs prep. Start Date | Interval | Interval | Interval | Quotations Submission Date | Interval | Comparaison of Quotations | Interval | Contract Draft | Interval | NOL Date | Interval | Contract Signature Date | Interval | Contract Start Date | Execution in days | Execution in months | Completion Date (original) | Completion Date (last revision) | Consultant Name | Comments
| A | B | C |  |  | D | F | G | H | I | I | K | L | M | N | O | P | Q | R | S | T | U | V | W | X | Y | Z | AC | AD
| P | SH001 | SHG001 | 2 | 2.1 | Pilot draft module for performance assessment program for principals | SH | PR | 1899-12-31 | 14 | 15 | 14 | 2013-02-02 | 7 | 2013-02-09 | 3 | 2013-02-12 | 14 | 2013-02-26 | 3 | 2013-03-01 | 14 | 2013-03-15 | 122 | 4 | 2013-07-15 | NA
| R | [7 empty] | 1899-12-31 | 14 | 15 | 14 | 2013-02-02 | 7 | 2013-02-09 | 3 | 2013-02-12 | 14 | 2013-02-26 | 3 | 2013-03-01 | 14 | 2014-03-15 | 122 | 4 | 2014-07-15
| A |  |  |  |  | I: 0; I: 0; K: 0; M: 0; O: 0; Q: 0; S: 0; U: 0; X: 0; Y: 0
| P | SH002 | SHG002 | 2 | 2.1 | Extending implementatiopn of module for performance assessment for programs for principals | SH | PO | 1899-12-31 | 14 | 15 | 14 | 2015-02-16 | 7 | 2015-02-23 | 3 | 2015-02-26 |  | 2015-02-26 | 3 | 2015-03-01 | 14 | 2015-03-15 | 366 | 12 | 2016-03-15 | NA
| R | [7 empty] | 1899-12-31 | 14 | 15 | 14 | 2015-02-16 | 7 | 2015-02-23 | 3 | 2015-02-26 |  | 2015-02-26 | 3 | 2015-03-01 | 14 | 2015-03-15 | 366 | 12 | 2016-03-15
| A |  |  |  |  | I: 0; I: 0; K: 0; M: 0; O: 0; Q: 0; S: 0; U: 0; X: 0; Y: 0
| P | SH003 | SHG003 | 2 | 2.1 | Pilot of draft module of school self assessment mechanism | SH | PO | 1899-12-31 | 14 | 15 | 14 | 2013-02-16 | 7 | 2013-02-23 | 3 | 2013-02-26 |  | 2013-02-26 | 3 | 2013-03-01 | 14 | 2013-03-15 | 122 | 4 | 2013-07-15 | NA
| R | [7 empty] | 1899-12-31 | 14 | 15 | 14 | 2015-02-16 | 7 | 2015-02-23 | 3 | 2015-02-26 |  | 2015-02-26 | 3 | 2015-03-01 | 14 | 2015-03-15 | 122 | 4 | 2015-07-15
| A |  |  |  |  | I: 0; K: 0; M: 0; O: 0; Q: 0; S: 0; U: 0; X: 0; Y: 0
| P | SH004 | SHG004 | 2 | 2.1 | Extend implementation of module for school self assessment mechanism | SH | PO | 1899-12-31 | 14 | 15 | 14 | 2013-02-16 | 7 | 2013-02-23 | 3 | 2013-02-26 |  | 2013-02-26 | 3 | 2013-03-01 | 14 | 2013-03-15 | 366 | 12 | 2014-03-16 | NA
| R | [7 empty] | 1899-12-31 | 14 | 15 | 14 | 2016-02-17 | 7 | 2016-02-24 | 3 | 2016-02-27 |  | 2016-02-27 | 3 | 2016-03-01 | 14 | 2016-03-15 | 366 | 12 | 2017-03-16
| A |  |  |  |  | I: 0; I: 0; K: 0; M: 0; O: 0; Q: 0; S: 0; U: 0; X: 0; Y: 0
| P | SH005 | SHG005 | 2 | 2.1 | new school vision printing of materials | SH | PR | 1899-12-31 | 14 | 15 | 14 | 2012-02-17 | 7 | 2012-02-24 | 3 | 2012-02-27 |  | 2012-02-27 | 3 | 2012-03-01 | 14 | 2012-03-15 | 30.5 | 1 | 2012-04-14 12:00 | NA
| R | [7 empty] | 2014-01-19 | 14 | 15 | 14 | 1900-01-28 | 7 | 1900-02-04 | 3 | 1900-02-07 |  | 1900-02-07 | 3 | 1900-02-10 | 14 | 2014-03-15 | 30.5 | 1 | 2014-04-14 12:00
| A |  |  |  |  | I: 0; I: 0; K: 0; M: 0; O: 0; Q: 0; S: 0; U: 0; X: 0; Y: 0
| P | SH006 | SHG006 | 2 | 2.1 | Workshops (lunch breaks, Coffee breaks) | SH | PO | 1899-12-31 | 14 | 15 | 14 | 2013-05-05 | 7 | 2013-05-12 | 3 | 2013-05-15 |  | 2013-05-15 | 3 | 2013-05-18 | 14 | 2013-06-01 | 1586 | 52 | 2017-10-04 | NA
| R | [7 empty] | 2014-07-07 | 14 | 15 | 14 | 1900-01-28 | 7 | 1900-02-04 | 3 | 1900-02-07 |  | 1900-02-07 | 3 | 1900-02-10 | 14 | 2014-03-15 | 1022.36 | 33.52 | 2016-12-31 08:38
| A |  |  |  |  | I: 0; I: 0; K: 0; M: 0; O: 0; Q: 0; S: 0; U: 0; X: 0; Y: 0
| P | SH007 | SHG007 | 3 | 3.2 | Financial information System | SH | PO | 1899-12-31 | 14 | 15 | 14 | 2012-04-11 | 7 | 2012-04-18 | 3 | 2012-04-21 |  | 2012-04-21 |  | 2012-04-21 | 14 | 2012-05-05 | 122 | 4 | 2012-09-04 | NA | Dynamesh | Completed
| R | [7 empty] | 2012-03-07 | 14 | 15 | 14 | 1900-01-28 | 0 | 1900-01-28 | 3 | 1900-01-31 | 14 | 1900-02-14 | 0 | 1900-02-14 | 14 | 1900-02-28 | 122 | 4 | 1900-06-30
| A | [7 empty] | 2012-01-12 | 14 | 15 | 14 | 2012-04-04 |  | 2012-04-04 | 3 | 2012-04-07 | 14 | 2012-04-21 | 0 | 2012-04-21 | 14 | 2012-05-05 | 122 | 4 | 2012-09-04 | 2012-09-04
| P | SH008 | SHG008 | 3 | 3.2 | Data Room Infrastructure Construction (Works might be done by Government-MEHE technical documents and supervision only ) | SH | PO | 1899-12-31 | 14 | 15 | 14 | 2013-09-07 | 7 | 2013-09-14 | 3 | 2013-09-17 |  | 2013-09-17 |  | 2013-09-17 | 14 | 2013-10-01 | 122 | 4 | 2014-01-31 | NA
| R |  |  |  |  | S: 0
A
| P | SH009 | SHG009 | 3 | 3.2 | Data Room Infrastructure Construction (Works might be done by Government-MEHE technical documents and supervision only ) | SH | PO | 1899-12-31 | 14 | 15 | 14 | 2013-09-07 | 7 | 2013-09-14 | 3 | 2013-09-17 |  | 2013-09-17 |  | 2013-09-17 | 14 | 2013-10-01 | 122 | 4 | 2014-01-31 | NA
| R |  |  |  |  | S: 0
A
| P | SH010 | SHG010 | 3 | 3.3 | Production and distribution of annual M&E report | SH | PO | 1899-12-31 | 14 | 15 | 14 | 2011-12-19 | 7 | 2011-12-26 | 3 | 2011-12-29 |  | 2011-12-29 | 3 | 2012-01-01 | 14 | 2012-01-15 | 1464 | 48 | 2016-01-18 | NA
| R | [7 empty] | 2013-11-21 | 14 | 15 | 14 | 1900-01-28 | 7 | 1900-02-04 | 3 | 1900-02-07 |  | 1900-02-07 | 3 | 1900-02-10 | 14 | 2014-01-15 | 1464 | 48 | 2018-01-18
| A |  |  |  |  | I: 0; I: 0; K: 0; M: 0; O: 0; Q: 0; S: 0; U: 0; X: 0; Y: 0
| P | SH011 | SHG011 | 3 | 3.3 | ESDS Office Equipment &Furniture | SH | PO | 1899-12-31 | 14 | 15 | 14 | 2013-10-05 | 7 | 2013-10-12 | 3 | 2013-10-15 |  | 2013-10-15 | 3 | 2013-10-18 | 14 | 2013-11-01 | 1464 | 24 | 2017-11-04 | NA
| R | [7 empty] | 2014-09-01 | 14 | 15 | 14 | 1900-01-28 | 7 | 1900-02-04 | 3 | 1900-02-07 |  | 1900-02-07 | 3 | 1900-02-10 | 14 | 2014-01-15 | 1081.835 | 35.47 | 2016-12-31 20:02
| A |  |  |  |  | I: 0; I: 0; K: 0; M: 0; O: 0; Q: 0; S: 0; U: 0; X: 0; Y: 0
| P | SH012 | SHG012 | 3 | 3.2 | Regional Office Data Centers Implementation | SH | PO | 1899-12-31 | 14 | 15 | 14 | 2013-10-05 | 7 | 2013-10-12 | 3 | 2013-10-15 |  | 2013-10-15 | 3 | 2013-10-18 | 14 | 2013-11-01 | 1464 | 24 | 2017-11-04 | NA
| R | [7 empty] | 2014-12-01 | 14 | 15 | 14 | 1900-01-28 | 7 | 1900-02-04 | 3 | 1900-02-07 |  | 1900-02-07 | 3 | 1900-02-10 | 14 | 2014-01-15 | 366 | 12 | 2015-01-16
| A |  |  |  |  | I: 0; I: 0; K: 0; M: 0; O: 0; Q: 0; S: 0; U: 0; X: 0; Y: 0
| P | SH013 | SHG013 | 3 | 3.3 | Storage (Enclosure and tapes) | SH | PO | 1899-12-31 | 14 | 15 | 14 | 2013-10-05 | 7 | 2013-10-12 | 3 | 2013-10-15 |  | 2013-10-15 | 3 | 2013-10-18 | 14 | 2013-11-01 | 1464 | 24 | 2017-11-04 | NA | Midware Data Systems Sal MDS | Completed
| R | [7 empty] | 2014-02-07 | 14 | 15 | 10 | 2014-03-10 | 15 | 2014-04-09 |  | N/A |  | N/A |  | 2014-05-12 | 0 | 2014-05-12 | 60 | 1.9672 | 2014-07-11
| A | [7 empty] | 2014-02-07 | 14 | 15 | 41693 | 2014-03-10 | 30 | 2014-04-09 |  | N/A |  | N/A |  | 2014-05-12 | 0 | 2014-05-12 | 60 | 1.9672 | 2014-07-11
| P | SH014 | SHG014 | 3 | 3.3 | Operating Costs | SH | NA | 1899-12-31 | 14 | 15 | 14 | 2013-10-05 | 7 | 2013-10-12 | 3 | 2013-10-15 |  | 2013-10-15 | 3 | 2013-10-18 | 14 | 2013-11-01 | 1464 | 24 | 2017-11-04 | NA |  | Ongoing
| R |  |  |  |  | H: 2013-06-01; Y: 2017-12-31
| A |  |  |  |  | H: NA; K: 0; M: 0; O: 0; Q: 0; S: 0; U: 0; X: 0; Y: 0
| P | SH014 | SHG015 | 3 | 3.1 | Physical Storage cabinet - National Exams Department Results Registers | SH | NA | 1899-12-31 | 14 | 15 | 14 | 2013-10-05 | 7 | 2013-10-12 | 3 | 2013-10-15 |  | 2013-10-15 | 3 | 2013-10-18 | 14 | 2013-11-01 | 1464 | 24 | 2017-11-04 | NA | Albert Massaad Sarl | Completed and Paid
| R | [7 empty] | 2014-10-23 | 18 | 19 | 22 | 1900-02-09 | 15 | 1900-02-24 |  | N/A |  | N/A |  | 2015-05-04 | 0 | 2015-05-04 | 45 | 1.4754 | 2015-06-18 | NA
| A |  |  |  |  | H: 2014-10-23; I: 19; I: 20; K: 21; L: 1900-02-09; M: 119; N: 1900-06-08; P: N/A; R: N/A; T: 2015-05-07; V: 2015-05-07; W: 45; X: 1.5; Y: 2015-06-21
Note on G29: Ghada Zeaiter: MOU between the Ministry and ECRD
Note on L46: Riwa ElKhoury: NO objection date
Note on P46: Riwa ElKhoury: Evaluation Report Date
Note on P52: Riwa ElKhoury: Evaluation Report Date

## Firms Cons.
PROCUREMENT PLAN FOR CONSULTANCY SERVICES - CONSULTING FIRMS
as of January 25, 2016
Costab ref | Plan vs. Actual | Proc. System Ref. # | SN. # | Comp | Sub-Comp | Location/ Description of Assignment | Unit (Mth/ Yr/ Study[Sty], Lumpsum [LS], Workshop [Wsh]) | Selection Method | Bank Rev. | TOR Start Date | Interval | TOR end Date | Interval | NOL Date | Interval | Adv. EOI end Date | Interval | Short Listing Report Date | Interval | NOL Date | Interval | RFP prep. | Interval | NOL Date | Interval | RFP Submission Date | Interval | Technical Evaluation Report Date | Interval | NOL Date | Interval | Finan. Public opening Date | Interval | Final Evaluation Report Date | Interval | Contract negotiation/Award- Draft | Interval | NOL Date | Interval | Contract signature Date | Interval | Contract Start Date | Execution in days | Execution in months | Completion Date (original) | Completion Date (last revision) | Consultant Name | Comments
| A | B | C |  |  | D | E | F | G | H | I | J | K | L | M | N | O | P | Q | R | S | T | U | V | W | X | Y | Z | AA | AB | AC | AD | AE | AF | AG | AH | AI | AJ | AK | AL | AM | AN | AO | AP | AQ | AR | AU | AV
| P | FC01 | FC01 | 1 | 1.2 | Consultancy Services for Design and supervision -Rehabilitation works of 144 pre-school sections |  | QCBS | PR | 2012-03-18 | 14 | 2012-04-01 |  | 2012-04-01 | 14 | 2012-04-15 | 7 | 2012-04-22 |  | 2012-04-22 | 7 | 2012-04-29 |  | 2012-04-29 | 28 | 2012-05-27 | 7 | 2012-06-03 |  | 2012-06-03 | 14 | 2012-06-17 | 5 | 2012-06-22 | 7 | 2012-06-29 |  | 2012-06-29 | 2 | 2012-07-01 | 2 | 2012-07-03 | 793 | 26 | 2014-09-04 | NA | Spectrum | Contract and Contract Amendment Signed and Ongoing
| R | [5 empty] | 0 |  |  | 2013-06-16 | 152 | 2013-11-15 | 3 | 2013-11-18 | 31 | 2013-12-19 | 21 | 2014-05-09 |  | 2014-05-14 |  | 2014-05-09 | 5 | 2014-05-14 | 46 | 2014-07-07 | 21 | 2014-07-28 | 14 | 2014-08-11 | 14 | 2014-08-25 | 7 | 2014-09-01 | 14 | 2014-09-15 | 14 | 2014-09-29 | 215 | 2015-05-02 | 14 | 2015-05-16 | 595 | 20 | 2016-12-31 | NA
| A | [8 empty] | 2013-06-16 | 152 | 2013-11-15 | 3 | 2013-11-18 | 31 | 2013-12-19 | 43 | 2014-05-09 | 5 | 2014-05-14 |  | 2014-05-09 | 5 | 2014-05-14 | 54 | 2014-07-07 | 54 | 2014-08-30 | 10 | 2014-09-09 | 7 | 2014-09-16 | 7 | 2014-09-23 |  | 2014-10-20 | 4 | 2014-10-24 | 238 | 2015-06-19 | 14 | 2015-07-03 | 547 | 18 | 2016-12-31 | N/A
| P | FC02 | FC02 | 1 | 1.2 | Early Childhood Education |  | QCBS | PO | 2011-04-18 | 14 | 2011-05-02 |  | 2011-05-02 | 14 | 2011-05-16 | 7 | 2011-05-23 |  | 2011-05-23 | 7 | 2011-05-30 |  | 2011-05-30 | 28 | 2011-06-27 | 7 | 2011-07-04 |  | 2011-07-04 | 14 | 2011-07-18 | 5 | 2011-07-23 | 7 | 2011-07-30 |  | 2011-07-30 | 2 | 2011-08-01 | 2 | 2011-08-03 | 91.5 | 3 | 2011-11-02 12:00 | NA
| R | [8 empty] | 2014-12-02 | 330 | 2015-10-28 | 3 | 2015-10-31 | 31 | 2015-12-01 | 14 | 2015-12-15 | 14 | 2015-12-29 | 7 | 2016-01-05 | 14 | 2016-01-19 | 42 | 2016-03-01 | 21 | 2016-03-22 | 14 | 2016-04-05 | 14 | 2016-04-19 | 7 | 2016-04-26 | 21 | 2016-05-17 | 14 | 2016-05-31 | 21 | 2016-06-21 | 3 | 2016-06-24 | 549 | 18 | 2017-12-25 | NA
| A |  |  |  |  | K: 0; M: 0; O: 0; Q: 0; S: 0; U: 0; W: 0; Y: 0; AA: 0; AC: 0; AE: 0; AG: 0; AI: 0; AK: 0; AM: 0; AP: 0
| P | FC03 | FC03 | 2 | 2.1 | Education LeadershipFirm I: Professional Development Program for School Principals &Administrators |  | QCBS | PR | 2013-07-01 | 14 | 2013-07-15 | 14 | 2013-07-29 | 14 | 2013-08-12 | 7 | 2013-08-19 | 14 | 2013-09-02 | 7 | 2013-09-09 | 14 | 2013-09-23 | 35 | 2013-10-28 | 7 | 2013-11-04 | 14 | 2013-11-18 | 14 | 2013-12-02 | 5 | 2013-12-07 | 7 | 2013-12-14 | 14 | 2013-12-28 | 2 | 2013-12-30 | 2 | 2014-01-01 | 1098 | 36 | 2017-01-03 | NA | Pearson - ERC | Contract signed and Ongoing
| R | [8 empty] | 2013-07-06 | 33 | 2013-08-08 | 26 | 2013-09-03 | 66 | 2013-11-08 | 50 | 2014-02-04 | 14 | 2014-02-18 | 7 | 2014-02-25 | 14 | 2014-03-11 | 63 | 2014-05-13 | 14 | 2014-07-15 | 14 | 2014-07-29 | 14 | 2014-08-12 | 5 | 2014-08-12 | 14 | 2014-10-08 | 8 | 2014-10-16 | 35 | 2014-11-20 | 7 | 2014-11-27 | 765 | 25.082 | 2016-12-31 | NA
| A | [8 empty] | 2013-07-06 | 33 | 2013-08-08 | 26 | 2013-09-03 | 66 | 2013-11-08 | 88 | 2014-02-04 | 34 | 2014-03-10 | 4 | 2014-03-14 | 0 | 2014-03-10 | 63 | 2014-05-12 | 64 | 2014-07-15 | 6 | 2014-07-21 | 3 | 2014-07-24 | 8 | 2014-08-01 | 68 | 2014-10-08 | 8 | 2014-10-16 |  | 2014-12-15 | 7 | 2014-12-15 | 747 | 24.4918 | 2016-12-31
| P | FC04 | FC04 | 2 | 2.1 | Education LeadershipFirm II: Consultancy Services for Design &Delivery of School Improvement Programs |  | QCBS | PR | 2013-12-15 | 14 | 2013-12-29 |  | 2013-12-29 | 14 | 2014-01-12 | 7 | 2014-01-19 |  | 2014-01-19 | 7 | 2014-01-26 |  | 2014-01-26 | 28 | 2014-02-23 | 7 | 2014-03-02 |  | 2014-03-02 | 14 | 2014-03-16 | 5 | 2014-03-21 | 7 | 2014-03-28 |  | 2014-03-28 | 2 | 2014-03-30 | 2 | 2014-04-01 | 732 | 24 | 2016-04-02 | NA | British Council, LU,LAU,Intertech Batinorm | Contract Signed and Ongoing
| R | [8 empty] | 2013-08-06 | 111 | 2013-11-25 | 3 | 2013-11-28 | 46 | 2014-01-13 | 116 | 2014-05-09 | 5 | 2014-05-14 |  | 2014-05-09 | 5 | 2014-05-14 | 47 | 2014-06-30 | 58 | 2014-08-27 | 14 | 2014-09-03 | 23 | 2014-09-26 | 171 | 2015-03-16 |  | 2015-03-16 | 4 | 2015-03-20 | 45 | 2015-05-04 | 7 | 2015-05-11 | 600 | 19.6721 | 2016-12-31 | NA
| A | [8 empty] | 2013-08-06 | 111 | 2013-11-25 | 3 | 2013-11-28 | 46 | 2014-01-13 | 116 | 2014-05-09 | 5 | 2014-05-14 |  | 2014-05-09 | 5 | 2014-05-14 | 47 | 2014-06-30 | 58 | 2014-08-27 |  | 2014-09-03 | 23 | 2014-09-26 | 171 | 2015-03-16 |  | 2015-03-16 | 4 | 2015-03-20 | 48 | 2015-05-07 |  | 2015-05-07 | 604 | 19.8033 | 2016-12-31
| P | FC05 | FC05 | 2 | 2.2 | Teacher professional development |  | QCBS | PR | 2013-12-15 | 14 | 2013-12-29 |  | 2013-12-29 | 14 | 2014-01-12 | 7 | 2014-01-19 |  | 2014-01-19 | 7 | 2014-01-26 |  | 2014-01-26 | 28 | 2014-02-23 | 7 | 2014-03-02 |  | 2014-03-02 | 14 | 2014-03-16 | 5 | 2014-03-21 | 7 | 2014-03-28 |  | 2014-03-28 | 2 | 2014-03-30 | 2 | 2014-04-01 | 915 | 30 | 2016-10-02 | NA
| R | [8 empty] | 2016-01-30 | 30 | 2016-02-29 | 14 | 2016-03-14 | 30 | 2016-04-13 | 21 | 2016-05-04 | 14 | 2016-05-18 | 7 | 2016-05-25 | 60 | 2016-07-24 | 42 | 2016-09-04 | 14 | 2016-09-18 | 14 | 2016-10-02 | 14 | 2016-10-16 | 5 | 2016-10-21 | 14 | 2016-11-04 | 14 | 2016-11-18 | 14 | 2016-12-02 | 7 | 2016-12-09 | 365 | 24 | 2017-12-09 | NA
A | bar: AR
| P | FC06 | FC06 | 2 | 2.2 | Training of surplus teachers on new assigned roales |  | SSS | PR | 2014-06-04 | 14 | 2014-06-18 | 14 | 2014-07-02 |  | 2014-07-02 |  | 2014-07-02 |  | 2014-07-02 | 2 | 2014-07-04 | 14 | 2014-07-18 | 28 | 2014-08-15 | 7 | 2014-08-22 | 14 | 2014-09-05 |  | 2014-09-05 | 1 | 2014-09-06 | 7 | 2014-09-13 | 14 | 2014-09-27 | 2 | 2014-09-29 | 2 | 2014-10-01 | 366 | 12 | 2015-10-02 | NA
| R | [8 empty] | 2016-02-08 | 14 | 2016-02-22 | 14 | 2016-03-07 |  | 2016-03-07 |  | 2016-03-07 |  | 2016-03-07 | 7 | 2016-03-14 | 14 | 2016-03-28 | 28 | 2016-04-25 | 14 | 2016-05-09 | 14 | 2016-05-23 |  | 2016-05-23 | 5 | 2016-05-28 | 14 | 2016-06-11 | 14 | 2016-06-25 | 2 | 2016-06-27 | 7 | 2016-07-04 | 366 | 12 | 2017-07-05 | NA
| A |  |  |  |  | I: 0; K: 0; M: 0; O: 0; Q: 0; S: 0; U: 0; W: 0; Y: 0; AA: 0; AC: 0; AE: 0; AG: 0; AI: 0; AK: 0; AM: 0; AP: 0; AQ: 0
| P | FC06 | FC06 | 3 | 3.1 | Firm to be named (NQF) |  | QCBS | PO | 2013-12-15 | 14 | 2013-12-29 |  | 2013-12-29 | 14 | 2014-01-12 | 7 | 2014-01-19 |  | 2014-01-19 | 7 | 2014-01-26 |  | 2014-01-26 | 28 | 2014-02-23 | 7 | 2014-03-02 |  | 2014-03-02 | 14 | 2014-03-16 | 5 | 2014-03-21 | 7 | 2014-03-28 |  | 2014-03-28 | 2 | 2014-03-30 | 2 | 2014-04-01 | 1098 | 36 | 2017-04-03 | NA
R | bar: AR
A
new | P | FC06 A | FC06 A | 3 | 3.1 | Development Regional Educational Offices, Budgeting & Accounting, Office management and Communication Procedures |  | QCBS | PR | 2014-02-28 | 33 | 2014-04-02 | 26 | 2014-04-28 | 66 | 2014-07-03 | 21 | 2014-07-24 | 14 | 2014-08-07 | 7 | 2014-08-14 | 60 | 2014-10-13 | 42 | 2014-11-24 | 14 | 2014-12-08 | 14 | 2014-12-22 | 14 | 2015-01-05 | 5 | 2015-01-10 | 14 | 2015-01-24 | 14 | 2015-02-07 | 14 | 2015-02-21 | 7 | 2015-02-28 | 1000 | 40 | 2017-11-24 | NA
| R | [8 empty] | 2016-03-01 | 33 | 2016-04-03 | 26 | 2016-04-29 | 66 | 2016-07-04 | 21 | 2016-07-25 | 14 | 2016-08-08 | 7 | 2016-08-15 | 60 | 2016-10-14 | 42 | 2016-11-25 | 14 | 2016-12-09 | 14 | 2016-12-23 | 14 | 2017-01-06 | 5 | 2017-01-11 | 14 | 2017-01-25 | 14 | 2017-02-08 | 14 | 2017-02-22 | 7 | 2017-03-01 | 305 | 10 | 2017-12-31 | NA
A
new | P | FC06 B | FC06 B | 3 | 3.1 | Development Private Education Service, Budgeting & Accounting, Office management and Communication Procedures |  | QCBS | PR | 2014-02-28 | 33 | 2014-04-02 | 26 | 2014-04-28 | 66 | 2014-07-03 | 21 | 2014-07-24 | 14 | 2014-08-07 | 7 | 2014-08-14 | 60 | 2014-10-13 | 42 | 2014-11-24 | 14 | 2014-12-08 | 14 | 2014-12-22 | 14 | 2015-01-05 | 5 | 2015-01-10 | 14 | 2015-01-24 | 14 | 2015-02-07 | 14 | 2015-02-21 | 7 | 2015-02-28 | 1000 | 40 | 2017-11-24 | NA
| R | [8 empty] | 2016-03-01 | 33 | 2016-04-03 | 26 | 2016-04-29 | 66 | 2016-07-04 | 21 | 2016-07-25 | 14 | 2016-08-08 | 7 | 2016-08-15 | 60 | 2016-10-14 | 42 | 2016-11-25 | 14 | 2016-12-09 | 14 | 2016-12-23 | 14 | 2017-01-06 | 5 | 2017-01-11 | 14 | 2017-01-25 | 14 | 2017-02-08 | 14 | 2017-02-22 | 7 | 2017-03-01 | 305 | 10 | 2017-12-31 | NA
A
new | P | FC06 C | FC06 C | 3 | 3.1 | Department d'orientation pedagogique: School Health Unit (1300 Schools) |  | QCBS | PR | 2014-02-28 | 33 | 2014-04-02 | 26 | 2014-04-28 | 66 | 2014-07-03 | 21 | 2014-07-24 | 14 | 2014-08-07 | 7 | 2014-08-14 | 60 | 2014-10-13 | 42 | 2014-11-24 | 14 | 2014-12-08 | 14 | 2014-12-22 | 14 | 2015-01-05 | 5 | 2015-01-10 | 14 | 2015-01-24 | 14 | 2015-02-07 | 14 | 2015-02-21 | 7 | 2015-02-28 | 1000 | 40 | 2017-11-24 | NA
| R | [8 empty] | 2016-03-01 | 33 | 2016-04-03 | 26 | 2016-04-29 | 66 | 2016-07-04 | 21 | 2016-07-25 | 14 | 2016-08-08 | 7 | 2016-08-15 | 60 | 2016-10-14 | 42 | 2016-11-25 | 14 | 2016-12-09 | 14 | 2016-12-23 | 14 | 2017-01-06 | 5 | 2017-01-11 | 14 | 2017-01-25 | 14 | 2017-02-08 | 14 | 2017-02-22 | 7 | 2017-03-01 | 305 | 10 | 2017-12-31 | NA
A
| P | FC06 | FC06 | 3 | 3.1 | Development /implementation of document management system, workflow and archiving needs |  | QCBS | PR | 2014-02-28 | 33 | 2014-04-02 | 26 | 2014-04-28 | 66 | 2014-07-03 | 21 | 2014-07-24 | 14 | 2014-08-07 | 7 | 2014-08-14 | 60 | 2014-10-13 | 42 | 2014-11-24 | 14 | 2014-12-08 | 14 | 2014-12-22 | 14 | 2015-01-05 | 5 | 2015-01-10 | 14 | 2015-01-24 | 14 | 2015-02-07 | 14 | 2015-02-21 | 7 | 2015-02-28 | 1000 | 40 | 2017-11-24 | NA
| R | [8 empty] | 2014-10-01 | 33 | 2014-11-03 | 26 | 2014-11-29 | 66 | 2015-02-03 | 21 | 2015-02-24 | 14 | 2015-03-10 | 7 | 2015-03-17 | 60 | 2015-05-16 | 42 | 2015-06-27 | 14 | 2015-07-11 | 14 | 2015-07-25 | 14 | 2015-08-08 | 5 | 2015-08-13 | 14 | 2015-08-27 | 14 | 2015-09-10 | 14 | 2015-09-24 | 7 | 2015-10-01 | 732 | 24 | 2017-10-02 | NA
A
new | P | FC06 D | FC06 D | 3 | 3.1 | Development /implementation of document management system, workflow and archiving needs |  | QCBS | PR | 2014-02-28 | 33 | 2014-04-02 | 26 | 2014-04-28 | 66 | 2014-07-03 | 21 | 2014-07-24 | 14 | 2014-08-07 | 7 | 2014-08-14 | 60 | 2014-10-13 | 42 | 2014-11-24 | 14 | 2014-12-08 | 14 | 2014-12-22 | 14 | 2015-01-05 | 5 | 2015-01-10 | 14 | 2015-01-24 | 14 | 2015-02-07 | 14 | 2015-02-21 | 7 | 2015-02-28 | 1000 | 40 | 2017-11-24 | NA
| R | [8 empty] | 2016-03-01 | 33 | 2016-04-03 | 26 | 2016-04-29 | 66 | 2016-07-04 | 21 | 2016-07-25 | 14 | 2016-08-08 | 7 | 2016-08-15 | 60 | 2016-10-14 | 42 | 2016-11-25 | 14 | 2016-12-09 | 14 | 2016-12-23 | 14 | 2017-01-06 | 5 | 2017-01-11 | 14 | 2017-01-25 | 14 | 2017-02-08 | 14 | 2017-02-22 | 7 | 2017-03-01 | 305 | 10 | 2017-12-31 | NA
A | bar: D
| P | FC06 | FC06 | 3 | 3.1 | Design and Delivery of MEHE National Exams Registers Archiving and Certification |  | QCBS | PO | 2014-02-28 | 33 | 2014-04-02 | 26 | 2014-04-28 | 66 | 2014-07-03 | 21 | 2014-07-24 | 14 | 2014-08-07 | 7 | 2014-08-14 | 60 | 2014-10-13 | 42 | 2014-11-24 | 14 | 2014-12-08 | 14 | 2014-12-22 | 14 | 2015-01-05 | 5 | 2015-01-10 | 14 | 2015-01-24 | 14 | 2015-02-07 | 14 | 2015-02-21 | 7 | 2015-02-28 | 1000 | 40 | 2017-11-24 | NA |  | On Hold
| R | [8 empty] | 2016-01-04 | 30 | 2016-02-03 | 14 | 2016-02-17 | 14 | 2016-03-02 | 30 | 2016-04-01 | 0 | N/A | 14 | 2016-04-15 | 0 | N/A | 45 | 2016-05-30 | 30 | 2016-06-29 |  | N/A | 14 | 2016-07-13 | 5 | 2016-07-13 | 14 | 2016-07-27 | 14 | 2016-08-10 | 14 | 2016-08-24 | 7 | 2016-08-31 | 365 | 12 | 2017-08-31 | NA
| A |  |  |  |  | H: 2014-03-26; I: 33; J: 2014-04-25; K: 10; L: 2014-05-05; M: 65; N: 2014-07-09; O: 56; P: 2014-09-03; R: N/A; T: 2014-10-20; V: N/A; X: 2014-12-02; Z: 2014-12-30; AB: N/A; AD: 2015-05-14
| P | FC07 | FC07 | 3 | 3.1 | Operational Training Program for MEHE personnel |  | QCBS | PO | 2011-08-18 | 14 | 2011-09-01 |  | 2011-09-01 | 14 | 2011-09-15 | 7 | 2011-09-22 |  | 2011-09-22 | 7 | 2011-09-29 |  | 2011-09-29 | 28 | 2011-10-27 | 7 | 2011-11-03 |  | 2011-11-03 | 14 | 2011-11-17 | 5 | 2011-11-22 | 7 | 2011-11-29 |  | 2011-11-29 | 2 | 2011-12-01 | 2 | 2011-12-03 | 366 | 12 | 2012-12-03 | NA
| R | [5 empty] | 0 |  |  | 2016-03-15 | 14 | 2016-03-29 |  | 2016-03-29 | 14 | 2016-04-12 | 7 | 2016-04-19 |  | 2016-04-19 | 7 | 2016-04-19 | 45 | 2016-06-03 | 28 | 2016-07-01 | 7 | 2016-07-08 |  | 2016-07-08 | 14 | 2016-07-22 | 5 | 2016-07-27 | 14 | 2016-08-10 |  | 2016-08-10 | 7 | 2016-08-17 | 3 | 2016-08-20 | 366 | 12 | 2017-08-21 | NA
| A |  |  |  |  | I: 0; K: 0; M: 0; O: 0; Q: 0; S: 0; U: 0; W: 0; Y: 0; AA: 0; AC: 0; AE: 0; AG: 0; AI: 0; AK: 0; AM: 0; AP: 0; AQ: 0
| P | FC08 | FC08 | 3 | 3.1 | Activation of a citizen service desk and development of guidelines and procedures for transaction |  | QCBS | PO | 2011-08-18 | 14 | 2011-09-01 |  | 2011-09-01 | 14 | 2011-09-15 | 7 | 2011-09-22 |  | 2011-09-22 | 7 | 2011-09-29 |  | 2011-09-29 | 28 | 2011-10-27 | 7 | 2011-11-03 |  | 2011-11-03 | 14 | 2011-11-17 | 5 | 2011-11-22 | 7 | 2011-11-29 |  | 2011-11-29 | 2 | 2011-12-01 | 2 | 2011-12-03 | 366 | 12 | 2012-12-03 | NA
| R | [5 empty] | 0 |  |  | 2015-04-03 | 14 | 2015-04-17 |  | 2015-04-17 | 14 | 2015-05-01 | 7 | 2015-05-08 |  | 2015-05-08 | 7 | 2015-05-15 |  | 2015-05-15 | 28 | 2015-06-12 | 7 | 2015-06-19 |  | 2015-06-19 | 14 | 2015-07-03 | 5 | 2015-07-08 | 14 | 2015-07-22 |  | 2015-07-22 | 7 | 2015-07-29 | 3 | 2015-08-01 | 274.5 | 9 | 2016-05-01 12:00 | NA
| A |  |  |  |  | I: 0; K: 0; M: 0; O: 0; Q: 0; S: 0; U: 0; W: 0; Y: 0; AA: 0; AC: 0; AE: 0; AG: 0; AI: 0; AK: 0; AM: 0; AP: 0; AQ: 0
| P | FC09 | FC09 | 3 | 3.1 | Delivery of training programs |  | QCBS | PO | 2010-09-18 | 14 | 2010-10-02 |  | 2010-10-02 | 14 | 2010-10-16 | 7 | 2010-10-23 |  | 2010-10-23 | 7 | 2010-10-30 |  | 2010-10-30 | 28 | 2010-11-27 | 7 | 2010-12-04 |  | 2010-12-04 | 14 | 2010-12-18 | 5 | 2010-12-23 | 7 | 2010-12-30 |  | 2010-12-30 | 2 | 2011-01-01 | 2 | 2011-01-03 | 1098 | 36 | 2014-01-05 | NA
| R | [8 empty] | 2013-09-05 | 14 | 2013-09-19 |  | 2013-09-19 | 14 | 2013-10-03 | 7 | 2013-10-10 |  | 2013-10-10 | 7 | 2013-10-17 |  | 2013-10-17 | 28 | 2013-11-14 | 7 | 2013-11-21 |  | 2013-11-21 | 14 | 2013-12-05 | 5 | 2013-12-10 | 14 | 2013-12-24 |  | 2013-12-24 | 7 | 2013-12-31 | 3 | 2014-01-03 | 1098 | 36 | 2017-01-05 | NA
| A |  |  |  |  | I: 0; K: 0; M: 0; O: 0; Q: 0; S: 0; U: 0; W: 0; Y: 0; AA: 0; AC: 0; AE: 0; AG: 0; AI: 0; AK: 0; AM: 0; AP: 0; AQ: 0
| P | FC10 | FC10 | 3 | 3.1 | Communication campaign |  | QCBS | PO | 2011-09-18 | 14 | 2011-10-02 |  | 2011-10-02 | 14 | 2011-10-16 | 7 | 2011-10-23 |  | 2011-10-23 | 7 | 2011-10-30 |  | 2011-10-30 | 28 | 2011-11-27 | 7 | 2011-12-04 |  | 2011-12-04 | 14 | 2011-12-18 | 5 | 2011-12-23 | 7 | 2011-12-30 |  | 2011-12-30 | 2 | 2012-01-01 | 2 | 2012-01-03 | 1098 | 36 | 2015-01-05 | NA
| R | [8 empty] | 2014-10-05 | 14 | 2014-10-19 |  | 2014-10-19 | 14 | 2014-11-02 | 7 | 2014-11-09 |  | 2014-11-09 | 7 | 2014-11-16 | 28 | 2014-12-14 | 28 | 2015-01-11 | 7 | 2015-01-18 |  | 2015-01-18 | 14 | 2015-02-01 | 5 | 2015-02-06 | 14 | 2015-02-20 |  | 2015-02-20 | 7 | 2015-02-27 | 3 | 2015-03-02 | 732 | 24 | 2017-03-03 | NA
| A |  |  |  |  | I: 0; K: 0; M: 0; O: 0; Q: 0; S: 0; U: 0; W: 0; Y: 0; AA: 0; AC: 0; AE: 0; AG: 0; AI: 0; AK: 0; AM: 0; AP: 0; AQ: 0
| P | FC11 | FC11 | 3 | 3.1 | TIMSS |  | SSS | PR | 2010-09-06 | 14 | 2010-09-20 | 14 | 2010-10-04 |  | 2010-10-04 |  | 2010-10-04 |  | 2010-10-04 | 2 | 2010-10-06 | 14 | 2010-10-20 | 28 | 2010-11-17 | 7 | 2010-11-24 | 14 | 2010-12-08 |  | 2010-12-08 | 1 | 2010-12-09 | 7 | 2010-12-16 | 14 | 2010-12-30 | 2 | 2011-01-01 | 2 | 2011-01-03 | 1830 | 60 | 2016-01-07 | NA | TIMSS | Ongoing
| R | [5 empty] | 0 |  |  | 2013-01-01 | 14 | 2013-01-15 | 14 | 2013-01-29 | 14 | 2013-02-12 |  | 2013-02-12 | 14 | 2013-02-26 | 7 | 2013-03-05 | 14 | 2013-03-19 | 28 | 2013-04-16 | 7 | 2013-04-23 | 14 | 2013-05-07 |  | 2013-05-07 | 3 | 2013-05-10 | 7 | 2013-05-17 | 14 | 2013-05-31 | 7 | 2013-06-07 | 3 | 2013-06-10 | 1098 | 36 | 2016-06-12 | NA
| A |  |  |  |  | H: 2013-01-01; AB: 2013-05-02; AD: 2013-05-02; AE: 3; AH: 0; AI: 14; AJ: 2013-05-05; AK: 7; AN: 2013-05-02; AO: 1339; AP: 43.9016; AQ: 2016-12-31
| P | FC12 | FC12 | 3 | 3.1 | PISA |  | SSS | PR | 2010-09-06 | 14 | 2010-09-20 | 14 | 2010-10-04 |  | 2010-10-04 |  | 2010-10-04 |  | 2010-10-04 | 2 | 2010-10-06 | 14 | 2010-10-20 | 28 | 2010-11-17 | 7 | 2010-11-24 | 14 | 2010-12-08 |  | 2010-12-08 | 1 | 2010-12-09 | 7 | 2010-12-16 | 14 | 2010-12-30 | 2 | 2011-01-01 | 2 | 2011-01-03 | 1830 | 60 | 2016-01-07 | NA | PISA
| R | [8 empty] | 2014-05-01 | 14 | 2014-05-15 | 14 | 2014-05-29 | 14 | 2014-06-12 |  | 2014-06-12 | 14 | 2014-06-26 | 7 | 2014-07-03 | 14 | 2014-07-17 | 28 | 2014-08-14 | 7 | 2014-08-21 | 14 | 2014-09-04 |  | 2014-09-04 | 3 | 2014-09-07 | 7 | 2014-09-14 | 14 | 2014-09-28 | 7 | 2014-10-05 | 3 | 2014-10-08 | 814.35 | 26.7 | 2016-12-30 08:24 | NA
| A |  |  |  |  | H: 2013-01-01; L: 0; AB: 2013-05-02; AD: 2013-05-02; AE: 3; AH: 0; AJ: 2013-05-05; AN: 2014-09-05; AO: 848.205; AP: 27.81; AQ: 2016-12-31 04:55
| P | FC13 | FC13 | 3 | 3.2 | Training Program - ICT of MEHE |  | QCBS | PO | 2013-12-15 | 14 | 2013-12-29 |  | 2013-12-29 | 14 | 2014-01-12 | 7 | 2014-01-19 |  | 2014-01-19 | 7 | 2014-01-26 |  | 2014-01-26 | 28 | 2014-02-23 | 7 | 2014-03-02 |  | 2014-03-02 | 14 | 2014-03-16 | 5 | 2014-03-21 | 7 | 2014-03-28 |  | 2014-03-28 | 2 | 2014-03-30 | 2 | 2014-04-01 | 1098 | 36 | 2017-04-03 | NA
| R | [8 empty] | 2014-10-16 | 14 | 2014-10-30 |  | 2014-10-30 | 14 | 2014-11-13 | 7 | 2014-11-20 |  | 2014-11-20 | 7 | 2014-11-27 |  | 2014-11-27 | 28 | 2014-12-25 | 7 | 2015-01-01 |  | 2015-01-01 | 14 | 2015-01-15 | 5 | 2015-01-20 | 7 | 2015-01-27 |  | 2015-01-27 | 3 | 2015-01-30 | 3 | 2015-02-02 | 1037 | 34 | 2017-12-05 | NA
| A |  |  |  |  | I: 0; K: 0; M: 0; O: 0; Q: 0; S: 0; U: 0; W: 0; Y: 0; AA: 0; AC: 0; AE: 0; AG: 0; AI: 0; AK: 0; AM: 0; AQ: 0
| P | FC14 | FC14 | 3 | 3.2 | Portal Software |  | QCBS | PO | 2011-07-19 | 14 | 2011-08-02 |  | 2011-08-02 | 14 | 2011-08-16 | 7 | 2011-08-23 |  | 2011-08-23 | 7 | 2011-08-30 |  | 2011-08-30 | 28 | 2011-09-27 | 7 | 2011-10-04 |  | 2011-10-04 | 14 | 2011-10-18 | 5 | 2011-10-23 | 7 | 2011-10-30 |  | 2011-10-30 | 2 | 2011-11-01 | 2 | 2011-11-03 | 732 | 24 | 2013-11-04 | NA
| R | [5 empty] | 0 |  |  | 2016-03-16 | 14 | 2016-03-30 |  | 2016-03-30 | 14 | 2016-04-13 | 7 | 2016-04-20 |  | 2016-04-20 | 7 | 2016-04-27 |  | 2016-04-27 | 28 | 2016-05-25 | 7 | 2016-06-01 |  | 2016-06-01 | 14 | 2016-06-15 | 5 | 2016-06-20 | 7 | 2016-06-27 |  | 2016-06-27 | 3 | 2016-06-30 | 3 | 2016-07-03 | 545.95 | 17.9 | 2017-12-30 22:48 | NA
| A |  |  |  |  | I: 0; K: 0; M: 0; O: 0; Q: 0; S: 0; U: 0; W: 0; Y: 0; AA: 0; AC: 0; AE: 0; AG: 0; AI: 0; AK: 0; AM: 0; AP: 0; AQ: 0
| P | FC14 | FC14 | 3 | 3.2 | Client Security Application (To be shifted to Goods) |  | QCBS | PO | 2011-03-18 | 14 | 2011-04-01 |  | 2011-04-01 | 14 | 2011-04-15 | 7 | 2011-04-22 |  | 2011-04-22 | 7 | 2011-04-29 |  | 2011-04-29 | 28 | 2011-05-27 | 7 | 2011-06-03 |  | 2011-06-03 | 14 | 2011-06-17 | 5 | 2011-06-22 | 7 | 2011-06-29 |  | 2011-06-29 | 2 | 2011-07-01 | 2 | 2011-07-03 | 366 | 12 | 2012-07-03 | NA
| R | [5 empty] | 0 |  |  | 2013-10-16 | 14 | 2013-10-30 |  | 2013-10-30 | 14 | 2013-11-13 | 7 | 2013-11-20 |  | 2013-11-20 | 7 | 2013-11-27 |  | 2013-11-27 | 28 | 2013-12-25 | 7 | 2014-01-01 |  | 2014-01-01 | 14 | 2014-01-15 | 5 | 2014-01-20 | 7 | 2014-01-27 |  | 2014-01-27 | 3 | 2014-01-30 | 3 | 2014-02-02 | 366 | 12 | 2015-02-03 | NA
| A |  |  |  |  | I: 0; K: 0; M: 0; O: 0; Q: 0; S: 0; U: 0; W: 0; Y: 0; AA: 0; AC: 0; AE: 0; AG: 0; AI: 0; AK: 0; AM: 0; AP: 0; AQ: 0
| P | FC15 | FC15 | 3 | 3.2 | Maintenance and enhancement of running application |  | QCBS | PR | 2011-03-18 | 14 | 2011-04-01 |  | 2011-04-01 | 14 | 2011-04-15 | 7 | 2011-04-22 |  | 2011-04-22 | 7 | 2011-04-29 |  | 2011-04-29 | 28 | 2011-05-27 | 7 | 2011-06-03 |  | 2011-06-03 | 14 | 2011-06-17 | 5 | 2011-06-22 | 7 | 2011-06-29 |  | 2011-06-29 | 2 | 2011-07-01 | 2 | 2011-07-03 | 366 | 12 | 2012-07-03 | NA
| R | [5 empty] | 0 |  |  | 2016-05-15 | 30 | 2016-06-14 | 14 | 2016-06-28 | 21 | 2016-07-19 | 14 | 2016-08-02 | 14 | 2016-08-16 | 7 | 2016-08-23 | 14 | 2016-09-06 | 42 | 2016-10-18 | 21 | 2016-11-08 | 14 | 2016-11-22 | 14 | 2016-12-06 | 7 | 2016-12-13 | 21 | 2017-01-03 | 14 | 2017-01-17 | 21 | 2017-02-07 | 14 | 2017-02-21 | 311.1 | 10.2 | 2017-12-29 02:24 | NA
| A |  |  |  |  | I: 0; K: 0; M: 0; O: 0; Q: 0; S: 0; U: 0; W: 0; Y: 0; AA: 0; AC: 0; AE: 0; AG: 0; AI: 0; AK: 0; AM: 0; AP: 0; AQ: 0
| P | FC16 | FC16 | 3 | 3.2 | Enhancement to EMIS |  | QCBS | PO | 2011-04-18 | 14 | 2011-05-02 |  | 2011-05-02 | 14 | 2011-05-16 | 7 | 2011-05-23 |  | 2011-05-23 | 7 | 2011-05-30 |  | 2011-05-30 | 28 | 2011-06-27 | 7 | 2011-07-04 |  | 2011-07-04 | 14 | 2011-07-18 | 5 | 2011-07-23 | 7 | 2011-07-30 |  | 2011-07-30 | 2 | 2011-08-01 | 2 | 2011-08-03 | 1098 | 36 | 2014-08-05 | NA
| R | [5 empty] | 0 |  |  | 2015-01-25 | 30 | 2015-02-24 | 14 | 2015-03-10 | 21 | 2015-03-31 | 14 | 2015-04-14 | 14 | 2015-04-28 | 7 | 2015-05-05 | 14 | 2015-05-19 | 42 | 2015-06-30 | 21 | 2015-07-21 | 14 | 2015-08-04 | 14 | 2015-08-18 | 7 | 2015-08-25 | 21 | 2015-09-15 | 14 | 2015-09-29 | 21 | 2015-10-20 | 14 | 2015-11-03 | 732 | 24 | 2017-11-04 | NA
| A |  |  |  |  | I: 0; K: 0; M: 0; O: 0; Q: 0; S: 0; U: 0; W: 0; Y: 0; AA: 0; AC: 0; AE: 0; AG: 0; AI: 0; AK: 0; AM: 0; AP: 0; AQ: 0
| P | FC17 | FC17 | 3 | 3.2 | Development and Consolidation of Applications |  | QCBS | PO | 2012-05-19 | 14 | 2012-06-02 |  | 2012-06-02 | 14 | 2012-06-16 | 7 | 2012-06-23 |  | 2012-06-23 | 7 | 2012-06-30 |  | 2012-06-30 | 28 | 2012-07-28 | 7 | 2012-08-04 |  | 2012-08-04 | 14 | 2012-08-18 | 5 | 2012-08-23 | 7 | 2012-08-30 |  | 2012-08-30 | 2 | 2012-09-01 | 2 | 2012-09-03 | 549 | 18 | 2014-03-06 | NA
| R | [8 empty] | 2016-06-17 | 14 | 2016-07-01 |  | 2016-07-01 | 14 | 2016-07-15 | 7 | 2016-07-22 |  | 2016-07-22 | 7 | 2016-07-29 |  | 2016-07-29 | 28 | 2016-08-26 | 7 | 2016-09-02 |  | 2016-09-02 | 14 | 2016-09-16 | 5 | 2016-09-21 | 7 | 2016-09-28 |  | 2016-09-28 | 3 | 2016-10-01 | 3 | 2016-10-04 | 366 | 12 | 2017-10-05 | NA
| A |  |  |  |  | I: 0; K: 0; M: 0; O: 0; Q: 0; S: 0; U: 0; W: 0; Y: 0; AA: 0; AC: 0; AE: 0; AG: 0; AI: 0; AK: 0; AM: 0; AP: 0; AQ: 0
| P | FC18 | FC18 | 3 | 3.1 | External Auditor |  | LCS | PR | 2012-11-18 | 14 | 2012-12-02 | 14 | 2012-12-16 | 14 | 2012-12-30 | 7 | 2013-01-06 |  | 2013-01-06 | 7 | 2013-01-13 | 14 | 2013-01-27 | 28 | 2013-02-24 | 7 | 2013-03-03 | 14 | 2013-03-17 | 14 | 2013-03-31 | 5 | 2013-04-05 | 7 | 2013-04-12 | 14 | 2013-04-26 | 2 | 2013-04-28 | 3 | 2013-05-01 | 2196 | 72 | 2019-05-06 | NA | PriceWaterHouseCoopers | Contract Signed and Ongoing
| R | [5 empty] | 0 |  |  | 2014-01-06 | 15 | 2014-01-21 | 3 | 2014-01-24 | 6 | 2014-01-30 | 7 | 2014-03-20 |  | 2014-03-31 | 7 | 2014-03-20 | 11 | 2014-03-31 | 22 | 2014-04-22 | 24 | 2014-05-16 | 14 | 2014-05-30 | 14 | 2014-06-13 | 5 | 2014-06-18 | 7 | 2014-06-25 | 14 | 2014-07-09 | 3 | 2014-07-12 | 3 | 2014-07-15 | 1098 | 36 | 2017-07-17 | NA
| A | [8 empty] | 2014-01-06 | 15 | 2014-01-21 | 3 | 2014-01-24 | 6 | 2014-01-30 | 36 | 2014-03-20 |  | 2014-03-31 |  | 2014-03-20 | 11 | 2014-03-31 | 22 | 2014-04-22 | 24 | 2014-05-16 | 7 | 2014-05-23 | 6 | 2014-05-29 | 7 | 2014-06-05 |  | 2014-06-05 | 6 | 2014-06-11 | 1 | 2014-06-12 | 0 | 2014-06-12 | 1145.275 | 37.55 | 2017-07-31 06:36
| P | FC19 | FC19 | 3 | 3.1 | Internal Auditor |  | LCS | PR | 2013-01-14 | 14 | 2013-01-28 |  | 2013-01-28 | 14 | 2013-02-11 | 7 | 2013-02-18 |  | 2013-02-18 | 7 | 2013-02-25 |  | 2013-02-25 | 28 | 2013-03-25 | 7 | 2013-04-01 |  | 2013-04-01 | 14 | 2013-04-15 | 5 | 2013-04-20 | 7 | 2013-04-27 |  | 2013-04-27 | 2 | 2013-04-29 | 2 | 2013-05-01 | 2196 | 72 | 2019-05-06 | NA | Grant Thornton | Contract Signed and Ongoing
| R | [5 empty] | 0 |  |  | 2013-08-05 | 23 | 2013-08-28 | 8 | 2013-09-05 | 62 | 2013-11-06 | 21 | 2013-12-19 |  | 2013-12-19 | 7 | 2013-12-19 | 14 | 2013-12-27 | 24 | 2014-01-20 | 22 | 2014-02-11 | 7 | 2014-02-18 | 14 | 2014-02-27 | 12 | 2014-03-11 |  | 2014-03-11 | 3 | 2014-03-14 | 3 | 2014-04-10 |  | 2014-04-10 | 1098 | 36 | 2016-12-31 | NA
| A | [8 empty] | 2013-08-05 | 23 | 2013-08-28 | 8 | 2013-09-05 | 62 | 2013-11-06 | 43 | 2013-12-19 |  | 2013-12-19 |  | 2013-12-19 | 8 | 2013-12-27 | 24 | 2014-01-20 | 22 | 2014-02-11 | 7 | 2014-02-18 | 9 | 2014-02-27 | 12 | 2014-03-11 |  | 2014-03-11 | 3 | 2014-03-14 | 27 | 2014-04-10 |  | 2014-04-10 | 1098 | 36 | 2016-12-31
| P | FC20 | FC20 | 3 | 3.3 | M&E Studies |  | QCBS | PO | 2013-03-17 | 14 | 2013-03-31 |  | 2013-03-31 | 14 | 2013-04-14 | 7 | 2013-04-21 |  | 2013-04-21 | 7 | 2013-04-28 |  | 2013-04-28 | 28 | 2013-05-26 | 7 | 2013-06-02 |  | 2013-06-02 | 14 | 2013-06-16 | 5 | 2013-06-21 | 7 | 2013-06-28 |  | 2013-06-28 | 2 | 2013-06-30 | 2 | 2013-07-02 | 1098 | 36 | 2016-07-04 | NA
| R | [8 empty] | 2016-03-10 | 14 | 2016-03-24 |  | 2016-03-24 | 14 | 2016-04-07 | 7 | 2016-04-14 |  | 2016-04-14 | 7 | 2016-04-21 |  | 2016-04-21 | 28 | 2016-05-19 | 7 | 2016-05-26 |  | 2016-05-26 | 14 | 2016-06-09 | 5 | 2016-06-14 | 7 | 2016-06-21 |  | 2016-06-21 | 3 | 2016-06-24 | 3 | 2016-06-27 | 549 | 18 | 2017-12-28 | NA
| A |  |  |  |  | I: 0; K: 0; M: 0; O: 0; Q: 0; S: 0; U: 0; W: 0; Y: 0; AA: 0; AC: 0; AE: 0; AG: 0; AI: 0; AK: 0; AM: 0; AP: 0; AQ: 0
| P | FC21 | FC21 | 3 | 3.3 | Development of M&E Framework |  | QCBS | PO | 2013-03-17 | 14 | 2013-03-31 |  | 2013-03-31 | 14 | 2013-04-14 | 7 | 2013-04-21 |  | 2013-04-21 | 7 | 2013-04-28 |  | 2013-04-28 | 28 | 2013-05-26 | 7 | 2013-06-02 |  | 2013-06-02 | 14 | 2013-06-16 | 5 | 2013-06-21 | 7 | 2013-06-28 |  | 2013-06-28 | 2 | 2013-06-30 | 2 | 2013-07-02 | 1098 | 36 | 2016-07-04 | NA
| R | [8 empty] | 2013-12-25 | 14 | 2014-01-08 |  | 2014-01-08 | 14 | 2014-01-22 | 7 | 2014-01-29 |  | 2014-01-29 | 7 | 2014-02-05 |  | 2014-02-05 | 28 | 2014-03-05 | 7 | 2014-03-12 |  | 2014-03-12 | 14 | 2014-03-26 | 5 | 2014-03-31 | 7 | 2014-04-07 |  | 2014-04-07 | 3 | 2014-04-10 | 3 | 2014-03-02 | 1098 | 36 | 2017-03-04 | NA
| A |  |  |  |  | I: 0; K: 0; M: 0; O: 0; Q: 0; S: 0; U: 0; W: 0; Y: 0; AA: 0; AC: 0; AE: 0; AG: 0; AI: 0; AK: 0; AM: 0; AP: 0; AQ: 0
Note on K1: Riwa ElKhoury:
Note on AC45: Riwa ElKhoury: Signed on March 31, 2015
Note on AC46: Riwa ElKhoury: Signed on March 31, 2015

## Ind. Cons.
PROCUREMENT PLAN FOR CONSULTANCY SERVICES - INDIVIDUAL CONSULTANTS
as of January 25, 2016
Costab ref | Plan vs. Actual | Proc. System Ref. # | SN. # | Comp | Sub-Comp | Location/ Description of Assignment | Unit (Mth/ Yr/ Study[Sty], Lumpsum [LS], Workshop [Wsh]) | Selection Method | Bank Rev. | TOR Start Date | Interval | TOR end Date | Interval | NOL Date | Interval | Adv. EOI end Date | Interval | Short Listing Report Date | Interval | NOL Date | Interval | Contract negotiation/Award- Draft | Interval | NOL Date | Interval | Contract signature Date | Interval | Contract Start Date | Execution in days | Execution in months | Completion Date (original) | Completion Date (last revision) | Consultant Name | Comments
| A | B | C |  |  | D | E | F | G | H | I | J | K | L | M | N | O | P | Q | R | S | T | U | V | W | X | Y | Z | AA | AB | AC | AD | AG | AH
NEW | P | IC020 | IC020 | 1 | 1.2 | Learning Difficulty Assessment Consultant (Early Childhood) |  | IC | PO | 2011-05-13 | 14 | 2011-05-27 |  | 2011-05-27 | 14 | 2011-06-10 | 7 | 2011-06-17 |  | 2011-06-17 | 7 | 2011-06-24 |  | 2011-06-24 | 7 | 2011-07-01 | 2 | 2011-07-03 | 1464 | 48 | 2015-07-06 | NA |  | Re-launched
| R | [8 empty] | 2014-06-04 | 14 | 2014-06-18 |  | 2014-06-25 | 14 | 2016-01-27 | 35 | 2016-03-02 |  | N/A |  | 2016-03-09 |  | 2016-03-16 | 7 | 2016-03-23 | 2 | 2016-03-25 | 40 | 2 | 2016-05-04 | NA
| A |  |  |  |  | H: 2014-06-04; I: 14; J: 2014-06-18; K: 12; L: 2014-06-30; N: 2016-01-27; R: N/A; U: 0; W: 0; Y: 0; AB: 0; AC: 0
NEW | P | IC033 | IC033 | 2 | 2.1 | Education Expert (Principals Standards and Principals Self-Assessment Model) |  | SSS | PR | 2011-05-13 | 14 | 2011-05-27 |  | 2011-05-27 | 14 | 2011-06-10 | 7 | 2011-06-17 |  | 2011-06-17 | 7 | 2011-06-24 |  | 2011-06-24 | 7 | 2011-07-01 | 2 | 2011-07-03 | 1464 | 48 | 2015-07-06 | NA | Rima Karami Akkary | Contract Signed and Ongoing( the level of effort is 35 working days not consecutive)
| R | [8 empty] | 2015-05-22 | 14 | 2015-06-05 | 5 | 2015-06-10 |  | N/A |  | N/A |  | N/A |  | 2015-06-17 | 7 | 2015-06-24 | 30 | 2015-07-24 | 2 | 2015-07-26 | 30.5 | 1 | 2015-08-25 12:00 | NA
| A | [8 empty] | 2015-05-22 | 14 | 2015-06-05 | 5 | 2015-06-10 |  | N/A |  | N/A |  | N/A |  | 2015-06-18 | 4 | 2015-06-22 | 35 | 2015-07-27 | 0 | 2015-07-27 | 35 | 1.1475 | 2016-12-31
1 | P | IC021 | IC021 | 2 | 2.1 | Development and delivery of training Program for WG members |  | IC | PO | 2011-05-13 | 14 | 2011-05-27 |  | 2011-05-27 | 14 | 2011-06-10 | 7 | 2011-06-17 |  | 2011-06-17 | 7 | 2011-06-24 |  | 2011-06-24 | 7 | 2011-07-01 | 2 | 2011-07-03 | 1464 | 48 | 2015-07-06 | NA
| R | [8 empty] | 2013-08-06 | 14 | 2013-08-20 |  | 2013-08-20 | 14 | 2013-09-03 | 7 | 2013-09-10 |  | 2013-09-10 | 7 | 2013-09-17 |  | 2013-09-17 | 7 | 2013-09-24 | 2 | 2013-10-01 | 30.5 | 1 | 2013-10-31 12:00 | NA
| A |  |  |  |  | I: 0; K: 0; M: 0; O: 0; Q: 0; S: 0; U: 0; W: 0; Y: 0; AB: 0; AC: 0
| P | IC022 | IC022 | 2 | 2.1 | Development and delivery of training Program for WG members |  | IC | PO | 2011-05-13 | 14 | 2011-05-27 |  | 2011-05-27 | 14 | 2011-06-10 | 7 | 2011-06-17 |  | 2011-06-17 | 7 | 2011-06-24 |  | 2011-06-24 | 7 | 2011-07-01 | 2 | 2011-07-03 | 1464 | 48 | 2015-07-06 | NA
| R | [8 empty] | 2013-08-06 | 14 | 2013-08-20 |  | 2013-08-20 | 14 | 2013-09-03 | 7 | 2013-09-10 |  | 2013-09-10 | 7 | 2013-09-17 |  | 2013-09-17 | 7 | 2013-09-24 | 2 | 2013-10-01 | 30.5 | 1 | 2013-10-31 12:00 | NA
| A |  |  |  |  | I: 0; K: 0; M: 0; O: 0; Q: 0; S: 0; U: 0; W: 0; Y: 0; AB: 0; AC: 0
| P | IC023 | IC023 | 2 | 2.1 | Development of School Princuipal Career Chart |  | IC | PO | 2011-05-13 | 14 | 2011-05-27 |  | 2011-05-27 | 14 | 2011-06-10 | 7 | 2011-06-17 |  | 2011-06-17 | 7 | 2011-06-24 |  | 2011-06-24 | 7 | 2011-07-01 | 2 | 2011-07-03 | 1464 | 48 | 2015-07-06 | NA
| R | [8 empty] | 2016-08-11 | 14 | 2016-08-25 |  | 2016-08-25 | 14 | 2016-09-08 | 7 | 2016-09-15 |  | 2016-09-15 | 7 | 2016-09-22 |  | 2016-09-22 | 7 | 2016-09-29 | 2 | 2016-10-01 | 91.5 | 3 | 2016-12-31 12:00 | NA
| A |  |  |  |  | I: 0; K: 0; M: 0; O: 0; Q: 0; S: 0; U: 0; W: 0; Y: 0; AB: 0; AC: 0
| P | IC024 | IC024 | 2 | 2.1 | Development and delivery of training Program for WG members |  | IC | PO | 2011-05-13 | 14 | 2011-05-27 |  | 2011-05-27 | 14 | 2011-06-10 | 7 | 2011-06-17 |  | 2011-06-17 | 7 | 2011-06-24 |  | 2011-06-24 | 7 | 2011-07-01 | 2 | 2011-07-03 | 1464 | 48 | 2015-07-06 | NA
| R | [5 empty] | #REF! |  |  | 2016-08-11 | 14 | 2016-08-25 |  | 2016-08-25 | 14 | 2016-09-08 | 7 | 2016-09-15 |  | 2016-09-15 | 7 | 2016-09-22 |  | 2016-09-22 | 7 | 2016-09-29 | 2 | 2016-10-01 | 91.5 | 3 | 2016-12-31 12:00 | NA
| A |  |  |  |  | I: 0; K: 0; M: 0; O: 0; Q: 0; S: 0; U: 0; W: 0; Y: 0; AB: 0; AC: 0
| P | IC025 | IC025 | 2 | 2.1 | Develop Draft Standards and regulation mechanism fro private school licensing |  | IC | PO | 2011-05-13 | 14 | 2011-05-27 |  | 2011-05-27 | 14 | 2011-06-10 | 7 | 2011-06-17 |  | 2011-06-17 | 7 | 2011-06-24 |  | 2011-06-24 | 7 | 2011-07-01 | 2 | 2011-07-03 | 1464 | 48 | 2015-07-06 | NA
| R | [8 empty] | 2014-09-02 | 14 | 2014-09-16 | 3 | 2014-09-19 | 14 | 2014-10-03 | 7 | 2014-10-10 | 2 | 2014-10-12 | 7 | 2014-10-19 | 2 | 2014-10-21 | 7 | 2014-10-28 | 2 | 2014-10-30 | 91.5 | 3 | 2015-01-29 12:00 | NA
| A |  |  |  |  | I: 0; K: 0; M: 0; O: 0; Q: 0; S: 0; U: 0; W: 0; Y: 0; AB: 0; AC: 0
| P | IC026 | IC026 | 3 | 3.1 | Manual for simplification and streamlining of administrative procedures |  | IC | PO | 2011-08-13 | 14 | 2011-08-27 |  | 2011-08-27 | 14 | 2011-09-10 | 7 | 2011-09-17 |  | 2011-09-17 | 7 | 2011-09-24 |  | 2011-09-24 | 7 | 2011-10-01 | 2 | 2011-10-03 | 61 | 2 | 2011-12-03 | NA
| R | [8 empty] | 2015-04-09 | 14 | 2015-04-23 | 3 | 2015-04-26 | 14 | 2015-05-10 | 7 | 2015-05-17 | 2 | 2015-05-19 | 7 | 2015-05-26 | 2 | 2015-05-28 | 7 | 2015-06-04 | 2 | 2015-06-06 | 244 | 8 | 2016-02-05 | NA
| A |  |  |  |  | I: 0; K: 0; M: 0; O: 0; Q: 0; S: 0; U: 0; W: 0; Y: 0; AB: 0; AC: 0
| P | IC027 | IC027 | 3 | 3.1 | Capacity building for MTEF and PBB |  | IC | PO | 2011-08-13 | 14 | 2011-08-27 |  | 2011-08-27 | 14 | 2011-09-10 | 7 | 2011-09-17 |  | 2011-09-17 | 7 | 2011-09-24 |  | 2011-09-24 | 7 | 2011-10-01 | 2 | 2011-10-03 | 1464 | 48 | 2015-10-06 | NA
| R | [8 empty] | 2013-12-02 | 14 | 2013-12-16 | 3 | 2013-12-19 | 14 | 2014-01-02 | 7 | 2014-01-09 | 2 | 2014-01-11 | 7 | 2014-01-18 | 2 | 2014-01-20 | 7 | 2014-01-27 | 2 | 2014-01-29 | 366 | 12 | 2015-01-30 | NA
| A |  |  |  |  | I: 0; K: 0; M: 0; O: 0; Q: 0; S: 0; U: 0; W: 0; Y: 0; AB: 0; AC: 0
| P | IC028 | IC028 | 3 | 3.2 | Consolidation of Application analysis |  | IC | PO | 2013-11-11 | 14 | 2013-11-25 |  | 2013-11-25 | 14 | 2013-12-09 | 7 | 2013-12-16 |  | 2013-12-16 | 7 | 2013-12-23 |  | 2013-12-23 | 7 | 2013-12-30 | 2 | 2014-01-01 | 61 | 2 | 2014-03-03 | NA
| R | [8 empty] | 2015-11-02 | 14 | 2015-11-16 | 3 | 2015-11-19 | 14 | 2015-12-03 | 7 | 2015-12-10 | 2 | 2015-12-12 | 7 | 2015-12-19 | 2 | 2015-12-21 | 7 | 2015-12-28 | 2 | 2015-12-30 | 366 | 12 | 2016-12-30 | NA
| A |  |  |  |  | I: 0; K: 0; M: 0; O: 0; Q: 0; S: 0; U: 0; W: 0; Y: 0; AB: 0; AC: 0
| P | IC029 | IC029 | 3 | 3.3 | Evaluation of Student Achievement Expert (Learning Assessment) |  | IC | PO | 2014-12-01 | 107 | 2015-03-18 |  | N/A | 1 | 2015-05-12 | 180 | 2015-11-08 | 7 | N/A | 14 | 2015-11-29 | 7 | N/A | 7 | 2015-12-13 | 3 | 2015-12-16 | 746 | 25 | 2017-12-31 | NA |  | Launched
| R |  |  |  |  | E: 0; H: 2014-12-01; I: 115; J: 2015-03-26; K: 1; L: 2015-03-27; M: 46; N: 2015-05-12; AD: NA
| A |  |  |  |  | I: 0; K: 0; M: 0; O: 0; Q: 0; S: 0; U: 0; W: 0; Y: 0; AB: 0; AC: 0
| P | S13-S20 | IC010 | 3 | 3.3 | Staff (Long term) |  | IC | PR | 2010-09-30 02:24 | 14 | 2010-10-14 02:24 | 14 | 2010-10-28 02:24 | 14 | 2010-11-11 02:24 | 7 | 2010-11-18 02:24 | 14 | 2010-12-02 02:24 | 7 | 2010-12-09 02:24 | 14 | 2010-12-23 02:24 | 7 | 2010-12-30 02:24 | 2 | 2011-01-01 02:24 | 2555.9 | 83.8 | 2017-12-31 | NA
R | bar: H; AD
| A |  |  |  |  | I: 0; K: 0; M: 0; O: 0; Q: 0; S: 0; U: 0; W: 0; Y: 0; AB: 0; AC: 0
| P | S1 | IC001 | 3 | 3.3 | ESDS Director |  | SSS | PR | 2010-11-04 02:24 | 14 | 2010-11-18 02:24 | 14 | 2010-12-02 02:24 |  | 2010-12-02 02:24 |  | 2010-12-02 02:24 |  | 2010-12-02 02:24 | 7 | 2010-12-09 02:24 | 14 | 2010-12-23 02:24 | 7 | 2010-12-30 02:24 | 2 | 2011-01-01 02:24 | 2555.9 | 83.8 | 2017-12-31 | NA | Nada Mneimneh | Completed (Resigned)
| R | [5 empty] | 0 |  |  | 2012-09-18 | 14 | 2012-10-02 | 14 | 2012-10-16 |  | 2012-10-16 |  | 2012-10-16 |  | 2012-10-16 | 7 | 2012-10-23 |  | 2012-10-23 | 7 | 2012-10-30 | 2 | 2012-11-01 | 425 | 14 | 2013-12-31 | NA
| A | [8 empty] | 2012-09-18 | 14 | 2012-10-02 | 14 | 2012-10-16 |  | 2012-10-16 |  | 2012-10-16 |  | 2012-10-16 | 7 | 2012-10-23 |  | 2012-10-23 | 7 | 2012-10-30 | 2 | 2012-11-01 | 425 | 14 | 2013-12-31 | 2014-12-31
| P | S2 | IC002 | 3 | 3.3 | School Improvement and Leadership Expert |  | SSS | PR | 2010-11-11 02:24 | 14 | 2010-11-25 02:24 |  | 2010-11-25 02:24 | 14 | 2010-12-09 02:24 | 7 | 2010-12-16 02:24 |  | 2010-12-16 02:24 | 7 | 2010-12-23 02:24 |  | 2010-12-23 02:24 | 7 | 2010-12-30 02:24 | 2 | 2011-01-01 02:24 | 2555.9 | 83.8 | 2017-12-31 | NA | Elham Komaty | Ongoing
| R | [8 empty] | 2012-09-18 | 14 | 2012-10-02 | 14 | 2012-10-16 |  | 2012-10-16 |  | 2012-10-16 |  | 2012-10-16 | 7 | 2012-10-23 |  | 2012-10-23 | 7 | 2012-10-30 | 2 | 2012-11-01 | 425 | 14 | 2013-12-31 | NA
| A | [8 empty] | 2012-09-18 | 14 | 2012-10-02 | 14 | 2012-10-16 |  | 2012-10-16 |  | 2012-10-16 |  | 2012-10-16 | 7 | 2012-10-23 |  | 2012-10-23 | 7 | 2012-10-30 | 2 | 2012-11-01 | 425 | 14 | 2013-12-31 | 2015-12-31
| P | S3 | IC003 | 3 | 3.3 | Financial Officer |  | SSS | PR | 2010-11-11 02:24 | 14 | 2010-11-25 02:24 |  | 2010-11-25 02:24 | 14 | 2010-12-09 02:24 | 7 | 2010-12-16 02:24 |  | 2010-12-16 02:24 | 7 | 2010-12-23 02:24 |  | 2010-12-23 02:24 | 7 | 2010-12-30 02:24 | 2 | 2011-01-01 02:24 | 2555.9 | 83.8 | 2017-12-31 | NA | Bilal Nasser | Ongoing
| R | [8 empty] | 2012-09-18 | 14 | 2012-10-02 | 14 | 2012-10-16 |  | 2012-10-16 |  | 2012-10-16 |  | 2012-10-16 | 7 | 2012-10-23 |  | 2012-10-23 | 7 | 2012-10-30 | 2 | 2012-11-01 | 425 | 14 | 2013-12-31 | NA
| A | [8 empty] | 2012-09-18 | 14 | 2012-10-02 | 14 | 2012-10-16 |  | 2012-10-16 |  | 2012-10-16 |  | 2012-10-16 | 7 | 2012-10-23 |  | 2012-10-23 | 7 | 2012-10-30 | 2 | 2012-11-01 | 425 | 14 | 2013-12-31 | 2015-12-31
| P | S4 | IC004 | 3 | 3.3 | Monitoring & Evaluation Specialist |  | SSS | PR | 2010-11-11 02:24 | 14 | 2010-11-25 02:24 |  | 2010-11-25 02:24 | 14 | 2010-12-09 02:24 | 7 | 2010-12-16 02:24 |  | 2010-12-16 02:24 | 7 | 2010-12-23 02:24 |  | 2010-12-23 02:24 | 7 | 2010-12-30 02:24 | 2 | 2011-01-01 02:24 | 2555.9 | 83.8 | 2017-12-31 | NA | Dana Shdeed | Completed (Resigned)
| R | [8 empty] | 2012-09-18 | 14 | 2012-10-02 | 14 | 2012-10-16 |  | 2012-10-16 |  | 2012-10-16 |  | 2012-10-16 | 7 | 2012-10-23 |  | 2012-10-23 | 7 | 2012-10-30 | 2 | 2012-11-01 | 425 | 14 | 2013-12-31 | NA
| A | [8 empty] | 2012-09-18 | 14 | 2012-10-02 | 14 | 2012-10-16 |  | 2012-10-16 |  | 2012-10-16 |  | 2012-10-16 | 7 | 2012-10-23 |  | 2012-10-23 | 7 | 2012-10-30 | 2 | 2012-11-01 | 425 | 14 | 2013-12-31 | 2014-04-04
| P | S5 | IC005 | 3 | 3.3 | Education Economist |  | SSS | PR | 2010-11-11 02:24 | 14 | 2010-11-25 02:24 |  | 2010-11-25 02:24 | 14 | 2010-12-09 02:24 | 7 | 2010-12-16 02:24 |  | 2010-12-16 02:24 | 7 | 2010-12-23 02:24 |  | 2010-12-23 02:24 | 7 | 2010-12-30 02:24 | 2 | 2011-01-01 02:24 | 2555.9 | 83.8 | 2017-12-31 | NA | Sara Zeineddine | Completed (Resigned)
| R | [8 empty] | 2012-09-18 | 14 | 2012-10-02 | 14 | 2012-10-16 |  | 2012-10-16 |  | 2012-10-16 |  | 2012-10-16 | 7 | 2012-10-23 |  | 2012-10-23 | 7 | 2012-10-30 | 2 | 2012-11-01 | 425 | 14 | 2013-12-31 | NA
| A | [8 empty] | 2012-09-18 | 14 | 2012-10-02 | 14 | 2012-10-16 |  | 2012-10-16 |  | 2012-10-16 |  | 2012-10-16 | 7 | 2012-10-23 |  | 2012-10-23 | 7 | 2012-10-30 | 2 | 2012-11-01 | 425 | 14 | 2013-12-31 | 31/12/2013
| P | S6 | IC006 | 3 | 3.3 | Architect Urban Planner |  | SSS | PR | 2010-11-11 02:24 | 14 | 2010-11-25 02:24 |  | 2010-11-25 02:24 | 14 | 2010-12-09 02:24 | 7 | 2010-12-16 02:24 |  | 2010-12-16 02:24 | 7 | 2010-12-23 02:24 |  | 2010-12-23 02:24 | 7 | 2010-12-30 02:24 | 2 | 2011-01-01 02:24 | 2555.9 | 83.8 | 2017-12-31 | NA | Maya Samaha | Ongoing
| R | [8 empty] | 2012-09-18 | 14 | 2012-10-02 | 14 | 2012-10-16 |  | 2012-10-16 |  | 2012-10-16 |  | 2012-10-16 | 7 | 2012-10-23 |  | 2012-10-23 | 7 | 2012-10-30 | 2 | 2012-11-01 | 425 | 14 | 2013-12-31 | NA
| A | [8 empty] | 2012-09-18 | 14 | 2012-10-02 | 14 | 2012-10-16 |  | 2012-10-16 |  | 2012-10-16 |  | 2012-10-16 | 7 | 2012-10-23 |  | 2012-10-23 | 7 | 2012-10-30 | 2 | 2012-11-01 | 425 | 14 | 2013-12-31 | 2015-12-31
| P | S7 | IC007 | 3 | 3.3 | Operations Specialist |  | SSS | PR | 2010-11-11 02:24 | 14 | 2010-11-25 02:24 |  | 2010-11-25 02:24 | 14 | 2010-12-09 02:24 | 7 | 2010-12-16 02:24 |  | 2010-12-16 02:24 | 7 | 2010-12-23 02:24 |  | 2010-12-23 02:24 | 7 | 2010-12-30 02:24 | 2 | 2011-01-01 02:24 | 2555.9 | 83.8 | 2017-12-31 | NA | Leen Ataya | Completed (Resigned)
| R | [5 empty] | 0 |  |  | 2012-09-18 | 14 | 2012-10-02 | 14 | 2012-10-16 |  | 2012-10-16 |  | 2012-10-16 |  | 2012-10-16 | 7 | 2012-10-23 |  | 2012-10-23 | 7 | 2012-10-30 | 2 | 2012-11-01 | 425 | 14 | 2013-12-31 | NA
| A | [8 empty] | 2012-09-18 | 14 | 2012-10-02 | 14 | 2012-10-16 |  | 2012-10-16 |  | 2012-10-16 |  | 2012-10-16 | 7 | 2012-10-23 |  | 2012-10-23 | 7 | 2012-10-30 | 2 | 2012-11-01 | 425 | 14 | 2013-12-31 | 2015-09-15
| P | S8 | IC008 | 3 | 3.3 | Staff (Long term retroactive basis) |  | SSS | PR | 2010-11-11 02:24 | 14 | 2010-11-25 02:24 |  | 2010-11-25 02:24 | 14 | 2010-12-09 02:24 | 7 | 2010-12-16 02:24 |  | 2010-12-16 02:24 | 7 | 2010-12-23 02:24 |  | 2010-12-23 02:24 | 7 | 2010-12-30 02:24 | 2 | 2011-01-01 02:24 | 2555.9 | 83.8 | 2017-12-31 | NA | Joelle H, Nadine T | Completed
| R | [8 empty] | 2012-09-18 | 14 | 2012-10-02 | 14 | 2012-10-16 |  | 2012-10-16 |  | 2012-10-16 |  | 2012-10-16 | 7 | 2012-10-23 |  | 2012-10-23 | 7 | 2012-10-30 | 2 | 2012-11-01 | 425 | 14 | 2013-12-31 | NA
| A | [8 empty] | 2010-11-18 | 14 | 2010-12-02 | 14 | 2010-12-16 |  | 2010-12-16 | 0 | 2010-12-16 |  | 2010-12-16 | 7 | 2010-12-23 | 0 | 2010-12-23 | 7 | 2010-12-30 | 2 | 2011-01-01 | 730 | 24 | 2012-12-31 | 31/12/2012
| P | S9 | IC009 | 3 | 3.3 | Procurement Consultant |  | SSS | PR | 2010-09-30 02:24 | 14 | 2010-10-14 02:24 | 14 | 2010-10-28 02:24 | 14 | 2010-11-11 02:24 | 7 | 2010-11-18 02:24 | 14 | 2010-12-02 02:24 | 7 | 2010-12-09 02:24 | 14 | 2010-12-23 02:24 | 7 | 2010-12-30 02:24 | 2 | 2011-01-01 02:24 | 2555.9 | 83.8 | 2017-12-31 | NA | Fady Barakat | Completed
R | bar: Z to AD
| A | [8 empty] | 2013-04-06 | 14 | 2013-04-20 | 14 | 2013-05-04 | 14 | 2013-05-18 | 7 | 2013-05-25 | 14 | 2013-06-08 | 7 | 2013-06-15 | 7 | 2013-06-22 | 7 | 2013-06-29 | 2 | 2013-07-01 | 91.5 | 3 | 2013-07-01 | 11/31/2013
| P | S10 | IC010 | 3 | 3.3 | Education Expert (TPD) |  | IC | PO | 2010-09-30 02:24 | 14 | 2010-10-14 02:24 | 14 | 2010-10-28 02:24 | 14 | 2010-11-11 02:24 | 7 | 2010-11-18 02:24 | 14 | 2010-12-02 02:24 | 7 | 2010-12-09 02:24 | 14 | 2010-12-23 02:24 | 7 | 2010-12-30 02:24 | 2 | 2011-01-01 02:24 | 2555.9 | 83.8 | 2017-12-31 | NA | Basma Frangieh | Signed and Being Implemented
| R | [8 empty] | 2014-12-01 | 107 | 2015-03-18 |  | N/A | 1 | 2015-05-12 | 160 | 2015-10-19 | 7 | 2015-10-26 | 14 | 2015-11-09 | 7 | 2015-11-16 | 7 | 2015-11-23 | 3 | 2015-11-26 | 766 | 25.5 | 2017-12-31 | NA
| A |  |  |  |  | H: 2014-12-01; I: 115; J: 2015-03-26; K: 1; L: 2015-03-27; M: 46; N: 2015-05-12; O: 213; P: 2015-12-11; R: N/A; T: N/A; V: N/A; X: 2016-01-16; Z: 2016-01-01; AA: 365; AB: 12; AC: 2016-12-31
| P | S11 | IC011 | 3 | 3.3 | Procurement Officer -1- |  | IC | PR | 2010-09-30 02:24 | 14 | 2010-10-14 02:24 | 14 | 2010-10-28 02:24 | 14 | 2010-11-11 02:24 | 7 | 2010-11-18 02:24 | 14 | 2010-12-02 02:24 | 7 | 2010-12-09 02:24 | 14 | 2010-12-23 02:24 | 7 | 2010-12-30 02:24 | 2 | 2011-01-01 02:24 | 2555.9 | 83.8 | 2017-12-31 | NA | Ghada Zeaiter | Completed (Resigned in 2013)
| R | [8 empty] | 2013-07-05 | 2 | 2013-07-07 | 3 | 2013-07-10 | 1 | 2013-07-11 | 80 | 2013-09-29 | 37 | 2013-11-05 |  | 2013-11-05 |  | 2013-11-05 |  | 2013-11-05 |  | 2013-11-05 | 1565.26 | 51.32 | 2017-12-31 | NA
| A | [8 empty] | 2013-07-05 | 2 | 2013-07-07 | 3 | 2013-07-10 | 1 | 2013-07-11 | 80 | 2013-09-29 | 37 | 2013-11-05 |  | 2013-11-05 |  | 2013-11-05 |  | 2013-11-05 |  | 2013-11-05 | 56 | 1.8667 | 2013-12-31 | 2013-12-31
| P | S12 | IC012 | 3 | 3.3 | Education Curriculum Expert (Lebanese Contribution) |  | IC | N/A | 2013-08-18 | 14 | 2013-09-01 | 14 | 2013-09-15 | 14 | 2013-09-29 | 7 | 2010-11-18 02:24 | 14 | 2010-12-02 02:24 | 7 | 2010-12-09 02:24 | 14 | 2010-12-23 02:24 | 7 | 2010-12-30 02:24 | 2 | 2011-01-01 02:24 | 2555.9 | 83.8 | 2017-12-31 | NA | Antoinette Sebaaly | Ongoing - LC
| R | [8 empty] | 2013-07-01 | 2 | 2013-07-03 | 3 | 2013-07-06 | 1 | 2013-07-07 | 76 | 2013-09-21 | 19 | 2013-10-10 | 14 | 2013-10-24 | 7 | 2013-10-31 | 14 | 2013-11-14 | 3 | 2013-11-17 | 1505 | 50.42 | 2017-12-31 | NA
| A | [8 empty] | 2013-07-01 | 2 | 2013-07-03 | 3 | 2013-07-06 | 1 | 2013-07-07 | 76 | 2013-09-21 | 19 | 2013-10-10 |  | 2013-12-15 |  | 2013-12-15 |  | 2013-12-15 | 17 | 2014-01-01 | 364 | 12 | 2014-12-31 | 2015-12-31
| P | S13 | IC013 | 3 | 3.3 | Procurement Assisstant (Senior) |  | IC | PR | 2010-09-30 02:24 | 14 | 2010-10-14 02:24 | 14 | 2010-10-28 02:24 | 14 | 2010-11-11 02:24 | 7 | 2010-11-18 02:24 | 14 | 2010-12-02 02:24 | 7 | 2010-12-09 02:24 | 14 | 2010-12-23 02:24 | 7 | 2010-12-30 02:24 | 2 | 2011-01-01 02:24 | 2555.9 | 83.8 | 2017-12-31 | NA |  | Frozen
| R | [8 empty] | 2013-09-14 | 14 | 2013-09-28 | 7 | 2013-10-05 | 1 | 2013-12-12 | 21 | 2014-01-02 | 7 | 2014-01-09 | 14 | 2014-01-23 | 7 | 2014-01-30 | 14 | 2014-02-13 | 3 | 2014-02-16 | 1414 | 49 | 2017-12-31 | NA
| A |  |  |  |  | H: 2013-09-14; I: 65; J: 2013-11-18; K: 3; L: 2013-11-21; M: 21; N: 2013-12-12
| P | S14 | IC014 | 3 | 3.3 | Procurement Assisstant (Junior) |  | IC | PO | 2010-09-30 02:24 | 14 | 2010-10-14 02:24 | 14 | 2010-10-28 02:24 | 14 | 2010-11-11 02:24 | 7 | 2010-11-18 02:24 | 14 | 2010-12-02 02:24 | 7 | 2010-12-09 02:24 | 14 | 2010-12-23 02:24 | 7 | 2010-12-30 02:24 | 2 | 2011-01-01 02:24 | 2555.9 | 83.8 | 2017-12-31 | NA |  | Launched - Frozen
| R | [8 empty] | 2014-12-01 | 107 | 2015-03-18 |  | N/A | 1 | 2015-05-12 | 180 | 2015-11-08 | 7 | N/A | 14 | 2015-11-29 | 7 | N/A | 7 | 2015-12-13 | 3 | 2015-12-16 | 746 | 25 | 2017-12-31 | NA
| A |  |  |  |  | H: 2014-12-01; I: 115; J: 2015-03-26; K: 1; L: 2015-03-27; M: 46; N: 2015-05-12
| P | S15 | IC015 | 3 | 3.3 | Financial Assistant |  | IC | PO | 2010-09-30 02:24 | 14 | 2010-10-14 02:24 | 14 | 2010-10-28 02:24 | 14 | 2010-11-11 02:24 | 7 | 2010-11-18 02:24 | 14 | 2010-12-02 02:24 | 7 | 2010-12-09 02:24 | 14 | 2010-12-23 02:24 | 7 | 2010-12-30 02:24 | 2 | 2011-01-01 02:24 | 2555.9 | 83.8 | 2017-12-31 | NA | Farah Fawaz | Signed and Being Implemented
| R | [8 empty] | 2014-12-01 | 107 | 2015-03-18 |  | N/A | 1 | 2015-05-12 | 188 | 2015-11-16 | 7 | N/A | 14 | 2015-12-07 | 7 | N/A | 7 | 2015-12-21 | 3 | 2015-12-24 | 746 | 25 | 2018-01-08 | NA
| A |  |  |  |  | H: 2014-12-01; I: 115; J: 2015-03-26; K: 1; L: 2015-03-27; M: 46; N: 2015-05-12; O: 188; P: 2015-11-16; R: N/A; T: N/A; V: N/A; X: 2016-01-04; Z: 2016-01-01; AA: 365; AB: 12; AC: 2016-12-31
| P | S16 | IC016 | 3 | 3.3 | Expert (Lebanese Contribution) |  | IC | n/a | 2010-09-30 02:24 | 14 | 2010-10-14 02:24 | 14 | 2010-10-28 02:24 | 14 | 2010-11-11 02:24 | 7 | 2010-11-18 02:24 | 14 | 2010-12-02 02:24 | 7 | 2010-12-09 02:24 | 14 | 2010-12-23 02:24 | 7 | 2010-12-30 02:24 | 2 | 2011-01-01 02:24 | 2555.9 | 83.8 | 2017-12-31 | NA | Karma El Hassan | Completed - LC
| R |  |  |  |  | H: 2013-12-03; J: 2013-12-03; L: 2013-12-03; M: 0; N: 2013-12-03; P: 2013-12-03; R: 2013-12-03; T: 2013-12-03; V: 2013-12-03; X: 2013-12-03; Z: 2013-12-03; AA: 18; AB: 48; AC: 2013-12-21; AD: NA
| A |  |  |  |  | H: 2013-12-03; J: 2013-12-03; L: 2013-12-03; M: 0; N: 2013-12-03; P: 2013-12-03; R: 2013-12-03; T: 2013-12-03; V: 2013-12-03; X: 2013-12-03; Z: 2013-12-03; AA: 18; AC: 2013-12-21; AD: 2013-12-21
| P | S17 | IC017 | 3 | 3.3 | Procurement Officer -2- |  | IC | PR | 2010-09-30 02:24 | 14 | 2010-10-14 02:24 | 14 | 2010-10-28 02:24 | 14 | 2010-11-11 02:24 | 7 | 2010-11-18 02:24 | 14 | 2010-12-02 02:24 | 7 | 2010-12-09 02:24 | 14 | 2010-12-23 02:24 | 7 | 2010-12-30 02:24 | 2 | 2011-01-01 02:24 | 2555.9 | 83.8 | 2017-12-31 | NA | Riwa El Khoury | Ongoing
| R |  |  |  |  | H: 2013-12-03; J: 2013-12-03; L: 2013-12-03; M: 0; N: 2013-12-03; P: 2013-12-03; R: 2013-12-03; T: 2013-12-03; V: 2013-12-03; X: 2013-12-03; Z: 2013-12-03; AA: 18; AB: 48; AC: 2013-12-21; AD: NA
| A | [8 empty] | 2013-07-05 | 2 | 2013-07-07 | 3 | 2013-07-10 | 1 | 2013-07-11 | 80 | 2013-09-29 | 37 | 2014-01-14 |  | 2014-01-14 |  | 2014-01-14 |  | 2014-02-04 |  | 2014-01-28 | 2014-12-31 |  | 2014-12-31 | 2015-12-31
| P | S18 | IC018 | 3 | 3.3 | Monitoring & Evaluation Specialist |  | IC | PO | 2010-09-30 02:24 | 14 | 2010-10-14 02:24 | 14 | 2010-10-28 02:24 | 14 | 2010-11-11 02:24 | 7 | 2010-11-18 02:24 | 14 | 2010-12-02 02:24 | 7 | 2010-12-09 02:24 | 14 | 2010-12-23 02:24 | 7 | 2010-12-30 02:24 | 2 | 2011-01-01 02:24 | 2555.9 | 83.8 | 2017-12-31 | NA |  | Launched
| R | [8 empty] | 2014-12-01 | 107 | 2015-03-18 |  | N/A | 1 | 2015-05-12 | 160 | 2015-10-19 | 7 | N/A | 14 | 2015-11-09 | 7 | N/A | 7 | 2015-11-23 | 3 | 2015-11-26 | 766 | 25.5 | 2017-12-31 | NA
| A |  |  |  |  | H: 2014-12-01; I: 115; J: 2015-03-26; K: 1; L: N/A; M: 46; N: 2015-05-12
| P | S19 | IC019 | 3 | 3.3 | Education Economist |  | IC | PO | 2010-09-30 02:24 | 14 | 2010-10-14 02:24 | 14 | 2010-10-28 02:24 | 14 | 2010-11-11 02:24 | 7 | 2010-11-18 02:24 | 14 | 2010-12-02 02:24 | 7 | 2010-12-09 02:24 | 14 | 2010-12-23 02:24 | 7 | 2010-12-30 02:24 | 2 | 2011-01-01 02:24 | 2555.9 | 83.8 | 2017-12-31 | NA |  | Launched
| R | [8 empty] | 2014-12-01 | 115 | 2015-03-26 |  | N/A | 1 | 2015-05-12 | 180 | 2015-11-08 | 7 | N/A | 14 | 2015-11-29 | 7 | N/A | 7 | 2015-12-13 | 3 | 2015-12-16 | 746 | 25 | 2017-12-31 | NA
| A |  |  |  |  | H: 2014-12-01; I: 115; J: 2015-03-26; K: 1; L: N/A; M: 46; N: 2015-05-12
| P | S30 | IC030 | 3 | 3.3 | Executive Assistant |  | IC | PO | 2010-09-30 02:24 | 14 | 2010-10-14 02:24 | 14 | 2010-10-28 02:24 | 14 | 2010-11-11 02:24 | 7 | 2010-11-18 02:24 | 14 | 2010-12-02 02:24 | 7 | 2010-12-09 02:24 | 14 | 2010-12-23 02:24 | 7 | 2010-12-30 02:24 | 2 | 2011-01-01 02:24 | 2555.9 | 83.8 | 2017-12-31 | NA |  | Launched
| R | [8 empty] | 2014-12-01 | 115 | 2015-03-26 |  | N/A | 1 | 2015-05-12 | 180 | 2015-11-08 | 7 | N/A | 14 | 2015-11-29 | 7 | N/A | 7 | 2015-12-13 | 3 | 2015-12-16 | 746 | 25 | 2017-12-31 | NA
| A |  |  |  |  | H: 2014-12-01; I: 115; J: 2015-03-26; K: 1; L: N/A; M: 46; N: 2015-05-12
| P | S31 | IC031 | 3 | 3.3 | Education Specialist |  | IC | PO | 2010-09-30 02:24 | 14 | 2010-10-14 02:24 | 14 | 2010-10-28 02:24 | 14 | 2010-11-11 02:24 | 7 | 2010-11-18 02:24 | 14 | 2010-12-02 02:24 | 7 | 2010-12-09 02:24 | 14 | 2010-12-23 02:24 | 7 | 2010-12-30 02:24 | 2 | 2011-01-01 02:24 | 2555.9 | 83.8 | 2017-12-31 | NA | Maya Fawaz | Signed and Being Implemented
| R | [8 empty] | 2014-12-01 | 115 | 2015-03-26 |  | N/A | 1 | 2015-05-12 | 180 | 2015-11-08 | 7 | N/A | 14 | 2015-11-29 | 7 | N/A | 7 | 2015-12-13 | 3 | 2015-12-16 | 746 | 25 | 2017-12-31 | NA
| A |  |  |  |  | H: 2014-12-01; I: 115; J: 2015-03-26; K: 1; L: N/A; M: 46; N: 2015-05-12; O: 185; P: 2015-11-13; R: N/A; T: N/A; V: N/A; X: 2016-01-04; Z: 2016-01-01; AA: 365; AB: 12; AC: 2016-12-31
| P | S32 | IC032 | 3 | 3.3 | ESDS Director |  | IC | PO | 2010-09-30 02:24 | 14 | 2010-10-14 02:24 | 14 | 2010-10-28 02:24 | 14 | 2010-11-11 02:24 | 7 | 2010-11-18 02:24 | 14 | 2010-12-02 02:24 | 7 | 2010-12-09 02:24 | 14 | 2010-12-23 02:24 | 7 | 2010-12-30 02:24 | 2 | 2011-01-01 02:24 | 2555.9 | 83.8 | 2017-12-31 | NA |  | Launched
| R | [8 empty] | 2014-12-01 | 115 | 2015-03-26 | 1 | 2015-03-27 | 46 | 2015-05-12 | 160 | 2015-10-19 | 7 | 2015-10-26 | 14 | 2015-11-09 | 7 | 2015-11-16 | 7 | 2015-11-23 | 3 | 2015-11-26 | 766 | 25.5 | 2017-12-31 | NA
| A |  |  |  |  | H: 2014-12-01; I: 115; J: 2015-03-26; K: 1; L: 2015-03-27; M: 46; N: 2015-05-12
NEW | P | S34 | IC034 | 3 | 3.3 | Project Assistant |  | SSS | PR | 2010-09-30 02:24 | 14 | 2010-10-14 02:24 | 14 | 2010-10-28 02:24 | 14 | 2010-11-11 02:24 | 7 | 2010-11-18 02:24 | 14 | 2010-12-02 02:24 | 7 | 2010-12-09 02:24 | 14 | 2010-12-23 02:24 | 7 | 2010-12-30 02:24 | 2 | 2011-01-01 02:24 | 2555.9 | 83.8 | 2017-12-31 | NA |  | Process Ongoing
| R | [8 empty] | 2015-12-15 | 20 | 2016-01-04 |  | N/A |  | N/A |  | N/A | 7 | N/A |  | 2016-01-19 | 7 | 2016-01-26 | 7 | 2016-02-02 | 3 | 2016-01-01 | 365 | 12 | 2016-12-31 | NA
| A |  |  |  |  | H: 2015-12-15; I: 20; J: 2016-01-04; L: N/A; N: N/A; P: N/A; Q: 7; R: N/A; T: 2016-01-19; U: 7
Note on G95: Riwa ElKhoury: re-added with a different proc ref
Note on G98: Riwa ElKhoury: re-added with a different proc ref
Note on G101: Riwa ElKhoury: was not part of the proc plan
Note on G104: Riwa ElKhoury: Newly Added was not part of proc plan
Note on G107: Riwa ElKhoury: Newly Added was not part of proc plan
Note on G110: Riwa ElKhoury: Newly Added was not part of proc plan

## School Grants
PLANNING FOR TRAINING
as of January 25, 2016
Costab ref | Plan vs. Actual | Proc. System Ref. # | SN. # | Comp | Sub-Comp | Location/ Description of Assignment | Unit (Mth/ Yr/ Study[Sty], Lumpsum [LS], Workshop [Wsh]) | Selection Method | Bank Rev. | TOR Start Date | Interval | TOR end Date | Interval | NOL Date | Interval | Training preparation | Interval | Training Start Date | Execution in days | Execution in months | Completion Date (original) | Completion Date (last revision) | Participants | Comments
| P |  | TR004 | 2 | 2.1 | School Grants |  | NA | PR | 2011-09-20 | 14 | 2011-10-04 | 14 | 2011-10-18 | 14 | 2011-11-01 | 2 | 2011-11-03 | 1464 | 48 | 2015-11-06 | NA
| R | [8 empty] | 2016-05-20 | 14 | 2016-06-03 | 14 | 2016-06-17 | 14 | 2016-07-01 | 2 | 2016-07-03 | 366 | 12 | 2017-07-04 | NA
A
Formulas:
TOR Start Date = [TOR end Date]-[Interval]
TOR end Date = [NOL Date]-[Interval]
TOR end Date = [TOR Start Date]+[Interval]
NOL Date = [Training preparation]-[Interval]
NOL Date = [TOR end Date]+[Interval]
Training preparation = +[Training Start Date]-[Interval]
Training preparation = [NOL Date]+[Interval]
Completion Date (original) = +[Execution in days]+[Training Start Date]
Completion Date (original) = [Training Start Date]+[Execution in days]
Training Start Date = [Training preparation]+[Interval]