## I  General

Agreed date of procurement Plan

Original:   November 6, 2007

Date of General Procurement Notice:  estimated December 2007

##### II. Goods and Works and non-consulting services

- Prior Review Threshold: Procurement Decisions subject to Prior Review by the Bank as stated in Appendix 1 to the Guidelines for Procurement:

|  | Procurement Method | Method Threshold | Prior Review Threshold /Comments |
| --- | --- | --- | --- |
| 1. | ICB for Goods | > $100,000 | All subject to prior review |
| 2. | Shopping Goods | < $100,000 | First 2 subject of prior review |

- Prequalification. Bidders shall be pre-qualified in accordance with the provisions of paragraphs 2.9 and 2.10 of the Guidelines: Not applicable.

- Proposed Procedures for CDD Components (as per paragraph. 3.17 of the Guidelines: No CDD is envisaged.

- Any Other Special Procurement Arrangements: None

Detailed procurement contracts for goods are enclosed in the table below (in paragraph III. 3. a).

##### III. Selection of Consultants

      - Prior Review Threshold: Selection decisions subject to Prior Review by Bank as stated in Appendix 1 to the Guidelines Selection and Employment of Consultants:

|  | Selection Method | Applicable Method Threshold | Prior Review Threshold / Comment |
| --- | --- | --- | --- |
| 1. | Competitive Methods (Firms) QCBS | >$100,000 | All prior review |
| 2. | Competitive Methods (Firms) LCS | <$100,000 | First contract and all more than $50,000 |
| 3. | Competitive Methods (Firms) CQ | <$ 100,000 | First two contracts and all more than $50,000 prior review |
| 4. | Individual consultants (Individual) | - | First two subject of prior review and all more than $25,000 |
| 5. | Single Source (Firms and individual) * | - | All subject of prior review |
| 6. | TOR for consulting contracts | All methods/values | All subject to prior review |

*)  All contracts subject to justification

      - Short list comprising entirely of national consultants: Not applicable.

      - Consulting Services assignment with selection methods and time schedule

(a) List of consulting assignments with short-list of international firms, etc.

| 1 | 2 | 5 | 6 | 7 | 8 | 9 |
| --- | --- | --- | --- | --- | --- | --- |
| Ref No. | Description of Assignment | Number of Contracts | Selection Method | Review by Bank (Prior/ Post) | (Expected) Contract signature Date | (Expected) Contract completion date |
| C.1 | Component 1 – Assistance to CBK |  |  |  |  |  |
|  | Sub-component 1.1 –CBK Institutional Strengthening and Sustainability |  |  |  |  |  |
| 1 | Assistance on preparation of development strategy for CBK based on market development trends and review of funding options | 1 | CQ | Prior | Jan 22, 2009 | April 28, ‘09 |
| 2 | Assistance to CBK for functional assessment and development of medium term staffing plan and revised staff incentives | 1 | CQ | Prior | Aug 13, 2009 | Oct 29, 2009 |
| 3 | Public awareness campaign to raise population awareness on financial products, returns and risks | 1 | CQ | Prior | Jan 2011 | June 2011 |
|  | Sub-component 1.2 – Regulatory and supervisory framework strengthening |  |  |  |  |  |
| 4.1 | Designing and implementation of a regulatory reporting database for off-site supervision | 1 | QCBS | Prior | Jan 2011 | June 2011 |
| 4.2 | Off-the-shelf software of designing data base for off-site supervision | 1 | ICB | Prior | April 2011 | June 2011 |
| 5 | Review of banking sector legal and regulatory framework | 1 | IC | Prior | Feb 2010 | May 2010 |
| 6 | Drafting Law for Regulation and Supervision of General Insurance (Assistance to insurance sector on off-site supervision, including insurance financial analysis and training for supervisors; supervisory strategy for each insurance institution; implementation of agreed strategy and training) | 1 | IC | Prior | (Nov 09) | (May 2010) |
|  | 6.1 | “Assessment of IAIS Core Principles for Effective Insurance Companies Supervision (life and non life)” | 1 | Prior | Jan 2011 | March 2011 | 0.040 |
| 7 | Training of banking sector staff in Central and Western European supervisory agencies (i.e. workshops, study tours, etc) | Multiple | - | Annual training plan | 2009/’10 | Training/ study tours |
|  | 7.1 | Mr. Afrim Asllani (Insurance Examiner, Insurance Directorate, CBK) Seminar on Applied Risk Management Techniques in the Insurance Sector, held in Beatenberg, Switzerland from 04- 08 October 10 | 1 | Training | Prior | 04 Oct 2010 | 08 Oct 2010 |
|  | 7.2 | Ms. Gentiana Godeni (Insurance and Pension Directorate, CBK) Training course for “Life insurance” issues, at Malta International Training Centre from 30 August-04 to September 2010 in Malta | 1 | Training | Prior | 04 Aug 2010 | 04 Sep 2010 |
|  | 7.3 | Mrs. Valbona Morina (Actuary, Insurance Directorate, CBK) Seminar on “Stochastic Methods of Claim Reserving”, organized by the European Actuarial Academy. The Seminar will be held in Zagreb, Croatia from 29-30 Nov 2010 | 1 | Training | Prior | 29 Nov 2010 | 30 Nov 2010 |
|  | 7.4 | 15 people from the Banking Supervision Directorate of CBK in a training with the subject on Basel II, that will be held in Istanbul, Turkey, from 20 to 24 December 2010 | 15 | Training | Prior | 20 Dec 2010 | 24 Dec 2010 |
|  | 7.5 | Ms. Suzan Dervari participation “World Islamic Finance Conference that will be held on 28 – 29 March 2011 in Park Plaza Victoria, London and a visit to Financial Stability Institute | 1 | Training | Prior | 28 March 2011 | 29 Mars 2011 |
|  | 7.6 | Participation of Mr. Merdian Kukleci and Mr. Alban Lufi at the “Certified Financial Risk Manager” Scheme organized by Global Association of Risk Professionals – GARP | 2 | Training | Prior | Dec 2011 | Dec 2011 |
| 8 | Assistance to the insurance sector in regard to supervision, reinsurance and intermediaries | 1 | IC | Prior | January 2011 | March 2011 |
| 9.1 | Assistance to the insurance sector in regard to third party liability on preparing legal framework, detailed functional, supervision and technical assessment of CTFL tariff liberalization | 1 | IC | Prior | May 4, 2009 | June 16, 2009 |
| 9.2 | Legal Framework for Compulsory Insurance | 1 | IC | Prior | March 16, 2009 | April 16, 2009 |
| 10 | Assistance to the insurance sector in regard to life insurance on preparing legal framework, regulations, carry out detailed actuarial assessment of Life insurance activities and products | 1 | CQ | Prior | April 24, 2009 | September 09, 2009 |
| 11 | Institutional development for insurance sector | 1 | CQ | Prior | January 2011 | April 2011 |
| 12 | Development of roadmap for Insurance Association of Kosovo (IAK), including development of an information system for CTLP | 1 | CQ | Prior | May 31, 2010 | Aug 2010 |
| 13 | Preparation of medium-term capital market development plan | 1 | IC | Prior | January 2011 | April 2011 |
| 14 | Review regulations for licensing of private pension funds, prepare regulations and rules for licensing and supervision of financial advisors, and provide training on the new rules and regulations | 2 | IC | Prior | January 2011 | July 2011 |
|  | 14.1 | Review Rules for Licensing and Supervision of Pension Fund Management Companies, and provide Training on the new Rules | 1 | IC | Prior | March 2011 | May 2011 |
| 14.2 | FM Specialist (Ms. Zylfije Murati) Contract | 1 | IC | Prior | March 2009 | June 2011 |
|  | Sub-component 1.3 |  |  |  |  |  |
| 14.3 | TA to support HR department to implement some key changed based on the new action plan | 1 | IC | Prior | Feb 8 2012 | Aug 8 2012 |
| 14.4 | Expert for implementing new insurance draft law and revise secondary legislation | 1 | IC | Prior | Feb 8 2012 | Aug 8 2012 |
| 14.5 | Expert for drafting/amending secondary legislation based on the new Banking sector law and implement action plan prepared by consultants | 1 | IC | Prior | Feb 8 2012 | Aug 8 2012 |
| 14.6 | Implementation law on compulsory insurance and establishing relevant institutions ( national insurance bureau, information center, etc) | 1 | IC | Prior | Feb 8 2012 | Aug 8 2012 |
| 14.7 | Assessment of existing insurance supervision software (on-line data base) | 1 | IC | Prior | Feb 8 2012 | Aug 8 2012 |
|  | C1 TOTAL |  |  |  |  |  |
| C.2 | Component 2 - Assistance to AMIK and microfinance industry |  |  |  |  |  |
| 15.1 | Training on the techniques of training/TOT | 1 | IC | Prior | Feb 3, 2009 | March 2, 2009 |
| 15.2 | Training on transforming into deposit-taking financial institutions. | 1 | IC | Prior | April 15, 2009 | May 12, 2009 |
| 15.3 | Training on microfinance operational management, liquidity management, market research and new product development | 1 | IC | Prior | June 1, 2009 | October 25, 2009 |
| 15.4 | Training on treasury management, risk and delinquency management , accounting for non finance-staff | 1 | IC | Prior | December 7, 2009 | January 25, 2010 |
| 15.5 | Training on business planning, Security/Change management, Marketing/Communications, Audit and Internal Control | 1 | IC | Prior | March 1, 2010 | June 14, 2010 |
| 15.6 | Corporate governance and Leadership, Human Resources Management | 1 | IC | Prior | September 10, 2010 | October 25, 2010 |
| 16 | Conduct an assessment on the impact of microfinance in Kosovo (on poverty, employment, SME development, etc) | 1 | CQ | Prior | May 2011 | August 2011 |
| 17 | Support AMIK staff in participation in study tours/workshop/conferences in support of microfinance industry | multiple | - | Annual training plan | 2008 / 2009 | Training/ study tours |
| 17.1 | IDLO Training in Romania | 1 | - | - | June 2008 | July 2008 |
| 17.2 | SEEP Annual Conference 2008 | 2 | Prior | - | Nov 4, 2008 | Nov 7, ‘08 |
| 17.3 | General Management Program, Bled School of Management, Slovenia | 1 | Prior | - | March 2008 | October ‘08 |
| 17.4 | SEEP Annual Conference 2009 | 1 | Prior | - | November 2, 2009 | Nov 6, 2009 |
| 17.5 | Ms. Edona Xhambazi participation at the Social Performance Management Task Force Meeting that will be held from 28 June – 2 July 2010 in Bern Switzerland | 1 | Prior | Training | 28 Jun 2010 | 2 July 2010 |
| 17.6 | Ms.Edona Kryeziu – Xhambazi participation at the Microfinance Forum 2010 “Fighting against Over indebtedness and Raising Capital in the Post Crises Environment” held in Prague, Czech Republic from 23 – 24 September 2010 | 1 | Prior | Training | 24 Sep 2010 | 24 Sep 2010 |
| 17.7 | Mrs. Violeta Arifi Krasniqi and Mrs. Edona Kryeziu – Xhambazi participation at the SEEP Network 2010, Global Network Summit and Annual Conference, that will be held from 1 – 5 November 2010, in Arlington, VA USA | 1 | Prior | Training | 1 Nov 2010 | 5 Nov 2010 |
| 17.8 | Mrs. Violeta Arifi Krasniqi SME Finance Summit 2011 (26 – 27 January 2011, in London – UK) and Microfinance Investment Summit (Amsterdam - The Netherland from 3-4 February 2011) | 2 | Prior | - | 26 – 27 Jan ‘11and 3-4 Feb ‘11 | 26 – 27 Jan ‘11and 3-4 Feb ‘11 |
| 17.9 | AFAS-Training on Accounting and Financial Statements analyses for AMIK Staff ( 5 days,training will be held from 18-22 Aprill 2011) | - | Training | Prior | 18 April 2011 | 22 April 2011 |
| 17.10 | Participation of Viopleta Arifi-Krasniqi & Saranda Rexha at the MFC Annual Confernce, in Prague, Czech Republic (May 17-20,2011) | 2 | Training | Prior | 17 May 2011 | 20 May 2011 |
| 17.9 | Participation of Ms. Edona Kryeziu -Xhambazi at Social Performance Task Force annual Meeting, which will be held in Hertogenbosch (Den Bosch), Netherland, from 19 – 24 June 2011 | 1 | Training | Prior | 19 June 2011 | 24 June 2011 |
|  | C2 TOTAL |  |  |  |  |  |
| C.3 | Component 3 – Assistance to KBA |  |  |  |  |  |
| 18.1 | Training for KBA in Trade Finance | 1 | Individual | Prior | December 8, 2008 | February 12, 2009 |
| 18.2 | Training for KBA in Operational Risk Management | 1 | Individual | Prior | Feb 20, 2009 | March 5, 2009 |
| 18.3 | Training for KBA in Corporate Banking and Corporate Financial Analysis | 1 | Individual | Prior | February 6, 2009 | February 11, 2009 |
| 18.4 | Training for KBA in Banking Sector development and pricing | 1 | Individual | Prior | January 21, 2009 | January 30, 2009 |
| 18.5 | Training for KBA in Credit Policy and Credit Process Control | 1 | Individual | Prior | October 2009 | February 2010 |
| 18.6 | Training for KBA in Audit Related Courses | 1 | Individual | Prior | June 2009 | Dec 2009 |
| 19 | Training for KBA trainers on advance banking sector topics based on training needs assessment | 1 | Individual | Prior | June 2009 | December 2009 |
| 19.1 | Training Needs Analysis (KBA) | 1 | CQ | Prior | December 2009 | February 2010 |
| 19.2 | Training on Train the Trainer | 1 | Individual | Prior | - | - |
| 19.3 | Marketing, Research, Planning and Communication | 1 | Individual | Prior | Nov 2010 | Dec 2010 |
| 19.4 | Trade finance course (new, from the savings) | 1 | Ind | Prior |  |  |
| 19.5 | Training on Business Communication and Writing Skills | 1 | Individual | Prior |  |  |
| 19.6 | Training on Taxes | 1 | Individual | Prior |  |  |
| 19.7 | Training on Housing Finance | 1 | Individual | Prior |  |  |
| 19.8 | Training on Math and MS Excel use in Financial Applications | 1 | Individual | Prior |  |  |
| 19.9 | Training on IFRS | 1 | Individual | Prior |  |  |
|  | C3 TOTAL |  |  |  |  |  |
|  | Project administration |  |  |  |  |  |
| 20 | Training in procurement and in financial management for CBK staff (procurement officer, and KBA/AMIK) | multiple | - | Annual training plan | February 2008 |  |
| 20.1 | General Management Program, Bled School of Management, Slovenia | 1 | - | - | March 2008 |  |
| 20.2 | ‘Project Cycle Management’ Course ITCILO (Ms. Zylfije Murati, Financial Specialist) | 1 | - | Prior | October 19, 2009 |  |
| 20.3 | ‘Equipment Procurement Management’ training ITCILO (Procurement Specialist) | 1 | - | Prior | October 11, 2009 |  |
| 20.4 | FM Specialist (Ms. Mirjeta Hysa) Contract | 1 | - | - | March 4, ‘08 |  |
| 20.5 | Zylfije Murati (FMS) in a training session on Project Cycle Management organized by ILO/Turin, from 19-30 October, 2009 | 1 | Training | Prior | 19 Oct 2009 |  |
| 20.6 | Valon Lepaja participation at the Seminar on Procurement under IBRD Loans and IDA Credits and Selection and Employment of Consultants by World Bank Borrowers; October 18-22, Zagreb, Croatia | 1 | Training | Prior | 18 Oct 2010 |  |
| 20.7 | Ms. Gentiana Godeni (FSTA Project Coordinator) the Course “Project Management in World Bank-funded projects Control and Project delivery” that will be held in Turin, Italy from 06 to 10 December | 1 | Training | Prior | Dec 6, ‘10 |  |
| 20.8 | Mrs. Zulfije Murati (FSTAP- Financial Specialist) participation at the Joint Financial Management and Disbursement Workshop for World Bank-financed Projects, that will be held from 19-21 January 2011, in Tirana, ALBANIA | 1 | Training | Prior | 18 Jan 2011 | 21 Jan 2011 |
| 21 | Project audit |  |  |  |  |  |
| 21.1 | Project audit (year 2008) | 1 | LCS | - | June 2009 | June 2009 |
| 21.2 | Project audit (year 2009) | 1 | LCS | - | 22 Jun 2010 | 23 July 2010 |
| 21.3 | Project audit (year 2010) | 1 | LCS | - |  |  |
|  | TOTAL $ 2 million |  |  |  |  |  |

# Footnotes

Reallocation from banking to insurance sector

Participant: Blerta Qerimi

14,483 taken for line 14.2 above

Participant: Diturie Hoxha (KBA)

# Comments

July 2011

# Text boxes

65529