## sepa
Project name: Odisha Disaster Recovery Project-IA BeMC |  | New Activities
Loan: TBD-IN-ODRP |  | Modified Activities
Procurement Plan Version: 2014-1 |  | Canceled Activities
Status: Approved |  | Activities without Modification
Date of Last Change of Status: 07/03/2014
Category Works: Activities ShowHide
Description | Reference # | Province/State | E/A | Amount in u$s | No Objection Documents | Publication / Invitation | Bid Opening | Evaluation of Bids | No Objection to Evaluation Report | Contract Signature Date | Total days of Process | End of Contract (Completed) | Comment
(between Bid Opening and Contract Signature Date)
P.P. - Executing Agency: 2014-1-BEHRA - Berhampur Municipal Corporation
Method: (National Competitive Bidding)
ODRP/BeMC/2.1 /013/CIB-S1 Provision of Roads, drains, water supply, sanitation in twelve selected slums in wards 1 to 3 in BeMC | ODRP-9-NCB-O- | Odisha | Est. | 561,278.16 | N/A | 15/07/15 | 14/08/15 | 14/09/15 | N/A | 07/10/15 | 54 | 07/01/17 | Correct it as component 2.1 28/02/2014 06:05
| Expected | [11 empty] | Add Comment
Post Review
| 661167 |  | Actual
ODRP/BeMC/2.1 /013/CIB-S2 Provision of Roads, drains, water supply, sanitation in eleven selected slums in wards 4 to 6 in BeMC | ODRP-10-NCB-O- | Odisha | Est. | 398,880.37 | N/A | 15/07/15 | 14/08/15 | 14/09/15 | N/A | 07/10/15 | 54 | 07/01/17 | Correct it as component 2.1Correct it as component 2.1 28/02/2014 06:05
| Expected | [11 empty] | Add Comment
Post Review
| 661176 |  | Actual
ODRP/BeMC/2.1 /013/CIB-S3 Provision of Roads, drains, water supply, sanitation in therteen selected slums in wards 7 to 15 | ODRP-11-NCB-O- | Odisha | Est. | 645,175.50 | N/A | 15/07/15 | 14/08/15 | 14/09/15 | N/A | 07/10/15 | 54 | 07/01/17 | Correct it as component 2.1 28/02/2014 06:06
| Expected | [11 empty] | Add Comment
Post Review
| 661179 |  | Actual
ODRP/BeMC/2.1 /013/CIB-S4 Provision of Roads,drains, water supply,sanitation in fourteen selected slums in wards 16to20 in BeMC | ODRP-12-NCB-O- | Odisha | Est. | 732,997.87 | N/A | 15/07/15 | 14/08/15 | 14/09/15 | N/A | 07/10/15 | 54 | 07/01/17 | Re-estimation of dates 17/02/2014 04:55
| Expected | [11 empty] | Add Comment
Post Review
| 661183 |  | Actual
ODRP/BeMC/2.1 /013/CIB-S5 Provision of Roads, drains, water supply, sanitation in Therteen selected slums in wards 21 to 28 BeMC | ODRP-13-NCB-O- | Odisha | Est. | 439,275.39 | N/A | 15/07/15 | 14/08/15 | 14/09/15 | N/A | 07/10/15 | 54 | 07/01/17 | Re-estimation of dates 15/02/2014 06:21
| Expected | [11 empty] | Add Comment
Post Review
| 661188 |  | Actual
ODRP/BeMC/2.1 /013/CIB-S6 Provision of Roads, drains, water supply, sanitation in Twelve selected slums in wards 28 to 33 BeMC | ODRP-15-NCB-O- | Odisha | Est. | 479,997.49 | N/A | 23/07/15 | 22/08/15 | 22/09/15 | N/A | 15/10/15 | 54 | 16/01/17 | Re-estimation of dates 15/02/2014 06:25
| Expected | [11 empty] | Add Comment
Post Review
| 661194 |  | Actual
ODRP/BeMC/2.1 /013/CIB-S7 Provision of Roads, drains, water supply, sanitation in nine selected slums in wards 34 to 37 BeMC | ODRP-16-NCB-O- | Odisha | Est. | 501,421.57 | N/A | 23/07/15 | 22/08/15 | 22/09/15 | N/A | 15/10/15 | 54 | 16/01/17 | Re-estimation of dates 15/02/2014 06:28
| Expected | [11 empty] | Add Comment
Post Review
| 661196 |  | Actual
ODRP/BeMC/2.1 /013/CIB-S8 Provision of solar power supported street lighting in 36 selected slums in wards 1 to 15 in BeMC | ODRP-18-NCB-O- | Odisha | Est. | 346,546.74 | N/A | 23/07/15 | 22/08/15 | 22/09/15 | N/A | 15/10/15 | 54 | 16/01/17 | Re-estimation of dates 15/02/2014 06:33
| Expected | [11 empty] | Add Comment
Post Review
| 661200 |  | Actual
ODRP/BeMC/2.1 /013/CIB-S9 Provision of solar power supported street lighting in 26 selected slums in wards 16 to 28 in BeMC | ODRP-19-NCB-O- | Odisha | Est. | 292,577.69 | N/A | 23/07/15 | 22/08/15 | 22/09/15 | N/A | 15/10/15 | 54 | 16/01/17 | Re-estimation of dates 15/02/2014 06:37
| Expected | [11 empty] | Add Comment
Post Review
| 661202 |  | Actual
ODRP/BeMC/2.1 /013/CIB-S10 Provision of solar power supported street lighting in 21 selected slums in wards 28 to 37 in BeMC | ODRP-21-NCB-O- | Odisha | Est. | 290,778.72 | N/A | 23/07/15 | 22/08/15 | 22/09/15 | N/A | 15/10/15 | 54 | 16/01/17 | Re-estimation of dates 15/02/2014 06:39
| Expected | [11 empty] | Add Comment
Post Review
| 661217 |  | Actual
ODRP/BeMC/2.2/013/CIB-D1 Construction of RCC drains of various sizes at Raghupathi nagar, Dhoba bandha huda and Uttarmukhi, chaitanyanagar | ODRP-23-NCB-O- | Odisha | Est. | 2,025,147.84 | N/A | 15/07/15 | 14/08/15 | 14/09/15 | N/A | 07/10/15 | 54 | 07/01/17 | Re-estimation of dates 15/02/2014 07:16
| Expected | [11 empty] | Add Comment
Post Review
| 661221 |  | Actual
ODRP/BeMC/2.2 /013/CIB-R6 Construction of Cement Concrete (C.C) roads in Nigam nagar near dhoba bandha, Raghupathi nagar, Pandara sahi etc.. | ODRP-24-NCB-O- | Odisha | Est. | 239,917.00 | N/A | 09/01/17 | 08/02/17 | 08/03/17 | N/A | 30/03/17 | 50 | 30/06/18 | Re-estimation of dates 06/02/2014 08:43
| Expected | [11 empty] | Add Comment
Post Review
| 661223 |  | Actual
ODRP/BeMC/2.2 /013/CIB-D2 Construction of RCC drains of various sizes at Bhabani nagar, Brama nagar and Aurobindo nagar, Tulasi nagar, Lingaraj nagar, AIR station, rotry club | ODRP-26-NCB-O- | Odisha | Est. | 1,872,890.00 | N/A | 15/07/15 | 14/08/15 | 14/09/15 | N/A | 07/10/15 | 54 | 07/01/17 | Re-estimation of dates 15/02/2014 07:17
| Expected | [11 empty] | Add Comment
Post Review
| 661227 |  | Actual
ODRP/BeMC/2.2 /013/CIB-D3 Construction of RCC drains of various sizes at Lingaraj theator, Neelkantnagar, Rajivnagar and Patitapaban nagar, Badrirajnagar, gosaninuagaon | ODRP-28-NCB-O- | Odisha | Est. | 1,951,554.00 | N/A | 23/07/15 | 22/08/15 | 22/09/15 | N/A | 15/10/15 | 54 | 16/01/17 | Re-estimation of dates 15/02/2014 07:20
| Expected | [11 empty] | Add Comment
Post Review
| 661229 |  | Actual
ODRP/BeMC/2.2 /013/CIB-D4 Construction of RCC drains of various sizes at Jaiprakashnagar, Baidyanath nagar, Jyothinagar, Tata Benz jn, Dharmanagar, Burma colony | ODRP-30-NCB-O- | Odisha | Est. | 1,628,394.00 | N/A | 23/07/15 | 22/08/15 | 22/09/15 | N/A | 15/10/15 | 54 | 16/01/17 | Re-estimation of dates 15/02/2014 07:22
| Expected | [11 empty] | Add Comment
Post Review
| 661231 |  | Actual
ODRP/BeMC/2.2 /013/CIB-D5 Construction of Storm Water Drains of various sizes at Harsha vihar ,from Godavarish Nagar to Medical Campus ,Defence colony, from Binayak Sabat residence to Dhoba Nalha. | ODRP-33-NCB-O- | Odisha | Est. | 767,342.00 | N/A | 23/07/15 | 22/08/15 | 22/09/15 | N/A | 15/10/15 | 54 | 16/01/17 | Re-estimation of dates 15/02/2014 07:24
| Expected | [11 empty] | Add Comment
Post Review
| 661234 |  | Actual
P.P. - Executing Agency: 2014-1-BEHRA - Berhampur Municpal Corporation
Method: (National Competitive Bidding)
ODRP/BeMC/2.2 /013/CIB-R7 Construction of C.C roads in Neelakantha nagar, Sashtri nagar, Madhura nagar etc.. | ODRP-25-NCB-O- | Odisha | Est. | 207,045.00 | N/A | 09/01/17 | 08/02/17 | 08/03/17 | N/A | 30/03/17 | 50 | 30/06/18 | Re-estimation of dates 06/02/2014 08:54
| Expected | [11 empty] | Add Comment
Post Review
| 661226 |  | Actual
ODRP/BeMC/2.2 /013/CIB-R8 Construction of C.C roads at Palia sahi, Badhei street, Golapalli street, ORT Colony, Laxmi nagar | ODRP-27-NCB-O- | Odisha | Est. | 271,808.00 | N/A | 09/01/17 | 08/02/17 | 08/03/17 | N/A | 30/03/17 | 50 | 30/06/18 | Update of the % of Bank Loan Amount (70) 06/02/2014 08:58
| Expected | [11 empty] | Add Comment
Post Review
| 661228 |  | Actual
ODRP/BeMC/2.2 /013/CIB-R9 Construction of C.C roads at New bustand, Manjuri nagar, Baikuntha nagar, Brahma nagar etc.. | ODRP-29-NCB-O- | Odisha | Est. | 194,779.00 | N/A | 09/01/17 | 08/02/17 | 08/03/17 | N/A | 30/03/17 | 50 | 30/06/18 | Update of the % of Bank Loan Amount (70) 06/02/2014 09:02
| Expected | [11 empty] | Add Comment
Post Review
| 661230 |  | Actual
ODRP/BeMC/2.2 /013/CIB-R10 Construction of C.C roads at Gandhi nagar, Sunder nagar, Burma colony, Somanath & Netabar nagar | ODRP-31-NCB-O- | Odisha | Est. | 235,501.00 | N/A | 09/01/17 | 08/02/17 | 08/03/17 | N/A | 30/03/17 | 50 | 30/06/18 | Update of the % of Bank Loan Amount (70) 06/02/2014 09:05
| Expected | [11 empty] | Add Comment
Post Review
| 661232 |  | Actual
ODRP/BeMC/2.2 /013/CIB-R11 Construction of C.C road and drains at Dharma nagar, Haradakhandi, Ganapathi, | ODRP-32-NCB-O- | Odisha | Est. | 480,652.00 | N/A | 09/01/17 | 08/02/17 | 08/03/17 | N/A | 30/03/17 | 50 | 30/06/18 | Update of the % of Bank Loan Amount (70) 06/02/2014 09:08
| Expected | [11 empty] | Add Comment
Post Review
| 661233 |  | Actual
ODRP/BeMC/2.2 /013/CIB-R12 Construction of C.C road and drains at Barajaraj nagar, Sriramnagar, Tulasi, pichpicha, Bishnu nagar | ODRP-34-NCB-O- | Odisha | Est. | 1,015,436.00 | N/A | 09/01/17 | 08/02/17 | 08/03/17 | N/A | 30/03/17 | 50 | 30/06/18 | Update of the % of Bank Loan Amount (70) 06/02/2014 09:11
| Expected | [11 empty] | Add Comment
Post Review
| 661235 |  | Actual
ODRP/BeMC/2.2 /013/CIB-R13 Construction of C.C road and drains at Jena colony, Adua st, Janaganbadi sahi and Prahalad nagar etc | ODRP-36-NCB-O- | Odisha | Est. | 357,013.00 | N/A | 09/01/17 | 08/02/17 | 08/03/17 | N/A | 30/03/17 | 50 | 30/06/18 | Update of the % of Bank Loan Amount (70) 06/02/2014 14:20
| Expected | [11 empty] | Add Comment
Post Review
| 661415 |  | Actual
ODRP/BeMC/2.2/013/CIB-R14 Construction of C.C road and drains at Coporation, urbanbank road, Khaja sahi, and Triveni nagar etc | ODRP-37-NCB-O- | Odisha | Est. | 358,976.00 | N/A | 09/01/17 | 08/02/17 | 08/03/17 | N/A | 30/03/17 | 50 | 30/06/18 | Update of the % of Bank Loan Amount (70) 06/02/2014 14:23
| Expected | [11 empty] | Add Comment
Post Review
| 661417 |  | Actual
ODRP/BeMC/2.2 /013/CIB-R15 Construction of C.C road and drains at Prem nagar, Ganesh nagar, Bimlanagar and Ramalingam tank. | ODRP-38-NCB-O- | Odisha | Est. | 680,991.00 | N/A | 09/01/17 | 08/02/17 | 08/03/17 | N/A | 30/03/17 | 50 | 30/06/18 | Update of the % of Bank Loan Amount (70) 06/02/2014 14:26
| Expected | [11 empty] | Add Comment
Post Review
| 661419 |  | Actual
ODRP/BeMC/2.2 /013/CIB-R16 Construction of C.C road and drains at Bijipur canal st, Charidiba& Bada sahi, Ganeshmandir hillpatna. | ODRP-39-NCB-O- | Odisha | Est. | 310,731.00 | N/A | 09/10/17 | 08/11/17 | 08/12/17 | N/A | 30/12/17 | 52 | 30/03/19 | Re-estimation of dates 15/02/2014 07:53
| Expected | [11 empty] | Add Comment
Post Review
| 661420 |  | Actual
ODRP/BeMC/2.2 /013/CIB-R17 Construction of C.C road &drains at Ashok nagar, cooperative colony, Santhinagar, ORT colony. | ODRP-40-NCB-O- | Odisha | Est. | 524,481.00 | N/A | 09/10/17 | 08/11/17 | 08/12/17 | N/A | 30/12/17 | 52 | 30/03/19 | Re-estimation of dates 15/02/2014 07:55
| Expected | [11 empty] | Add Comment
Post Review
| 661422 |  | Actual
ODRP/BeMC/2.2 /013/CIB-R18 Construction of C.C road and drains at Krushna nagar, Langipalli colony, Chanukyanagar, Uma nagar | ODRP-41-NCB-O- | Odisha | Est. | 520,883.00 | N/A | 09/05/16 | 10/06/16 | 09/07/16 | N/A | 30/08/16 | 81 | 30/11/17 | Re-estimation of dates 15/02/2014 08:01
| Expected | [11 empty] | Add Comment
Post Review
| 661423 |  | Actual
ODRP/BeMC/2.2 /013/CIB-R19 Construction of C.C road and drains at Ganesh nagar, Indira nagar,forest colony, Nigam nagar near industrial estate | ODRP-42-NCB-O- | Odisha | Est. | 604,290.00 | N/A | 09/05/16 | 09/06/16 | 08/07/16 | N/A | 30/08/16 | 82 | 30/11/17 | Re-estimation of dates 15/02/2014 08:05
| Expected | [11 empty] | Add Comment
Post Review
| 661424 |  | Actual
ODRP/BeMC/2.2 /013/CIB-R20 Construction of C.C road and drains at Gajapathi nagar, Sidhard nagar,Ramnagar, Ayodyanagar etc | ODRP-43-NCB-O- | Odisha | Est. | 538,382.00 | N/A | 09/05/16 | 09/06/16 | 08/07/16 | N/A | 30/08/16 | 82 | 30/11/17 | Re-estimation of dates 15/02/2014 08:07
| Expected | [11 empty] | Add Comment
Post Review
| 661425 |  | Actual
ODRP/BeMC/2.2 /013/CIB-R21 Construction of C.C road and drains at Alekha nagar, Niranjan nagar, Rajib nagar and DIG colony | ODRP-44-NCB-O- | Odisha | Est. | 1,016,744.00 | N/A | 09/05/16 | 10/06/16 | 11/07/16 | N/A | 30/08/16 | 81 | 30/11/17 | Re-estimation of dates 15/02/2014 08:11
| Expected | [11 empty] | Add Comment
Post Review
| 661426 |  | Actual
ODRP/BeMC/2.2 /013/CIB-R1 Military Line main Road, Haridakhandi to Chandania Pahad,Hanumaan Bazar Square to Sub-Register Square, Aska Road near Labour office to NH-59 via niladri vihar somanath nagar,Sub-Register office Jn. to Aska Road, NH-59 to Hotel Mourya Chhaka via Gramadebathi sahi,thakurani temple, bada bazar to Gajapathi statue jn.Internal Road of BRIT Colony | ODRP-45-NCB-O- | Odisha | Est. | 1,066,625.00 | N/A | 08/04/16 | 08/05/16 | 08/06/16 | N/A | 30/07/16 | 83 | 30/10/17 | Re-estimation of dates 06/02/2014 23:18
| Expected | [11 empty] | Add Comment
Post Review
| 661646 |  | Actual
ODRP/BeMC/2.2 /013/CIB-R2 Corporation Road,City Bus-Stand Junction to Bajpayee Road,Utakal Ashram Road via Kali Mandir,Ramakrishna Nagar, Hati Bandha street,Subarao Jn. to Utkal Ashram Tower via Khaikote college Junction,Tata Benz Jn. to Old Bus-Stand via utkal ashram road,Suraj Bihar main road and internal roads,Const. of Road from S.N.T Temple Jn. to City Hospital road ,Jagannath vihar ,Harsha Vihar,Santhi Marga,Somanath nagar and Sriram Nagar | ODRP-46-NCB-O- | Odisha | Est. | 882,803.00 | N/A | 08/04/16 | 08/05/16 | 08/06/16 | N/A | 30/07/16 | 83 | 30/10/17 | Update of the % of Bank Loan Amount (70) 06/02/2014 23:27
| Expected | [11 empty] | Add Comment
Post Review
| 661647 |  | Actual
ODRP/BeMC/2.2 /013/CIB-R3 Station Road Near Nehuru Park to Gandhi Nagar Sai Complex via santoshi maa temple road,sunari bandha sahi , ambika nagar,City Bus-Stand to Bhaba Nagar chhaka via Kali Temple Jn. , Godavarish Nagar Main road, B.N.T road and Ashok Nagar main road,Patitapaban Nagar, | ODRP-47-NCB-O- | Odisha | Est. | 1,061,718.00 | N/A | 08/04/16 | 08/05/16 | 08/06/16 | N/A | 30/07/16 | 83 | 30/10/17 | Update of the % of Bank Loan Amount (70) 06/02/2014 23:30
| Expected | [11 empty] | Add Comment
Post Review
| 661648 |  | Actual
ODRP/BeMC/2.2 /013/CIB-R4 Komapalli Square to Goilundi Square,N.H -59 near S.B.I ADB branch to Sidharth Nagar Jn. or Bhabinipur Road,Gajapathi Nagar main road to N.H-59 Jn. to Nilanchal Nagar,Lanjipalli Jn. to N.H-5 via Kanjiamma temple,Congress office chowk to Bijipur chowk and P.V N Rao petrol pump Jn. to Mango marketGandhi Nagar, Sub-Register office chowk Prem Nagar. | ODRP-48-NCB-O- | Odisha | Est. | 872,500.00 | N/A | 08/04/16 | 08/05/16 | 08/06/16 | N/A | 30/07/16 | 83 | 30/10/17 | Update of the % of Bank Loan Amount (70) 06/02/2014 23:32
| Expected | [11 empty] | Add Comment
Post Review
| 661649 |  | Actual
ODRP/BeMC/2.2 /013/CIB-R5 Banchanidhi Nagar -Kalinga Nagar Main Road,Saradhabali main Road,Basudev nagar main Road,Alakapuri Road to Ambapua Kalimanditr Jn. to NH-59 via Khodasingi ,Const. of Road at Sri krishna Vihar & diffence colony by the side of Jyothi Restaurent,Tata benz Square to Station Road (via Ganesh Mandir to Nehuru Park),nternal Road of Maruthi Vihar and Gandhi Nagar,City Bus-Stand Junction to City Hospital near Satsang Temple | ODRP-49-NCB-O- | Odisha | Est. | 729,563.00 | N/A | 08/04/16 | 08/05/16 | 08/06/16 | N/A | 30/07/16 | 83 | 30/10/17 | Update of the % of Bank Loan Amount (70) 06/02/2014 23:34
| Expected | [11 empty] | Add Comment
Post Review
| 661650 |  | Actual
ODRP/BeMC/2.2 /013/CIB-WS1 Providing Pumping/gravity Ductile Iron pipe lines from Ruskulya river collector well to Kaliabali MBR, Mandia Palli Jn. On the NH upto Karapalli Chhak, and Karapalli Jn to M.E.S at Golabandha | ODRP-50-NCB-O- | Odisha | Est. | 3,326,619.70 | N/A | 25/08/15 | 25/09/15 | 26/10/15 | N/A | 20/11/15 | 56 | 22/05/17 | Correct it as component 2.2 28/02/2014 06:25
| Expected | [11 empty] | Add Comment
Post Review
| 661651 |  | Actual
ODRP/BeMC/2.2 /013/CIB-WS2 Repair, renovation, rehabilitation and water proofing of existing damaged 4.5 million gallon capacity clear water reservoir at Kaliabali to increase its useful life | ODRP-51-NCB-O- | Odisha | Est. | 268,209.84 | N/A | 25/08/15 | 25/09/15 | 26/10/15 | N/A | 20/11/15 | 56 | 20/02/17 | Correct it as component 2.2 28/02/2014 06:25
| Expected | [11 empty] | Add Comment
Post Review
| 661652 |  | Actual
Category Goods: Activities ShowHide
Description | Reference # | Province/State | E/A | Amount in u$s | No Objection Documents | Publication / Invitation | Bid Opening | Evaluation of Bids | No Objection to Evaluation Report | Contract Signature Date | Total days of Process | End of Contract (Completed) | Comment
(between Bid Opening and Contract Signature Date)
P.P. - Executing Agency: 2014-1-BEHRA - Berhampur Muincipal Cororation
Method: SH (Shopping)
ODRP/BeMC/4.2 /013/CIB-G2 IT equipment like, laptop/desk top, printers, ploters, mobile & wire less communication (walkie Talkie) etc | ODRP-17-CP-B- | Odisha | Est. | 139,011.00 | N/A | 16/06/14 | 01/07/14 | 08/07/14 | N/A | 21/07/14 | 20 | 30/08/14 | Update / Change Associated Component (Component 4.2) 15/02/2014 08:29
| Expected | [11 empty] | Add Comment
Post Review
| 661199 |  | Actual
P.P. - Executing Agency: 2014-1-BEHRA - Berhampur Muncipal Corporation
Method: SH (Shopping)
ODRP/BeMC/4.2 /013/CIB-G1 Office furniture for Project implementation unit in BeMC | ODRP-14-CP-B- | Odisha | Est. | 106,303.00 | N/A | 16/06/14 | 01/07/14 | 08/07/14 | N/A | 21/07/14 | 20 | 30/08/14 | Update / Change Associated Component (Component 4.2) 15/02/2014 08:26
| Expected | [11 empty] | Add Comment
Post Review
| 661189 |  | Actual
P.P. - Executing Agency: 2014-1-BEHRA - Berhampur Municipal Corporation
Method: SH (Shopping)
ODRP/BeMC/4.2 /013/CIB-G3 Air conditioners, fridge, TV etc for PIU | ODRP-20-CP-B- | Odisha | Est. | 98,126.00 | N/A | 16/06/14 | 01/07/14 | 08/07/14 | N/A | 21/07/14 | 20 | 30/08/14 | Update / Change Associated Component (Component 4.2) 15/02/2014 08:29
| Expected | [11 empty] | Add Comment
Post Review
| 661212 |  | Actual
ODRP/BeMC/4.2 /013/CIB-G4 Software like, MS office, AutoCAD, project planning etc | ODRP-22-CP-B- | Odisha | Est. | 89,948.00 | N/A | 16/06/14 | 01/07/14 | 08/07/14 | N/A | 21/07/14 | 20 | 30/08/14 | Update / Change Associated Component (Component 4.2) 15/02/2014 08:28
| Expected | [11 empty] | Add Comment
Post Review
| 661218 |  | Actual
ORDP/BeMC/4.2/013/CIB-G5:Hiring of vehicles for day to day work at PIU | ODRP-70-CP-B- | Odisha | Est. | 141,301.00 | N/A | 16/06/14 | 04/07/14 | 08/07/14 | N/A | 21/07/14 | 17 | 31/05/17 | Re-estimation of dates 01/03/2014 06:13
| Expected | [11 empty] | Add Comment
Post Review
| 675105 |  | Actual
Category Consultants - Firms: Activities ShowHide
Description | Reference # | Province/State | E/A | Amount in u$s | Request for Proposal (RFP) and Short List | No Objection to RFP and Short List | Invitation for RFP | Bid Opening | Technical Evaluation | No Objection to Technical Evaluation | Final Evaluation and Negotiation | No Objection to Contract | Contract Signature Date | Total days of Process | End of Contract (Completed) | Comment
(between Bid Opening and Contract Signature Date)
P.P. - Executing Agency: 2014-1-BEHRA - Berhampur Municipal Corporation
Method: QCBS (Quality and Cost Based Selection)
ODRP/2.4/CIIB/LF/013/001-Preparation of strom water drainage master plan for BeMC area,DPR for drain & Roads including Bid Documents in line with master plan(excluding Slums ) | ODRP-1-SBCC-CF- | Odisha | Est. | 278,022.00 | 01/06/14 | N/A | 15/06/14 | 15/07/14 | 14/08/14 | N/A | 07/10/14 | N/A | 30/10/14 | 107 | 30/04/15 | Update / Change Associated Component (Component 2) 01/03/2014 01:55
| Expected | [14 empty] | Add Comment
Post Review
| 659797 |  | Actual
ODRP/4.2 /CIIB/LF/013/002 Consultancy services for Project Management, Supervision and Quality control Consultancy through Establishment of Project Implementation Unit (PIU) in Berhampur MC | ODRP-2-SBCC-CF- | Odisha | Est. | 837,338.00 | 01/06/14 | 07/06/14 | 15/06/14 | 15/07/14 | 14/08/14 | 21/08/14 | 07/10/14 | 14/10/14 | 30/10/14 | 107 | 30/04/15 | Re-estimation of dates 15/02/2014 05:52
| Expected | [14 empty] | Add Comment
Prior Review
| 661122 |  | Actual
ODRP/4.2 /CIIB/LF/013/003 Consultancy services for preparaton of DPRs in all the wards for83 slums infrastructure works under CIIP in Berhampur MC | ODRP-3-SBCC-CF- | Odisha | Est. | 278,022.00 | 01/08/14 | N/A | 16/08/14 | 16/09/14 | 14/10/14 | N/A | 08/12/14 | N/A | 30/12/14 | 105 | 30/06/15 | Re-estimation of dates 15/02/2014 05:49
| Expected | [14 empty] | Add Comment
Post Review
| 661123 |  | Actual
ODRP/2.4/CIIB/LF/013/004 Consultancy services for preparation of Liquid waste management and treatment master plan (including septage management) for Berhampur Municipal Corporation area, preparation of DPR for sewerage & septage including bid document in line with Master plan in BeMC | ODRP-4-SBCC-CF- | Odisha | Est. | 212,605.00 | 11/08/14 | N/A | 25/08/14 | 25/09/14 | 24/10/14 | N/A | 15/12/14 | N/A | 07/01/15 | 104 | 07/07/15 | Update / Change Associated Component (Component 2) 01/03/2014 01:57
| Expected | [14 empty] | Add Comment
Post Review
| 661124 |  | Actual
ODRP/2.4/CIIB/LF/013/005 Consultancy services for preparation of master plan for street vending and vending zone for Berhampur Municipal Corporation area, preparation of DPR including bid document in line with Master plan in BeMC | ODRP-5-SBCC-CF- | Odisha | Est. | 66,071.00 | 10/08/14 | N/A | 25/08/14 | 24/09/14 | 24/10/14 | N/A | 15/12/14 | N/A | 07/01/15 | 105 | 07/01/15 | Update / Change Associated Component (Component 2) 01/03/2014 01:59
| Expected | [14 empty] | Add Comment
Post Review
| 661125 |  | Actual
ODRP/4.2 /CIIB/LF/013/006 Engagement of Chatered Accontant firm for internal audit and preparation of IFR | ODRP-6-SBCC-CF- | Odisha | Est. | 49,717.00 | 01/10/14 | N/A | 15/10/14 | 15/11/14 | 15/12/14 | N/A | 05/02/15 | N/A | 27/03/15 | 132 | 30/03/19 | Re-estimation of dates 16/02/2014 13:28
| Expected | [14 empty] | Add Comment
Post Review
| 661127 |  | Actual
ODRP/4.2 /CIIB/LF/013/007 Engagement of agency for Third Party Quality Audit | ODRP-7-SBCC-CF- | Odisha | Est. | 66,071.00 | 10/08/15 | N/A | 25/08/15 | 24/09/15 | 23/10/15 | N/A | 15/12/15 | N/A | 07/01/16 | 105 | 30/03/19 | Re-estimation of dates 16/02/2014 13:31
| Expected | [14 empty] | Add Comment
Post Review
| 661148 |  | Actual
ODRP4.2 /CIIB/LF/013/008 Engagement of agency for auidt of Social and environmental compliances | ODRP-8-SBCC-CF- | Odisha | Est. | 77,519.00 | 01/11/14 | N/A | 15/11/14 | 15/12/14 | 14/01/15 | N/A | 05/03/15 | N/A | 27/03/15 | 102 | 30/03/19 | Re-estimation of dates 17/02/2014 02:54
| Expected | [14 empty] | Add Comment
Post Review
| 661160 |  | Actual
Category Consultants - Individuals: Activities ShowHide
Description | Reference # | Province/State | E/A | Amount in u$s | No Objection to the TOR | Contract Signature Date | Total days of Process | End Date of Activity | Comment
P.P. - Executing Agency: 2014-1-BEHRA - Berhampur Municipal Corporation
Method: IC (Selection of Individual Consultants)
ODRP/4.2 /CIIB/LIC/013/002 National Expert-Community Development - STC | ODRP-64-IC-CI- | Odisha | Est. | 104,667.26 | N/A | 15/12/14 |  | 30/03/19 | Re-estimation of dates 16/02/2014 10:15
| Expected | [7 empty] | Add Comment
Post Review
| 666698 |  | Actual
ODRP/4.2 /CIIB/LIC/013/003 National Expert - Urban infrastructure - STC | ODRP-65-IC-CI- | Odisha | Est. | 104,667.26 | N/A | 15/10/14 |  | 30/03/19 | Re-estimation of dates 16/02/2014 09:59
| Expected | [7 empty] | Add Comment
Post Review
| 666699 |  | Actual
ODRP/4.2 /CIIB/LIC/013/004 National Expert- Financial management - STC | ODRP-66-IC-CI- | Odisha | Est. | 104,667.26 | N/A | 15/10/14 |  | 30/03/19 | Re-estimation of dates 16/02/2014 10:02
| Expected | [7 empty] | Add Comment
Post Review
| 666700 |  | Actual
ODRP/4.2 /CIIB/LIC/013/005 National Expert - Procurement - STC | ODRP-67-IC-CI- | Odisha | Est. | 104,667.26 | N/A | 15/10/14 |  | 30/03/19 | Re-estimation of dates 16/02/2014 10:05
| Expected | [7 empty] | Add Comment
Post Review
| 666701 |  | Actual
ODRP/4.2 /CIIB/LIC/013/006 National expert - Envirnoment - STC | ODRP-68-IC-CI- | Odisha | Est. | 67,054.00 | N/A | 15/12/14 |  | 30/03/19 | Re-estimation of dates 16/02/2014 10:09
| Expected | [7 empty] | Add Comment
Post Review
| 666702 |  | Actual
ODRP/4.2 /CIIB/LIC/013/001 National Expert - Urban Planning - STC | ODRP-69-IC-CI- | Odisha | Est. | 104,667.26 | N/A | 15/12/14 |  | 30/03/19 | Re-estimation of dates 16/02/2014 10:12
| Expected | [7 empty] | Add Comment
Post Review
| 666703 |  | Actual