## General
Attachment 3. Procurement Plan
I. General
1. | Project Information
| Project Name: | Institutional Support Project
| Country: | Yemen
| Project ID: | P117608
| Loan/Credit Numbers: | H570-RY
| Closing date | 30 spet 2016
2. | Bank's approval date of Procurement Plan | Original:27/04/2010
Revision 1: November 14 2010
Revision : December 8 2011
Revision 3:March 2012
Revision 4: June 9, 2012
Revision 5: August 2012
Revision 6: April 2013
Revision 7: May 2014
Revision 8: Sep 2014
3. | Date of General Procurement Notice
II. Goods, Work and Non-Consulting Services Thresholds
1. | Prior Review Threshold. Procurement Decisions subject to Prior Review by the Bank as stated in Appendix 1 to the Guidelines for Procurement
1a. | Procurement Category | Prior Review Threshold (USD) | Comments
| Goods | >=500,000 and first package irrespective of the value
| Works | N/A
| Non-Consultant Services | all
1b. | Procurement Method | Procurement Method Threshold (USD) | Comments
| ICB (Goods) | >=500,000
| NCB (Goods) | <500000
| Shopping (Goods) | <50000
| ICB (Works) | -
| NCB (Works) | -
| ICB (Non-Consultant Services) | -
2. | Prequalification. N/A
3. | Proposed Procedures for CDD Components (as per paragraph 3.17 of the Guidelines): N/A
4. | Reference to (if any) Project Operational/Procurement Manual: NIL
5. | Any Other Special Procurement Arrangements: [NIL
6. | Procurement Packages with Methods and Time Schedule: See attached "Goods and Works" sheet
III. Selection of Consultants
1. | Prior Review Threshold: Selection decisions subject to Prior Review by Bank as stated in Appendix 1 to the Guidelines Selection and Employment of Consultants:
1a. | Procurement Category | Prior Review Threshold (USD) | Comments
| Consulting Firms (Competitive) | 200000
| Consulting Firms (Sole Source) | all
| Individual Consultants (Competitive) | 50000
| Individual Consultants (Sole Source) | all
1b. | Procurement Method | Procurement Method Threshold (USD) | Comments
| QCBS | >=300000
| FBS | > 300,000
| LCS | > 300,000
| CQS | <200,000
| Consulting Firms (Sole Source) | No threshold
| Individual Consultants (Competitive) | > 50,000
| Individual Consultants (Sole Source) | No threshold
2. | Short list comprising entirely of national consultants: -Short list of consultants for services, estimated to cost less than US$300,000 equivalent per contract, may comprise entirely national consultants in accordance with the provisions of paragraph 2.7 of the Consultant Guidelines.
3. | Any Other Special Procurement Arrangements: Single sourcing of firms and sole sourcing of individual consultants may be exceptionally used as per the Bank’s guidelines.
4. | Consultancy Assignments with Selection Methods and Time Schedule: See attached "Consulting Services" sheet
IV. Implementing Agency Capacity Building Activities with Time Schedule: See attached "Capacity Building" sheet
Legend:
ICB = International Competitive Bidding
NCB = National Competitive Bidding
SH = Shopping
QCBS = Quality and Cost-based Selection
CQS = Selection Based on consultants' Qualifications
IC = Selection of Individual Consultants
FBS = selection under a Fixed Budget

## ICB and NCB
Review date: October 2014
Sr No |  | Package/ Reference No. | Description of Goods | Goods/ NCS | Review by Bank (Prior/ Post) | Method of Selection | Domestic Preference (yes/no) | Preparation of Bid Document (Date) | Bank’s No Objection to Bidding Document (Date)** | Bid Invitation (Date) | Bid opening (Date) | Contract Award Decision (Date) | Bank’s No Objection to Bid Evaulation Report and Contract Award (Date)** | Contract Signed (Date) | Contract Value | Contract Currency | Contract No. | Name, City, and Country of Supplier (incl. Zip Code if US) | Completion of Contract (Date) | Expenditure incurred to Date
1 | Planned | G1 | Supply Furniture for Head office and 23 Branches ( under component 1.1) and 20 districts | Goods | PRIOR | NCB | No | 2011-07-01 | 2011-07-16 | 2011-07-30 | 2011-10-22 | 2011-11-22 | 2011-11-30 | 2011-12-15
| Revised 9-Nov 11 |  |  |  | PRIOR | NCB | No | 2011-07-01 | 2011-07-21 | 2011-07-24 | 2011-09-07 | 2011-10-07 | 2011-10-17 | 2011-10-20
| Revised Dec 2011 |  |  |  | PRIOR | NCB | No | 2012-02-01 | 2012-02-21 | 2012-02-24 | 2012-04-09 | 2012-05-09 | 2012-05-19 | 2012-05-22
| Revised Feb 2012 |  |  |  | PRIOR | NCB | No | 2013-03-10 | 2013-03-25 | 2013-04-08 | 2013-05-20 | 2013-06-19 | 2013-07-04 | 2013-07-11
| Revised June 2012 |  |  |  | PRIOR | NCB | No | 2013-05-07 | 2013-05-22 | 2013-06-05 | 2013-07-17 | 2013-08-16 | 2013-08-31 | 2013-09-07 |  |  |  |  | 2014-01-05
| Revised August 2012 |  |  |  | PRIOR | NCB | No | 2013-06-27 | 2013-07-12 | 2013-07-26 | 2013-09-06 | 2013-10-06 | 2013-10-21 | 2013-10-28 |  |  |  |  | 2014-02-25
| Revised Dec 2013 |  |  |  | PRIOR | NCB | No | 2014-05-30 | 2014-06-14 | 2014-06-28 | 2014-08-09 | 2014-09-08 | 2014-09-23 | 2014-09-30 |  |  |  |  | 2015-01-28
| Revised May 2014 |  |  |  | Post | NCB | No | 2014-08-28 | N/A | 2014-08-28 | 2014-09-27 | 2014-10-27 | N/A | 2014-11-03 |  |  |  |  | 2015-01-02
| Revised sep 2014 |  |  |  | Post | NCB | No | 2014-09-30 | N/A | 2014-09-30 | 2014-10-30 | 2014-11-29 | N/A | 2014-12-06
| revised October 2014 |  |  |  | Prior | ICB | No | 2014-11-10 | N/A | 2014-11-10 | 2014-12-10 | 2015-01-09 | N/A | 2015-01-16
Actual
2 | Planned | G2 | supply Computers & Peripherals for head office and 23 branches and 25 districts (under Componnet 1.1) | Goods | PRIOR | NCB | No | 2011-07-01 | 2011-07-16 | 2011-07-30 | 2011-10-22 | 2011-11-22 | 2011-11-30 | 2011-12-15
| Revised 9-Nov 11 |  |  |  | PRIOR | NCB | No | 2011-07-01 | 2011-07-21 | 2011-07-24 | 2011-09-07 | 2011-10-07 | 2011-10-17 | 2011-10-20
| Revised Dec 2011 |  |  |  | PRIOR | NCB | No | 2012-02-01 | 2012-02-21 | 2012-02-24 | 2012-04-09 | 2012-05-09 | 2012-05-19 | 2012-05-22
| Revised Feb 2012 |  |  |  | PRIOR | NCB | No | 2013-03-10 | 2013-03-25 | 2013-04-08 | 2013-05-20 | 2013-06-19 | 2013-07-04 | 2013-07-11
| Revised June 2012 |  |  |  | PRIOR | NCB | No | 2013-05-07 | 2013-05-22 | 2013-06-05 | 2013-07-17 | 2013-08-16 | 2013-08-31 | 2013-09-07 |  |  |  |  | 2014-01-05
| Revised August 2012 |  |  |  | PRIOR | NCB | No | 2013-06-27 | 2013-07-12 | 2013-07-26 | 2013-09-06 | 2013-10-06 | 2013-10-21 | 2013-10-28 |  |  |  |  | 2014-02-25
| Revised Dec 2013 |  |  |  | PRIOR | NCB | No | 2014-05-30 | 2014-06-14 | 2014-06-28 | 2014-08-09 | 2014-09-08 | 2014-09-23 | 2014-09-30 |  |  |  |  | 2015-01-28
| Revised May 2014 |  |  |  | PRIOR | NCB | No | 2014-05-30 | 2014-06-14 | 2014-06-21 | 2014-07-21 | 2014-09-30 | 2014-10-15 | 2014-10-22 |  |  |  |  | 2014-12-21
| revised October 2014 |  |  |  | PRIOR | NCB | No |  |  |  |  | 2014-11-07 | 2014-11-12 | 2014-11-14
| Actual |  |  |  | PRIOR | NCB | No | 2014-05-27 | 2014-06-03 | 2014-06-21 | 2014-08-04
3 | Planned | G3 | Goods for implementing communications strategy (under component 1.2) (Cancelled) | Goods 4 contracts | Post | NCB | No | - | N.A | 2011-12-01 | 2011-12-18 | 2011-12-25 | N.A | 2012-01-02
| Revised 9-Nov 11 |  |  |  | Post | NCB | No | 2011-11-25 | N.A | 2011-12-01 | 2011-12-31 | 2012-01-15 | N.A | 2012-01-20
| Revised 20 Jul11 |  |  |  | Post | NCB | No | 2012-12-25 | N.A | 2013-01-01 | 2013-01-31 | 2013-02-15 | N.A | 2013-02-20
| Revised Feb 2012 |  |  |  | Post | NCB | No | 2015-03-13 | N.A | 2015-03-27 | 2015-04-26 | 2015-05-26 | N.A | 2015-06-02
| Revised June 2012 |  |  |  | Post | NCB | No | 2015-05-10 | N.A | 2015-05-24 | 2015-06-23 | 2015-07-23 | N.A | 2015-07-30 |  |  |  |  | 2015-11-27
| Revised August 2012 |  |  |  | Post | NCB | No | 2015-06-30 | N.A | 2015-07-14 | 2015-08-13 | 2015-09-12 | N.A | 2015-09-19 |  |  |  |  | 2016-01-17
| Revised Dec 2013 |  |  |  | Post | NCB | No | 2015-12-25 | N.A | 2016-01-08 | 2016-02-07 | 2016-03-08 | N.A | 2016-03-15 |  |  |  |  | 2016-07-13
| Revised May 2014 |  |  |  | Post | NCB | No | 2015-02-01 | N.A | 2015-02-01 | 2015-03-03 | 2015-04-02 | N.A | 2015-04-09 |  |  |  |  | 2015-08-07
| revised October 2014 |  |  |  | Post | NCB | No | 2015-04-01 | N.A | 2015-04-01 | 2015-05-01 | 2015-05-31 | N.A | 2015-06-07
Actual
4 | Planned | G4 | supply Furniture for Head Office and 20 districts (under component 2) (Cancelled) | Goods | Post | NCB | NO | 2011-10-01 | 2011-07-16 | 2011-07-30 | 2011-10-22 | 2011-11-22 | 2011-11-30 | 2011-12-15
| Revised 9-Nov 11 |  |  |  | Post | NCB | NO | 2011-10-01 | 2011-10-21 | 2011-10-24 | 2011-12-08 | 2012-01-07 | 2012-01-17 | 2012-01-20
| Revised Dec 2011 |  |  |  | Post | NCB | NO | 2012-07-01 | 2012-07-21 | 2012-07-27 | 2012-09-10 | 2012-10-10 | 2012-10-20 | 2012-10-23
| Revised Feb 2012 |  |  |  | Post | NCB | NO | 2013-03-03 | 2013-03-18 | 2013-04-01 | 2013-05-13 | 2013-06-12 | 2013-06-27 | 2013-07-04
| Revised June 2012 |  |  |  | Post | NCB | NO | 2013-11-20 | 2013-12-05 | 2013-12-19 | 2014-01-30 | 2014-03-01 | 2014-03-16 | 2014-03-23 |  |  |  |  | 2014-07-21
| Revised August 2012 |  |  |  | Post | NCB | NO | 2014-01-10 | 2014-01-25 | 2014-02-08 | 2014-03-22 | 2014-04-21 | 2014-05-06 | 2014-05-13 |  |  |  |  | 2014-09-10
| Revised Dec 2013 |  |  |  | Post | NCB | NO | 2014-12-13 | 2014-12-28 | 2015-01-11 | 2015-02-22 | 2015-03-24 | 2015-04-08 | 2015-04-15 |  |  |  |  | 2015-08-13
| Revised May 2014 |  |  |  | Post | NCB | NO | 2014-08-01 | 2014-08-16 | 2014-08-30 | 2014-10-11 | 2014-11-10 | 2014-11-25 | 2014-12-02 |  |  |  |  | 2015-04-01
| revised October 2014 |  |  |  | Post | NCB | NO | 2015-05-15 | 2015-05-30 | 2015-06-13 | 2015-07-25 | 2015-08-24 | 2015-09-08 | 2015-09-15
Actual
5 | Planned | G5 | supply Computers & peripherals for Head Office and 23 branches (under component 1 | Goods | Post | NCB | NO | 2011-10-01 | 2011-07-16 | 2011-07-30 | 2011-10-22 | 2011-11-22 | 2011-11-30 | 2011-12-15
| Revised 9-Nov 11 |  |  |  | Post | NCB | NO | 2011-10-01 | 2011-10-21 | 2011-10-24 | 2011-12-08 | 2012-01-07 | 2012-01-17 | 2012-01-20
| Revised Dec 2011 |  |  |  | Post | NCB | NO | 2012-07-01 | 2012-07-21 | 2012-07-27 | 2012-09-10 | 2012-10-10 | 2012-10-20 | 2012-10-23
| Revised Feb 2012 |  |  |  | Post | NCB | NO | 2013-03-03 | 2013-03-18 | 2013-04-01 | 2013-05-13 | 2013-06-12 | 2013-06-27 | 2013-07-04
| Revised June 2012 |  |  |  | Post | NCB | NO | 2013-11-20 | 2013-12-05 | 2013-12-19 | 2014-01-30 | 2014-03-01 | 2014-03-16 | 2014-03-23 |  |  |  |  | 2014-07-21
| Revised August 2012 |  |  |  | Post | NCB | NO | 2014-01-10 | 2014-01-25 | 2014-02-08 | 2014-03-22 | 2014-04-21 | 2014-05-06 | 2014-05-13 |  |  |  |  | 2014-09-10
| Revised Dec 2013 |  |  |  | Post | NCB | NO | 2014-12-13 | 2014-12-28 | 2015-01-11 | 2015-02-22 | 2015-03-24 | 2015-04-08 | 2015-04-15 |  |  |  |  | 2015-08-13
| Revised May 2014 |  |  |  | Post | NCB | NO | 2014-08-01 | 2014-08-16 | 2014-08-30 | 2014-10-11 | 2014-11-10 | 2014-11-25 | 2014-12-02 |  |  |  |  | 2015-04-01
| Revised October 2014 |  |  |  | Post | NCB | NO | 2015-01-01 | 2015-01-16 | 2015-01-30 | 2015-03-13 | 2015-04-12 | 2015-04-27 | 2015-05-04
Actual
6 | Planned | G6 | Suuply of Generators for power supply (under component 1.1) (Cancelled) | Goods | Post | NCB | NO | 2011-09-11 | N.A | 2011-09-30 | 2011-12-18 | 2012-01-11 | N.A | 2012-01-26
| Revised 9-Nov 11 |  |  |  | Post | NCB | NO | 2011-09-11 | 2011-10-01 | 2011-10-04 | 2011-11-18 | 2011-12-18 | 2012-01-02 | 2012-01-09
| Revised Dec 2011 |  |  |  | Post | NCB | NO | 2012-09-01 | 2012-09-21 | 2012-09-24 | 2012-11-08 | 2012-12-08 | 2012-12-23 | 2012-12-30
| Revised Feb 2012 |  |  |  | Prior | NCB | NO | 2013-04-02 | 2013-04-17 | 2013-05-01 | 2013-06-12 | 2013-07-12 | 2013-07-27 | 2013-08-03
| Revised June 2012 |  |  |  | Prior | NCB | NO | 2013-12-20 | 2014-01-04 | 2014-01-18 | 2014-03-01 | 2014-03-31 | 2014-04-15 | 2014-04-22 |  |  |  |  | 2014-08-20
| Revised August 2012 |  |  |  | Prior | NCB | NO | 2014-02-09 | 2014-02-24 | 2014-03-10 | 2014-04-21 | 2014-05-21 | 2014-06-05 | 2014-06-12 |  |  |  |  | 2014-10-10
| Revised Dec 2013 |  |  |  | Prior | NCB | NO | 2015-01-12 | 2015-01-27 | 2015-02-10 | 2015-03-24 | 2015-04-23 | 2015-05-08 | 2015-05-15 |  |  |  |  | 2015-09-12
| Revised May 2014 |  |  |  | Prior | NCB | NO | 2014-08-31 | 2014-09-15 | 2014-09-29 | 2014-11-10 | 2014-12-10 | 2014-12-25 | 2015-01-01 |  |  |  |  | 2015-05-01
Actual
7 | Planned | G7 | Solar System for H.Q. 23 governorates + 20 districts | Goods | Post | NCB | NO | 2015-04-15 | N/A | 2015-04-15 | 2015-05-15 | 2015-06-14 | N.A | 2015-06-21 |  |  |  |  | 2015-10-19
| Revised May 2014 |  |  |  | Post | NCB | NO | 2015-04-15 | N/A | 2015-04-15 | 2015-05-27 | 2015-06-26 | N.A | 2015-07-03 |  |  |  |  | 2015-10-31
| Revised October 2014 |  |  |  | Post | NCB | NO | 2014-11-30 | N/A | 2014-11-30 | 2015-01-11 | 2015-02-10 | N.A | 2015-02-17
Actual
Formulas:
Bid Invitation (Date) = [Preparation of Bid Document (Date)]
Bid Invitation (Date) = [Preparation of Bid Document (Date)]+14
Bid opening (Date) = [Bid Invitation (Date)]+45
Contract Award Decision (Date) = [Bid opening (Date)]+30
Contract Signed (Date) = [Contract Award Decision (Date)]+7
Preparation of Bid Document (Date) = [Preparation of Bid Document (Date), row above]
Completion of Contract (Date) = [Contract Signed (Date)]+30*4

## Shopping
Review date: October 2014
Sr No |  | Package/ Reference No. | Description of Goods | Goods/ NCS | Review by Bank (Prior/ Post) | Method of Selection | Domestic Preference (yes/no) | Preparation of Bid Document (Date) | Bid Invitation (Date) | Bid Opening (Date) | Contract Award Decision (Date) | Contract Signed (Date) | Contract Value | Contract Currency | Contract No. | Name, City, and Country of Supplier (incl. Zip Code if US) | Completion of Contract (Date) | Expenditure incurred to Date
3 | Planned | G1 | Generators for power supply (under component 1.1) | Goods | post | NS | No | - | 2011-11-15 | 2011-12-18 | 2012-01-11 | 2012-01-26
| Revised 9-Nov 11 |  |  |  | post | NS | No | 2011-11-10 | 2011-11-15 | 2011-12-15 | 2011-12-30 | 2012-01-04
| Revised Dec 2011 |  |  |  | post | NS | No | 2012-03-10 | 2012-03-13 | 2012-04-12 | 2012-04-27 | 2012-05-02
| Revised Feb 2012 |  |  |  | post | NS | No | 2013-04-09 | 2013-04-23 | 2013-05-23 | 2013-06-22 | 2013-06-29
| Revised June 2012 |  |  |  | post | NS | No | 2013-06-06 | 2013-06-20 | 2013-07-20 | 2013-08-19 | 2013-08-26 |  |  |  |  | 2013-12-24
| Revised August 2012 |  |  |  | post | NS | No | 2013-07-27 | 2013-08-10 | 2013-09-09 | 2013-10-09 | 2013-10-16 |  |  |  |  | 2014-02-13
| Revised Dec 2013 |  |  |  | post | NS | No | 2014-06-29 | 2014-07-13 | 2014-08-12 | 2014-09-11 | 2014-09-18 |  |  |  |  | 2015-01-16
| Revised May 2014 |  |  |  | post | NS | No | 2014-06-29 | 2014-07-13 | 2014-08-12 | 2014-09-11 | 2014-09-18 |  |  |  |  | 2015-01-16
Actual
8 | Planned | G4 | Furniture for the PST* (under component 1) | Goods | Prior | NS | NO | 2010-12-15 | 2010-12-25 | 2011-01-24 | 2011-02-13 | 2011-02-18 | 4980 | $ |  | AlHadha Hadfur | 2011-03-20 | $ 5000
| Revised 9-Nov 11 |  |  |  | Prior | NS | NO | 2010-12-15 | 2011-01-02 | 2011-02-01 | 2011-02-21 | 2011-02-26 |  |  |  |  | 2011-03-28
| Revised May 2014 |  |  |  |  | NS
| Actual |  |  |  |  | NS |  | 2011-01-03 | 2011-03-20 | 2011-04-06 | 2011-05-05 | 2011-07-10 |  |  |  |  | 9-Augs-11
9 | Planned | G5 | Computers and peripherals for the PST (under component 1)(Cancelled) | Goods | Post | NS | NO | 2010-12-15 | 2010-12-25 | 2011-01-24 | 2011-02-13 | 2011-02-18 |  |  |  |  | 2011-03-20
| Revised 9-Nov 11 |  |  |  | Post | NS | NO | 2010-12-15 | 2011-01-02 | 2011-02-01 | 2011-02-21 | 2011-02-26 |  |  |  |  | 2011-03-28
Revised May 2014
| Actual | [6 empty] | 2011-01-03 | 2011-03-20 | 2011-04-09 | 2011-06-26 | cancelled |  |  |  |  | cancelled
10 | Planned | G5 | Computers and peripherals for the PST (under component 1) (Cancelled) | Goods | Post | NS | NO | 2011-06-01 | 2011-06-06 | 2011-07-06 | 2011-07-26 | 2011-07-31 |  |  |  |  | 2011-08-30
| Actual |  |  |  | Post | NS | NO | 2011-06-01 | 2011-06-27 | 2011-07-13 |  | cancelled
11 | Planned | G5.2 | Computers and peripherals for the PST (under component 1)Cancelled | Goods | Post | NS | NO | 2012-06-09 | 2012-06-10 | 2012-07-01 | 2012-08-31 | 2012-09-05 |  |  |  |  | 2012-10-05
| Actual |  |  |  | Post | NS | NO | 2012-06-10 | N/A | 2102-06-22 |  |  |  | US$ | 334 | Natco Information Technology - San'a Yemen | Cancelled
12 | Planned | G5.3 | Computers and peripherals for the PST (under component 1) | Goods | Post | NS | NO | 30-Dec -2012 | 2013-01-05 | 2013-01-20 | 2013-02-20 | 2013-04-28 | 28909.74 |  |  |  | 2013-06-27
| Actual |  |  |  | Post | NS | NO | 2013-01-15 | 2013-01-19 | 2013-02-12 | 2013-04-21 | 2013-04-28
13 | Planned | G6 | Interpretation Services | Goods | Post | NS | NO | 2013-04-15 | 2013-04-22 | 2013-04-27 | 2013-05-02 | 2013-05-04 | 19387.75 | US$ | 339 | Mr. Akram Ali Al-Hindi, Sana'a - Yemen | 2013-07-03
| Revised |  |  |  | Post | NS | NO | 2013-04-15 | 2013-04-22 | 2013-04-27 | 2013-05-02 | 2013-05-04 |  |  |  |  | 2014-05-08
| Actual |  |  |  | Post | NS | NO | 2013-04-15 | 2013-04-22 | 2013-04-27 |  | 2013-05-08
14 | Planned | G7 | Office Furniture | Goods | Post | NS | No | 2013-12-18 | 2013-12-19 | 2013-12-24 | 2013-12-29 | 2013-12-31 | 3585.57 | US$ | 363 | MUJALLY Corp for Fur Sana,a Yemen | 29-12-2013
| Revised |  |  |  | Post | NS | No | 2013-12-18 | 2013-12-19 | 2013-12-24 | 2013-12-29 | 2013-12-31
| Actual |  |  |  | Post | NS | No | 2013-12-18 | 2013-12-19 | 2013-12-24 | 2014-12-25 | 26-12-2103 |  |  |  |  | 2014-01-12
15 | Planned | G8 | Glass separationfor Ayala Office | Goods | Post | NS | No | 2013-12-18 | 2013-12-19 | 2013-12-24 | 2013-12-29 | 2013-12-31 | 193242 | YR | 368 | AlMufty for Glass Sana'a Yemen | 2014-01-01
| Revised |  |  |  | Post | NS | No | 2013-12-18 | 2013-12-19 | 2013-12-24 | 2013-12-29 | 2013-12-31
| Actual |  |  |  | Post | NS |  | 2013-12-18 | 2013-12-19 | 2013-12-24 | 26-12-2013 | 2013-12-31 |  |  |  |  | 15-1-2014
16 | Planned | G9 | Air condition | Goods | Post | NS | NO | 2014-01-12 | 14-1-2014 | 20-1-2014 | 25-1-2014 | 27-1-2014 | 1339.78 | US$ | 27 | Modern Hous show sana'a Yemen | 26-1-2014
| Revised |  |  |  | Post | NS | NO | 2014-01-12 | 14-1-2014 | 20-1-2014 | 25-1-2014 | 27-1-2014
| Actual |  |  |  | Post | NS | NO | 2014-01-12 | 14-1-2014 | 20-1-2014 | 21-1-2014 | 23-1-2014 |  |  |  |  | 2014-02-10
17 | Planned | G10 | Glass separationfor PST Office | Goods | Post | NS | NO | 2014-01-13 | 14-1-2014 | 16-1-2014 | 20-1-2014 | 22-1-2014 | 262150 | YR | 26 | AlMufty for Glass Sana'a Yemen | 25-1-2014
| Revised |  |  |  | Post | NS | NO | 2014-01-13 | 14-1-2014 | 16-1-2014 | 20-1-2014 | 22-1-2014
| Actual |  |  |  | Post | NS | NO | 2014-01-13 | 14-1-2014 | 16-1-2014 | 21-1-2014 | 23-1-2014 |  |  |  |  | 2014-02-10
18 | Planned | G11 | Electrical Generating set | Goods | Post | NS | NO | 25-1-2014 | 25-1-2014 | 27-1-2014 | 2014-03-02 | 2014-02-05
| Revised |  |  |  | Post | NS | NO | 25-1-2014 | 25-1-2014 | 27-1-2014 | 2014-03-02 | 2014-02-05
| Actual |  |  |  | Post | NS | NO | 25-1-2014 | 27-1-2014 | 29-1-2014 | Cancelled
19 | Planned | G12 | Finger Print System with Accessories | Goods | Post | NS | NO | 2014-02-02 | 2014-02-03 | 13-2-2014 | 16-2-2014 | 18-2-2014 | 3860 | US$ | 64 | Smart Soft Yemen | 2014-03-09
| Revised |  |  |  | Post | NS | NO | 2014-02-02 | 2014-02-03 | 18-2-2014 | 20-2-2014 | 23-2-2014
| Actual |  |  |  | Post | NS | NO | 2014-02-03 | 2014-02-05 | 23-2-2014 | 2014-03-02 | 2014-03-06 |  |  |  |  | 2014-04-08
20 | Planned | G13 | Video Camara and LCD Projector | Goods | Post | NS | NO | 2014-02-02 | 2014-02-03 | 13-2-2014 | 16-2-2014 | 18-2-2014 | 2100 | US$ | 65 | Smart Soft Yemen | 2014-03-09
| Revised |  |  |  | Post | NS | NO | 2014-02-02 | 2014-02-03 | 13-2-2014 | 16-2-2014 | 18-2-2014
| Actual |  |  |  | Post | NS | NO | 2014-02-03 | 2014-02-05 | 19-2-2014 | 2014-03-02 | 2014-03-06 |  |  |  |  | 2014-03-25
21 | Planned | G14 | Purchase accounting sytem for ISP | Goods | Post | NS | NO | 2014-03-15 | 2014-03-17 | 2014-03-31 | 2014-04-20 | 2014-04-25
| Revised |  |  |  | Post | NS | NO | 2014-03-15 | 2014-03-17 | 2014-03-31 | 2014-12-10 | 2014-12-12
| Actual |  |  |  | Post | NS | NO | 2014-03-31 | 2014-04-20 | 2014-05-05
22 | Planned | G15 | Solar System for the Head Quarter and one governerate and one district (Cancelled) | Goods | Post | NS | NO | 2014-07-01 | 2014-07-01 | 2014-07-16 | 2014-07-31 | 2014-08-07 |  |  |  |  | 2014-10-06
| Revised |  |  |  | Post | NS | NO | 2014-09-15 | 2014-09-15 | 2014-09-30 | 2014-10-15 | 2014-10-22 |  |  |  |  | 2014-12-21
| Revised October 12 2014 |  |  |  | Post | NS | NO | 2014-11-01 | 2014-11-01 | 2014-11-16 | 2014-12-01 | 2014-12-08
Actual
23 | Planned | G16 | Communication Material for Component 1 (Batch 1) | Goods | Post | NS | NO | 2014-06-07 | 2014-06-07 | 2014-06-22 | 2014-07-07 | 2014-07-14 |  |  |  |  | 2014-07-29
| Revised |  |  |  | Post | NS | NO | 2014-09-15 | 2014-09-15 | 2014-09-30 | 2014-10-15 | 2014-10-22 |  |  |  |  | 2014-11-06
| Revised October 2014 | [9 empty] | 2014-11-15 | 2014-11-22
| Actual |  |  |  | Post | NS | NO | 2014-09-09 | 2014-09-16 | 2014-09-30
24 | Planned | G17 | Communication Material for Component 1 (Batch 2) | Goods | Post | NS | NO | 2015-04-01 | 2015-04-04 | 2015-04-19 | 2015-05-04 | 2015-05-09
| Revised |  |  |  | Post | NS | NO | 2015-04-01 | 2015-04-04 | 2015-04-19 | 2015-05-04 | 2015-05-09
Actual
25 | Planned | G18 | Communication Material for Component 1 (Batch 3) | Goods | Post | NS | NO | 2015-07-01 | 2015-07-04 | 2015-07-19 | 2015-08-03 | 2015-08-08
| Revised |  |  |  | Post | NS | NO | 2015-04-01 | 2015-04-04 | 2015-04-19 | 2015-05-04 | 2015-05-09
Actual
26 | Planned | G19 | Communication Material for Component 1 (Batch 4) | Goods | Post | NS | NO | 2015-11-01 | 2015-11-04 | 2015-11-19 | 2015-12-04 | 2015-12-09
| Revised |  |  |  | Post | NS | NO | 2015-11-01 | 2015-11-04 | 2015-11-19 | 2015-12-04 | 2015-12-09
Actual
26 | Planned | G20 | Communication Material for Component 2 | Goods | Post | NS | NO | 2015-03-04 | 2015-03-07 | 2015-03-22 | 2015-04-06 | 2015-04-11
| Revised |  |  |  | Post | NS | NO | 2015-03-04 | 2015-03-07 | 2015-03-22 | 2015-04-06 | 2015-04-11
Actual
Note: * Package G4, (Furniture for PST ( under component 1) was subject to prior review. The following prior reviews date applies to this package.
Bank’s No Objection to Bidding Document (Date): March 16, 2011
Bank’s No Objection to Bid Evaulation Report and Contract Award (Date): 30 June 2011
Formulas:
Bid Opening (Date) = [Bid Invitation (Date)]+30
Contract Award Decision (Date) = [Bid Opening (Date)]+15
Contract Signed (Date) = [Contract Award Decision (Date)]+5
Bid Invitation (Date) = [Preparation of Bid Document (Date)]+3
Bid Invitation (Date) = [Bid Invitation (Date), row above]
Preparation of Bid Document (Date) = [Preparation of Bid Document (Date), row above]
Completion of Contract (Date) = [Contract Signed (Date)]+30*4
Completion of Contract (Date) = [Contract Signed (Date)]+30

## Consultant services- Firms
Procurement Plan for Consultant Services
SWF Institutional Support Project
Review Date: October 2014
SL No. |  | Package/ Reference No. | Description of Services | Review by Bank (Prior/ Post) | Method of Selection | TOR to be Finalised (Date) | No Objection from Bank for TOR (Date)** | Advertising for Short listing (Date) | Shortlist to be Finalised (Date) | RFP Final Draft to be forwarded to the Bank (Date) | No Objection from Bank for Shortlist (Date)** | No Objection from Bank for Final RFP (Date)** | RFP Issued (Date) | Proposal Submission Deadline (Date) | No Objection by the Bank to the Technical Evaluation Report (Date)** | No Objection by the Bank (Technical/ #Combined/ Draft Contract/ Final Contract) (Date)** | Contract Signed (Date) | Contract Value | Contract Currency | Contract No. | Name, City, and Country of Contractor (incl. Zip Code if US) | Services Completion (Date) | Expenses Incurred to Date
1 | Planned | C1 | Long-term Advisor to strengthen targeting, Mgt and Admin Process | PRIOR | QCBS | 2010-09-10 | 2010-09-24 | 2010-07-28 |  | 2010-09-10 | 2010-09-24 | 2010-11-07 | 2010-11-14 | 2011-01-13 | 2011-02-17 |  | 2011-04-21 | 2134836 | US$ | 4 | Ayala Consulting Group - Quito -Ecuador | 2016-05-19
| Revised |  |  | PRIOR | QCBS | 2010-12-15 | 2010-12-30 | 2010-11-15 | 2010-12-15 | 2010-12-20 | 2010-12-30 | 2010-12-30 | 2011-01-04 | 2011-02-18 | 2011-03-20 | 2011-04-09 | 2011-05-09 |  |  |  |  | 2016-04-13
| Revised 9-Nov 10 |  |  | PRIOR | QCBS | 2010-11-25 | 2010-11-30 | 2010-12-05 | 2011-01-04 | 2011-01-06 | 2011-01-11 | 2011-01-11 | 2011-01-14 | 2011-02-28 | 2011-03-30 | 2011-04-19 | 2011-04-29 |  |  |  |  | 2016-04-13
| Revised Dec 2011 |  |  | PRIOR | QCBS | 2010-11-25 | 2010-11-30 | 2010-12-05 | 2011-01-04 | 2011-01-06 | 2012-01-01 | 2012-01-01 | 2012-01-04 | 2012-02-18 | 2012-03-19 | 2012-04-08 | 2012-04-18 |  |  |  |  | 2016-12-01
| Revised Feb 2012 |  |  | PRIOR | QCBS | 2012-02-07 | 2012-04-18 | 2012-02-27 | 2012-04-18 | 2012-04-18 | 2012-05-03 | 2012-05-03 | 2012-05-10 | 2012-06-21 | 2012-07-21 | 2012-09-01 | 2012-09-11 |  |  |  |  | 2015-09-11
| Revised June 2012 |  |  | PRIOR | QCBS | 2012-02-07 | 2012-06-30 | 2012-02-27 | 2012-06-03 | 2012-06-03 | 2012-06-30 | 2012-06-30 | 2012-07-07 | 2012-08-18 | 2012-09-17 | 2012-10-29 | 2012-11-08 |  |  |  |  | 2015-11-08
| Revised August 2012 |  |  | PRIOR | QCBS | [5 empty] | 2012-08-20 | 2012-08-20 | 2012-08-27 | 2012-10-08 | 2012-11-07 | 2012-12-19 | 2012-12-29
| Revised April 2013 | [6 empty] | 2012-02-27 | 2012-06-03 | 2012-06-03 | [5 empty] | 2013-06-15 | 2013-06-25 |  |  |  |  | 2016-12-01
| Actual |  |  | PRIOR | QCBS | 2012-02-07 |  | 2012-02-27 | 2012-06-03 | 2012-06-03 | 2012-08-14 | 2012-08-14 | 2012-11-07 | 2013-01-06 | 2013-02-27 | 2013-11-16 | 2013-12-01
2 | Planned | C3 | Consultant for Communications Strategy | PRIOR | QCBS | 2011-05-12 | 2011-05-19 | 2011-04-21 |  | 2011-05-19 | 2011-05-19 | 2011-06-23 | 2011-06-30 | 2011-08-30 | 2011-10-31 | 2011-11-30 | 2011-12-30 |  |  |  |  | 2012-10-23
| Revised |  |  | PRIOR | QCBS | 2011-05-21 | 2011-06-05 | 2011-04-21 |  | 2011-05-26 | 2011-06-05 | 2011-06-05 | 2011-06-10 | 2011-07-25 | 2011-08-24 | 2011-09-13 | 2011-10-13 |  |  |  |  | 2012-09-07
| Revised 9-Nov 10 |  |  | PRIOR | QCBS | 2011-05-21 | 2011-05-26 | 2011-05-31 | 2011-06-30 | 2011-07-02 | 2011-07-07 | 2011-07-07 | 2011-07-10 | 2011-08-24 | 2011-09-23 | 2011-10-13 | 2011-10-23 |  |  |  |  | 2012-09-07
| Revised Dec 2011 |  |  | PRIOR | QCBS | 2012-06-20 | 2012-06-25 | 2012-06-30 | 2012-07-30 | 2012-08-01 | 2012-08-06 | 2012-08-06 | 2012-08-09 | 2012-09-23 | 2012-10-23 | 2012-11-12 | 2012-11-22 |  |  |  |  | 2013-02-23
| Revised Feb 2012 |  |  | PRIOR | QCBS | 2013-06-15 | 2013-06-30 | 2013-07-07 | 2013-08-06 | 2013-08-06 | 2013-08-21 | 2013-08-21 | 2013-08-28 | 2013-10-09 | 2013-11-08 | 2013-12-20 | 2013-12-30 |  |  |  |  | 2014-10-26
| Revised June 2012 |  |  | PRIOR | QCBS | 2013-08-12 | 2013-08-27 | 2013-09-03 | 2013-10-03 | 2013-10-03 | 2013-10-18 | 2013-10-18 | 2013-10-25 | 2013-12-06 | 2014-01-05 | 2014-02-16 | 2014-02-26 |  |  |  |  | 2014-12-23
| Revised August 2012 |  |  | PRIOR | QCBS | 2013-10-02 | 2013-10-17 | 2013-10-24 | 2013-11-23 | 2013-11-23 | 2013-12-08 | 2013-12-08 | 2013-12-15 | 2014-01-26 | 2014-02-25 | 2014-04-08 | 2014-04-18 |  |  |  |  | 2015-02-12
| Revised Dec 2013 |  |  | PRIOR | QCBS | 2014-03-29 | 2014-04-13 | 2014-04-20 | 2014-05-20 | 2014-05-20 | 2014-06-04 | 2014-06-04 | 2014-06-11 | 2014-07-23 | 2014-08-22 | 2014-10-03 | 2014-10-13
| Revised May 2014 |  |  | PRIOR | QCBS | 2014-12-03 | 2014-12-18 | 2014-12-25 | 2015-01-24 | 2015-01-24 | 2015-02-08 | 2015-02-08 | 2015-02-15 | 2015-03-29 | 2015-04-28 | 2015-06-09 | 2015-06-19
| Actual |  | Cancelled
3 | Planned | C4 | Media service to develop and air the communications strategy | PRIOR | CQS | 2012-05-12 | 2012-05-20 | 2012-04-21 |  | 2012-05-15 | 2012-05-20 | 2012-05-31 | 2012-06-05 | 2012-06-30 | NA | 2012-07-07 | 2012-07-15 |  |  |  |  | 2014-03-11
| Revised |  |  | PRIOR | CQS | 2012-05-12 | 2012-05-22 | 2012-04-21 |  | 2012-05-17 | 2012-05-22 | 2012-05-22 | 2012-05-27 | 2012-06-26 | NA | 2012-07-31 | 2012-08-30 |  |  |  |  | 2014-03-31
| Revised 9-Nov 10 |  |  | PRIOR | CQS | 2012-05-12 | 2012-05-17 | 2012-05-22 | 2012-06-21 | 2012-06-23 | 2012-06-28 | 2012-06-28 | 2012-07-01 | 2012-08-15 | 2012-09-14 | 2012-09-14 | 2012-09-24 |  |  |  |  | 2014-04-30
| Revised Dec 2011 |  |  | PRIOR | CQS | 2013-01-01 | 2013-01-06 | 2013-01-11 | 2013-02-10 | 2013-02-12 | 2013-02-17 | 2013-02-17 | 2013-02-20 | 2013-04-06 | 2013-05-06 | 2013-05-06 | 2013-05-16 |  |  |  |  | 2014-05-30
| Revised Feb 2012 |  |  | PRIOR | CQS | 2014-06-28 | 2014-07-13 | 2014-07-20 | 2014-08-19 | 2014-08-19 | 2014-09-03 | 2014-09-03 | 2014-09-10 | 2014-10-22 | 2014-11-21 | 2015-01-02 | 2015-01-12 |  |  |  |  | 2016-09-03
| Revised June 2012 |  |  | PRIOR | CQS | 2014-08-25 | 2014-09-09 | 2014-09-16 | 2014-10-16 | 2014-10-16 | 2014-10-31 | 2014-10-31 | 2014-11-07 | 2014-12-19 | 2015-01-18 | 2015-03-01 | 2015-03-11 |  |  |  |  | 2016-10-31
| Revised August 2012 |  |  | PRIOR | CQS | 2014-10-15 | 2014-10-30 | 2014-11-06 | 2014-12-06 | 2014-12-06 | 2014-12-21 | 2014-12-21 | 2014-12-28 | 2015-02-08 | 2015-03-10 | 2015-04-21 | 2015-05-01 |  |  |  |  | 2016-12-21
| Revised Dec 2013 |  |  | PRIOR | CQS | 2015-04-11 | 2015-04-26 | 2015-05-03 | 2015-06-02 | 2015-06-02 | 2015-06-17 | 2015-06-17 | 2015-06-24 | 2015-08-05 | 2015-09-04 | 2015-10-16 | 2015-10-26 |  |  |  |  | 2017-03-31
| Revised May 2014 |  |  | PRIOR | CQS | 2015-02-01 | 2015-02-16 | 2015-02-23 | 2015-03-25 | 2015-03-25 | 2015-04-09 | 2015-04-09 | 2015-04-16 | 2015-05-28 | 2015-06-27 | 2015-08-08 | 2015-08-18
| Revised Oct 2014 |  |  | PRIOR | CQS | 2015-02-01 | 2015-02-16 | 2015-02-23 | 2015-03-25 | N/A | N/A | N/A | 2015-03-30 | 2015-04-29 | N/A | N/A | 2015-05-29
Actual
4 | Planned | C7 | Beneficiary assessment /Impact evaluation | PRIOR | QCBS | 2011-02-05 | 2011-01-01 | 2011-01-08 |  | 2011-02-05 | 2011-02-19 | 2011-03-31 | 2011-04-12 | 2011-06-14 | 2011-07-11 | 2011-08-11 | 2011-08-20 |  |  |  |  | 2016-07-02
| Revised |  |  | PRIOR | QCBS | 2011-04-29 | 2011-05-09 | 2011-03-15 | 2011-04-29 | 2011-05-04 | 2011-04-29 | 2011-04-29 | 2011-05-04 | 2011-06-18 | 2011-07-18 | 2011-08-07 | 2011-09-06 |  |  |  |  | 2016-04-02
| Revised 9-Nov 10 |  |  | PRIOR | QCBS | 2011-04-29 | 2011-05-04 | 2011-05-09 | 2011-06-08 | N/A | 2011-06-13 | N/A | N/A | N/A | 2011-06-28 | 2011-07-08 | 2011-07-18 |  |  |  |  | 2016-02-17
| Revised Dec 2011 |  |  | PRIOR | QCBS | 2012-08-25 | 2012-08-30 | 2012-09-04 | 2012-10-04 | N/A | 2012-10-09 | N/A | N/A | N/A | 2012-10-24 | 2012-11-03 | 2012-11-13 |  |  |  |  | 2016-08-30
| Revised Feb 2012 |  |  | PRIOR | QCBS | 2012-12-03 | 2012-12-18 | 2012-12-25 | 2013-01-24 | 2013-01-24 | 2013-02-08 | 2013-02-08 | 2013-02-15 | 2013-03-29 | 2013-04-28 | 2013-06-09 | 2013-06-19 |  |  |  |  | 31/3/2017
| Revised June 2012 |  |  | PRIOR | QCBS | 2013-08-22 | 2013-09-06 | 2013-09-13 | 2013-10-13 | 2013-10-13 | 2013-10-28 | 2013-10-28 | 2013-11-04 | 2013-12-16 | 2014-01-15 | 2014-02-26 | 2014-03-08 |  |  |  |  | 31/3/2017
| Revised August 2012 |  |  | PRIOR | QCBS | 2013-10-12 | 2013-10-27 | 2013-11-03 | 2013-12-03 | 2013-12-03 | 2013-12-18 | 2013-12-18 | 2013-12-25 | 2014-02-05 | 2014-03-07 | 2014-04-18 | 2014-04-28 |  |  |  |  | 31/3/2017
| Revised Dec 2013 |  |  | PRIOR | QCBS | 2014-09-14 | 2014-09-29 | 2014-10-06 | 2014-11-05 | 2014-11-05 | 2014-11-20 | 2014-11-20 | 2014-11-27 | 2015-01-08 | 2015-02-07 | 2015-03-21 | 2015-03-31 |  |  |  |  | 31/3/2017
| Revised May 2014 |  |  | PRIOR | QCBS | 2015-07-01 | 2015-07-16 | 2015-07-23 | 2015-08-22 | 2015-08-22 | 2015-09-06 | 2015-09-06 | 2015-09-13 | 2015-10-25 | 2015-11-24 | 2016-01-05 | 2016-01-15
| Revised Oct 12 2014 |  |  | Post | CQS | 2015-03-31 | 2015-04-15 | 2015-04-22 | 2015-05-22 | N/A | N/A | N/A | 2015-05-27 | 2015-06-26 | N/A | N/A | 2015-07-26
Actual
5 | Planned | C16 | Auditor | Post | COCA | 1-May -11 | 1-June -11 | N.A | N.A | N.A | N.A | N.A | N.A | N.A | N.A | N.A | 2011-07-30 | 9000 | $ | 2 | Grant Thronton | 2017-12-30
| Revised June 2012 | [6 empty] | N.A | N.A | N.A | N.A | N.A | N.A | N.A | N.A | 2012-03-28 | 2012-05-02 |  |  |  |  | 2014-06-30
| Actual |  |  |  |  | 2011-06-25 | 2011-07-19 | N.A | N.A | N.A | N.A | N.A | N.A | N.A | N.A | 2012-03-28 | 2012-05-02
6 | Planned | C18 | English Training Course | PRIOR | CQS | 2012-05-12 | 2012-05-20 | 2012-06-25 | 2012-07-25 | N/A | N/A | N/A | 2012-07-31 | 2012-08-21 | NA | N/A | 2012-09-20 | 11280 | $ | 3 | YALI Institute | 2013-05-18
| Revised |  |  | PRIOR | CQS | 2012-05-12 | 2012-05-20 | 2012-06-27 | 2012-08-16 | N/A | N/A | N/A | 2012-08-22 | 2012-09-12 | NA | N/A | 2012-10-12 |  |  |  |  | 2013-08-26
| Actual |  |  |  |  | 2012-05-02 | 2012-05-08 | N/A | N/A | N/A | N/A | N/A | 2012-09-24 | 2012-10-06 | N/A | N/A | 2012-11-26
7 | Planned | C19 | Component Evaluation for ESSN | PRIOR | SSS | 2012-05-03 | 2012-05-03 | N/A | N/A | N/A | N/A | N/A | 2012-05-15 | 2012-05-23 | NA | 2012-06-16 | 2012-06-22 | 52000 | € | 1378 | EMCC | 2013-02-17
| Revised |  |  | PRIOR | SSS | 2012-05-03 | 2012-05-03 | N/A | N/A | N/A | N/A | N/A | 2012-05-15 | 2012-05-28 | NA | 2012-06-15 | 2012-06-22 |  |  |  |  | 2013-02-17
| Actual |  |  | PRIOR | SSS | 2012-05-03 | 2012-05-03 | N/A | N/A | N/A | N/A | N/A | 2012-05-15 | 2012-05-28 | N/A | 2012-07-13 | 2012-07-15 |  |  |  |  | 2013-03-12
8 | Planned | C20 | Accounting firm for SWF Financial Depratment (cancelled) | Post | CQS | 2014-02-23 | 2014-02-24 | N/A | 2014-05-30 | 2014-06-04 | 2014-06-09 | 2014-06-09 | 2014-06-12 | 2014-07-03 | N/A | 2014-07-23 | 2014-07-28 | Cancelled
| Revised May 2014 |  |  | Post | CQS | 2014-02-23 | 2014-02-24 | N/A | 2014-05-30 | N/A | N/A | N/A | 2014-11-01 | 2014-11-21 | N/A | 2014-12-11 | 2014-12-16
| Actual |  |  | Post | CQS | 2014-02-23 | 2014-02-25 | N/A | 2014-03-04 | 2011-02-05: N/A; 2011-02-19: N/A; 2011-03-31: N/A
9 | Planned | C34 | Accounting firm for SWF Financial Depratment | Post | COCA | 2014-02-23 | 2014-02-25 |  |  | 2011-08-11: 2014-11-21; 2011-08-20: 2014-12-01
| Revised Oct 2014 |  |  | Post | COCA | 2014-02-23 | 2014-02-25 |  |  | 2011-08-11: 2014-11-21; 2011-08-20: 2014-12-01
Actual
10 | Planned | C2 | Beneficiary satisfaction assessment for the ECRP | Post | CQS | 2014-06-08 | 2014-06-13 | 2014-06-15 | 2014-06-30 | N/A | N/A | N/A | 2014-07-05 | 2014-08-04 | N/A | N/A | 2014-09-03 |  |  |  |  | 2015-01-01
| Revised May 2014 |  |  | Post | CQS | 2014-06-08 | 2014-06-23 | 2014-06-30 | 2014-07-30 | N/A | N/A | N/A | 2014-08-04 | 2014-09-03 | N/A | N/A | 2014-10-03 |  |  |  |  | 2015-01-31
| Revised Oct 2014 |  |  | Post | [5 empty] | 2011-07-11: N/A; 2011-08-11: N/A; 2011-08-20: 2014-11-01
| Actual |  |  | Post | CQS | 2014-03-17 | 2014-03-22 | N/A | 2014-06-03 | N/A | 2014-06-17 | N/A | 2014-06-29 | 2014-09-10
11 | Actual | C33 | Auditor for 2014 | Post | COCA | 2014-05-18 | 2014-05-20 | N.A | N.A | N.A | N.A | N.A | N.A | N.A | N.A |  |  |  |  | C33
12 | Planned | C30 | assessment for the post office services | Prior | CQS | 2014-07-31 | 2014-08-05 | 2014-08-07 | 2014-08-22 | 2014-08-27 | 2014-09-01 | 2014-09-01 | 2014-09-04 | 2014-09-25 | 2014-10-10 | 2014-10-25 | 2014-10-30 |  |  |  |  | 2015-02-27
| Revised Oct 2014 |  |  | Prior | CQS |  |  | 2014-11-05 | 2014-11-20 | 2014-11-25 | 2014-11-30 | 2014-11-30 | 2014-12-03 | 2014-12-24 | 2015-01-08 | 2015-01-23 | 2015-01-28 |  |  |  |  | 2015-05-28
| Actual |  |  | Post | CQS | 2014-08-22 | 2014-09-30
13 | Planned | C35 | process evaluation for Cash transfer | Prior | CQS | 2015-01-15 | 2015-01-30 | 2015-02-06 | 2015-03-08 | N/A | N/A | N/A | 2015-03-13 | 2015-04-12 | N/A | N/A | 2015-05-12
| Revised Oct 2014 |  |  | Post | CQS | 2015-01-15 | 2015-01-30 | 2015-02-06 | 2015-03-08 | N/A | N/A | N/A | 2015-03-13 | 2015-04-12 | N/A | N/A | 2015-05-12
Actual
14 | Planned | C36 | Consultancy services for Software and tablets for enrollment and case management | Post | CQS | 2015-03-31 | 2015-04-15 | 2015-04-22 | 2015-05-22 | N/A | N/A | N/A | 2015-05-27 | 2015-06-26 | N/A | N/A | 2015-07-26
| Revised Oct 2014 |  |  | Post | CQS | 2015-03-31 | 2015-04-15 | 2015-04-22 | 2015-05-22 | N/A | N/A | N/A | 2015-05-27 | 2015-06-26 | N/A | N/A | 2015-07-26
Actual
15 | Planned | C37 | NGO for Component 2 for the implementation of Pilot - Youth Employability | Prior | CQS | 2014-12-20 | 2015-01-04 | 2015-01-11 | 2015-02-10 | N/A | N/A | N/A | 2015-02-15 | 2015-03-17 | N/A | N/A | 2015-04-16
| Revised Oct 2014 |  |  | Prior | CQS | 2014-12-20 | 2015-01-04 | 2015-01-11 | 2015-02-10 | N/A | N/A | N/A | 2015-02-15 | 2015-03-17 | N/A | N/A | 2015-04-16
Actual
16 | Planned | C38 | NGO for Component 2 for the implementation of Pilot - Learning for Life | Prior | CQS | 2014-12-20 | 2015-01-04 | 2015-01-11 | 2015-02-10 | N/A | N/A | N/A | 2015-02-15 | 2015-03-17 | N/A | N/A | 2015-04-16
| Revised Oct 2014 |  |  | Prior | CQS | 2014-12-20 | 2015-01-04 | 2015-01-11 | 2015-02-10 | N/A | N/A | N/A | 2015-02-15 | 2015-03-17 | N/A | N/A | 2015-04-16
Actual
17 | Planned | C39 | NGO for Component 2 for the implementation of Pilot - Livellihood improvement | Prior | CQS | 2014-12-20 | 2015-01-04 | 2015-01-11 | 2015-02-10 | N/A | N/A | N/A | 2015-02-15 | 2015-03-17 | N/A | N/A | 2015-04-16
| Revised Oct 2014 |  |  | Prior | CQS | 2014-12-20 | 2015-01-04 | 2015-01-11 | 2015-02-10 | N/A | N/A | N/A | 2015-02-15 | 2015-03-17 | N/A | N/A | 2015-04-16
Actual
18 | Planned | C42 | Support for the Internal Control Department - SWF | Post | CQS | 2014-12-01 | 2014-12-16 | 2014-12-23 | 2015-01-22 | N/A | N/A | N/A | 2015-01-27 | 2015-02-26 | N/A | N/A | 2015-03-28
| Revised Oct 2014 |  |  | Post | CQS | 2014-12-01 | 2014-12-16 | 2014-12-23 | 2015-01-22 | N/A | N/A | N/A | 2015-01-27 | 2015-02-26 | N/A | N/A | 2015-03-28
Actual
Formulas:
TOR to be Finalised (Date) = [Shortlist to be Finalised (Date)]
TOR to be Finalised (Date) = [Advertising for Short listing (Date)]+30
No Objection from Bank for TOR (Date)** = [TOR to be Finalised (Date)]+5
No Objection from Bank for TOR (Date)** = [Shortlist to be Finalised (Date)]
Advertising for Short listing (Date) = [No Objection from Bank for TOR (Date)**]+5
Shortlist to be Finalised (Date) = [Advertising for Short listing (Date)]+30
Shortlist to be Finalised (Date) = [Advertising for Short listing (Date)]+36+15
Proposal Submission Deadline (Date) = [RFP Issued (Date)]+45
Services Completion (Date) = [Services Completion (Date), row above]
Services Completion (Date) = [Contract Signed (Date)]+365*3

## Consultant services- Individual
Procurement Plan for Consultant Services
SWF Institutional Support Project
Review Date: October 2014
SL No. |  | Package/ Reference No. | Description of Services | Review by Bank (Prior/ Post) | Method of Selection | TOR to be Finalised (Date) | No Objection from Bank for TOR (Date)** | Advertising for Short listing (Date) | Shortlist to be Finalised (Date) | No Objection from Bank for Shortlist (Date)** | No Objection by the Bank to the final Evaluation Report (Date)** | No Objection by the Bank (Technical/ #Combined/ Draft Contract/ Final Contract) (Date)** | Contract Signed (Date) | Contract Value | Contract Currency | Contract No. | Name, City, and Country of Contractor (incl. Zip Code if US) | Services Completion (Date) | Expenses Incurred to Date
1 | Planned | C2 | Consultant for targeting policy options | PRIOR | IC | 2011-04-26 | 2011-05-03 | 2011-03-29 |  | NA | NA | 2011-06-13 | 2011-06-16 |  |  |  |  | 2011-09-04
| Revised |  |  | PRIOR | IC | 2011-04-26 | 2011-05-06 | 2010-03-29 | 2011-04-26 | 2011-05-18 | 2011-05-18 | 2011-05-28 | 2011-06-27 |  |  |  |  | 2011-08-15
| Revised 9-Nov 10 |  |  | PRIOR | IC | 2011-04-26 | 2011-05-01 | 2011-05-06 | 2011-06-05 | 2011-06-10 | 2011-06-25 | 2011-07-05 | 2011-07-15 |  |  |  |  | 2011-08-15
| Revised Dec 2011 |  |  |  |  | 2013-01-09 | 2013-01-14 | 2013-01-21 | 2013-02-20 | 2013-03-07 | 2013-03-22 | 2013-04-06 | 2013-04-16 |  |  |  |  | 2013-08-14
| Revised June 2012 |  |  |  |  | 2013-03-08 | 2013-03-13 | 2013-03-20 | 2013-04-19 | 2013-05-04 | 2013-05-19 | 2013-06-03 | 2013-06-13 |  |  |  |  | 2013-10-11
| Revised August 2012 |  |  |  |  | 2013-04-28 | 2013-05-03 | 2013-05-10 | 2013-06-09 | 2013-06-24 | 2013-07-09 | 2013-07-24 | 2013-08-03 |  |  |  |  | 2013-12-01
| Revfised Dec2013 |  |  |  |  | 2013-10-23 | 2013-10-28 | 2013-11-04 | 2013-12-04 | 2013-12-19 | 2014-01-03 | 2014-01-18 | 2014-01-28 |  |  |  |  | 2014-05-28
| Revised May 2014 |  |  |  |  | 2014-06-29 | 2014-07-04 | 2014-07-11 | 2014-08-10 | 2014-08-25 | 2014-09-09 | 2014-09-24 | 2014-10-04
| Actual |  | Cancelled
2 | Planned | C5 | Consultant to prepare TORs & support selection of consultants | PRIOR | IC | 2010-05-15 | 2010-05-31 | 2010-05-07 |  | NA | NA | NA | 2010-06-15 |  |  |  |  | 2010-10-01
| Revised |  |  | PRIOR | IC | 2014-08-25: 2010-10-25; 2014-09-09: 2010-10-25; 2014-09-24: 2010-11-04; 2014-10-04: 2010-12-04 |  |  |  |  | 2010-12-31
| Actual |  | Cancelled | PRIOR | IC | 2014-06-29: 2010-05-25; 2014-07-04: 2010-05-27; 2014-07-11: 2010-05-20
3 | Planned | C6 | Long-term Advisor for Comp 2 Design & Imp | PRIOR | QCBS | 2010-10-13 | 2010-10-20 | 2010-09-22 |  | 2010-10-20 | 2011-02-02 | 2011-03-02 | 2011-04-03 | 117021.5 | $ |  | Ms. Houda Baladi | 2015-12-07
| Revised |  |  | PRIOR | QCBS | 2011-02-21 | 2011-03-08 | 2011-01-22 |  | 2011-03-08 | 2011-05-27 | 2011-06-16 | 2011-07-16 |  |  |  |  | 2015-12-31
| Revised 9-Nov 10 |  |  | PRIOR | IC | 2010-11-20 | 2010-11-25 | 2010-11-30 | 2010-12-30 | 2011-01-04 | 2011-01-19 | 2011-01-29 | 2011-02-08 |  |  |  |  | 2015-12-31
| Revised Dec 2011 |  |  | PRIOR | IC | 2012-03-20 | 2012-03-25 | 2012-03-30 | 2012-04-29 | 2012-05-04 | 2012-05-19 | 2012-05-29 | 2012-06-08 |  |  |  |  | 30 -Feb16
| Revised Feb 2012 |  |  | PRIOR | IC | 2012-05-20 | 2012-06-04 | 2012-06-11 | 2012-07-11 | 2012-07-26 | 2012-08-10 | 2012-08-25 | 2012-09-04 |  |  |  |  | 2017-03-02
| Revised June 2012 |  |  | PRIOR | IC | 2013-02-06 | 2013-02-21 | 2013-02-28 | 2013-03-30 | 2013-04-14 | 2013-04-29 | 2013-05-14 | 2013-05-24 |  |  |  |  | 2017-11-19
| Revised August 2012 |  |  | PRIOR | IC | 2013-03-29 | 2013-04-13 | 2013-04-20 | 2013-05-20 | 2013-06-04 | 2013-06-19 | 2013-07-04 | 2013-07-14 |  |  |  |  | 2018-01-09
| Revfised April 2013 |  |  | PRIOR | IC | 2013-09-23 | 2013-10-08 | 2013-10-15 | 2013-11-14 | 2013-11-29 | 2013-12-14 | 2013-12-29 | 2014-01-08 |  |  |  |  | 2018-07-06
| Revised Dec 21, 2013 |  |  | PRIOR | IC | 2014-03-01 | 2014-03-16 | 2014-03-23 | 2014-04-22 | 2014-05-07 | 2014-05-22 | 2014-06-06 | 2014-06-16 |  |  |  |  | 2015-04-06
| Actual |  |  | PRIOR | IC | 2013-06-05 | 2013-07-25 | 2013-08-28 | 2014-01-21 | 2014-01-30 | 2014-03-18 | 2014-04-03 | 2014-04-07
4 | Planned | C14 | MIS Data Specialist | PRIOR | SS | 2010-12-31 | 2011-01-05 | 2011-01-10 | 2011-02-09 | 2011-02-14 | 2011-03-01 | 2011-03-11 | 2011-03-21 | 5000 | $ | MISD-05 ISP | Khaled Mokred Sana'a Yemen | 2016-12-31
| Revised 21 Dec 10 |  |  | PRIOR | SS | 2010-12-31 | 2011-01-05 | N/A | N/A | 2010-12-31 | 2011-01-15 | 2011-01-25 | 2011-02-04 |  |  |  |  | 2012-02-07
| Actual |  |  |  | SS | 2010-12-13 | 2010-12-16 | N/A | N/A | 07-Feb-11 | N/A | 22-Feb-11 | 2011-03-08 |  |  |  |  | 2012-02-07
5 | Planned | C14.1 | MIS Data Specialist - 2 | PRIOR | SS | 2010-12-13 | 2010-12-18 | N/A | N/A | 2012-06-20 | 2012-07-05 | 2012-07-15 | 2012-07-25 | 5000 | $ | MISD-08 ISP | Khaled Mokred Sana'a Yemen | 2016-12-31
| Revfised April 2013 |  |  | PRIOR | SS | 2010-12-13 | 2010-12-18 | N/A | N/A | 2012-06-20 | 2012-07-05 | 2012-07-15 | 2012-07-25 |  |  |  |  | 2013-06-30
| Actual |  |  |  | SS | 2010-12-13 | 2010-12-16 | N/A | N/A | N/A | N/A | 2012-07-20 | 2012-07-27 |  |  |  |  | 2013-06-30
6 | Planned | C17 |  | PRIOR | IC | 2012-03-06 | 2012-03-21 | N/A | 2012-03-31 | 2012-04-15 | 2012-05-15 | 2012-06-14 | 2012-06-19 | 2000 | $ | ISP-006 | Mohammed Ali Mahyoub | 2012-06-29
| Revised Mar 2012 |  | Evaluation expert for C1-LTA | PRIOR | IC | 2012-03-06 | 2012-03-21 | N/A | 2012-03-31 | 2012-04-15 | 2012-05-15 | 2012-06-14 | 2012-06-19 |  |  |  |  | 2012-06-29
| Actual |  |  |  | IC | 2012-03-06 | 2012-04-24 | N/A | 2012-04-29 | 2012-05-08 | 2012-05-08 | 2012-05-10 | 2012-05-12 |  |  |  |  | 2012-05-31
7 | Planned | C20 | Imternational Evaluation Consltant for C1-LTA | PRIOR | SS | 2012-12-01 | 2012-12-05 | N/A | N/A | 2012-12-20 | 2012-12-25 | 2012-12-30 | 2013-01-05 | 2978.2 | $ | ISP-009 | Roger Pearson | 2013-01-31
|  |  |  | PRIOR | SS | 2012-12-01 | 2012-12-05 | N/A | N/A | 2012-12-20 | 2012-12-25 | 2012-12-30 | 2013-01-05 |  |  |  |  | 2013-03-15
| Actual |  |  | PRIOR | SS | 2012-12-15 | 2012-12-20 | N/A | N/A | N/A | N/A | 2013-01-15 | 2013-02-04 |  |  |  |  | 2013-03-15
8 | Planned | C25 | Consultant for the development of the website | Post | IC | 2014-06-07 | 2014-06-12 | N/A | N/A | N/A | N/A | 2014-07-03 | 2014-07-05 |  |  |  |  | 2014-09-13
| Revised |  |  | Post | IC | 2014-06-07 | 2014-06-12 | N/A | 2014-09-15 | N/A | N/A | N/A | 2014-09-30 |  |  |  |  | 2014-12-09
| Revised Oct 2014 |  |  | Post | IC |  |  |  | 2014-11-05 | N/A | N/A | N/A | 2014-11-20
| Actual |  |  | Post | IC | 2014-06-29: 2014-08-29; 2014-07-04: N/A; 2014-07-11: N/A
9 | Planned | C26 | Program assistant for C2 | Post | IC | 2014-06-07 | 2014-06-12 | N/A | N/A | N/A | N/A | 2014-07-12 | 2014-07-14 | 5400 | $ | C26 | Ms. Hnana AL Zubaidi, Sana'a-Yemen | 2015-01-10
| Revised |  |  | Post | IC | 2014-06-07 | 2014-06-12 | N/A | N/A | N/A | N/A | 2014-07-12 | 2014-07-14 |  |  |  |  | 2015-01-12
| Actual |  |  | Post | IC | 2014-07-03 | N/A | N/A | N/A | N/A | N/A | N/A | 2014-07-13
10 | Planned | C27 | Consultant for C2 in Mukallah | PRIOR | SS | 2014-06-07 | 2014-06-12 | N/A | N/A | N/A | N/A | 2014-06-22 | 2014-06-24 | 3000 | $ | 27 | Mr. Salem Saleh Mohammed Bin Mukhashen-Mukallah- Yemen | 2014-09-22
| Revised |  |  | PRIOR | SS | 2014-06-07 | 2014-06-12 | N/A | N/A | N/A | N/A | 2014-06-22 | 2014-06-24 |  |  |  |  | 2014-09-30
| Actual |  |  | PRIOR | SS | 2014-06-14 | 2014-06-17 | N/A | N/A | N/A | N/A | 2014-07-14 | 2014-07-15
11 | Planned | C28 | Consultant for C2 in Aden | PRIOR | SS | 2014-06-07 | 2014-06-12 | N/A | N/A | N/A | N/A | 2014-06-22 | 2014-06-24 | 2600 | $ | 28 | Ms. Liqua'a Ahmed Mohammed Hussein - Aden Yemen | 2014-09-22
| Revised |  |  | PRIOR | SS | 2014-06-07 | 2014-06-12 | N/A | N/A | N/A | N/A | 2014-06-22 | 2014-06-24 |  |  |  |  | 2014-09-30
| Actual |  |  | PRIOR | SS | 2014-06-14 | 2014-06-17 | N/A | N/A | N/A | N/A | 2014-06-30 | 2014-07-01
12 | Planned | C29 | Consultant for C2 in Houdeidah | PRIOR | SS | 2014-06-07 | 2014-06-12 | N/A | N/A | N/A | N/A | 2014-06-22 | 2014-06-24 | 3000 | $ | 29 | Mr. Turky Ali Ben Ahmed Yussef - Houddeidah - Yemen | 2014-09-22
| Revised |  |  | PRIOR | SS | 2014-06-07 | 2014-06-12 | N/A | N/A | N/A | N/A | 2014-06-22 | 2014-06-24 |  |  |  |  | 2014-09-30
| Actual |  |  | PRIOR | SS | 2014-06-14 | 2014-06-17 | N/A | N/A | N/A | N/A | 2014-06-30 | 2014-07-01
13 | Planned | C31 | Developper for Component 2 | PRIOR | IC | 2014-07-31 | N/A | N/A | 2014-08-15 | N/A | N/A | N/A | 2014-08-30
| Revised |  |  | PRIOR | IC | 2014-08-23 | N/A | N/A | 2014-09-07 | N/A | N/A | N/A | 2014-09-14
| Revised Oct 2014 |  |  | PRIOR | IC |  |  |  | 2014-10-26 | N/A | N/A | N/A | 2014-11-02
| Actual |  |  | PRIOR | IC | 2014-06-29: 2014-08-23; 2014-07-04: N/A; 2014-07-11: N/A
14 | Planned | C32. | Monitoring and Evaluation Officer | PRIOR | IC | 2014-08-23 | 2014-08-30 | 2014-09-02 | 2014-10-02 | 2014-10-09 | 2014-10-16 | 2014-10-31 | 2014-11-03 |  |  |  |  | 2017-03-31
| Revised |  |  | PRIOR | IC | 2014-08-23 | 2014-09-15 | 2014-09-18 | 2014-10-18 | 2014-10-25 | 2014-11-01 | 2014-11-16 | 2014-11-19 |  |  |  |  | 2017-03-31
| Revised Oct 2014 |  |  | PRIOR | IC | 2014-11-15 | 2014-11-20 | 2014-11-23 | 2014-12-23 | 2014-12-30 | 2015-01-06 | 2015-01-21 | 2015-01-24
| Actual |  |  | PRIOR | IC
12 | Planned | C40 | Long-term Advisor for Comp 2 Design & Imp | PRIOR | SS | 2013-06-05 | 2013-07-25 | N/A | N/A | N/A | N/A | 2015-03-15 | 2015-03-17 |  |  |  |  | 2017-03-31
| Revised |  |  | PRIOR | SS | 2013-06-05 | 2013-07-25 | N/A | N/A | N/A | N/A | 2015-03-15 | 2015-03-17 |  |  |  |  | 2017-03-31
| Actual |  |  |  |  | 2014-06-29: 2013-06-05; 2014-07-04: 2013-07-25
14 | Planned | C41 | Communication Officer for Component 2 | PRIOR | IC | 2014-11-22 | 2014-11-29 | 2014-12-02 | 2015-01-01 | 2015-01-08 | 2015-01-15 | 2015-01-30 | 2015-02-02 |  |  |  |  | 2015-03-02
| Revised Oct 2014 |  |  | PRIOR | IC | 2014-11-22 | 2014-11-29 | 2014-12-02 | 2015-01-01 | 2015-01-08 | 2015-01-15 | 2015-01-30 | 2015-02-02 |  |  |  |  | 2015-03-02
| Actual |  |  | PRIOR | IC
Formulas:
Shortlist to be Finalised (Date) = [TOR to be Finalised (Date)]
Shortlist to be Finalised (Date) = [Advertising for Short listing (Date)]+30
TOR to be Finalised (Date) = [TOR to be Finalised (Date), row above]
No Objection from Bank for TOR (Date)** = [TOR to be Finalised (Date)]+5
Advertising for Short listing (Date) = [No Objection from Bank for TOR (Date)**]+5
Services Completion (Date) = [Services Completion (Date), row above]
Services Completion (Date) = [Contract Signed (Date)]+120

## Consultant services- PST Staff
Procurement Plan for Consultant Services
SWF Institutional Support Project
Review Date: October 2014
SL No. |  | Package/ Reference No. | Description of Services | Review by Bank (Prior/ Post) | Method of Selection | TOR to be Finalised (Date) | No Objection from Bank for TOR (Date)** | Advertising for Short listing (Date) | Shortlist to be Finalised (Date) | No Objection from Bank for Shortlist (Date)** | No Objection by the Bank to the final Evaluation Report (Date)** | No Objection by the Bank (Technical/ #Combined/ Draft Contract/ Final Contract) (Date)** | Contract Signed (Date) | Contract Value | Contract Currency | Contract No. | Name, City, and Country of Contractor (incl. Zip Code if US) | Services Completion (Date) | Expenses Incurred to Date
8 | Planned | C8 | Technical Coordinator round 1 | PRIOR | IC | 2010-03-30 | NA | 2010-03-08 |  | NA | NA |  | 2010-06-19 |  |  |  |  | 2016-09-27
| Revised | [9 empty] | 2010-10-10 | 2010-10-20 | 2010-11-19 |  |  |  |  | 2016-09-27
| Actual |  | Procurement Process did not go through | PRIOR | IC |  | 2010-01-20 | 2010-02-14 | 2010-05-09 | 2010-05-11 | N/A | 2010-08-07 | Slection process cancelled
8.1 | Planned | C8.1 | Technical Coordinator Round 2 | PRIOR | IC | 2010-03-30 | NA | 2010-03-08 |  | NA | NA |  | 2010-06-19 | 96750 | US$ | TC-05 ISP | Nabeel Kobati Yemen | 2016-09-27
| Revised |  |  |  | IC | [5 empty] | 2010-10-10 | 2010-10-20 | 2010-11-19 |  |  |  |  | 2015-05-15
| Actual |  |  | PRIOR | IC |  | 2010-01-20 | N/A |  | 2010-05-11 | 2011-01-05 | 2011-01-18 | 2011-01-22
9 | Planned | C9 | Procurement Officer | PRIOR | IC | 2010-05-15 | NA | 2010-05-01 |  | NA | NA |  | 2010-01-19 | 67200 | US$ | PO-03 ISP | AbdulDaem AL-Bokhari Sana'a, Yemen | 2016-12-01
| Revised |  |  |  | IC | 2010-10-10 |  |  |  | 2010-10-25 | 2010-10-25 | 2010-11-04 | 2010-11-09 |  |  |  |  | 2014-10-31
| Actual |  |  | PRIOR | IC | 2010-05-11 | 2010-05-19 | 2010-08-04 | 2010-10-09 |  | 2010-10-18 | 13-Dec-10 | 2010-11-13 |  |  |  |  | 04-31-2014
10 | Planned | C10 | Financial Officer* | PRIOR | IC | 2010-05-14 | N/A | 2010-01-01 |  | NA | NA |  | 2010-06-18 | 76800 | US$ | 2658 | Akram Naji Sana'a Yemen | 2015-09-02
| Revised | [16 empty] | 2014-03-31
| Actual |  |  | PRIOR | IC | 2009-11-24 |  | 2009-10-11 | 2009-11-24 | NA | NA | 2009-12-08 | 2010-07-14
11 | Planned | C11 | Executive Secretary | PRIOR | IC | 2010-05-15 | NA | 2010-05-01 |  | NA | NA |  | 2010-06-19 | 25648 | US$ | ES-04 ISP | Amani Ali Albaidhani Sana'a, Yemen | 2016-11-30
| Revised |  |  |  |  | 2010-10-20 |  |  |  | 2010-11-04 | 2010-11-04 | 2010-11-14 | 2010-12-14 |  |  |  |  | 2014-10-19
| Actual |  |  | PRIOR | IC | 2010-05-11 | 2010-05-19 | 2010-08-04 | 2010-10-09 |  | 2010-10-18 | 2010-12-13 | 2010-12-05 |  |  |  |  | 2014-04-11
12 | Planned | C12 | Procurement Advisor | PRIOR | IC | 2010-05-15 | NA | 2010-05-01 |  | NA | NA |  | 2010-09-09 | 117637.75 | US$ | 1 | Nathalie Gebrayel Beirut-Lebanon | 2010-10-08
| Revised | [16 empty] | 2014-06-30
| Actual |  |  | PRIOR | IC | 2010-05-11 | 2010-05-26 | N/A | 2010-05-11 |  | NA | 2010-08-26 | 2010-09-15 |  |  |  |  | 2014-06-30
13 | Planned | C13 | MIS Specialist | PRIOR | IC | 2010-12-31 | 2011-01-05 | 2011-01-10 | 2011-02-09 | 2011-02-14 | 2011-03-01 | 2011-03-11 | 2011-03-21 |  |  |  |  | 2016-12-31
| Revised 21 Dec 10 |  |  | PRIOR | IC | 2010-12-31 | 2011-01-05 | 2010-12-26 | 2011-01-25 | 2011-01-30 | 2011-02-14 | 2011-02-24 | 2011-03-06 |  |  |  |  | 2016-12-31
| Revised Dec 2011 | [8 empty] | 2012-01-15 | 2012-02-04 | 2012-02-19 | 2012-02-24 |  |  |  |  | 2016-12-31
| Actual |  | Cancelled |  |  | 2010-12-13 | 2010-12-16 | 2011-01-20 | 11-Apr-11
| Planned |  | MIS Specialist | PRIOR | IC | 2012-08-31 | 2012-09-15 | 2012-09-25 | 2012-10-25 | 2012-11-09 | 2012-12-09 | 2012-12-24 | 2012-12-29 |  |  |  |  | 2016-12-31
13.1 | Revised Apr 2013 | C13.1 |  |  | IC | 2012-08-31 | 2013-04-28 | 2013-05-08 | 2013-06-07 | 2013-06-22 | 2013-07-22 | 2013-08-06 | 2013-08-11 |  |  |  |  | 2016-12-31
| Actual |  | Cancelled |  | IC | 2013-03-19
15 | Planned | C15 | Accountant | PRIOR | IC | 2010-12-31 | 2011-01-05 | 2011-01-10 | 2011-02-09 | 2011-02-14 | 2011-03-01 | 2011-03-11 | 2011-03-21 |  |  |  |  | 2016-12-31
| Revised 21 Dec 10 |  |  | PRIOR | IC | 2010-12-31 | 2011-01-05 | 2011-01-10 | 2011-02-09 | 2011-02-14 | 2011-03-01 | 2011-03-11 | 2011-03-21 |  |  |  |  | 2016-12-31
| Revised Dec 2011 | [7 empty] | 2011-07-31 | 2011-08-10 | 2011-08-30 | 2011-09-14 | 2011-09-19 |  |  |  |  | 2016-12-31
| Actual |  | Cancelled |  |  | 2010-12-12 | 2011-01-05 | 2011-01-20 | 2011-08-10
15.1 | Planned |  |  | PRIOR | IC | 2012-08-31 | 2012-09-15 | 2012-09-25 | 2012-10-25 | 2012-11-09 | 2012-12-09 | 2012-12-24 | 2012-12-29 |  |  |  | Abdul Hakeem Abdu Ahmad Sana'a - Yemen | 2016-12-31
| RevisedApril 2013 | C15.1 | Accountant | PRIOR | IC | 2012-08-31 | 2012-09-15 | 2012-09-25 | 2012-10-25 | 2013-04-30 | 2013-05-30 | 2013-06-14 | 2013-06-19 |  |  |  |  | 2014-08-31
| Actual |  |  | PRIOR | IC | 2012-09-05 | 2012-11-06 | 2012-11-24 | 2013-03-11 | 2013-05-20 | 2013-06-30 | 2013-08-26 | 2013-08-29 | 10200 | US$ | AC-10 ISP
16 | Revised |  | Financial Officer-2 |  | SSS | 2014-03-16 | 2014-03-20 | N/A | N/A | N/A | N/A | 2014-05-21 | 2014-06-02 | 12420 | US$ | FO-011-ISP | Akram Naji Sana'a Yemen | 2014-12-31
| Actual | C21 |  | PRIOR | SSS | 2014-03-16 | 2014-03-20 | N/A | N/A | N/A | N/A | 2014-05-21 | 2014-06-15 | 12420 | US$
17 | Planned | C22 | Financial Officer-3 | PRIOR | IC | 2014-07-01 | 2014-07-16 | 2014-07-26 | 2014-08-25 | 2014-09-09 | 2014-10-09 | 2014-10-24 | 2014-10-29 |  | US$ |  |  | 2017-03-31
| RevisedApril 2013 |  |  | PRIOR | IC | 2014-07-01 | 2014-07-16 | 2014-07-26 | 2014-08-25 | 2014-09-09 | 2014-10-09 | 2014-10-24 | 2014-10-29 |  | US$ |  |  | 2017-03-31
| Revised Oct 2014 | [9 empty] | 2014-10-25 | 2014-11-09 | 2014-11-14
| Actual |  |  | PRIOR | IC | 2014-06-10 | 2014-06-24 | 2014-07-01 | 2014-08-25 | 2014-09-11
| Planned | C23 |  | PRIOR | IC | N/A | N/A | 2014-04-01 | 2014-05-01 | 2014-05-16 | 2014-06-15 | 2014-06-30 | 2014-07-05 | 6600 | US$ | AC-12-ISP | Mr. Mohammed Rawia - Sana'a - Yemen | 2015-08-14
18 | Revised April 2013 |  | Executive Secretary - 2 | PRIOR | IC | N/A | N/A | 2014-04-01 | 2014-05-01 | 2014-05-16 | 2014-06-15 | 2014-06-30 | 2014-07-05 |  |  |  |  | 2015-08-14
| Actual |  |  | PRIOR | IC | N/A | N/A | 2014-04-07 | 2014-06-22 | 2014-06-24 | 2014-08-05 | 2014-08-15 | 2014-08-15
| Planned | C24 |  | PRIOR | IC | N/A | N/A | 2014-05-07 | 2014-06-06 | 2014-06-21 | 2014-07-21 | 2014-08-05 | 2014-08-10 |  | US$ |  |  | 2014-08-09
18 | RevisedApril 2013 |  | Procurement Officer-2 | PRIOR | IC | N/A | N/A | 2014-05-07 | 2014-06-06 | 2014-06-21 | 2014-09-15 | 2014-09-30 | 2014-10-05 |  | US$ |  |  | 2015-10-04
| Recised Oct 2014 | [9 empty] | 2014-10-25 | 2014-11-09 | 2014-11-14 |  | US$ |  |  | 2014-11-13
| Actual |  |  | PRIOR | IC | N/A | N/A | 2014-05-07 | 2014-07-17 | N/A | 2014-10-22 | 2014-11-06 | 2014-11-11
13 | Recised Oct 2014
| Actual | C30 | Procurement Advisor - Contract 2 | PRIOR | SS | 2010-05-15 | NA | N/A | N/A | N/A | N/A | 2014-07-02 | 2014-07-03 | 27872 | US$ | C30-ISP | Ms. Nathalie Gebrayel - Beirut - Lebanon | 2015-06-30
Formulas:
No Objection from Bank for TOR (Date)** = [TOR to be Finalised (Date)]+5
No Objection from Bank for TOR (Date)** = [TOR to be Finalised (Date), row below]+40
TOR to be Finalised (Date) = [Shortlist to be Finalised (Date)]
TOR to be Finalised (Date) = [TOR to be Finalised (Date), row below]
Shortlist to be Finalised (Date) = [Advertising for Short listing (Date)]+30
Services Completion (Date) = [Services Completion (Date), row above]
Advertising for Short listing (Date) = [No Objection from Bank for TOR (Date)**]+5
Advertising for Short listing (Date) = [Advertising for Short listing (Date), row above]
Note on U29: Nathalie Gebrayel: T ocheck with the WB if this is still needed. Done

## Capacity building
Review Date:June 2012
Capacity Building Activities
SL No. | Expected Outcome/ Activity Description | Estimated Duration | Start Date | Completion Date |  | Comments | Actual
1 | training for SWF staff | 5 years | 2012-01-01 | 2016-02-01 |  | 1
2 | training for SWF staff | 5 years | 2012-01-01 | 2016-02-01 |  | 2
3 | Targeting Policy Workshop | 5 years | 2012-01-01 | 2016-02-01 |  | 2
4 | English courses | 9 month | 2012-12-01 | 2013-10-30 | Yali institute |  | #REF!
5 | Team Building | 5 days | 2012-03-16 | 2012-03-20 | Thabet Bagash |  | 1500
6 | PO Training in India
| total | [5 empty] | #REF!
Note on B11: Nathalie: Value to be provided by AbdulHakim next week

## Procurement Information
Review Date:
Sl No | Type of procurement | As planned |  | As contracted |  |  | To be renewed |  | To be contracted |  | Remarks
|  | Number | Value | Number | Value in Euros | Value in US$ |  |  | Number | Value
1 | Goods | 9 | #REF! | 1 |  | #REF! | 0 | 0 | 8 | #REF! | G4 Furniture Planned Value is $20000 But actual Is $ 4,980
2 | Non consultant services | 3 | #REF! | [5 empty] | 3 | #REF! | This includes the planned training activities
3 | Works | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A
4 | Consultant services | 19 | #REF! | 10 | 52000 | #REF! | 8 | #REF! | 9 | #REF! | The IC contracts are subject to renewal and therefore the planned amounts are not 100% committed at this stage
5 | Others

## Budgeting
| Actual | PAD
NCB | #REF!
Shopping | #REF!
subtotal 1 | #REF! | 1600000 |  |  | #REF!
Firm | #REF!
IC | #REF!
PST | #REF!
subtotal 2 Consultant | #REF! | 2904000 |  |  | #REF!
Training | #REF! | 2230000 |  |  | #REF!
Operating Cost |  | 2816000 |  |  | #REF!
¦Unallocated |  | 450000 |  |  | #REF!
Total | #REF! | 10000000 |  |  | #REF!
| Committed | Disbursed | Planned as per proc plan including committed | Planned as per MTR | NEW as per MTR
Goods | 66280.9423 |  | #REF!
Consultancies | 2795383.45 |  | #REF!
Training | 109158 |  | 109158
OC | 64890 |  | 64890
Unallocated |  |  | #REF!
Total | 3035712.3923 |  | #REF!
Planned including committed
Component 1 | #REF!
Component 2 | #REF!
Component 3 | #REF!
Training | 109158
OC | 64890
#REF!
| #REF! |  | #REF!
Component 3
Planned including committed
Goods | #REF!
Consulting Firm | #REF!
PST Staff | #REF!
Individual Consultant | #REF!
Training
OC