## Goods
Country/Organisation: Federal Democrtic Repulic of Ethiopia/Ministry of Water and Energy | [10 empty] | Final with comments
Project/Programme: Ethiopian Water Supply and Sanitation Project
Cr. No. 3901-ET and Grant No. H085-ET and TF-91704 | [7 empty] | Draft Bid Documents, including specs and quantities, draft SPN
|  | BASIC DATA | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  | Contract Implementation
Description | Package Number | Lot Number | Estimated Amount in USD | Procurement Method | Pre-or Post Qualification | Prior or Post Review | Plan vs. Actual | Prep & Submission by Ex Agency | No-objection Date | On-line UNDB Gateway Nat Press | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Plan vs. Actual | Contract Amount in Birr | Date Contract Award | Date Contract Signature | Opening of Let of Credit | Arrival of Goods | Inspection Final Acceptance
List of Contracts
1. Office Equipments | MoWE/IDA-DFID/G/NCB-01/12 | 01 | 60179.95 | NCB | Post | Post | Plan | 2012-07-25 | NA | NA | 2012-08-01 | 2012-08-31 | 2012-09-10 | NA | Plan | 60179.95 | 2012-09-17 | 2012-10-02 | NA | 2012-11-01 | 2012-11-06
[7 empty] | Rev-1 | 2012-07-25 | NA | NA | 2012-08-01 | 2012-08-31 | 2012-09-10 | NA | Rev-1 | 60179.95 | 2012-09-17 | 2012-10-02 | NA | 2012-11-01 | 2012-11-08
[7 empty] | Actual | [7 empty] | Actual
2. Office Furnitue | MoWE/IDA-DFID/G/NCB-01/12 | 01 | 34844.1926 | NCB | Post | Post | Plan | 2012-07-25 | NA | NA | 2012-08-01 | 2012-08-31 | 2012-09-21 | NA | Plan | 34844.1926 | 2012-10-01 | 2012-10-16 | NA | 2012-11-15 | 2012-11-20
[7 empty] | Rev-1 | 2012-07-25 | NA | NA | 2012-08-01 | 2012-08-31 | 2012-09-21 | NA | Rev-1 | 34844.19 | 2012-09-28 | 2012-10-13 | NA | 2012-11-12 | 2012-11-19
[7 empty] | Actual | [7 empty] | Actual
3. 11Vehicles | MoWE/IDA-DFID/G/ICB-01/12 | 01 | 985237 | ICB | Post | Prior | Plan | 2012-06-06 | 2012-06-21 | 2012-07-06 | 2012-07-06 | 2012-08-20 | 2012-09-10 | 2012-09-25 | Plan | 985237 | 2012-09-20 | 2012-10-05 | 2012-11-04 | 2013-03-04 | 2013-03-14
[7 empty] | Rev-1 | 2012-06-06 | 2012-06-16 | 2012-07-01 | 2012-07-01 | 2012-08-15 | 2012-09-05 | 2012-09-15 | Rev-1 | 985237 | 2012-09-22 | 2012-10-07 | 2012-11-06 | 2013-03-06 | 2013-03-16
[7 empty] | Actual | 06-Jun-12 | [6 empty] | Actual
1080261.1426
Formulas:
Bidding Period = [Prep & Submission by Ex Agency]+7
Bidding Period = [Spec Proc Notice Advert]+0
Bid Closing-Opening = [Bidding Period]+30
Bid Closing-Opening = [Spec Proc Notice Advert]+45
Bid Evaluation = [Bid Closing-Opening]+10
Date Contract Award = [Bid Evaluation]+7
Date Contract Award = [No-objection Date]+7
Date Contract Signature = [Date Contract Award]+15
Contract Implementation = [Date Contract Signature]+30
Contract Implementation = [Opening of Let of Credit]+120
Inspection Final Acceptance = [Contract Implementation]+5
No-objection Date = [Prep & Submission by Ex Agency]+15
No-objection Date = [Bid Evaluation]+15
Spec Proc Notice Advert = [No-objection Date]+15
Opening of Let of Credit = [Date Contract Signature]+30

## Works (hidden)
[10 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
Loan #: |  |  | Basic Data | [8 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  | Contract Implementation
Description* | QTY | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Estimated Amount in Birr | Pre-or Post Qualification | Prior or Post Review | Plan vs. Actual | Prep & Submission by Ex Agency | No-objection Date | On-line UNDB Gateway Nat Press | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Plan vs. Actual | Contract Amount in Birr | Date Contract Award | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost
Norm Duration of Proc Steps | [6 empty] | If Prequalification |  | Plan | 4 - 7 wks | 1 - 1.5 wks | 1.5 - 2 wks | 1.5 - 2 wks | 6 to | 12 wks | 1.5 - 3 wks | Plan |  | 1 wk | 1.5-3 wks
[7 empty] | add 7-13 wks |  | Actual | [7 empty] | Actual
List of Contracts
[9 empty] | Plan | [7 empty] | Plan
[9 empty] | Actual | [7 empty] | Actual
[9 empty] | Plan | [7 empty] | Plan
[9 empty] | Actual | [7 empty] | Actual
[9 empty] | Plan | [7 empty] | Plan
[9 empty] | Actual | [7 empty] | Actual
[9 empty] | Plan | [7 empty] | Plan
[9 empty] | Actual | [7 empty] | Actual
[9 empty] | Plan | [7 empty] | Plan
[9 empty] | Actual | [7 empty] | Actual
[9 empty] | Plan | [7 empty] | Plan
[9 empty] | Actual | [7 empty] | Actual
[9 empty] | Plan | [7 empty] | Plan
[9 empty] | Actual | [7 empty] | Actual
Total | [5 empty] | 0

## Consultancy
Country/Organisation: FEDERAL DEMOCRATIC REPUBLIC OF ETHIOPIA/Ministry of Water and Energy
Project/Programme: Ethiopia Water Supply aand Sanitation project
Cr. No. 3901-ET and Grant No. H085-ET and TF-91704 | [8 empty] | Request for Expression of Interest (when required)
Loan #: Credit No. 4292-ET and Grant No. 287-ET |  |  | Contract Type |  |  |  | Preparation Request for Proposals |  |  |  | Short List |  |  | Consultant Proposals |  | Proposal Evaluation Technical (T) & Financial (F) | [5 empty] | Negotiations |  |  | Contract Finalization |  |  |  | Contract Implementation
Description | Qty | Selection Method | Lumpsum or Time-Based | Estimated Amount in USD | Prior/Post Review | Plan vs. Actual | Prep & Submission by Ex Ag | No-objection Date | On-line UNDB Gateway/ Nat Press | Lead-time before shortlist | Submission Date | Internal No-objection Date | Plan vs. Actual | Invitation Date | Submission/ Opening Date | Submission Evaluation Report (T) | No-objection Evaluation Report (T) | Opening Financial Proposals | Submission Eval Report (T) (F) | No-objection Eval Report (T) (F) | Plan vs. Actual | Negotiations | Submission Draft Contract | No-objection Negotiations | Contract Amount in US$ | Contract ward | Contract Signature | Plan vs. Actual | Mobilization Advance Payment | Draft Report | Final Report | Final Cost
List of Contracts | [6 empty] | 3 - 6 wks | 1 - 2 wks | 1 - 1.5 wks | 2 wks |  | 1 - 2 wks |  | 4 to | 12 wks | 2 - 3 wks | 0.5 - 2 wks | 2 wks | 1 - 2 wks | 1 - 1,5 wks |  | 2 wks | 1 - 2 wks | 1 - 2 wks |  | 1 wk | 1 - 3 wks
1. Lead Urban National Consultant | 01 | IC | Time Based | 18048.7106 | Post | Plan | N/A | N/A | 2011-10-30 | 2011-11-14 | 2011-11-29 | 2011-12-14 | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | 2011-12-29 | 2012-01-13 | N/A | 18048.71 | 2012-01-28 | 2012-02-07 | Plan | N/A | N/A | 2013-02-06
[6 empty] | Actual | N/A | N/A | 2011-10-30 | 2011-11-14 | 2011-11-29 | 2011-12-14 | Actual | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Actual | 2011-12-29 | 2012-01-13 | N/A | 18048.71 | 2012-01-28 | 2012-02-07 | Actual | N/A | N/A
2. Business Plan and Management Consultant | 01 | IC | Time Based | 17292.2636 | Post | Plan | N/A | N/A | 2011-11-18 | 2011-12-03 | 2011-12-18 | 2012-01-02 | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | 2012-01-17 | 2012-02-01 | N/A | 17292.2636 | 2012-02-16 | 2012-02-26 | Plan | N/A | N/A | 2013-02-25
[6 empty] | Actual | N/A | N/A | 2011-11-18 | 2011-12-03 | 2011-12-18 | 2012-01-02 | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | 2012-01-17 | 2012-02-01 | N/A | 17292.2636 | 2012-02-16 | 2012-02-26 | Plan | N/A | N/A
3. Procurement Management Consultant | 01 | IC | Time Based | 23002.8653 | Post | Plan | N/A | N/A | 2011-11-10 | 2011-11-25 | 2011-12-10 | 2011-12-25 | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | 2012-01-09 | 2012-01-24 | N/A | 23002.8653 | 2012-02-08 | 2012-02-18 | Plan | N/A | N/A | 2013-02-17
[6 empty] | Actual | N/A | N/A | 2011-11-10 | 2011-11-25 | 2011-12-10 | 2011-12-25 | Actual | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Actual | 2012-01-09 | 2012-01-24 | N/A | 23002.8653 | 2012-02-08 | 2012-02-18 | Actual | N/A | N/A
4. Consulting Firm for Project Completin Report | 01 | QCBS | Lumpusm | 150000 | Post | Plan | 2012-07-08 | N/A | 2012-07-18 | 2012-08-08 | 2012-08-23 | 2012-09-02 | Plan | 2012-09-07 | 2012-10-05 | 2012-10-20 | N/A | 2012-10-30 | 2012-11-09 | N/A | Plan | 2012-11-19 | 2012-11-29 | N/A | 150000 | 2012-12-06 | 2012-12-16 | Plan | 2012-12-31 | 2013-03-01 | 2013-03-31
[6 empty] | Rev-1 | 2012-07-15 | NA | 2012-07-25 | 2012-08-09 | 2012-08-24 | 2012-09-03 | Rev-1 | 2012-09-18 | 2012-10-18 | 2012-11-02 | NA | 2012-11-17 | 2012-12-02 | NA | Rev-1 | 2012-12-17 | 2012-12-27 | NA | 150000 | 2013-01-03 | 2013-01-18 | Rev-1 | 2013-02-02 | 2013-04-03 | 2013-05-03
Actual
Total Cost |  |  |  | 208343.8395
Formulas:
On-line UNDB Gateway/ Nat Press = [Lead-time before shortlist]-15
On-line UNDB Gateway/ Nat Press = [Preparation Request for Proposals]+10
Lead-time before shortlist = [Short List]-15
Lead-time before shortlist = [On-line UNDB Gateway/ Nat Press]+15
Short List = [Internal No-objection Date]-15
Short List = [Lead-time before shortlist]+15
Internal No-objection Date = [Negotiations]-15
Internal No-objection Date = [Consultant Proposals]-5
Negotiations = [Submission Draft Contract]-15
Negotiations = [Submission Eval Report (T) (F)]+15
Submission Draft Contract = [Contract ward]-15
Submission Draft Contract = [Negotiations]+10
Contract ward = [Contract Signature]-10
Contract ward = [Submission Draft Contract]+7
Contract Signature = [Final Report]-365
Contract Signature = [Contract Implementation]-15
Consultant Proposals = [Submission/ Opening Date]-28
Consultant Proposals = [Internal No-objection Date]+15
Submission/ Opening Date = [Submission Evaluation Report (T)]-15
Submission/ Opening Date = [Consultant Proposals]+30
Submission Evaluation Report (T) = [Opening Financial Proposals]-10
Submission Evaluation Report (T) = [Submission/ Opening Date]+15
Opening Financial Proposals = [Submission Eval Report (T) (F)]-10
Opening Financial Proposals = [Submission Evaluation Report (T)]+15
Submission Eval Report (T) (F) = [Negotiations]-10
Submission Eval Report (T) (F) = [Opening Financial Proposals]+15
Contract Implementation = [Draft Report]-60
Contract Implementation = [Contract Signature]+15
Draft Report = [Final Report]-30
Draft Report = [Contract Implementation]+60
Final Report = [Draft Report]+30
Note on D7: IC= Individual Consultant
Note on D10: IC=Individual Conslltant
Note on D13: IC=Indiviudal Consultant
Note on I15: cbe: For BD preparation time is required!