## TOTAL_HSIP
Approved ___________ Minister of Health
_____ 2013
Total planned cost under the Grant USD 19,8 mln.
No | Costs Category | Total amount (USD equivalent) | %
1 | RBF Payments ( Including of the first verification by SHASS ) | 8060000 | 40.71%
3 | Works | 1910000 | 9.646%
4 | Goods | 2812000 | 14.2%
5 | Consultative services | 3723500 | 18.81%
6 | Training and workshops | 2296950 | 11.6%
7 | Operational expenditures | 997550 | 5.038%
8 | Contingencies | 0 | 0%
TOTAL |  | 19800000 | 100%
| TOTAL, Project costs | 19800000

## Total_components
№№ | Project Component/ Category | Total amount (USD equivalent) | %
Component 1. Result-based Financing (10,8 mln USD)
1 | RBF Payments | 7560000 | 38.18%
2 | Verification Level 1 ( SHASS) | 500000 | 2.525%
3 | Services | 1919500 | 9.694%
4 | Goods | 0 | 0%
5 | Workshops and training | 820500 | 4.144%
TOTAL for Component 1. |  | 10800000 | 54.55%
Component 2. Strengthening of the Primary Health Care (6,0 mln USD)
Subcomponent 2.1. PHC Quality Improvement
1 | Services | 206000 | 1.04%
2 | Goods | 1167000 | 5.894%
3 | Workshops and training | 1127000 | 5.692%
Total for Sub Component 2.1. |  | 2500000 | 12.63%
Subcomponent 2.2. PHC Infrastructure Improvement
1 | Services | 210000 | 1.061%
2 | Goods | 1380000 | 6.97%
3 | Works | 1910000 | 9.646%
4 | Workshops and training |  | 0%
Total for Sub Component 2.2 |  | 3500000 | 17.68%
Total for Component 2 |  | 6000000 | 30.3%
Component 3.Project management (3,0 mln USD)
1 | Services | 1388000 | 7.01%
2 | Goods | 265000 | 1.338%
3 | Workshops and training | 349450 | 1.765%
4 | Operational expenditures | 997550 | 5.038%
Total for Component 3. |  | 3000000 | 15.15%
Contingencies |  | 0 | 0%
TOTAL |  | 19800000 | 100%

## Goods
[10 empty] | Approved by_________ |  | Minister of Health
Republic of Tajikistan
MINISTRY OF HEALTH
Grant Project " Health Services Improvement Project in Tajikistan ( Grant No___)
PROCUREMENT PLAN - GOODS
(Date of PP: ______________2013; Update No.___; Date of WB NOL: ___________ 2013)
No. | Package Number | Description | Plan vs. Actual | Estimated Cost (US$ equivalent) | Procu. Method | WB Review (Prior/ Post) | Date of Draft BD to WB | WB No-objection to BD | Date of Invitation to Bids | Date of Bid Opening | Bid Evaluation Report | WB No-objection to Contract Award | Date of Contract Signing | Date of Contract Completion | Award of contract
Component 1. Performance-based Financing
Total, Component 1 |  |  | plan | 0
actual
Component 2: Primary Health Care Strengthening
Sub-component 2.1. Quality improvement
2.1.1.Training for the FM doctors and nurses
1 | MOH/RBF/SHG/014/002 | Procurement of the medical wallets for doctors and nurses in Spitamen rayon ( 60 doctors and 114 nurses) | plan | 50000 | SHG | post | n/a | n/a | Oct-13 | Oct-13 | Nov-13 | n/a | Jan-14 | Feb-14
actual
2 | MOH/RBF/SHG/014/003 | Procurement of the medical wallets for doctors and nurses in Sughd Oblast (Gonchi(19 & 27), J.Rasulov (53 & 115), Mastcho rayon (32 & 50) | plan | 100000 | SHG | post | n/a | n/a | Mar-14 | Mar-14 | Apr-14 | n/a | May-14 | Jun-14
actual
3 | MOH/RBF/SHG/015/001 | Procurement of the medical wallets for doctors and nurses in Khatlon Oblast (Rumi (18 & 15), Khamadoni ( 27 & 62) ,Kabadiyon (16 & 125) and Yavan ( 27 & 137)) | plan | 100000 | SHG | post | n/a | n/a | Mar-15 | Mar-15 | Apr-15 | n/a | May-15 | Jun-15
actual
4 | MOH/RBF/SHG/014/004 | Procurement of the Medicine literature for pilots rayons | plan | 60000 | SHG | post | Feb-14 | Mar-14 | Mar-14 | Mar-14 | April-14 | Apr-14 | May-14 | Jul-14
actual
5 | MOH/RBF/NCB/014/007 | Procurement of visual aids,stimulants and moulages for the FM Centers | plan | 180000 | NCB | prior | Mar-14 | Apr-14 | Apr-14 | May-14 | Jun-14 | Jun-14 | Jul-14 | Sep-14
actual
6 | MOH/RBF/SHG/014/005 | Replidcation of the clinical protocols and training on their proper use for the health staff in 8 rayons | plan | 80000 | SHG | post | n/a | n/a | Mar-14 | Mar-14 | April-14 | n/a | May-14 | Jul-14
actual
7 | MOH/RBF/SHG/014/006 | Replication of the training FM materials | plan | 15000 | SHG | post | n/a | n/a | Mar-14 | Mar-14 | April-14 | n/a | May-14 | Jul-14
actual
8 | MOH/RBF/SHG/015/002 | Replication of the training FM materials | plan | 15000 | SHG | post | n/a | n/a | Jan-15 | Jan-15 | Feb-15 | n/a | Mar-15 | Apr-15
actual
9 | MOH/RBF/SHG/016/001 | Replication of the training FM materials | plan | 15000 | SHG | post | n/a | n/a | Jan-16 | Jan-16 | Feb-16 | n/a | Mar-16 | Apr-16
actual
10 | MOH/RBF/SHG/017/001 | Replication of the training FM materials | plan | 15000 | SHG | post | n/a | n/a | Jan-17 | Jan-17 | Feb-17 | n/a | Mar-17 | Apr-17
actual
11 | MOH/RBF/SHG/014/001 | Procurement and installation of the computer and office equipment for Consultants (12) | plan | 60000 | SHG | prior | Nov-13 | Dec-13 | Jan-14 | Feb-14 | Feb-14 | Mar-14 | Mar-14 | Apr-14
actual
12 | MOH/RBF/ICB/015/001 | Procurement of vehicles for 8 DHD ( Mobile Verification Group) | plan | 200000 | ICB | prior | Mar-14 | Apr-14 | May-14 | July-14 | July-14 | Aug-14 | Aug-14 | Dec-14
actual
13 | MOH/RBF/SHG/014/007 | Procurement ans installation of the computer and office equipment for RHDs in 3 pilot rayons in Sughd Oblast | plan | 80000 | SHG | post | n/a | n/a | Feb-14) | Mar-14 | April-14 | n/a | May-14 | Jul-14
actual
14 | MOH/RBF/SHG/015/005 | Procurement ans installation of the computer and office equipment for RHDs in 4 pilot rayons in Khatlon Oblast | plan | 95000 | SHG | post | n/a | n/a | Oct-14 | Oct-14 | Nov-14 | n/a | Jan-15 | Mar-15
actual
15 | MOH/RBF/SHG/014/008 | Replication of the Visit Register for 8 pilot rayons | plan | 32000 | SHG | post | n/a | n/a | Sep-14 | Sep-14 | Oct-14 | n/a | Nov-14 | Dec-14
actual
16 | MOH/RBF/SHG/014/009 | Procurement of office supply for 7 pilot rayons | plan | 70000 | SHG | post | n/a | n/a | Sep-14 | Sep-14 | Oct-14 | n/a | Nov-14 | Dec-14
actual
Total, Subcomponent 2.1 |  |  |  | 1167000
2.2. Physical Infrastructure Improvement in pilot rayons
17 | MOH/RBF/ICB/014/001 | Procurement of the clinical medical equipment for 114 RHC и 218 HH | plan | 1000000 | ICB | prior | Feb-14 | Mar-14 | Apr-14 | Jun-14 | July-14 | July-14 | Aug-14 | Aug-15
actual
18 | MOH/RBF/ICB/014/002 | Procurement of the office and medical furniture for 24 RHC | plan | 380000 | ICB | prior | Feb-14 | Mar-14 | Apr-14 | Jun-14 | July-14 | July-14 | Aug-14 | Aug-15
actual
| Total, Subcomponent 2.2. |  | plan | 1380000
actual
| TOTAL , Component 2 |  | plan | 2547000
actual
Component 3. Project Management
3.1. Project Management
19 | MOH/RBF/SHG/016/002 | Procurement and installation of the computer and office equipment for the Coordination Group Consultants under the MoH | plan | 50000 | SHG | post | n/a | n/a | Jan-16 | Jan-16 | Feb-16 | n/a | Mar-16 | Apr-16
actual
20 | MOH/RBF/SHG/015/004 | Procurement of vehicles for the Coordination Group inder the MoH, RBF Unit | plan | 100000 | SHG | post | n/a | n/a | Jan-15 | Jan-15 | Feb-15 | n/a | Mar-15 | Apr-15
actual
21 | MOH/RBF/SHG/014/010 | Procurement of the copying machine and presentation equipment for the MoH CG, RBF Unit | plan | 50000 | SHG | post | n/a | n/a | Mar-14 | Mar-14 | Apr-14 | n/a | Mar-14 | Jul-14
actual
22 | MOH/RBF/SHG/017/002 | Procurement of the computer and office equipment for the Coordination Group Consultants under the MoH | plan | 20000 | SHG | post | n/a | n/a | Jan-17 | Jan-17 | Feb-17 | n/a | Mar-17 | Apr-17
actual
23 | MOH/RBF/SHG/014/011 | Procurement ans installation of the computer and office equipment, deliverables for the RBF Unit in Khatlon Oblsat | plan | 15000 | SHG | post | n/a | n/a | Sep-14 | Sep-14 | Sep-14 | n/a | Nov-14 | Dec-14
actual
24 | MOH/RBF/SHG/014/012 | Procurement of the required office furniture (strong boxes (safes), iron closets, file cabinets) for the RBF material storage | plan | 20000 | SHG | post | n/a | n/a | Oct-13 | Oct-13 | Oct-13 | n/a | Jan-14 | Feb-14
actual
25 | MOH/RBF/SHG/014/013 | Installation of the local network ( MoH CG, RBF Unit in MoH, RBF Departments in Sughd and Khatlon) | plan | 10000 | SHG | post | n/a | n/a | Jan-14 | Feb-14 | Mar-14 | n/a | Apr-14 | Jun-14
actual
| Total, Component 3 |  | plan | 265000
actual
| TOTAL, GOODS |  | plan | 2812000
actual

## Works
[10 empty] | Approved by_________ |  | Minister of Health
__________ 2013
Republic of Tajikistan
MINISTRY OF HEALTH
Grant Project " Health Services Improvement Project in Tajikistan (Grant No.)
Procurement Plan -Works
(PP Date: ___2013; Update No. ____________; WB No Objection Date: _____2013)
No. | Package Number | Description | Plan vs. Actual | Estimated Cost (US$ equivalent) | Procu. Method | WB Review (Prior/ Post) | Date of Draft BD to WB | WB No-objection to BD | Date of Invitation to Bids | Date of Bid Opening | Bid Evaluation Report | WB No-objection to Contract Award | Date of Contract Signing | Date of Contract Completion | Award of contract
WORKS
Component 2.2.
1 | MOH/RBF/NCB/014/001 | Rehabilitation of 4- RHC in Yavan rayon ** | Plan | 305000 | NCB | Prior* | Feb-14 | Feb-14 | Mar-14 | Mar-14 | Apr-14 | Apr-14 | May-14 | Dec-15
Actual
2 | MOH/RBF/NCB/014/002 | Rehabilitation of 4-RHC in Hamadoni rayon** | Plan | 305000 | NCB | Prior* | Feb-14 | Feb-14 | Mar-14 | Mar-14 | Apr-14 | Apr-14 | May-14 | Dec-15
Actual
3 | MOH/RBF/NCB/014/003 | Rehabilitation of 4- RHC in Rumi rayon** | Plan | 305000 | NCB | Post | n/a | n/a | Mar-14 | Mar-14 | Apr-14 | n/a | May-14 | Dec-15
Actual
4 | MOH/RBF/NCB/014/004 | Rehabilitationof 4- RHC in Gonchi rayon** | Plan | 305000 | NCB | Post | n/a | n/a | Mar-14 | Apr-14 | May-14 | n/a | May-14 | Dec-15
Actual
5 | MOH/RBF/NCB/014/005 | Rehabilitation of 4- RHC in Matcho rayon ** | Plan | 305000 | NCB | Post | n/a | n/a | Mar-14 | Apr-14 | May-14 | n/a | May-14 | Dec-15
Actual
6 | MOH/RBF/NCB/014/006 | Rehabilitation of 4- RHC in Jabbor Rasulov rayon ** | Plan | 305000 | NCB | Post | n/a | n/a | Mar-14 | Apr-14 | May-14 | n/a | May-14 | Dec-15
Actual
7 | MOH/RBF/SHW/013/001 | Premises repair works for the Project Consultants (under MoH) | Plan | 80000 | SHW | Post | n/a | n/a | Aug-13 | Aug-13 | Sep-13 | n/a | Sep-13 | May-14
Actual
Total, Component 2.2. |  |  | Plan | 1910000
Actual
TOTAL, WORKS |  |  | Plan | 1910000
Note: * - Following thresholds are subject to the preliminary WB review, used for the Grant: Two NCB Contracts , **Names of RHC's will be indicated after approval by MOH and WB

## Services
Republic of Tajikistan
MINISTRY OF HEALTH
Grant Project " Health Services Improvement Project in Tajikistan (Grant No.)
PROCUREMENT PLAN - CONSULTANTING SERVICES
(Date of PP: _______ 2013; Update No.___________; Date of WB NOL: ___________ 2013)
No | Package Number | Description | Plan vs. Actual | Estimated Cost (US$ equivalent) | Firm or Ind. | Select. Method | WB Review (Prior/ Post) | Request for Exp. Of Interest | Draft RFP (incl. TOR, Short List) | WB No-objection to RFP (full package) | RFP Issued | Date of Proposal Submission | Tech. Evaluation Report (TER) | WB No-objection to TER | Combined Tech & Fin Eval. Report | Draft Final Contract | WB No-objection to Draft Contract | Date of Contract Signing | Date of Contract Completion | Award of Contract
Component 1. Performance-based Financing
1.2. RBF Administration
1.2.1. PBF Unit in MoH
1 | MOH/RBF/LIC/014/024 | RBF Financial Management Head Specialist | plan | 60000 | Ind. | IC | Prior | Sep-13 | N/A | Sep-13( No Obj. for ToR) | N/A | N/A | Oct-13 | Oct-13 | N/A | Nov-13 | Dec-13 | Jan 2014 | Jan 2019
actual
2 | MOH/RBF/LIC/014/025 | Disbursement Specialist (RBF) for Khatlon Oblast | plan | 36000 | Ind. | IC | Post | 2014-09-01 | N/A | Sep-14( No Obj. for ToR) | N/A | N/A | Oct-14 | N/A | N/A | Nov-14 | N/A | Jan 2015 | Jan 2019
actual
3 | MOH/RBF/LIC/014/026 | Disbursement Specialist (RBF) for Sughd Oblast | plan | 48000 | Ind. | IC | Post | Sep-13 | N/A | Sep-13( No Obj. for ToR) | N/A | N/A | Oct-13 | N/A | N/A | Nov-13 | N/A | Jan 2014 | Jan 2019
actual
4 | MOH/RBF/LIC/014/027 | Operations Analyst | plan | 48000 | Ind. | IC | Post | Sep-13 | N/A | Sep-13( No Obj. for ToR) | N/A | N/A | Oct-13 | N/A | N/A | Nov-13 | N/A | Jan 2014 | Jan 2019
actual
5 | MOH/RBF/IC/014/028 | MIS Data Base Administrator on RBF web-site | plan | 48000 | Ind. | IC | Post | Sep-13 | N/A | Sep-13( No Obj. for ToR) | N/A | N/A | Oct-13 | N/A | N/A | Nov-13 | N/A | Jan 2014 | Jan 2019
actual
6 | MOH/RBF/LIC/014/029 | Verification Commission Coordinator | plan | 48000 | Ind. | IC | Post | Sep-13 | N/A | Sep-13( No Obj. for ToR) | N/A | N/A | Oct-13 | N/A | N/A | Nov-13 | N/A | Jan 2014 | Jan 2019
actual
7 | MOH/RBF/LIC/014/030 | TA for the RBF web-site development/Web-design Consultant | plan | 24000 | Ind. | IC | Post | Sep-13 | N/A | Sep-13( No Obj. for ToR) | N/A | N/A | Oct-13 | N/A | N/A | Nov-13 | N/A | Jan 2014 | Jan 2019
actual
8 | MOH/RBF/LIC/014/031 | TA for the software development /Web Developer of the Financial Module of the Web RBF MIS&Accounting system | plan | 48000 | Ind. | IC | Post | Sep-13 | N/A | Sep-13( No Obj. for ToR) | N/A | N/A | Oct-13 | N/A | N/A | Nov-13 | N/A | Jan 2014 | Jan 2019
actual
1.2.2. PBF Unit in OblastHD in Sughd Oblast
9 | MOH/RBF/LIC/014/032 | RBF Management Head Specialist in Sughd Oblast | plan | 48000 | Ind. | IC | Post | Sep-13 | N/A | Sep-13( No Obj. for ToR) | N/A | N/A | Oct-13 | N/A | N/A | Nov-13 | N/A | Jan 2014 | Jan 2019
actual
10 | MOH/RBF/LIC/014/033 | RBF Disbursement Specialist | plan | 38000 | Ind. | IC | Post | Sep-13 | N/A | Sep-13( No Obj. for ToR) | N/A | N/A | Oct-13 | N/A | N/A | Nov-13 | N/A | Jan 2014 | Jan 2019
actual
11 | MOH/RBF/LIC/014/034 | PHC service quality assessment Specialist | plan | 38000 | Ind. | IC | Post | Sep-13 | N/A | Sep-13( No Obj. for ToR) | N/A | N/A | Oct-13 | N/A | N/A | Nov-13 | N/A | Jan 2014 | Jan 2019
actual
12 | MOH/RBF/LIC/014/035 | RBF MIS Data Monitoring Specialist | plan | 38000 | Ind. | IC | Post | Sep-13 | N/A | Sep-13( No Obj. for ToR) | N/A | N/A | Oct-13 | N/A | N/A | Nov-13 | N/A | Jan 2014 | Jan 2019
actual
13 | MOH/RBF/LIC/014/036 | IT Specialist | plan | 32000 | Ind. | IC | Post | Sep-13 | N/A | Sep-13( No Obj. for ToR) | N/A | N/A | Oct-13 | N/A | N/A | Nov-13 | N/A | Jan 2014 | Jan 2019
actual
1.2.3.PBF Unit in Oblast Health Department in Khatlon Oblast
Dec 2017
14 | MOH/RBF/LIC/014/037 | RBF Management Head Specialist in Khatlon Oblast | plan | 36000 | Ind. | IC | Post | Sep-14 | N/A | Sep-14( No Obj. for ToR) | N/A | N/A | Oct-14 | N/A | N/A | Nov-14 | N/A | Jan 2015 | Jan 2019
actual
15 | MOH/RBF/LIC/014/038 | RBF Disbursement Specialist | plan | 28500 | Ind. | IC | Post | Sep-14 | N/A | Sep-14( No Obj. for ToR) | N/A | N/A | Oct-14 | N/A | N/A | Nov-14 | N/A | Jan 2015 | Jan 2019
actual
16 | MOH/RBF/LIC/014/039 | PHC service quality assessment Specialist | plan | 28500 | Ind. | IC | Post | Sep-14 | N/A | Sep-14( No Obj. for ToR) | N/A | N/A | Oct-14 | N/A | N/A | Nov-14 | N/A | Jan 2015 | Jan 2019
actual
17 | MOH/RBF/LIC/014/040 | RBF MIS Data Monitoring Specialist | plan | 28500 | Ind. | IC | Post | Sep-14 | N/A | Sep-14( No Obj. for ToR) | N/A | N/A | Oct-14 | N/A | N/A | Nov-14 | N/A | Jan 2015 | Jan 2019
actual
18 | MOH/RBF/LIC/014/041 | IT Specialist | plan | 24000 | Ind. | IC | Post | Sep-14 | N/A | Sep-14( No Obj. for ToR) | N/A | N/A | Oct-14 | N/A | N/A | Nov-14 | N/A | Jan 2015 | Jan 2019
actual
1.3. RBF Introduction in pilot rayons
19 | MOH/RBF/QCBS/014/001 | TA for the RBF implementation in pilot rayons | plan | 500000 | Firm | QCBS | Prior | Dec-13 | Dec-13 | Jan-14 | Jan-14 | Feb-14 | Mar-14 | Mar-14 | Apr-14 | May-14 | May-14 | Jun-14 | Jun-16
actual
20 | MOH/RBF/SSS/014/001 | TA for conducting independent Verification Level II (UNICEF) | plan | 720000 | Firm | SSS | Prior | Sep-13 | Sep-13 | Oct-13 | Oct-13 | Oct-13 | n/a | Nov-13 | N/A | Nov-13 | Nov-13 | Dec-13 | Jan 2019
actual
Total, Component 1 |  |  | plan | 1919500
actual
Component 2: Primary Health Care Strengthening
Subcomponent 2.1. Quality Improvement
2.1.1. Trainingfor the Family Medicine docotrs and nurses
21 | MOH/RBF/LIC/014/042 | Training Coordinator | plan | 60000 | Ind. | IC | Prior | Sep-13 | N/A | Sep-13( No Obj. for ToR) | N/A | N/A | Oct-13 | Oct-13 | N/A | Nov-13 | Dec-13 | Jan 2014 | Jan 2019
actual
22 | MOH/RBF/LIC/014/043 | Training Coordinator in Sughd Oblast | plan | 48000 | Ind. | IC | Post | Sep-13 | N/A | Sep-13( No Obj. for ToR) | N/A | N/A | Oct-13 | N/A | N/A | Nov-13 | N/A | Jan 2014 | Jan 2019
actual
23 | MOH/RBF/LIC/014/044 | Training Coordinator in Khatlon Oblast | plan | 48000 | Ind. | IC | Post | Sep-13 | N/A | Sep-13( No Obj. for ToR) | N/A | N/A | Oct-13 | N/A | N/A | Nov-13 | N/A | Jan 2014 | Jan 2019
actual
24 | MOH/RBF/IIC/014/001 | TA Development of collaborative quality assurance mechanizm | plan | 50000 | ind | IC | Prior | Jan-14 | Jan-14 | Jan-14 | N/A | Feb-14 | n/a | Feb-14 | n/a | Mar-14 | Mar-14 | Apr-14 | Dec-14
actual
Total for subcomponent 2.1 |  |  | plan | 206000
actual
2.2. Physical Infrastructure Improvement in 6 pilot rayons
25 | MOH/RBF/IC/014/045 | Construction Coordinator | plan | 28000 | Ind. | IC | Post | Nov-13 | N/A | Nov-13( No Obj. for ToR) | N/A | N/A | Dec-13 | N/A | N/A | Dec-13 | N/A | Jan 2014 | Dec 2015
actual
26 | MOH/RBF/IC/014/046 | Estimator-Engineer | plan | 24000 | Ind. | IC | Post | Nov-13 | N/A | Nov-13( No Obj. for ToR) | N/A | N/A | Dec-13 | N/A | N/A | Dec-13 | N/A | Jan 2014 | Dec 2015
actual
27 | MOH/RBF/IC/014/047 | Construction Inspector in Sughd Oblast | plan | 24000 | Ind. | IC | Post | Nov-13 | N/A | Nov-13( No Obj. for ToR) | N/A | N/A | Dec-13 | N/A | N/A | Dec-13 | N/A | Jan 2014 | Dec 2015
actual
28 | MOH/RBF/IC/014/048 | Construction Inspector in Khatlon Oblast | plan | 24000 | Ind. | IC | Post | Nov-13 | N/A | Nov-13( No Obj. for ToR) | N/A | N/A | Dec-13 | N/A | N/A | Dec-13 | N/A | Jan 2014 | Dec 2015
actual
29 | MOH/RBF/CQS/013/001 | Development of project design and cost estimates for rehabilitation of 24 health facilities in 6 pilot rayons and supervision | plan | 80000 | Firm | SQC | Prior | Sep-13 | Sep-13 | Sep-13( No Obj. for ToR) | Sep | Sep | Oct-13 | Oct-13 | Nov-13 | Nov-13 | Dec-13 | Jan-14 | Dec 2015
actual
30 | MOH/RBF/CQS/014/001 | TA independent Enviromental Monitoirng | plan | 30000 | Firm | SQC | Post | Sep-13 | N/A | Sep-13( No Obj. for ToR) | Sep | Sep | Oct-13 | N/A | N/A | Nov-13 | N/A | Jan-14 | Dec 2015
actual
| Total for subcomponent 2.2 |  | plan | 210000
actual
| TOTAL, Component 2 |  | plan | 416000
actual
Component 3. Project Management
3.1. Project Management, Coordination Group under the Ministry of Health of Tajikistan
31 | MOH/RBF/LIC/014/001 | Project Officer | plan | 85000 | ind | IC | Prior | Sep-13 | N/A | Sep-13( No Obj. for ToR) | N/A | N/A | Oct-13 | Nov-13 | N/A | Nov-13 | Dec-13 | Jan 2014 | Jan 2019
actual
32 | MOH/RBF/LIC/014/002 | Assistant to Coordinator | plan | 58000 | ind | IC | Post | Sep-13 | N/A | Sep-13( No Obj. for ToR) | N/A | N/A | Oct-13 | N/A | N/A | Nov-13 | N/A | Jan 2014 | Jan 2019
actual
33 | MOH/RBF/LIC/014/003 | Financial Management Consultant | plan | 80000 | ind | IC | Prior | Sep-13 | N/A | Sep-13( No Obj. for ToR) | N/A | N/A | Oct-13 | Nov-13 | N/A | Nov-13 | Dec-13 | Jan 2014 | Jan 2019
actual
34 | MOH/RBF/LIC/014/004 | Disbursement Consultant | plan | 58000 | ind | IC | Post | Sep-13 | N/A | Sep-13( No Obj. for ToR) | N/A | N/A | Oct-13 | N/A | N/A | Nov-13 | N/A | Jan 2014 | Jan 2019
actual
35 | MOH/RBF/LIC/014/005 | Procurement Consultant | plan | 80000 | ind | IC | Prior | Sep-13 | N/A | Sep-13( No Obj. for ToR) | N/A | N/A | Oct-13 | Nov-13 | N/A | Nov-13 | Dec-13 | Jan 2014 | Jan 2019
actual
37 | MOH/RBF/IC/014/007 | Office Manager | plan | 58000 | ind | IC | Post | Sep-13 | N/A | Sep-13( No Obj. for ToR) | N/A | N/A | Oct-13 | N/A | N/A | Nov-13 | N/A | Jan 2014 | Jan 2019
actual
38 | MOH/RBF/LIC/014/008 | IT Specialist-1 | plan | 48000 | ind | IC | Post | Sep-13 | N/A | Sep-13( No Obj. for ToR) | N/A | N/A | Oct-13 | N/A | N/A | Nov-13 | N/A | Jan 2014 | Jan 2019
actual
39 | MOH/RBF/LIC/014/009 | IT Specialist-2 | plan | 48000 | ind | IC | Post | Sep-13 | N/A | Sep-13( No Obj. for ToR) | N/A | N/A | Oct-13 | N/A | N/A | Nov-13 | N/A | Jan 2014 | Jan 2019
actual
40 | MOH/RBF/LIC/014/010 | Translator/Interpreter Eng/Rus-1 | plan | 48000 | ind | IC | Post | Sep-13 | N/A | Sep-13( No Obj. for ToR) | N/A | N/A | Oct-13 | N/A | N/A | Nov-13 | N/A | Jan 2014 | Jan 2019
actual
41 | MOH/RBF/LIC/014/011 | Translator/Interpreter Eng/Rus--2 | plan | 48000 | ind | IC | Post | Sep-13 | N/A | Sep-13( No Obj. for ToR) | N/A | N/A | Oct-13 | N/A | N/A | Nov-13 | N/A | Jan 2014 | Jan 2019
actual
42 | MOH/RBF/LIC/014/012 | Translator/Interpreter Rus/Tajik | plan | 38000 | ind | IC | Post | Sep-13 | N/A | Sep-13( No Obj. for ToR) | N/A | N/A | Oct-13 | N/A | N/A | Nov-13 | N/A | Jan 2014 | Jan 2019
actual
43 | MOH/RBF/LIC/014/013 | Legal Consultant | plan | 58000 | ind | IC | Prior | Sep-13 | N/A | Sep-13( No Obj. for ToR) | N/A | N/A | Oct-13 | Nov-13 | N/A | Nov-13 | Dec-13 | Jan 2014 | Jan 2019
actual
44 | MOH/RBF/LIC/014/014 | Project M&E Consultant | plan | 85000 | ind | IC | Prior | Sep-13 | N/A | Sep-13( No Obj. for ToR) | N/A | N/A | Oct-13 | Nov-13 | N/A | Nov-13 | Dec-13 | Jan 2014 | Jan 2019
actual
45 | MOH/RBF/LIC/014/015 | Consultant on health economic and financial issues | plan | 85000 | ind | IC | Prior | Sep-13 | N/A | Sep-13( No Obj. for ToR) | N/A | N/A | Oct-13 | Nov-13 | N/A | Nov-13 | Dec-13 | Jan 2014 | Jan 2019
actual
46 | MOH/RBF/LIC/014/016 | RBF HMIS Consultant | plan | 85000 | ind | IC | Prior | Sep-13 | N/A | Sep-13( No Obj. for ToR) | N/A | N/A | Oct-13 | Nov-13 | N/A | Nov-13 | Dec-13 | Jan 2014 | Jan 2019
actual
47 | MOH/RBF/LIC/014/017 | Project PubIC Relations Consultant under MoH | plan | 58000 | ind | IC | Post | Sep-13 | N/A | Sep-13( No Obj. for ToR) | N/A | N/A | Oct-13 | N/A | N/A | Nov-13 | N/A | Jan 2014 | Jan 2019
actual
48 | MOH/RBF/LIC/014/018 | Office Administrator in Khatlon Oblast | plan | 34000 | ind | IC | Post | Sep-13 | N/A | Sep-13( No Obj. for ToR) | N/A | N/A | Oct-13 | N/A | N/A | Nov-13 | N/A | Jan 2014 | Jan 2019
actual
49 | MOH/RBF/LIC/014/019 | Office Administrator in Sughd Oblast | plan | 34000 | ind | IC | Post | Sep-13 | N/A | Sep-13( No Obj. for ToR) | N/A | N/A | Oct-13 | N/A | N/A | Nov-13 | N/A | Jan 2014 | Jan 2019
actual
50 | MOH/RBF/LIC/014/020 | Project Officer/Coordinator in Sughd Oblast | plan | 48000 | ind | IC | Post | Sep-13 | N/A | Sep-13( No Obj. for ToR) | N/A | N/A | Oct-13 | N/A | N/A | Nov-13 | N/A | Jan 2014 | Jan 2019
actual
51 | MOH/RBF/LIC/014/021 | Project officer /Coordinator in Khatlon Oblast | plan | 36000 | ind | IC | Post | Sep-14 | N/A | Sep-14( No Obj. for ToR) | N/A | N/A | Oct-14 | N/A | N/A | Nov-14 | N/A | Jan 2015 | Jan 2019
actual
52 | MOH/RBF/LIC/014/022 | Project PubIC Relations Consultant in Sughd Oblast | plan | 38000 | ind | IC | Post | Sep-13 | N/A | Sep-13( No Obj. for ToR) | N/A | N/A | Oct-13 | N/A | N/A | Nov-13 | N/A | Jan 2014 | Jan 2019
actual
53 | MOH/RBF/LIC/014/023 | Project PubIC Relations Consultant in Khatlon Oblast | plan | 38000 | ind | IC | Post | Sep-13 | N/A | Sep-13( No Obj. for ToR) | N/A | N/A | Oct-13 | N/A | N/A | Nov-13 | N/A | Jan 2014 | Jan 2019
actual
54 | as defined by the Investment Committee | Project Audit 2014-2018 | plan | 140000 | firm | LCS | Prior | Selection and contract signing will be performed by the State Investment Committee | [10 empty] | May-14-19
actual
| Total, Component 3 |  | plan | 1388000
actual
| Total, Services |  | plan | 3723500
actual
Notes: * - Every Consultancy ToR is sibject to the WB Preview (IC-Individual Consultant, LCS- Least Cost Selection, QCBS - Quality and Cost-based Selection) ** - Following thresholds are used under the Grant No : 1)All contract with the cost over USD 100 000 for the firms; 2) First Contract for SQC; 3) All contracts costing over USD 50 000 USD for thу Individual Consultant; 4) All Contracts are from the single source ***- Selected procurement method has been agreed with the WB.

## Training
Republic of Tajikistan
MINISTRY OF HEALTH
Grant Project " Health Services Improvement Project in Tajikistan (Grant No.)
TRAINING PLAN (INCL. WORKSHOPS AND SEMINARS)
(Date of PT: ____________; Update No.____; Date of WB NOL: ___________ 2013)
№ | Description | Plan vs. Actual | WB Review (Prior/ Post) | Estimated Cost (US$ equivalent) | Sending of the training budget, program and participants' list for Bank's review and NOL | Bank's NOL to conduct training | Start of training | Training completion
Component 1. Result-based Financing
1 | ТоТ for the Oblast trainers training /re-training (these trainers will conduct Modules No.No 2-4 under the RBF Component and participate in Oblast Payment Handling Commissions) | Plan | Training program & budget is prior review | 24000
Actual
2 | Contract award to the PHC providers under the RBF Program (i)(i) Regulatory aspects of the Agreement; (ii) Statistic analysis of the previous period and conclusions (problem pyramid, focus on the basic services and recommended managerial decisions); (iii) Development of the indicators and scheduled scope of services; (iv) Conditions of the RBF Program involvement; (v) Agreement on the RBF SW service cost; (vi) Agreement preparation and conclusion | Plan | Training program & budget is prior review | 35000
Actual
3 | Health sraff training to maintain basic accounting of the PHC services provided and submit reports for the RBF payments: Workshop on keeping baseline accounting: (i) filling in of the Logbook; (ii) development of the staff individual report for calculating RBF disbursements and data verification; (iii) report submission procedures to the RHC Director and baseline data storage; (iv) Checking of the staff individual reports in a health facility | Plan | Training program & budget is prior review | 115000
Actual
4 | Training for Managers on RBF HIS web system usage: Data transfer to the RBF HMIS Web-system: (i) Training on equipment usage and RBF HIS; (ii) Digitization in the system of the PHC Service Agreement (tariffication, staff, identification and scanning and upload of the Provider Agreement with the MoH/OHD); (iii) Digitization of the staff individual reports in the RBF Web-system (transfer to the electronic form on the web-site, hard copy scanning and server upload); (iv) Facility MIS Invoicing (staff and facility bonuses) and disbursement history tracking in the RBF Web-system; (v) Receipt of the recommendation on the RBF MIS improvement (data collection, interface and software functions) | Plan | Training program & budget is prior review | 96000
Actual
5 | Verification, quality assessment, RBF ivoice payments: Verification on the Rayon PHC Department level (reconcilement methodology of the electronic reports and scanned versions on the server), data approval in the system and directing RBF account to the Oblast/MoH level | Plan | Training program & budget is prior review | 12000
Actual
6 | Data and accounts verification on the oblast level (i) Work with the accounting web-system and RBF MIS payments; (ii) Data tracking (Primary data collection methodology and their digitization into the RBF MIS system, for process knowledge of the modules 2-4); (iii) Primary data verification methodology (Health staff registers, staff individual reports, RBF MIS data); (iv) Approval for settlement of accounts in the RBF MIS web-system; (v) Account divergence and re-calculation | Plan | Training program & budget is prior review | 38500
Actual
7 | Concordance of the fiscal quarter results, accounts approval (disbursements, disbursement denial, reimbursement requirements and control reinforcement following the accounts processing results, quarterly, 4 qrts x 4 years x 2 Oblasts) | Plan | Training program & budget is prior review | 30000
Actual
8 | Semiannual General Workshops on PHC services quality assessment | Plan | Training program & budget is prior review | 18000
Actual
9 | Study tours to the countries practicing RBF | Plan | Training program & budget is prior review | 375000
Actual
10 | RBF Web MIS Training for the RBF Unit staff (payment handling functions, bonus accrual and penalty deduction, Treasury entry) | Plan | Training program & budget is prior review | 22000
Actual
11 | RBF Outcomes General conferences: Submission of the RBF Program implementation outcomes and recommendations reconcilement, including: (i) Oblast Commissions activity outcomes; (ii) Independent audit outcomes (UNICEF); (iii) Development of recommendations and RBF indicators concordance; (iv) Concurrence of tasks for improving data collection mechanism (data tracking); (v) Concurrence of tasks for improving data verification mechanism; (vi) Concurrence of tasks on financial transfer within the treasury; (vii) Concurrence of tasks on debt replenishment and terms of involvement in the RBF Program and in the agreement with providers; (viii) Needs to develop national and sub-sectoral programs (coupled with RBF) having an impact on the PHC services quality improvement in the context of the general health policy | Plan | Training program & budget is prior review | 55000
Actual
Total for Component 1. |  | Plan |  | 820500
Actual
Component 2.
12 | Family Medicine Re-training (Gonchi & Mastcho, Kabodiyon, Rumi, Yavan) | Plan | Training program & budget is prior review | 800000
Actual
13 | Strengthening of the trainers capacity of the Clinical Training FM Centers | Plan | Training program & budget is prior review | 20000
Actual
14 | Study tour for FM trainers | Plan | Training program & budget is prior review | 80000
Actual
15 | Continuous PHC health staff training | Plan | Training program & budget is prior review | 142000
Actual
16 | Postgraduate training for the FM doctors and nurses (trained 5 years ago) | Plan | Training program & budget is prior review | 85000
Actual
| TOTAL for Component 2. | Plan |  | 1127000
Actual
Component 3. Project Management
17 | Capacity Improvement Study tours of the MoH, Coordination Group, Oblast Health Department (Flagship training courses, training for Coordinators and Coordination Group's specialists involved into the Project Management, including MIS, IT, PR, M&E, Family Medicine, Procurement & Financial Management) | Plan | Training program & budget is prior review | 293450
Actual
18 | Workshops on project implementation on the Oblast and rayon level | Plan | Training program & budget is prior review | 26000
Actual
19 | Briefing for public (PR, publication in mass media) | Plan | Training program & budget is prior review | 30000
Actual
| TOTAL for Component 3. |  |  | 349450
Actual
TOTAL, Training |  | Planned |  | 2296950
Actual

## Operating_costs_MOHCG
Republic of Tajikistan
MINISTRY OF HEALTH
Grant Project " Health Services Improvement Project in Tajikistan (Grant No.)
OPERATING COSTS
(Date of OC: ___________; Update No.___; Date of WB NOL: ___________ 2013)
Recurrent costs/ operating costs of MOH's CG under Project
Item | Description of expenditures | Per month | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 (6 month) | TOTAL
1 | DHL services | 200 | 2400 | 2400 | 2400 | 2400 | 2400 | 1200 | 13200
2 | Advertisment | 100 | 1200 | 1200 | 1200 | 1200 | 1200 | 0 | 6000
4 | Installation/maintenance telephone | 300 | 3600 | 3600 | 3600 | 3600 | 3600 | 0 | 18000
5 | E-mail; Internet | 700 | 8400 | 8400 | 8400 | 8400 | 8400 | 4200 | 46200
6 | Fuel (benzine, diesel, gasoline) | 1200 | 14400 | 14400 | 14400 | 14400 | 14400 | 7200 | 79200
7 | Stationary/housewares | 600 | 7200 | 7200 | 7200 | 7200 | 7200 | 3600 | 39600
8 | Repair & maintenance cars/Insurance/tax | 500 | 6000 | 6000 | 6000 | 6000 | 6000 | 1500 | 31500
9 | Repair & maintenance office equipment | 200 | 2400 | 2400 | 2400 | 2400 | 2400 | 1200 | 13200
10 | Office space repair * | 200 | 18000 | 2400 | 2400 | 2400 | 2400 | 1200 | 28800
11 | Local travel Expenses | 1000 | 12000 | 12000 | 12000 | 12000 | 12000 | 3000 | 63000
12 | Other unexpected costs | 300 | 3600 | 3600 | 3600 | 3600 | 3600 | 1800 | 19800
13 | Bank charges | 1000 | 12000 | 12000 | 12000 | 12000 | 12000 | 3000 | 63000
14 | Driver(3) | 450 | 16200 | 16200 | 16200 | 16200 | 16200 | 5400 | 86400
15 | Cleaner(2) | 100 | 1200 | 2400 | 2400 | 2400 | 2400 | 1200 | 9600
16 | Quard(3) | 150 | 1800 | 5400 | 5400 | 5400 | 5400 | 2700 | 32400
Total |  | 7000 | 110400 | 94200 | 94200 | 94200 | 94200 | 34500 | 549900
*Additional office space for local consultants and RBF consultants

## Operating_costs_RBF_consult
Republic of Tajikistan
MINISTRY OF HEALTH
Grant Project " Health Services Improvement Project in Tajikistan (Grant No.)
OPERATING COSTS
(Date of OC: ___________; Update No.___; Date of WB NOL: ___________ 2013)
Recurrent costs/ operating costs of RBF consultants MoH under Project
Item | Description of expenditures | Per month | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 (6 month) | TOTAL
1 | Internet | 400 | 4800 | 4800 | 4800 | 4800 | 4800 | 2400 | 26400
2 | Telephone | 100 | 1200 | 1200 | 1200 | 1200 | 1200 | 600 | 6600
3 | Fuel (benzine, diesel) | 400 | 4800 | 4800 | 4800 | 4800 | 4800 | 2400 | 26400
4 | Stationary/housewares | 100 | 1200 | 1200 | 1200 | 1200 | 1200 | 600 | 6600
5 | Repair & maintenance cars/insurance/tax | 100 | 1200 | 1200 | 1200 | 1200 | 1200 | 600 | 6600
6 | Repair & maintenance office equipment | 100 | 1200 | 1200 | 1200 | 1200 | 1200 | 600 | 6600
7 | Local travel Expenses | 200 | 2400 | 2400 | 2400 | 2400 | 2400 | 1200 | 13200
Total |  | 1400 | 16800 | 16800 | 16800 | 16800 | 16800 | 8400 | 92400

## Operating_costs_Sugd
Recurrent costs/ operating costs of Sughd field office under Project
Item | Description of expenditures | Per month | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 (6 month) | TOTAL
| Office space rent | The office space will be provided by Oblast Health Department
1 | Telephone | 50 | 600 | 600 | 600 | 600 | 600 | 350 | 3350
2 | E-mail; Internet | 450 | 5400 | 5400 | 5400 | 5400 | 5400 | 2700 | 29700
3 | Fuel (benzine, diesel) | 450 | 5400 | 5400 | 5400 | 5400 | 5400 | 2700 | 29700
4 | Stationary/housewares | 200 | 2400 | 2400 | 2400 | 2400 | 2400 | 1200 | 13200
5 | Repair & maintenance cars | 150 | 1800 | 1800 | 1800 | 1800 | 1800 | 900 | 9900
6 | Repair & maintenance office equipment | 100 | 1200 | 1200 | 1200 | 1200 | 1200 | 600 | 6600
7 | Local travel Expenses | 300 | 3600 | 3600 | 3600 | 3600 | 3600 | 1800 | 19800
8 | Driver(2) | 400 | 9600 | 9600 | 9600 | 9600 | 9600 | 4800 | 52800
9 | Cleaner (2) | 100 | 2400 | 2400 | 2400 | 2400 | 2400 | 600 | 12600
10
Total |  | 2200 | 32400 | 32400 | 32400 | 32400 | 32400 | 15650 | 177650

## Operating_costs_Khatlon
Recurrent costs/ operating costs of Khatlon field office under Project
Item | Description of expenditures | Per month | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 (6 month) | TOTAL
| Office space rent | The office space will be provided by Oblast Health Department*
1 | Telephone | 50 | 600 | 600 | 600 | 600 | 600 | 300 | 3300
2 | E-mail; Internet | 450 | 5400 | 5400 | 5400 | 5400 | 5400 | 2700 | 29700
3 | Fuel (benzine, diesel) | 450 | 5400 | 5400 | 5400 | 5400 | 5400 | 2700 | 29700
4 | Stationary/housewares | 200 | 2400 | 2400 | 2400 | 2400 | 2400 | 1200 | 13200
5 | Repair & maintenance cars | 150 | 1800 | 1800 | 1800 | 1800 | 1800 | 900 | 9900
6 | Repair & maintenance office equipment | 100 | 1200 | 1200 | 1200 | 1200 | 1200 | 600 | 6600
7 | Local travel Expenses | 300 | 3600 | 3600 | 3600 | 3600 | 3600 | 1800 | 19800
8 | Driver (2) | 400 | 9600 | 9600 | 9600 | 9600 | 9600 | 4800 | 52800
9 | Cleaner(2) | 100 | 2400 | 2400 | 2400 | 2400 | 2400 | 600 | 12600
Total |  | 2200 | 32400 | 32400 | 32400 | 32400 | 32400 | 15600 | 177600

## Total_opearting_costs
Total operating costs under HSIP project
The total amount of operating costs under HSIP
Item | Receiver | Operating costs
1 | Ministry of Health's Coordination Group operating cost | 549900
2 | Consultants in the MOH ( RBFand IDF) | 92400
3 | Office in Sughd | 177650
4 | Office in Khatlon | 177600
The total amount of operating costs under Project |  | 997550