## General
Procurement Plan
I. General
1. | Project Information
| Project Name: | Public Finance Modernization Project
| Country: | Republic of Yemen
| Project ID: | P117363
| Loan/Credit/Grant Numbers: | H8470-RY
2. | Bank's approval date of Procurement Plan | Original: | 2013-03-10
Revision 1:
Revision 2:
3. | Date of General Procurement Notice
II. Goods, Work and Non-Consulting Services Thresholds
1. | Prior Review Threshold. Procurement Decisions subject to Prior Review by the Bank will be as follows
1a. | Procurement Category | Prior Review Threshold (USD) | Comments
| Goods | ≥500,000 | All Contracts+ first two contracts less than the threshold
| Works | NA | NA
| Non-Consultant Services | ≥ 20,000 | All contracts
| Direct contract |  | All contracts
1b. | Procurement Method | Procurement Method Threshold (USD) | Comments
1 | ICB and LIB (Goods) | >= 500,000 | All Contracts
2 - a | NCB (Goods) | < 500,000
2 - b | Shopping (Goods) | <50,000
2 - c | Direct Contracting
| ICB (Works) | NA | NA
| NCB (Works) | NA | NA
NCB (Non-Consultant Services)
Include all methods authorized by the loan agreement
2. | Prequalification. Bidders for bid ( …………………...) shall be prequalified in accordance with the provisions of paragraphs 2.9 and 2.10 of the Guidelines.
3. | Proposed Procedures for CDD Components NA
4. | Reference to (if any) Project Operational/Procurement Manual: under approval process
5. | Any Other Special Procurement Arrangements: [including advance procurement and retroactive financing, if applicable
6. | Procurement Packages with Methods and Time Schedule: See attached "Goods and Works" sheet
III. Selection of Consultants
1. | Prior Review Threshold: Selection decisions subject to Prior Review by Bank as stated in Appendix 1 to the Guidelines Selection and Employment of Consultants:
1a. | Procurement Category | Prior Review Threshold (USD) | Comments
| Consulting Firms (Competitive) | > = 200,000 | All contracts
Consulting Firms (QBS)
| Individual Consultants (Competitive) | > 50,000
| Individual Consultants (Sole Source) |  | All SS contracts
| Consulting Firms (Sole Source) |  | All SS contracts
1b. | Procurement Method | Procurement Method Threshold (USD) | Comments
1 | Quality and Cost based Selection (QCBS) | > = 200,000
2 - a | Quality Based Selection (QBS ) | <200,000
2 - b | Selection Under a Fixed Budget (SFB)
2 - c | Least Cost Selection ( LCS ) | <200,000
2 - d | Consultant Qualification Selection ( CQS ) | < 200,000
2 - e | Single Source Selection | <100,000
2 - f | Procedure Paragraph 5.2 section V Selection of Individual Consultant (IC )
Procedure Paragraph 5.3 section V Selection of Individual Consultant ( IC )
2 - g | Sole Source Procedures For Selection of Individual Consultant ( IC )
Include all methods authorized by the Grant agreement
2. | Note: procurement following DC and SS will be under taken only if these are agreed to by IDA based on justification from the project, other wise competitive method will be followed.
| Note: OPCPR list of ceilings can be found here: | http://go.worldbank.org/MKXO98RY40
3. | Any Other Special Selection Arrangements: [including advance procurement and retroactive financing, if applicable]
4. | Consultancy Assignments with Selection Methods and Time Schedule: See attached "Consulting Services" sheet
IV. Implementing Agency Capacity Building Activities with Time Schedule: See attached "Capacity Building" sheet

## Goods & Works
Procurement Plan for Goods/Works/Non-Consulting Services
|  |  | ** Applicable in case of Bank's prior review | [6 empty] | Prequalification
SL No. | Reference No. | Package/ Reference No. |  | Package/ Reference No. | Description of Goods/ Works | Goods/ Works/ NCS | Review by Bank (Prior/ Post) | Method of Selection | Domestic Preference (yes/no) | Prequalification (yes/no) | No Objection from Bank for Draft Prequalification documents (Date)** | No Objection from Bank for Evaluation of Prequalification Application (Date)** | Preparation of Bid Document (Date) | Bank’s No Objection to Bidding Document (Date)** | Bid Invitation (Date) | Bid Closing (Date) | Bid Opening (Date) | Contract Award Decision (Date) | Bank’s No Objection to Bid Evaluation Report and Contract Award (Date)** | Contract Signed (Date) | Contract Value | Contract Currency | Contract No. | Name, City, and Country of Contractor (incl. Zip Code if US) | Completion of Contract (Date) | Expenditure incurred to Date | Comments
1 | 01/C1.1/G/NCB/PFMP-AF/13 | C1.1 | Planned |  | Equipments for Reveneus Budget and PSFS Department | Goods | Post | NCB |  |  |  |  | 2013-08-01 | NA | 2013-08-08 | 2013-09-07 | 2013-09-07 | 2013-09-17 | NA | 2013-10-01 |  |  |  |  | 2013-10-31
|  |  | Revised | [9 empty] | 2014-10-22 | NA | 2014-10-29 | 2014-11-28 | 2014-11-28 | 2014-12-19 | NA | 2015-01-02 |  |  |  |  | 2015-02-01
Actual
2 | 02/C1.1/G/NS/PFMP-AF/13 | C1.1 | Planned |  | Equipments for Budget section | Goods | Post | NS |  |  |  |  | 2013-10-07 | NA | 2013-10-14 | 2013-11-13 | 2013-11-13 | 2013-11-20 | NA | 2013-12-04 |  |  |  |  | 2014-01-03
|  |  | Revised | [9 empty] | 2015-03-01 |  | 2015-03-08 | 2015-03-22 | 2015-03-22 | 2015-04-05 |  | 2015-04-19 |  |  |  |  | 2015-05-19
Actual
| 03/C1.4/G/NCB/PFMP-AF/13 | C1.4 | Planned |  | Supplying PDAs and other equipments for SNA Department | Goods | Post | NCB |  |  |  |  | 2013-08-15 | NA | 2013-08-22 | 2013-09-21 | 2013-09-21 | 2013-10-05 | NA | 2013-10-19 |  |  |  |  | 2013-12-18
3 |  |  | Revised | [9 empty] | 2014-06-15 | NA | 2014-06-22 | 2014-07-22 | 2014-07-22 | 2014-08-05 | NA | 2014-08-19
| 03/C1.4A/G/NCB/PFMP-AF/13 | C1.4A | Revised |  | Supply PDAs and other Equipment |  | Post | NCB |  |  |  |  | 2014-08-15 | NA | 2014-08-22 | 2014-09-21 | 2014-09-21 | 2014-10-05 | NA | 2014-10-19 |  |  |  |  | 2014-12-18
|  |  | Actual | [9 empty] | 2014-06-25 | NA | 2014-07-09 | 2014-08-18 | 2014-08-18
| 03/C1.4B/G/NS/PFMP-AF/13 | C1.4B | Revised |  | Furnitures |  | Post | NS |  |  |  |  | 2014-10-01 | NA | 2014-10-08 | 2014-10-22 | 2014-10-22 | 2014-11-05 | NA | 2014-11-19 |  |  |  |  | 2015-01-03
Actual
4 | 04/C1.5/G/NCB/PFMP-AF/13 | C1.5 | Planned |  | Equipments for Economic Sector | Goods | Post | NCB |  |  |  |  | 2013-09-01 | NA | 2013-09-08 | 2013-10-08 | 2013-10-08 | 2013-10-18 | NA | 2013-11-01 |  |  |  |  | 2013-12-01
|  |  | Revised | [9 empty] | 2014-10-01 | NA | 2014-10-08 | 2014-11-07 | 2014-11-07 | 2014-11-17 | NA | 2014-12-01 |  |  |  |  | 2014-12-31
Actual
Total of C1
5 | 05/C2.1/G/ICB/PFMP-AF/13 | C2.1 | Planned |  | Roll-out of AFMIS to CBY (20 branches)+CBY HQ Turn-key vendor ( Procure hardware build infrastructure) | Goods | Prior | ICB |  |  |  |  | 2013-06-15 | 2013-06-22 | 2013-06-29 | 2013-08-13 | 2013-08-13 | 2013-09-03 | 2013-09-17 | 2013-10-01 |  |  |  |  | 2013-12-30 |  | central Bank need to facilitate this activity
Revised
Actual
6 | 06/C2.1/G/ICB/PFMP-AF/13 | C2.1 | Planned |  | Disaster Recovery Site | Goods | Prior | ICB |  |  |  |  | 2013-09-15 | 2013-09-22 | 2013-09-29 | 2013-11-13 | 2013-11-13 | 2013-12-04 | 2013-12-18 | 2014-01-01 |  |  |  |  | 2014-04-01 |  | هذا النشاط يفترض أن ينفذ بعد الانتهاء من مركز البيانات الرئيسي والاحتياطي بحسب توصية الشركة الاستشارية مع الأخذ بعين الاعتبار أن هذا المبلغ لن يكون كافي بحسب التكلفة المقدمة في مناقصة المركز الرئيسي
|  |  | Revised | [9 empty] | 2014-12-15 | 2014-12-22 | 2014-12-29 | 2015-02-12 | 2015-02-12 | 2015-03-05 | 2015-03-19 | 2015-04-02 |  |  |  |  | 2015-09-29
Actual
7 | 07/C2.1/G/NCB/PFMP-AF/14 | C2.1 | Planned |  | Rolling AFMIS to the left out of 3 Governorates | Goods | Post | NCB |  |  |  |  | 2014-04-01 | NA | 2014-04-08 | 2014-05-08 | 2014-05-08 | 2014-05-18 | NA | 2014-06-01 |  |  |  |  | 2014-07-01
|  |  | Revised | [9 empty] | 2015-03-25 |  | 2015-04-01 | 2015-05-01 | 2015-05-01 | 2015-05-11 | NA | 2015-05-25 |  |  |  |  | 2015-06-24
Actual
8 | 08/C2.1/NCS/DC/PFMP-AF/14 | C2.1 | Planned |  | Telecommunication fees for AFMIS ( General Corporation for Telecommunication 2014) | NCS | Prior | DC |  |  |  |  | NA | NA | NA | NA | NA | NA | 2013-12-01 | 2014-01-01 |  |  |  |  | 2014-12-31
|  |  | Revised | [9 empty] | 2015-03-19: 2014-07-01; 2015-04-02: 2014-08-01 |  |  |  |  | 2015-07-31
|  |  | Actual | [9 empty] | 2015-03-19: 2014-06-25; 2015-04-02: 2014-07-07 |  |  |  |  | 2015-07-31
9 | 09/C2.1/NCS/DC/PFMP-AF/15 | C2.1 | Planned |  | Telecommunication fees for AFMIS ( General Corporation for Telecommunication 2015) | NCS | Prior | DC |  |  |  |  | NA | NA | NA | NA | NA | NA | 2014-12-01 | 2015-01-01 |  |  |  |  | 2015-12-31
|  |  | Revised | [9 empty] | 2015-03-19: 2015-07-01; 2015-04-02: 2015-08-01 |  |  |  |  | 2016-07-30
Actual
10 | 10/C2.1/NCS/DC/PFMP-AF/14 | C2.1 | Planned |  | Telecommuniacation fees for rolling AFMIS to CBY | NCS | Prior | DC |  |  |  |  | NA | NA | NA | NA | NA | NA | 2013-12-01 | 2014-01-01 |  |  |  |  | 2015-12-31 |  | central Bank need to facilitate this activity
Revised
Actual
Total of C2
11 | 11/C3.2/G/NCB/PFMP-AF/13 | C3.2 | Planned |  | Equipments for the FI (Lot B) | Goods | Post | NCB |  |  |  |  | 2013-10-01 | NA | 2013-10-08 | 2013-11-07 | 2013-11-07 | 2013-11-17 | NA | 2013-12-01 |  |  |  |  | 2013-12-31
| 11/C3.2B1/G/NCB/PFMP-AF/14 | LOT-B1 | Revised |  | Supply additional office equipment |  | Post | NCB |  |  |  |  | 2014-08-11 | NA | 2014-08-25 | 2014-09-24 | 2014-09-24 | 2014-10-22 | NA | 2014-11-05 |  |  |  |  | 2015-03-05
Actual
| 11/C3.2.B2/G/NS/PFMP-AF/14 | LOT-B2 | Revised |  | Supply office furnitures |  | Post | NS |  |  |  |  | 2014-08-11 | NA | 2014-08-25 | 2014-09-08 | 2014-09-08 | 2014-10-06 | NA | 2014-10-20 |  |  |  |  | 2015-02-17
Actual
12 | 12/C3.3/G/NS/PFMP-AF/13 | C3.3 | Planned |  | Supply of equipment for the web portal | Goods | Post | NS |  |  |  |  | 2013-11-10 | NA | 2013-11-17 | 2013-12-01 | 2013-12-01 | 2013-12-08 | NA | 2013-12-15 |  |  |  |  | 2014-01-14
|  |  | Revised | [9 empty] | 2015-01-01 | NA | 2015-01-08 | 2015-01-22 | 2015-01-22 | 2015-01-29 | NA | 2015-02-05 |  |  |  |  | 11-Jan-15
Actual
Total of C3
|  |  | Planned |  | Installlation Financial Software | Goods | prior | SSS
| 13/C5-OP/G/NS/PFMP-AF/13 |  | Revised | [20 empty] | CEW
|  |  | Actual | [9 empty] | 2014-12-22: 2013-07-21; 2015-04-02: 2013-02-25 | 6000
| Grand Total | [19 empty] | 0
Formulas:
Bid Invitation (Date) = [Preparation of Bid Document (Date)]+7
Bid Closing (Date) = [Bid Invitation (Date)]+30
Bid Opening (Date) = [Bid Closing (Date)]
Contract Award Decision (Date) = [Bid Opening (Date)]+10
Contract Signed (Date) = [Contract Award Decision (Date)]+14
Completion of Contract (Date) = [Contract Signed (Date)]+30

## Consultant Services
Procurement Plan for Consultant Services
** Applicable in case of Bank's prior review | [10 empty] | In some contracts, one or more of these approvals may be contained in one Bank communication.
SL No. | Reference No. |  | SL No. | Description of Services | Review by Bank (Prior/ Post) | Type of Consultant (Firm/ Individual) | Method of Selection | Advertising for Short listing (Date) | TOR/Shortlist to be Finalized (Date) | RFP Final Draft to be forwarded to the Bank (Date) | No Objection from Bank for TOR (Date)** | No Objection from Bank for Shortlist (Date)** | No Objection from Bank for Final RFP (Date)** | RFP Issued (Date) | Proposal Submission Deadline (Date) | No Objection by the Bank to the Technical Evaluation Report (Date)** | No Objection by the Bank (Technical/ #Combined/ Draft Contract/ Final Contract) (Date)** | Contract Award Date | Contract Signed (Date) | Contract Value | Contract Currency | Contract No. | Name, City, and Country of Contractor (incl. Zip Code if US) | Contract Value | Contract Currency | Name, City, and Country of Contractor (incl. Zip Code if US) | Services Completion (Date) | Expenses Incurred to Date | Comments
1 | O1/C1.4/CS/IC/PFMP-AF/13 | Planned | C1.4 | TA to develop methodologies and update use of manuals and systems to apply the new system | Post | IC | CQS | 2013-12-01 | 2013-12-31 | NA | NA | NA | NA | NA | 2014-01-14 | NA | NA | 2014-01-28 | 2014-02-04
|  | Revised | [5 empty] | 2015-01-01 | 2015-01-31 | NA | NA | NA | NA | NA | 2015-02-14 | NA | NA | 2015-02-28 | 2015-03-07
Actual
2 | O2/C2.1-A/CS/F/PFMP-AF/13 | Planned | C2.1-A | Inspection for the ICB Goods No. (4/C2.1-A/G/ICB/PFMP/13) | Post | CF | LCS | 2013-06-15 | 2013-07-15 | NA | NA | NA | NA | NA | 2013-07-29 | NA | NA | 2013-08-12 | 2013-08-19 | [9 empty] | THIS ACTIVITY COULD BE DONE BY TECHNICAL TEAM
|  | Revised | [5 empty] | 2014-06-01 | 2014-07-01 | NA | NA | NA | NA | NA | 2014-07-15 | NA | NA | 2014-07-29 | 2014-08-05
Actual
3 | O3/C2.1/CS/IC/PFMP-AF/13 | Planned | C2.1 | Developing AFMIS | Post | IC | CQS | 2013-07-01 | 2013-07-31 | NA | NA | NA | NA | NA | 2013-08-14 | NA | NA | 2013-08-28 | 2013-09-04 | [9 empty] | central Bank need to facilitate this activity
Revised
Actual
4 | O4/C2.1-B/CS/F/PFMP-AF/13 | Planned | C2.1-B | Inspection for the ICB Goods No. (05/C2.1/G/ICB/PFMP-AF/13) | Post | CF | LCS | 2013-08-01 | 2013-08-31 | NA | NA | NA | NA | NA | 2013-09-14 | NA | NA | 2013-09-28 | 2013-10-05 | [9 empty] | THIS ACTIVITY COULD BE DONE BY TECHNICAL TEAM
Revised
Actual
5 | O5/C2.1-C/CS/F/PFMP-AF/13 | Planned | C2.1-C | Inspection for the ICB Goods No. (06/C2.1/G/ICB/PFMP-AF/13) | Post | CF | LCS | 2013-11-01 | 2013-12-01 | NA | NA | NA | NA | NA | 2013-12-15 | NA | NA | 2013-12-29 | 2014-01-05 | [9 empty] | THIS ACTIVITY COULD BE DONE BY TECHNICAL TEAM
|  | Revised | [5 empty] | 2015-02-05 | 2015-03-07 | [5 empty] | 2015-03-21 |  |  | 2015-04-04 | 2015-04-11
Actual
6 | O6/C2.3/CS/IC/PFMP-AF/15 | Planned | C2.3 | System Improvement | Post | IC | CQS | 2015-01-01 | 2015-01-31 | NA | NA | NA | NA | NA | 2015-02-14 | NA | NA | 2015-02-28 | 2015-03-07
Revised
Actual
7 | O7/C3.2/CS/IC/PFMP-AF/14 | Planned | C3.2 | TOT program for FI's trainers | Prior | IC | CQS | 2014-01-01 | 2014-01-31 | 2014-02-07 | 2014-02-14 | 2014-02-14 | 2014-02-14 | 2014-02-21 | 2014-02-14 | 2014-02-21 | 2014-03-07 | 2014-03-14 | 2014-03-21 | [9 empty] | This activity transferred to the capacity building
|  | Revised |  |  | Prior | IC | CQS | [6 empty] | 2014-03-27 | 2014-04-10 | 2014-04-17 | 2014-05-01 | 2014-05-08 | 2014-05-18
Actual
8 | O8/C3.3/CS/IC/PFMP-AF/14 | Planned | C3.3 | TA to review and update Inspection Visits and Compliance Monitoring Guidelines (IVCMG), and train HATC staff on conduct of the inspection visits. | Prior | IC | CQS | 2014-02-01 | 2014-03-03 | 2014-03-10 | 2014-03-17 | 2014-03-17 | 2014-03-17 | 2014-03-24 | 2014-03-17 | 2014-03-24 | 2014-04-07 | 2014-04-14 | 2014-04-21
|  | Revised | [5 empty] | 2014-05-15 | 2014-06-14 | 2014-06-21 | 2014-06-28 | 2014-06-28 | 2014-06-28 | 2014-07-05 | 2014-06-28 | 2014-07-05 | 2014-07-19 | 2014-07-26 | 2014-08-02
Actual
9 | O9/C3.3/CS/IC/PFMP-AF/14 | Planned | C3.3 | TA to design and establish a monitoring mechanism for PMIS. | Prior | IC | CQS | 2014-03-01 | 2014-03-31 | 2014-04-07 | 2014-04-14 | 2014-04-14 | 2014-04-14 | 2014-04-21 | 2014-04-14 | 2014-04-21 | 2014-05-05 | 2014-05-12 | 2014-05-19
|  | Revised | [5 empty] | 2014-06-01 | 2014-07-01 | 2014-07-08 | 2014-07-15 | 2014-07-15 | 2014-07-15 | 2014-07-22 | 2014-07-15 | 2014-07-22 | 2014-08-05 | 2014-08-12 | 2014-08-19
Actual
10 | 10/C3.3/CS/IC/PFMP-AF/13 | Planned | C3.3 | TA to develop the existing HATC Website | Post | IC | CQS | 2013-08-01 | 2013-08-31 | NA | NA | NA | NA | NA | 2013-09-14 | NA | NA | 2013-09-28 | 2013-10-05
|  | Revised |  |  | Post | Firm | CQS | 2013-09-14 |  |  | 28-ِAug-13 |  |  | 2014-03-14 | 2014-04-14 |  |  | 2014-05-12 | 2014-05-12
|  | Actual | [8 empty] | 2013-09-03 | 2013-12-11
11 | 11/C3.3/CS/IC/PFMP-AF/15 | Planned | C3.3 | TA to prepare procurement system assessment for establishing Basline Indicators BLI | Prior | IC | CQS | 2015-01-01 | 2015-01-31 | 2015-02-07 | 2015-02-14 | 2015-02-14 | 2015-02-14 | 2015-02-21 | 2015-02-14 | 2015-02-21 | 2015-03-07 | 2015-03-14 | 2015-03-21
|  | Revised | [5 empty] | 2014-09-12 | 2014-10-12 | 2014-10-19 | 2014-10-26 | 2014-10-26 | 2014-10-26 | 2014-11-02 | 2014-10-26 | 2014-11-02 | 2014-11-16 | 2014-11-23 | 2014-11-30
|  | Actual | [8 empty] | 2014-08-06
12 | 12/C5-OP11/IC/PFMP-AF/13 | Planned | CS-OP-11 | Procurement Assistance | Prior | IC | IC | 2013-09-04 | 2013-06-05 | NA | 2013-06-01 |  | NA | NA | NA | NA |  |  | 2013-07-01 | [7 empty] | 2015-12-31
Revised
|  | Actual | [5 empty] | 2013-09-04 |  |  | 27-May-13 | 01-Jun -13 |  |  |  | 2014-12-08 | 2013-12-19 |  | 2014-01-12 | [7 empty] | 2014-12-31
13 | 13/C1.2-CA /IC/PFMP-AF/13 | Planned | C1.2-CA | Tranlation Contract | Prior | IC | SSS |  |  | NA |  |  | NA | NA | NA | NA |  |  | 2013-12-23 | [7 empty] | 2015-12-31
Revised
Actual
14 | 14/C3.2 /IC/PFMP-AF/13 | Planned | C3.2 | Developing FI website | Post | IC | IC | 2014-02-23 | 2014-03-25 | NA | NA | NA | NA | 2014-04-05 | 2014-04-29 | NA | NA | 2013-05-20 | 2-June14
|  | Revised | [23 empty] | Star for Translation
|  | Actual | [16 empty] | 2013-04-10
15 | 15/C3.2 /IC/PFMP-AF/14 | Planned | C3.2 | Developing an organizational strategy for the FI | Post | IC | CQS | 2013-12-15 | 2014-01-15 | NA | NA | NA | NA | 2014-01-30 | 2014-02-25 | NA | NA | 2014-03-30 | 2014-04-14
|  | Revised | [26 empty] | advertisenment announced for shortlisting, and a consultant was selected, but this activity had been suspended upon request by FI
|  | Actual | [5 empty] | 2013-11-25 |  |  | 11-Oct-13
16 | 16/C5-OP/F/PFMP/-AF/14 | Planned | C5-OP | External Auditor | post | Firm | LCS | 2014-05-12 | 2014-06-01 | NA | 2014-05-07 | 2014-06-06 | NA | NA | NA | NA | 2014-06-22 |  | 2014-06-29
Revised
Actual
| Grand Total | [22 empty] | 0
Formulas:
TOR/Shortlist to be Finalized (Date) = [Advertising for Short listing (Date)]+30
Proposal Submission Deadline (Date) = [TOR/Shortlist to be Finalized (Date)]+14
Proposal Submission Deadline (Date) = [RFP Issued (Date)]+14
Contract Award Date = [Proposal Submission Deadline (Date)]+14
Contract Signed (Date) = [Contract Award Date]+7
No Objection from Bank for TOR (Date)** = [Advertising for Short listing (Date)]-5

## Capacity Building
Capacity Building Activities
SL No. | Component | Expected Outcome/ Activity Description | Start Date | Completion Date | Comments
1 | C1.1 | Training on performance budgeting and budget reform | 2015-01-01 | 2015-06-30
2 | C1.1 | Training on the Revised Unified Accounting Manual | 2015-06-01 | 2015-12-31
3 | C1.1 | Workshop to discuss the First Revised Draft of Unified Accounting Manual | 2014-04-01 | 2015-05-31
4 | C1.2 | National Training Plan for Gov. Accounting Manuals (580 Trainees) | 2015-01-01 | 2015-12-31 | already exist in original PP
5 | C1.2 | TA to revise the Publics Business Enterprises Accounting manual to be in line with the international Accounting standards IFRS | 2015-01-01 | 2015-12-31 | already exist in original PP
6 | C1.3 | Strengthing the Internal Audit System | 2014-09-01 | 2015-12-31
7 | C1.4 | Training on electronic data collection by devices and Piloting | 2014-11-15 | 2015-12-31
8 | C1.4 | Training in Oracle for CSO staff | 2015-01-15 | 2015-12-31
9 | C1.4 | study tour to a country with experience in collecting data for prices index using PDAs for CSO | 2014-08-01 |  | visit to Morrocofor four CSO was done
10 | C1.4 | Training in the Applications and concepts of SNA 2008 | 2014-09-15 | 2015-12-31
11 | C1.4 | Training in developing methodologies and updating manuals and systems | 2014-03-01 | 2014-09-15
12 | C1.4 | Organize a workshop to disseminate for the new system; data producers, users and sources will participate in the workshop |  |  | DONE
13 | C1.4 | Training in compilation of supply and use matrix for CSO | 2015-03-01 | 2015-12-31 | TOR or detail plan to be prepared by CSO
14 | C1.4 | Training in compilation of input-output tables for CSO | 2015-03-01 | 2015-12-31 | TOR or detail plan to be prepared by CSO
15 | C1.4 | Training in compiling price indices producers PPI for CSO | 2014-06-01 | 2015-12-31 | TOR or detail plan to be prepared by CSO
16 | C1.4 | Training in drawing and selecting samples for economic surveys | 2014-11-01 | 2015-05-15 | TOR or detail plan to be prepared by CSO
17 | C1.4 | Study Visit to an experienced country in SNA 2008 | 2014-03-15 |  | visit toTunisia was done
18 | C1.4 | Train in compiling GDP of current and fixed prices by methods of expenditure, production and income | 2015-03-01 | 2015-12-31 | TOR or detail plan to be prepared by CSO
19 | C1.5 | Strengthening the capacity of Ministry of Finance | 2014-08-15 | 2015-12-31
20 | C2.1 | Training AFMIS users for CBY Roll-out |  |  | previous comments regarding CBY
21 | C2.3 | Training MOF staff | 2015-06-01 | 2015-12-31
22 | C3.1 | National training courses for tender committees (Phase Two) | 2015-07-01 | 2015-12-31
23 | C3.2 | Training for FI management and staff | 2015-01-01
| C3.2 | TOT Programme for FI's Trainers | 2014-01-01 | 2015-12-31 | already exist in consultancy
24 | C3.3 | Organisation management, Management development for senior executives ( 4 trainees) | 2014-10-01 | 2015-12-31
25 | C3.3 | HATC Procurement Management Training in public sector | 2014-09-01 | 2015-09-01
26 | C3.3 | HATC Procurement Auditing Training for executives | 2014-09-01 | 2014-12-31
27 | C3.3 | HATC Study tours to a country where there is a similar HATC | 2014-09-01 | 2014-12-31
| C3.3 | Training in Complaint review procdures |  |  | transferred from original grant
28 | C4.2 | Training (2) of COCA's staff in GAO | 2015-01-01 | 2015-11-30
29 | C4.2 | Study Tour for COCA's staff | 2015-06-15
30 | C4.2 | Training COCA's staff to obtain AII Certification | 2014-06-15
Total

## OC
Republic of Yemen, Public Financial Modernization Project –P117363, Procurement Plan
PMU Operating Cost
S. | Expected Outcome/ Activity Description | Cost | Estimated Cost US $ | Actual | Remarks
1 | Salary Increase for PMU staff + new posts |  | 20000
2 | Travel Allowances/Per Diem |  | 100000
Equipements and Maintenance
3 | Office Supplies |  | 15000
4 | Transportation costs and Fuels |  | 15000
5 | Capacity Building for PMU staff
6 | Financial Management System Maintenance |  |  | Moved to Goods
| Externl Auditor |  |  | Moved to Consultant
Car rental
7 | Vehicle for the PFMP - (one)
8 | Advertisement |  | 70000
| Total |  | 220000 | 0