## Cover-Updated
PROCUREMENT PLAN
HEALTH SYSTEM STRENGTHENING AND SUPPORT PROJECT (HSSSP)
Revision 2.0
I. General
1. Project Information
|  |  | Country |  | : | TURKEY
|  |  | Borrower |  | :
|  |  | Project Name |  | : | HEALTH SYSTEM STRENGTHENING AND SUPPORT PROJECT (HSSSP)
|  |  | Project No |  | : | P152799
|  |  | Loan No |  | : | 8531-TR
|  |  | Implementing Agency |  | :
|  | 2. Bank's Approval Date of the Procurement Plan |  |  | : | 2015-05-27
|  | 3. Date of General Procurement Notice |  |  | : | 2015-09-15
|  | 4. Period Covered with this procurement plan |  |  | : | 01 October 2015- 31 March 2017
|  | 5. Closing date |  |  | : | 2020-05-30
II. Goods, Works and Non-consulting Services
1. Prior Review Threshold : Procurement decisions subject to Prior Review by the Bank as stated in Appendix 1 to the
Procurement Guidelines.
|  |  | Procurement Method | Procurement Method Threshold |  | Prior Review Threshold
|  |  | International Competitive Bidding (ICB) | Contracts valued ≥$ 1,000,000 - Goods (including SI for IT Contracts) |  | All contracts
|  |  | National Competitive Bidding (NCB) | Contracts valued <$ 1,000,000 - Goods |  | First contract of each category from each implementing unit
Contracts valued <$ 1,000,000 - Non-Consulting Services & Smaller Works
|  |  | Shopping | Contracts valued <$ 100,000 - Goods |  | First contract of each category from each implementing unit
Contracts valued < $ 200,000 - Smaller Works
Contracts valued < $ 100,000 - Non Consulting Services & (including logistic services for workshops and similar events)
|  |  | Direct Contracting | No threshold |  | All contracts are subject to prior review
III. Selection of Consultants
1. Prior Review Threshold : Selection decisions subject to Prior Review by the Bank as stated in Appendix 1 to the
Consultant Guidelines
|  |  | Selection Method | Selection Method Threshold |  | Prior Review Threshold
|  |  | Quality and Cost Based Selection (QCBS) | Default Method (No selection method threshold) |  | Contracts valued ≥ $ 350,000 | Irrespective of the selection method and contract amount first contracts are subject to prior review
|  |  | Quality Based Selection (QBS) | No selection method threshold |  | Contracts valued ≥ $ 350,000
|  |  | Fixed Budget Selection (FBS) | No selection method threshold |  | Contracts valued ≥ $ 350,000
|  |  | Least Cost Selection (LCS) | No selection method threshold |  | Contracts valued ≥ $ 350,000
|  |  | Selection Based on Consultants Qualification (CQS) | Contracts valued <$ 300,000
|  |  | Single Source Selection of Firms (SSS) | No selection method threshold |  | All contracts are subject to prior review
|  |  | Individual Consultants (IC) | No selection method threshold |  | Contracts valued ≥ $ 100,000 and,
the first individual consultant contract and all single source individual contracts are subject to Bank's prior review irrespective of contract amount.
The TORs and selection processes for financial management, audit, procurement or legal contracts financed by the Project, even those are below the prior review threshold, shall be subject to Bank's prior review.
2. Short list comprising entirely of national consultants: Short list of consultants for services estimated to cost less than US$ 500,000 equivalent per contract, may comprise entirely of national consultants in accordance with provisions of paragraph 2.7 of the Consultant Guidelines.
IV. Any Other Special Procurement Arrangements:
Logistical and organizational services required for the International and National Symposium, Seminars, Workshop, and other training programs shall be procured by Shopping procedures as the Non consulting services, if the contract size is less than US$100,000 equivalent. Training activities in the form of study tours, or participating in national or international workshops and training programs shall be procured in accordance with the procedures agreed with the Bank.
Special Procurement Arrangements. The following contracts originally signed under PSRHS are eligible for financing from the proceeds of new HSSSP: (i) individual consultants providing fiduciary services for the PMSU and implementing units selected according to the Consultant Guidelines under the PSRHS and whose contracts have not been completed by the closing date of PSRHS or been extended to continue under the HSSSP on a SSS basis, -SSYYDP/PYDB/2015/CS/A.7.1.1/SSS/04, Financial Management Specialist -SSYYDP/PYDB/2015/CS/A.7.1.1/SSS/05, Financial Management Specialist -SSYYDP/PYDB/2015/CS/A.7.1.1/SSS/23, Finance Assistant Consultant -SSYYDP/PYDB/2015/CS/A.7.1.1/SSS/24, Finance Assistant Consultant -SSYYDP/THSK/2015/CS/A.8.7.1/SSS/01 Procurement Specialist -SSYYDP/SAGM/2015/CS/A.4.1.1/SSS/01, Procurement Specialist and (ii) firms/individuals selected or by the PMSU and implementing units according to the Procurement/Consultant Guidelines under the PSRHS whose contracts have been signed but not completed as of the PSRHS loan closing date as listed below. -SDSGRP/GDHR/2012/TS/A.4.4.1/NCB/03, Procurement of Services for Healthcare Employee Satisfaction Survey (Contract Amount: USD 225,511) -SDSGRP/GDHR/2012/CS/A.4.4.1/IC/05, Consultant for Detailed Analysis and Evaluation of Healthcare Employee Satisfaction Survey Those contracts shall also be listed in the procurement plan of the MoH as ongoing contracts.
MOH may sign a consultancy services contract with World Health Organization (WHO) by using Single Source Selection Method in line with Article 3.15 of Bank's Consultant Guidelines to conduct a thorough survey to monitor the implementation of project activities to raise awareness on risk factors related associated with NCDs and to promote healthy life styles and behavior change. WHO’s STEPs survey brings is a unique methodology and tool for this purpose and the Bank agrees with the use of SSS Method for hiring WHO for this purpose at an estimated cost of EUR 900,000 (approx. USD 1,000,000).
Any contract for which Single Source Selection Method or Direct Contracting Method is specified as the procurement method in the attached tables, the procurement method is applicable only if the MOH provides appropriate justification for the use of these methods and obtains the Bank's prior no-objection.
V. Procurement Packages with Methods and Time Schedule
The estimated costs in the attached tables (sheets) include all the taxes (including VAT).

## All Components Bank Format
[5 empty] | 1 | 2 |  | 3 | 4 | 5 | 5 | 5 | 5 | 6 | 7 | 8 | 9 | 10 (Estimated Time Schedule)
Item No. | Unit in Charge | Activity Package No | Year | Item No | Conract No | Description | Type Desc | Type | Number of Contracts | Estimated Cost(US$) | Estimated Cost (Euro) | Estimated Cost(US$) | Estimated Cost (Euro) | Procurement Method | Prequalification (Yes/No) | Review Method (Prior/Post) (#b) | Domestic Preference (Yes/No) | RfEOI and Shortlisting | Expected (BD/SPN/RFP) Issue Date | Expected Bid/Proposal Opening Date | Expected Contract Signing Date | Expected Completion Time excl. Warranty Prd.
A. GOODS, WORKS AND NON-CONSULTING SERVICES | [5 empty] | A. GOODS, WORKS AND NON-CONSULTING SERVICES
1 | SAGEM | E.2.1.1.6 | 2016 | 1 | SAGEM/2016/G/E.2.1.1.6/NCB/1 | Server Storage | G, W&NCS | G | 1 | 199999.9904 | 178571.42 | 200000 | 178580 | NCB | No | Prior | No | N/A | 2016-04-02 | 2016-05-17 | 2016-06-01 | 2016-07-31
2 | SAGEM | E.2.1.1.6 | 2016 | 2 | SAGEM/2016/G/E.2.1.1.6/S/2 | Firewall | G, W&NCS | G | 1 | 4999.9936 | 4464.28 | 5000 | 4470 | S | No | Post | No | N/A | 2016-05-02 | 2016-05-02 | 2016-06-01 | 2016-07-01
3 | TKHK | N.3.1.4.1 | 2015 | 1 | TKHK/2015/SI/N.3.1.4.1/ICB/1 | Rational Drug and Medical Supply Management System Hardware-Software Development Service | G, W&NCS | SI | 1 | 2500000.0032 | 2232142.86 | 2500000 | 2232150 | ICB | No | Prior | No | N/A | 2015-12-31 | 2016-02-29 | 2016-04-29 | 2017-03-01
4 | TKHK | N.3.1.1.1 | 2016 | 1 | TKHK/2016/G/N.3.1.1.1/S /1 | SOURCE BOOKS | G, W&NCS | G | 1 | 16250.0016 | 14508.93 | 16250 | 14510 | S | No | Prior | No | N/A | 2016-01-01 | 2016-01-01 | 2016-01-01 | 2016-01-31
5 | TKHK | N.3.1.1.1 | 2015 | 2 | TKHK/2015/G/N.3.1.1.1/S /2 | SOURCE SOFTWARES | G, W&NCS | G | 1 | 82499.9952 | 73660.71 | 82500 | 73670 | S | No | Post | No | N/A | 2015-12-02 | 2015-12-02 | 2016-01-01 | 2016-01-31
6 | SYGM | F.3.1.4.1 | 2015 | 1 | SYGM/2015/NCS/F.3.1.4.1/S /1 | Translation of international standards and documents | G, W&NCS | NCS | Multiple | 150000.48 | 133929 | 150000 | 133930 | S | No | Post | No | N/A | N/A | N/A | 2015-10-01 | 2017-03-01
7 | SHGM | A.1.1.1.2 | 2015 | 1 | SHGM/2015/NCS/A.1.1.1.2/S/1 | Technical Service for Survey Study | G, W&NCS | NCS | 1 | 40000.0048 | 35714.29 | 40000 | 35720 | S | No | Prior | No | N/A | 2015-12-02 | 2015-12-02 | 2016-01-01 | 2016-01-01
8 | SHGM | A.1.2.2.7 | 2016 | 1 | SHGM/2016/NCS/A.1.2.2.7/S/1 | Design and publication of benchmark guidelines | G, W&NCS | NCS | 1 | 5000.0048 | 4464.29 | 5000 | 4470 | S | No | Post | No | N/A | 2016-11-01 | 2016-11-01 | 2016-12-01 | 2016-12-01
9 | SHGM | A.1.3.4.6 | 2016 | 1 | SHGM/2016/G/A.1.3.4.6/S/1 | Tablet computer procurement | G, W&NCS | G | 1 | 95000.0016 | 84821.43 | 95000 | 84830 | S | No | Post | No | N/A | 2016-09-01 | 2016-09-01 | 2016-10-01 | 2016-10-31
10 | ASHGM | B.1.1.2.7 | 2016 | 1 | ASHGM/2016/G/B.1.1.2.7/S/1 | Procurement of models to be used during training | G, W&NCS | G | 1 | 50000.0032 | 44642.86 | 50000 | 44650 | S | No | Post | No | N/A | 2016-09-01 | 2016-09-01 | 2016-10-01 | 2016-10-31
11 | DISAB | G.1.1.2.3 | 2016 | 1 | DISAB/2016/NCS/G.1.1.2.3/S/1 | Translation Service Procurement 1 | G, W&NCS | NCS | 1 | 29120 | 26000 | 29120 | 26000 | S | No | Post | No | N/A | 2016-07-02 | 2016-07-02 | 2016-08-01 | 2016-07-01
12 | DISAB | G.1.1.2.3 | 2017 | 1 | DISAB/2017/NCS/G.1.1.2.3/S/1 | Procurement of Document Printing Service 2 | G, W&NCS | NCS | 1 | 28336 | 25300 | 28336 | 25300 | S | No | Post | No | N/A | 2017-01-02 | 2017-01-02 | 2017-02-01 | 2017-02-01
13 | DISAB | G.1.1.2.3 | 2016 | 2 | DISAB/2016/NCS/G.1.1.2.3/S/2 | Procurement of Document Printing Service 1 | G, W&NCS | NCS | 1 | 28336 | 25300 | 28336 | 25300 | S | No | Post | No | N/A | 2016-09-01 | 2016-09-01 | 2016-10-01 | 2016-10-01
14 | DISAB | G.1.1.2.3 | 2016 | 3 | DISAB/2016/NCS/G.1.1.2.3/S/3 | Translation Service Procurement 2 | G, W&NCS | NCS | 1 | 29120 | 26000 | 29120 | 26000 | S | No | Post | No | N/A | 2016-11-01 | 2016-11-01 | 2016-12-01 | 2016-12-01
15 | SAGEM | E.1.1.1.3 | 2015 | 1 | SAGEM/2015/G/E.1.1.1.3/S/1 | Computers | G, W&NCS | G | 1 | 36699.992 | 32767.85 | 36700 | 32770 | S | No | Prior | No | N/A | 2015-10-01 | 2015-10-01 | 2015-10-01 | 2015-10-31
16 | SAGEM | E.5.3.1.4 | 2016 | 1 | SAGEM/2016/NCS/E.5.3.1.4/S/1 | Service procurement for publication and delivery of Healthcare System Evaluation Report | G, W&NCS | NCS | 1 | 10000 | 8928.5714 | 10000 | 8930 | S | No | Post | No | N/A | 2016-09-03 | 2016-09-03 | 2016-10-01 | 2016-10-01
17 | SAGEM | E.5.3.2.2 | 2016 | 1 | SAGEM/2016/NCS/E.5.3.2.2/S/1 | Turkish-English Translation Service for Training Modules of HTP Policies Evaluation | G, W&NCS | NCS | 1 | 2999.9984 | 2678.57 | 3000 | 2680 | S | No | Post | No | N/A | 2016-09-03 | 2016-09-03 | 2016-10-01 | 2016-10-01
18 | SAGEM | E.5.3.2.2 | 2016 | 2 | SAGEM/2016/NCS/E.5.3.2.2/S/2 | Turkish-Arabic Translation Service for Training Modules of HTP Policies Evaluation | G, W&NCS | NCS | 1 | 4500.0032 | 4017.86 | 4500 | 4020 | S | No | Post | No | N/A | 2016-08-04 | 2016-08-04 | 2016-09-01 | 2016-09-01
19 | SAGEM | E.5.1.2.2 | 2015 | 1 | SAGEM/2015/NCS/E.5.1.2.2/NCB/1 | Field research service for researching the causes of low birth weight and premature birth in Turkey (1) | G, W&NCS | NCS | 1 | 379999.9952 | 339285.71 | 380000 | 339290 | NCB | No | Post | No | N/A | 2015-11-02 | 2015-12-17 | 2016-01-01 | 2016-12-31
20 | SAGEM | E.5.1.2.2 | 2015 | 2 | SAGEM/2015/NCS/E.5.1.2.2/NCB/2 | Field research service for patient satisfaction (1) | G, W&NCS | NCS | 1 | 292000.0048 | 260714.29 | 292000 | 260720 | NCB | No | Post | No | N/A | 2015-11-02 | 2015-12-17 | 2016-01-01 | 2016-12-31
21 | SAGEM | E.5.1.2.2 | 2015 | 3 | SAGEM/2015/NCS/E.5.1.2.2/NCB/3 | Field research service for patient satisfaction (1) | G, W&NCS | NCS | 1 | 292000.0048 | 260714.29 | 292000 | 260720 | NCB | No | Post | No | N/A | 2015-11-02 | 2015-12-17 | 2016-01-01 | 2016-12-31
22 | SAGEM | E.5.1.2.2 | 2015 | 4 | SAGEM/2015/NCS/E.5.1.2.2/NCB/4 (SDSGRP/GDHR/2012/TS/A.4.4.1/NCB/03) | Ongoing contract from PSRHS : Procurement of Services for Healthcare Employee Satisfaction Survey | G, W&NCS | NCS | 1 | 124320 | 111000 | 124320 | 111000 | NCB | No | Prior | No | N/A | 2012-10-01 | 2012-11-01 | 2013-01-01 | 2015-12-01
23 | SAGEM | E.5.1.2.2 | 2017 | 1 | SAGEM/2017/NCS/E.5.1.2.2/S/1 | Translation fee for articles (medical and scientific translation) | G, W&NCS | NCS | 1 | 2499.9968 | 2232.14 | 2500 | 2240 | S | No | Post | No | N/A | 2017-02-01 | 2017-02-01 | 2017-03-01 | 2017-03-01
24 | SAGEM | E.4.1.2.2 | 2016 | 1 | SAGEM/2016/G/E.4.1.2.2/NCB/1 | Application Servers | G, W&NCS | G | 1 | 299999.9968 | 267857.14 | 300000 | 267860 | NCB | No | Post | No | N/A | 2016-02-01 | 2016-03-17 | 2016-04-01 | 2016-06-01
25 | SAGEM | E.4.1.2.2 | 2016 | 2 | SAGEM/2016/G/E.4.1.2.2/NCB/2 | Database Server | G, W&NCS | G | 1 | 499999.9984 | 446428.57 | 500000 | 446430 | NCB | No | Post | No | N/A | 2016-02-01 | 2016-03-17 | 2016-04-01 | 2016-06-01
26 | PYDB | P.5 | 2015 | 1 | PYDB/2015/G/P.5/S/1 | Hardware and software (UPS, penetration test, IS Management Software, IT and office supplies) | G, W&NCS | G | 2 | 70000 | 62500 | 70000 | 62500 | S | No | Prior | No | N/A | 2015-12-04 | 2015-12-04 | 2016-01-01 | 2016-01-31
27 | PYDB | P.5 | 2015 | 1 | PYDB/2015/NCS/P.5/S/1 | Procurement of Social Media Follow-up Service | G, W&NCS | NCS | 1 | 33000.0048 | 29464.29 | 33000 | 29470 | S | No | Post | No | N/A | 2015-10-01 | 2015-10-01 | 2015-12-04 | 2015-12-04
28 | SHGM | A.3.1.3.1 | 2016 | 1 | SHGM/2016/G/A.3.1.3.1/NCB/1 | Miscellenous Office Materials for Rehabilitation Centers | G, W&NCS | G | 1 | 700560 | 625500 | 700560 | 625500 | NCB | No | Prior | No | N/A | 2016-02-01 | 2016-03-17 | 2016-04-01 | 2016-05-31
29 | SHGM | A.3.1.3.1 | 2016 | 2 | SHGM/2016/G/A.3.1.3.1/NCB/2 | Miscellenous Office Materials for Rehabilitation Centers | G, W&NCS | G | 1 | 700560 | 625500 | 700560 | 625500 | NCB | No | Post | No | N/A | 2016-08-02 | 2016-09-16 | 2016-10-01 | 2016-11-30
30 | SHGM | A.3.1.3.1 | 2015 | 1 | SHGM/2015/G/A.3.1.3.1/S/1 | Laptop Computers (3) | G, W&NCS | G | 1 | 7999.04 | 7142 | 8000 | 7150 | S | No | Post | No | N/A | 2015-10-02 | 2015-10-02 | 2015-11-01 | 2015-12-01
31 | TKHK | N.3.1.5.1 | 2016 | 1 | TKHK/2016/SI/N.3.1.5.1/ICB/1 | Needs Management Software Development Service | G, W&NCS | SI | 1 | 3000000.0016 | 2678571.43 | 3000000 | 2678580 | ICB | No | Prior | No | N/A | 2016-03-01 | 2016-04-30 | 2016-06-29 | 2017-03-01
32 | TKHK | N.3.1.3.1 | 2016 | 1 | TKHK/2016/SI/N.3.1.3.1/ICB/1 | Clinical engineering management system development service | G, W&NCS | SI | 1 | 1499999.9952 | 1339285.71 | 1500000 | 1339290 | ICB | No | Prior | No | N/A | 2016-03-01 | 2016-04-30 | 2016-06-29 | 2017-03-01
33 | TKHK | N.3.1.6.1 | 2016 | 1 | TKHK/2016/SI/N.3.1.6.1/ICB/1 | Digital stock management model development service | G, W&NCS | SI | 1 | 999999.9968 | 892857.14 | 1000000 | 892860 | ICB | No | Prior | No | N/A | 2016-03-01 | 2016-04-30 | 2016-06-29 | 2017-03-01
34 | TKHK | N.3.1.7.1 | 2016 | 1 | TKHK/2016/SI/N.3.1.7.1/ICB/1 | Institution's Performance Analysis and Management System Development Service | G, W&NCS | SI | 1 | 1300000.0048 | 1160714.29 | 1300000 | 1160720 | ICB | No | Prior | No | N/A | 2016-03-01 | 2016-04-30 | 2016-06-29 | 2017-03-01
35 | SAGEM | E.4.1.1.1 | 2015 | 1 | SAGEM/2015/SI/E.4.1.1.1/ICB/1 | System and Software Development Service for Evidence-based Medicine Guidelines | G, W&NCS | SI | 1 | 3500000 | 3125000 | 3500000 | 3125000 | ICB | No | Prior | No | N/A | 2015-12-31 | 2016-02-29 | 2016-04-29 | 2019-09-01
36 | TKHK | N.3.1.1 | 2015 | 1 | TKHK/2015/NCS/N.3.1.1/S/1 | Translation services | G, W&NCS | NCS | Multiple | 93749.9808 | 83705.34 | 93750 | 83710 | S | No | Post | No | N/A | N/A | N/A | 2015-12-01 | 2019-09-01
37 | SHGM | A.1.2.3.1 | 2016 | 1 | SHGM/2016/NCS/A.1.2.3.1/S/1 | Procurement of Software Technical Service | G, W&NCS | NCS | 1 | 10000 | 8928.5714 | 10000 | 8930 | S | No | Post | No | N/A | No | 2016-05-02 | 2016-06-01 | 2016-06-01
38 | DISAB | G.1.1.5.3 | 2015 | 1 | DISAB/2015/NCS/G.1.1.5.3/NCB/1 | Printing Services - Promotion of Turkish Health System at Int Fora | G, W&NCS | NCS | 1 | 196164.7968 | 175147.14 | 196165 | 175150 | NCB | No | Prior | No | N/A | 2015-12-03 | 2016-01-17 | 2016-02-01 | 2016-03-02
39 | SHGM | A.3.1.3.1 | 2016 | 1 | SHGM/2016/W/A.3.1.3.1/S/1 | Minor paint jobs, mechanical and electrical installation works, etc., for rehabilitation centers (Aksaray) | G, W&NCS | W | 1 | 151200 | 135000 | 151200 | 135000 | S | No | Prior | No | N/A | 2016-02-01 | 2016-03-02 | 2016-04-01 | 2016-05-31
40 | SHGM | A.3.1.3.1 | 2016 | 2 | SHGM/2016/W/A.3.1.3.1/S/2 | Minor paint jobs, mechanical and electrical installation works, etc., for rehabilitation centers (Mersin) | G, W&NCS | W | 1 | 151200 | 135000 | 151200 | 135000 | S | No | Post | No | N/A | 2016-04-02 | 2016-05-02 | 2016-06-01 | 2016-07-31
41 | SHGM | A.3.1.3.1 | 2016 | 3 | SHGM/2016/W/A.3.1.3.1/S/3 | Minor paint jobs, mechanical and electrical installation works, etc., for rehabilitation centers (Manisa) | G, W&NCS | W | 1 | 151200 | 135000 | 151200 | 135000 | S | No | Post | No | N/A | 2016-06-02 | 2016-07-02 | 2016-08-01 | 2016-09-30
42 | SHGM | A.3.1.3.1 | 2016 | 4 | SHGM/2016/W/A.3.1.3.1/S/4 | Minor paint jobs, mechanical and electrical installation works, etc., for rehabilitation centers (Diyarbakır) | G, W&NCS | W | 1 | 151200 | 135000 | 151200 | 135000 | S | No | Post | No | N/A | 2016-08-02 | 2016-09-01 | 2016-10-01 | 2016-11-30
43 | SHGM | A.3.1.3.1 | 2017 | 1 | SHGM/2017/W/A.3.1.3.1/S/1 | Minor paint jobs, mechanical and electrical installation works, etc., for rehabilitation centers (Çanakkale) | G, W&NCS | W | 1 | 151200 | 135000 | 151200 | 135000 | S | No | Post | No | N/A | 2017-01-31 | 2017-03-02 | 2017-04-01 | 2017-05-31
44 | SHGM | A.3.1.5.1 | 2017 | 1 | SHGM/2017/NCS/A.3.1.5.1/S/1 | Printing of Training Materials | G, W&NCS | NCS | 1 | 40320 | 36000 | 40320 | 36000 | S | No | Post | No | N/A | 2017-01-02 | 2017-01-02 | 2017-02-01 | 2017-02-01
45 | SAGEM | E.6.1.1.3 | 2016 | 1 | SAGEM/2016/NCS/E.6.1.1.3/S/1 | Printing Services | G, W&NCS | NCS | Multiple | 19500.0064 | 17410.72 | 19500 | 17420 | S | No | Post | No | N/A | No | N/A | 2016-06-01 | 2017-03-01
46 | SAGEM | E.5.3.1.3 | 2015 | 1 | SAGEM/2015/NCS/E.5.3.1.3/S/1 | Translation of reports | G, W&NCS | NCS | Multiple | 8500.0048 | 7589.29 | 8500 | 7590 | S | No | Post | No | N/A | 2015-10-04 | 2015-10-04 | 2015-11-01 | 2018-12-01
47 | TKHK | N.3.1.3.1 | 2016 | 1 | TKHK/2016/G/N.3.1.3.1/S /1 | Printing services and office materials | G, W&NCS | G | 1 | 25000.0016 | 22321.43 | 25000 | 22330 | S | No | Post | No | N/A | 2016-08-02 | 2016-08-02 | 2016-09-01 | 2016-12-01
48 | TKHK | N.3.1.1.1 | 2015 | 1 | TKHK/2015/G/N.3.1.1.1/S /1 | SOURCE SOFTWARES | G, W&NCS | G | 1 | 95000.0016 | 84821.43 | 95000 | 84830 | S | No | Post | No | N/A | 2015-10-01 | 2015-10-01 | 2015-10-31 | 2015-11-30
49 | TKHK | N.3.1.1.1 | 2016 | 2 | TKHK/2016/G/N.3.1.1.1/S /2 | SOURCE BOOKS | G, W&NCS | G | 1 | 16250.0016 | 14508.93 | 16250 | 14510 | S | No | Prior | No | N/A | 2016-01-01 | 2016-01-01 | 2016-01-01 | 2016-01-31
50 | TKHK | N.3.1.4.1 | 2016 | 1 | TKHK/2016/G/N.3.1.4.1/S /1 | Printing services and office materials | G, W&NCS | G | 1 | 50000.0032 | 44642.86 | 50000 | 44650 | S | No | Post | No | N/A | 2016-08-02 | 2016-08-02 | 2016-09-01 | 2016-12-01
51 | TKHK | N.3.1.5.1 | 2016 | 2 | TKHK/2016/SI/N.3.1.5.1/ICB/2 | Data Mining Software Development Service | G, W&NCS | SI | 1 | 386999.9952 | 345535.71 | 387000 | 345540 | ICB | No | Prior | No | N/A | 2016-03-01 | 2016-04-30 | 2016-06-29 | 2017-03-01
52 | TKHK | N.3.1.6.1 | 2016 | 1 | TKHK/2016/G/N.3.1.6.1/S /1 | Printing services and office materials | G, W&NCS | G | 1 | 25000.0016 | 22321.43 | 25000 | 22330 | S | No | Post | No | N/A | 2016-08-02 | 2016-08-02 | 2016-09-01 | 2016-12-01
53 | TKHK | N.3.1.7.1 | 2016 | 1 | TKHK/2016/G/N.3.1.7.1/S /1 | Printing services and office materials | G, W&NCS | G | 1 | 25000.0016 | 22321.43 | 25000 | 22330 | S | No | Post | No | N/A | 2016-08-02 | 2016-08-02 | 2016-09-01 | 2016-12-01
54 | TKHK | N.3.1.8.1 | 2016 | 1 | TKHK/2016/G/N.3.1.8.1/S /1 | Printing services and office materials | G, W&NCS | G | 1 | 25000.0016 | 22321.43 | 25000 | 22330 | S | No | Post | No | N/A | 2016-08-02 | 2016-08-02 | 2016-09-01 | 2016-12-01
55 | TKHK | N.3.1.8.1 | 2015 | 1 | TKHK/2015/SI/N.3.1.8.1/ICB/1 | Software Infrastructure Development for Improving Health Managers | G, W&NCS | SI | 1 | 350000 | 312500 | 350000 | 312500 | ICB | No | Prior | No | N/A | 2015-12-31 | 2016-02-29 | 2016-04-29 | 2017-03-01
56 | TKHK | N.3.1.8.1 | 2015 | 2 | TKHK/2015/SI/N.3.1.8.1/ICB/2 | Software Development for Efficiency Modelling and Supplementary Payments | G, W&NCS | SI | 1 | 999999.9968 | 892857.14 | 1000000 | 892860 | ICB | No | Prior | No | N/A | 2015-12-31 | 2016-02-29 | 2016-04-29 | 2017-03-01
57 | TKHK | N.3.1.9.1 | 2016 | 1 | TKHK/2016/G/N.3.1.9.1/S /1 | Printing services and office materials | G, W&NCS | G | 1 | 25000.0016 | 22321.43 | 25000 | 22330 | S | No | Post | No | N/A | 2016-08-02 | 2016-08-02 | 2016-09-01 | 2016-12-01
58 | SYGM | F.3.1.1.3 | 2015 | 1 | SYGM/2015/G/F.3.1.1.3/S /1 | Computers | G, W&NCS | G | 1 | 50000.16 | 44643 | 50000 | 44650 | S | No | Post | No | N/A | 2015-10-01 | 2015-10-01 | 2015-10-01 | 2015-11-15
59 | SYGM | F.3.1.1.3 | 2015 | 2 | SYGM/2015/G/F.3.1.1.3/NCB/2 | Software (AUTOCAD, NETCAD, etc.) | G, W&NCS | G | 1 | 150000.48 | 133929 | 150000 | 133930 | NCB | No | Post | No | N/A | 2015-10-02 | 2015-10-02 | 2015-12-01 | 2016-01-15
60 | SYGM | F.1.2.1.2 | 2015 | 1 | SYGM/2015/G/F.1.2.1.2/S /1 | Office equipment and computers | G, W&NCS | G | 1 | 99680 | 89000 | 99680 | 89000 | S | No | Post | No | N/A | 2015-10-01 | 2015-10-01 | 2015-10-01 | 2015-11-15
61 | SYGM | F.2.1.1.2 | 2015 | 1 | SYGM/2015/G/F.2.1.1.2/S /1 | Computers | G, W&NCS | G | 1 | 10000.48 | 8929 | 10000 | 8930 | S | No | Post | No | N/A | 2015-10-01 | 2015-10-01 | 2015-10-01 | 2015-11-15
62 | SYGM | F.2.1.1.2 | 2015 | 2 | SYGM/2015/G/F.2.1.1.2/S /2 | Software (AUTOCAD, NETCAD, etc.) | G, W&NCS | G | 1 | 54999.84 | 49107 | 55000 | 49110 | S | No | Post | No | N/A | 2015-10-01 | 2015-10-01 | 2015-10-01 | 2015-11-15
63 | THSK | L.2.1.2.4 | 2016 | 1 | THSK/2016/NCS/L.2.1.2.4/S/1 | Printing and distribution of training materials | G, W&NCS | NCS | 1 | 30004.8 | 26790 | 30000 | 26790 | S | No | Post | No | N/A | 2016-11-01 | 2016-11-01 | 2016-12-01 | 2016-12-01
64 | THSK | L.2.3.2.1 | 2016 | 1 | THSK/2016/NCS/L.2.3.2.1/S/1 | Printing and distribution of training materials | G, W&NCS | NCS | 1 | 55048 | 49150 | 55048 | 49150 | S | No | Post | No | N/A | 2016-11-01 | 2016-11-01 | 2016-12-01 | 2016-12-01
65 | THSK | L.2.3.2.2 | 2016 | 2 | THSK/2016/G/L.2.3.2.2/NCB/2 | Material procurement for field research | G, W&NCS | G | 1 | 150080 | 134000 | 150080 | 134000 | NCB | No | Prior | No | N/A | 2016-07-03 | 2016-08-17 | 2016-09-01 | 2016-10-31
66 | THSK | L.2.3.2.2 | 2016 | 1 | THSK/2016/G/L.2.3.2.2/NCB/1 | Material procurement for field research | G, W&NCS | G | 1 | 200032 | 178600 | 200000 | 178600 | NCB | No | Post | No | N/A | 2016-12-03 | 2017-01-17 | 2017-02-01 | 2017-04-02
67 | THSK | L.2.4.2.1 | 2015 | 1 | THSK/2015/G/L.2.4.2.1/S/1 | Training module (Palliative care services) | G, W&NCS | G | 1 | 89999.84 | 80357 | 90000 | 80360 | S | No | Post | No | N/A | 2015-10-03 | 2015-10-10 | 2015-10-15 | 2015-11-14
68 | THSK | L.2.4.2.1 | 2015 | 1 | THSK/2015/NCS/L.2.4.2.1/S/1 | Translation of the training module (Palliative care services) | G, W&NCS | NCS | 1 | 39999.68 | 35714 | 40000 | 35720 | S | No | Post | No | N/A | 2015-10-15 | 2015-10-22 | 2015-10-25 | 2015-12-31
69 | THSK | L.2.4.3.3 | 2016 | 1 | THSK/2016/NCS/L.2.4.3.3/S/1 | Printing service for national standards guidelines | G, W&NCS | NCS | 1 | 39999.68 | 35714 | 40000 | 35720 | S | No | Post | No | N/A | 2016-08-01 | 2016-08-08 | 2016-09-01 | 2016-09-01
70 | THSK | L.2.5.4.2 | 2016 | 1 | THSK/2016/G/L.2.5.4.2/S/1 | Procurement of goods for increasing the participation in cancer screening (leaflet, etc.) | G, W&NCS | G | 1 | 30000.32 | 26786 | 30000 | 26790 | S | No | Post | No | N/A | 2016-09-01 | 2016-09-08 | 2016-10-01 | 2016-10-31
71 | THSK | L.2.11.1.1 | 2016 | 3 | THSK/2016/NCS/L.2.11.1.1/S/3 | Printing and Distribution of Materials within the scope of the Diabetes Program for Schools | G, W&NCS | NCS | 1 | 24999.52 | 22321 | 25000 | 22330 | S | No | Post | No | N/A | 2016-08-01 | 2016-08-08 | 2016-09-01 | 2016-10-01
72 | THSK | L.2.12.1.1 | 2016 | 1 | THSK/2016/NCS/L.2.12.1.1/S/1 | Translation of the National Salt Consumption Guidebook | G, W&NCS | NCS | 1 | 24999.52 | 22321 | 25000 | 22330 | S | No | Post | No | N/A | 2016-04-01 | 2016-04-08 | 2016-04-01 | 2016-04-01
73 | THSK | L.2.12.1.1 | 2016 | 2 | THSK/2016/NCS/L.2.12.1.1/S/2 | Preparation of Posters and Brochures on Healthy Nutrition, Obesity and Physical Exercises | G, W&NCS | NCS | 1 | 25000.64 | 22322 | 25000 | 22330 | S | No | Post | No | N/A | 2016-04-01 | 2016-04-01 | 2016-05-01 | 2016-05-31
74 | THSK | L.2.12.1.1 | 2016 | 3 | THSK/2016/NCS/L.2.12.1.1/S/3 | Printing and distribution of the National Salt Consumption Guidebook | G, W&NCS | NCS | 1 | 24999.52 | 22321 | 25000 | 22330 | S | No | Post | No | N/A | 2016-09-01 | 2016-09-08 | 2016-10-01 | 2016-10-01
75 | THSK | L.2.12.1.1 | 2016 | 4 | THSK/2016/NCS/L.2.12.1.1/S/4 | Printing and distribution of the Book on Weight Management in Primary Healthcare | G, W&NCS | NCS | 1 | 24999.52 | 22321 | 25000 | 22330 | S | No | Post | No | N/A | 2016-10-01 | 2016-10-08 | 2016-11-01 | 2016-11-01
76 | THSK | L.2.12.1.1 | 2016 | 5 | THSK/2016/NCS/L.2.12.1.1/S/5 | Printing and distribution of the Book on Weight Management for Children | G, W&NCS | NCS | 1 | 24999.52 | 22321 | 25000 | 22330 | S | No | Post | No | N/A | 2016-10-01 | 2016-10-08 | 2016-11-01 | 2016-11-01
77 | THSK | L.2.12.1.1 | 2016 | 6 | THSK/2016/NCS/L.2.12.1.1/S/6 | Printing and distribution of Obesity Guidelines for Family Physicians | G, W&NCS | NCS | 1 | 24999.52 | 22321 | 25000 | 22330 | S | No | Post | No | N/A | 2016-11-01 | 2016-11-08 | 2016-12-01 | 2016-12-01
78 | THSK | L.2.12.1.1 | 2016 | 1 | THSK/2016/NCS/L.2.12.1.1/NCB/1 | Preparation of public information advertisements | G, W&NCS | NCS | 1 | 200000.64 | 178572 | 200000 | 178580 | NCB | No | Post | No | N/A | 2016-02-01 | 2016-03-02 | 2016-04-01 | 2016-04-01
79 | THSK | L.2.12.2.1 | 2016 | 1 | THSK/2016/G/L.2.12.2.1/S/1 | Procurement of devices and tools | G, W&NCS | G | 1 | 99904 | 89200 | 99904 | 89200 | S | No | Post | No | N/A | 2016-03-01 | 2016-04-01 | 2016-05-01 | 2016-05-31
80 | THSK | L.2.12.2.1 | 2016 | 2 | THSK/2016/G/L.2.12.2.1/S/2 | Computer procurement for data input | G, W&NCS | G | 1 | 80000.48 | 71429 | 80000 | 71430 | S | No | Post | No | N/A | 2016-04-01 | 2016-04-08 | 2016-05-01 | 2016-05-31
81 | THSK | L.2.12.2.2 | 2016 | 1 | THSK/2016/NCS/L.2.12.2.2/S/1 | Collecting the results into a book (printing services) | G, W&NCS | NCS | 1 | 19520.48 | 17429 | 19521 | 17430 | S | No | Post | No | N/A | 2016-11-01 | 2016-11-08 | 2016-12-01 | 2016-12-31
82 | THSK | L.2.12.3.1 | 2016 | 2 | THSK/2016/NCS/L.2.12.3.1/S/2 | Printing, optical reading and distributing forms to provinces | G, W&NCS | NCS | 1 | 19999.84 | 17857 | 20000 | 17860 | S | No | Post | No | N/A | 2016-04-01 | 2016-04-08 | 2016-05-01 | 2016-06-01
83 | THSK | L.2.12.3.2 | 2016 | 1 | THSK/2016/NCS/L.2.12.3.2/S/1 | Printing, optical reading and distributing forms to provinces | G, W&NCS | NCS | 1 | 19999.84 | 17857 | 20000 | 17860 | S | No | Post | No | N/A | 2016-04-01 | 2016-04-08 | 2016-05-01 | 2016-06-01
84 | THSK | L.2.12.3.2 | 2016 | 2 | THSK/2016/NCS/L.2.12.3.2/S/2 | Printing and distribution of the research report | G, W&NCS | NCS | 1 | 19999.84 | 17857 | 20000 | 17860 | S | No | Post | No | N/A | 2016-10-01 | 2016-10-08 | 2016-11-01 | 2016-12-01
85 | THSK | L.2.12.6.1 | 2016 | 1 | THSK/2016/G/L.2.12.6.1/S/1 | Computer procurement for data input | G, W&NCS | G | 1 | 80000.48 | 71429 | 80000 | 71430 | S | No | Post | No | N/A | 2016-01-15 | 2016-01-22 | 2016-01-28 | 2016-02-27
86 | THSK | L.2.18.3.1 | 2016 | 1 | THSK/2016/NCS/L.2.18.3.1/S/1 | Printing of leaflets and visual materials | G, W&NCS | NCS | 1 | 4999.68 | 4464 | 5000 | 4470 | S | No | Post | No | N/A | 2016-10-01 | 2016-10-08 | 2016-11-01 | 2016-12-01
87 | THSK | L.2.20.2.3 | 2017 | 1 | THSK/2017/NCS/L.2.20.2.3/S/1 | Translations of foreign publications | G, W&NCS | NCS | 1 | 4999.68 | 4464 | 5000 | 4470 | S | No | Post | No | N/A | 2017-01-30 | 2017-01-30 | 2017-03-01 | 2017-03-01
88 | THSK | L.2.20.3.6 | 2016 | 1 | THSK/2016/G/L.2.20.3.6/S/1 | Software systems to be used in desk unit | G, W&NCS | G | 1 | 50000.16 | 44643 | 50000 | 44650 | S | No | Post | No | N/A | 2016-01-31 | 2016-01-31 | 2016-03-01 | 2016-05-30
89 | THSK | L.2.20.4.4 | 2016 | 1 | THSK/2016/NCS/L.2.20.4.4/S/1 | Preparation and use of short sms | G, W&NCS | NCS | 1 | 10000.48 | 8929 | 10000 | 8930 | S | No | Post | No | N/A | 2016-01-02 | 2016-01-02 | 2016-02-01 | 2016-02-27
90 | THSK | L.2.20.6.2 | 2016 | 1 | THSK/2016/NCS/L.2.20.6.2/NCB/1 | Field Research of Current Situation | G, W&NCS | NCS | 1 | 299999.84 | 267857 | 300000 | 267860 | NCB | No | Post | No | N/A | 2016-05-02 | 2016-06-16 | 2016-07-01 | 2016-09-01
91 | THSK | L.2.20.3.3 | 2015 | 1 | THSK/2015/NCS/L.2.20.3.3/S/1 | Printing of training modules | G, W&NCS | NCS | 1 | 50000.16 | 44643 | 50000 | 44650 | S | No | Post | No | N/A | 2015-12-02 | 2015-12-02 | 2016-01-01 | 2016-05-30
92 | THSK | L.2.20.3.3 | 2015 | 1 | THSK/2015/G/L.2.20.3.3/NCB/1 | Technical equipment to be used in desk unit | G, W&NCS | G | 1 | 200000.64 | 178572 | 200000 | 178580 | NCB | No | Post | No | N/A | 2015-11-02 | 2015-12-17 | 2016-01-01 | 2016-05-30
93 | THSK | L.2.20.2.3 | 2016 | 1 | THSK/2016/NCS/L.2.20.2.3/S/1 | Translations of foreign publications | G, W&NCS | NCS | Multiple | 25000.64 | 22322 | 25000 | 22330 | S | No | Post | No | N/A | 2016-01-31 | 2016-01-31 | 2016-03-01 | 2016-11-30
94 | THSK | L.2.20.1.3 | 2016 | 1 | THSK/2016/NCS/L.2.20.1.3/S/1 | Preparation of distance learning modules | G, W&NCS | NCS | 1 | 19999.84 | 17857 | 20000 | 17860 | S | No | Post | No | N/A | 2016-03-02 | 2016-03-02 | 2016-04-01 | 2016-04-30
95 | THSK | L.2.20.1.4 | 2016 | 1 | THSK/2016/NCS/L.2.20.1.4/S/1 | Printing of training modules | G, W&NCS | NCS | 1 | 19999.84 | 17857 | 20000 | 17860 | S | No | Post | No | N/A | 2016-01-15 | 2016-01-22 | 2016-03-01 | 2016-03-30
96 | THSK | L.4.6.3.4 | 2016 | 1 | THSK/2016/G/L.4.6.3.4/NCB/1 | Miscellaneous Sports Tools and Equipment | G, W&NCS | G | 1 | 500000.48 | 446429 | 500000 | 446430 | NCB | No | Post | No | N/A | 2016-01-01 | 2016-02-15 | 2016-03-01 | 2016-04-30
97 | THSK | L.4.6.3.4 | 2016 | 2 | THSK/2016/G/L.4.6.3.4/NCB/2 | Miscellaneous office equipment and hardware | G, W&NCS | G | 1 | 500000.48 | 446429 | 500000 | 446430 | NCB | No | Post | No | N/A | 2016-01-01 | 2016-02-15 | 2016-03-01 | 2016-04-30
98 | THSK | L.4.6.3.4 | 2016 | 3 | THSK/2016/G/L.4.6.3.4/NCB/3 | Miscellaneous outpatient clinic equipment | G, W&NCS | G | 1 | 299999.84 | 267857 | 300000 | 267860 | NCB | No | Post | No | N/A | 2016-01-01 | 2016-02-15 | 2016-03-01 | 2016-04-30
99 | THSK | L.4.6.4.2 | 2016 | 1 | THSK/2016/NCS/L.4.6.4.2/NCB/1 | Guidebooks, banners and leaflets to be distributed in HLC | G, W&NCS | NCS | 1 | 83333.6 | 74405 | 83334 | 74410 | NCB | No | Post | No | N/A | 2016-01-15 | 2016-02-29 | 2016-03-15 | 2016-04-29
100 | THSK | L.4.6.4.2 | 2016 | 2 | THSK/2016/NCS/L.4.6.4.2/NCB/2 | Guidebooks, banners and leaflets to be distributed in HLC | G, W&NCS | NCS | 1 | 83333.6 | 74405 | 83334 | 74410 | NCB | No | Post | No | N/A | 2016-12-31 | 2017-02-14 | 2017-03-01 | 2017-04-15
101 | THSK | L.2.11.1.1 | 2016 | 2 | THSK/2016/NCS/L.2.11.1.1/S/2 | Printing and Distribution of Clinical Guidelines on Obesity and Diabet for Adults | G, W&NCS | NCS | 1 | 24999.52 | 22321 | 25000 | 22330 | S | No | Post | No | N/A | 2016-05-02 | 2016-05-02 | 2016-06-01 | 2016-06-01
102 | THSK | L.2.11.1.1 | 2016 | 1 | THSK/2016/NCS/L.2.11.1.1/S/1 | Printing and Distribution of Posters and Leaflets on Diabet | G, W&NCS | NCS | 1 | 24999.52 | 22321 | 25000 | 22330 | S | No | Post | No | N/A | 2016-01-02 | 2016-01-02 | 2016-02-01 | 2016-02-01
103 | THSK | L.4.3.3.1 | 2016 | 1 | THSK/2016/NCS/L.4.3.3.1/S/1 | Printing Materials and distribution | G, W&NCS | NCS | 1 | 9999.36 | 8928 | 10000 | 8930 | S | No | Post | No | N/A | 2016-09-01 | 2016-09-01 | 2016-10-01 | 2016-10-30
104 | SBSGM | D.2.1.2.4 | 2016 | 1 | SBSGM/2016/G/D.2.1.2.4/NCB/1 | Purchasing Server | G, W&NCS | G | 1 | 149999.36 | 133928 | 150000 | 133930 | NCB | No | Prior | No | N/A | 2016-06-02 | 2016-07-02 | 2016-08-01 | 2016-08-30
105 | SBSGM | D.2.1.2.4 | 2016 | 2 | SBSGM/2016/G/D.2.1.2.4/NCB/2 | Purchasing Software | G, W&NCS | G | 1 | 149999.36 | 133928 | 150000 | 133930 | NCB | No | Post | No | N/A | 2016-06-02 | 2016-07-02 | 2016-08-01 | 2016-08-30
106 | SBSGM | D.2.1.1.1 | 2015 | 1 | SBSGM/2015/G/D.2.1.1.1/S/1 | Laptop/Tablet Computer and Additional Equipment | G, W&NCS | G | 1 | 50000.16 | 44643 | 50000 | 44650 | S | No | Post | No | N/A | 2015-10-02 | 2015-10-02 | 2015-11-01 | 2015-12-01
107 | SBSGM | D.1.3.1.8 | 2016 | 1 | SBSGM/2016/SI/D.1.3.1.8/ICB/1 | License and Application Software for HMS Database Management System | G, W&NCS | SI | 1 | 2150000.0032 | 1919642.86 | 2150000 | 1919650 | ICB | No | Prior | No | N/A | 2016-06-01 | 2016-07-31 | 2016-09-29 | 2017-05-01
108 | THSK | L.4.5.5.2 | 2016 | 1 | THSK/2016/NCS/L.4.5.5.2/S/1 | Printing Field Guide | G, W&NCS | NCS | 1 | 50000.16 | 44643 | 50000 | 44650 | S | No | Post | No | N/A | 2016-03-02 | 2016-03-02 | 2016-04-01 | 2016-04-30
[6 empty] | A.SUBTOTAL |  |  |  | 26639221.3504 | 23785019.0629 | 26639188 | 23785460
B. CONSULTANTS' SERVICES | [5 empty] | B. CONSULTING SERVICES
109 | TKHK | N.3.1.7 | 2015 | 4 | TKHK/2015/CS/N.3.1.7/IC/4 | Procurement Specialist | CS | CS | 1 | 196806.4 | 175720 | 196800 | 175720 | IC | N/A | Prior | N/A | 2015-10-01 | N/A | 2015-10-01 | 2015-10-01 | 2019-09-01
110 | SBSGM | D.1.3.1.1 | 2015 | 5 | SBSGM/2015/CS/D.1.3.1.1/IC/5 | Procurement Specialist | CS | CS | 1 | 196806.4 | 175720 | 196800 | 175720 | IC | N/A | Prior | N/A | 2015-10-01 | N/A | 2015-10-01 | 2015-10-01 | 2019-09-01
111 | SYGM | F.3.1.1.3 | 2015 | 13 | SYGM/2015/CS/F.3.1.1.3/IC/13 | Procurement Specialist | CS | CS | 1 | 196806.4 | 175720 | 196800 | 175720 | IC | N/A | Prior | N/A | 2015-10-01 | N/A | 2015-10-01 | 2015-10-01 | 2019-09-01
112 | SAGEM | E.5.3.3.1 | 2015 | 3 | SSYYDP/SAGM/2015/CS/A.4.1.1/SSS/01 (SAGEM/2015/CS/E.5.3.3.1/IC/3) | Procurement Specialist | CS | CS | 1 | 196806.4 | 175720 | 196800 | 175720 | SSS | N/A | Prior | N/A | 2015-10-01 | N/A | 2015-10-01 | 2015-10-01 | 2019-09-01
113 | THSK | L.2.20.1.2 | 2015 | 3 | SSYYDP/THSK/2015/CS/A.8.7.1/SSS/1 (THSK/2015/CS/L.2.20.1.2/IC/2) | Procurement Specialist | CS | CS | 1 | 235737.6 | 210480 | 235738 | 210480 | SSS | N/A | Prior | N/A | 2015-10-02 | N/A | 2015-10-02 | 2015-11-01 | 2019-09-01
114 | SAGEM | E.5.3.3.1 | 2015 | 5 | SDSGRP/GDHR/2012/CS/A.4.4.1/IC/05 (SAGEM/2015/CS/E.5.3.3.1/IC/5) | Consultant for Detailed Analysis and Evaluation of Healthcare Employee Satisfaction Survey | CS | CS | 1 | 8960 | 8000 | 8960 | 8000 | IC | N/A | Post | N/A | 2012-08-01 | 2012-08-01 | 2012-09-01 | 2012-12-01 | 2015-12-01
115 | SAGEM | E.5.1.2.2 | 2015 | 1 | SAGEM/2015/CS/E.5.1.2.2/SSS/1 | Field research service for national household health survey (1) | CS | CS | 1 | 995000.0032 | 888392.86 | 995000 | 888400 | SSS | N/A | Prior | N/A | N/A | 2015-12-02 | 2016-01-16 | 2016-03-01 | 2016-12-01
116 | SAGEM | E.2.1.1.1 | 2015 | 1 | SAGEM/2015/CS/E.2.1.1.1/IC/1 | Software Specialist | CS | CS | 1 | 206208.0048 | 184114.29 | 206209 | 184120 | IC | N/A | Prior | N/A | 2015-10-01 | N/A | 2015-10-01 | 2015-10-01 | 2019-09-01
117 | SAGEM | E.2.1.1.1 | 2015 | 2 | SAGEM/2015/CS/E.2.1.1.1/IC/2 | Training Technologist 1 | CS | CS | 1 | 206208.0048 | 184114.29 | 206209 | 184120 | IC | N/A | Prior | N/A | 2015-10-01 | N/A | 2015-10-01 | 2015-10-01 | 2019-09-01
118 | SAGEM | E.2.1.1.1 | 2015 | 3 | SAGEM/2015/CS/E.2.1.1.1/IC/3 | Assessment and Evaluation Specialist 1 | CS | CS | 1 | 206208.0048 | 184114.29 | 206209 | 184120 | IC | N/A | Prior | N/A | 2015-10-01 | N/A | 2015-10-01 | 2015-10-01 | 2019-09-01
119 | SAGEM | E.2.1.1.1 | 2015 | 4 | SAGEM/2015/CS/E.2.1.1.1/IC/4 | Visual Graphic Design and Animation | CS | CS | 1 | 206208.0048 | 184114.29 | 206209 | 184120 | IC | N/A | Prior | N/A | 2015-10-01 | N/A | 2015-10-01 | 2015-10-01 | 2019-09-01
120 | SAGEM | E.2.1.1.1 | 2015 | 5 | SAGEM/2015/CS/E.2.1.1.1/IC/5 | Training Support Specialist | CS | CS | 1 | 97823.8464 | 87342.72 | 97824 | 87350 | IC | N/A | Post | N/A | 2015-10-01 | N/A | 2015-10-01 | 2015-10-01 | 2019-09-01
121 | SAGEM | E.2.1.1.6 | 2017 | 1 | SAGEM/2017/CS/E.2.1.1.6/IC/1 | Field Consultant | CS | CS | 1 | 3940.6976 | 3518.48 | 3941 | 3520 | IC | N/A | Post | N/A | 2017-01-02 | N/A | 2017-01-02 | 2017-02-01 | 2017-02-01
122 | SAGEM | E.2.1.2.1 | 2016 | 1 | SAGEM/2016/CS/E.2.1.2.1/IC/1 | Consultant for sector analysis and accreditation coordination (report-based) | CS | CS | 1 | 124253.8192 | 110940.91 | 124254 | 110950 | IC | N/A | Post | N/A | 2016-03-02 | N/A | 2016-03-02 | 2016-04-01 | 2019-09-01
123 | TKHK | N.3.1.1 | 2015 | 1 | TKHK/2015/CS/N.3.1.1/IC/1 | EXPERT - GRAPHIC DESIGN, PRESS | CS | CS | 1 | 169919.7696 | 151714.08 | 169920 | 151720 | IC | N/A | Post | N/A | 2015-10-01 | N/A | 2015-10-01 | 2015-10-01 | 2019-09-01
124 | TKHK | N.3.1.4 | 2015 | 1 | TKHK/2015/CS/N.3.1.4/IC/1 | EXPERT - HOSPITAL PHARMACY (report based) | CS | CS | 5 | 424799.872 | 379285.6 | 424800 | 379290 | IC | N/A | Post | N/A | 2015-12-01 | N/A | 2015-12-01 | 2015-12-01 | 2019-09-01
125 | TKHK | N.3.1.3 | 2015 | 1 | TKHK/2015/CS/N.3.1.3/IC/1 | SOFTWARE SPECIALIST - MID LEVEL (Project Phase) | CS | CS | 1 | 212399.8464 | 189642.72 | 212400 | 189650 | IC | N/A | Prior | N/A | 2015-10-01 | N/A | 2015-10-01 | 2015-10-01 | 2019-09-01
126 | TKHK | N.3.1.5 | 2015 | 1 | TKHK/2015/CS/N.3.1.5/IC/1 | HIGH LEVEL PROGRAM OFFICE MANAGER - SOFTWARE SYSTEMS | CS | CS | 1 | 446040.2688 | 398250.24 | 446041 | 398260 | IC | N/A | Prior | N/A | 2015-10-01 | N/A | 2015-10-01 | 2015-10-01 | 2019-09-01
127 | TKHK | N.3.1.5 | 2015 | 2 | TKHK/2015/CS/N.3.1.5/IC/2 | SOFTWARE SPECIALIST - MID LEVEL (Clinical Engineering Phase) | CS | CS | 1 | 212399.8464 | 189642.72 | 212400 | 189650 | IC | N/A | Prior | N/A | 2015-10-01 | N/A | 2015-10-01 | 2015-10-01 | 2019-09-01
128 | TKHK | N.3.1.3 | 2015 | 2 | TKHK/2015/CS/N.3.1.3/IC/2 | EXPERT - HEK (SCRAP) AND MEDICAL WASTE MANAGEMENT (Report based) | CS | CS | 1 | 60179.9184 | 53732.07 | 60180 | 53740 | IC | N/A | Post | N/A | 2015-12-01 | N/A | 2015-12-01 | 2015-12-01 | 2019-09-01
129 | TKHK | N.3.1.3 | 2015 | 3 | TKHK/2015/CS/N.3.1.3/IC/3 | EXPERT - CLINICAL FIELD DESIGN | CS | CS | 1 | 169919.7696 | 151714.08 | 169920 | 151720 | IC | N/A | Post | N/A | 2015-10-01 | N/A | 2015-10-01 | 2015-10-01 | 2019-09-01
130 | TKHK | N.3.1.3 | 2015 | 4 | TKHK/2015/CS/N.3.1.3/IC/4 | EXPERT - CLINICAL FIELD DESIGN (reprot based) | CS | CS | 1 | 84959.9744 | 75857.12 | 84960 | 75860 | IC | N/A | Post | N/A | 2015-12-01 | N/A | 2015-12-01 | 2015-12-01 | 2019-09-01
131 | TKHK | N.3.1.3 | 2015 | 5 | TKHK/2015/CS/N.3.1.3/IC/5 | EXPERT - CLINICAL SERVICE MANAGEMENT (report based) | CS | CS | 1 | 84959.9744 | 75857.12 | 84960 | 75860 | IC | N/A | Post | N/A | 2015-10-01 | N/A | 2015-10-01 | 2015-10-01 | 2019-09-01
132 | TKHK | N.3.1.3 | 2015 | 6 | TKHK/2015/CS/N.3.1.3/IC/6 | EXPERT - FUND RAISING (report based) | CS | CS | 1 | 84959.9744 | 75857.12 | 84960 | 75860 | IC | N/A | Post | N/A | 2015-12-01 | N/A | 2015-12-01 | 2015-12-01 | 2019-09-01
133 | TKHK | N.3.1.7 | 2015 | 1 | TKHK/2015/CS/N.3.1.7 /IC/1 | EXPERT - COST ANALYSIS | CS | CS | 1 | 169919.7696 | 151714.08 | 169920 | 151720 | IC | N/A | Post | N/A | 2015-10-01 | N/A | 2015-10-01 | 2015-10-01 | 2019-09-01
134 | TKHK | N.3.1.3 | 2015 | 7 | TKHK/2015/CS/N.3.1.3/IC/7 | EXPERT - TRANSLATOR | CS | CS | 1 | 169919.7696 | 151714.08 | 169920 | 151720 | IC | N/A | Post | N/A | 2015-10-01 | N/A | 2015-10-01 | 2015-10-01 | 2019-09-01
135 | TKHK | N.3.1.3 | 2015 | 8 | TKHK/2015/CS/N.3.1.3/IC/8 | EXPERT - MEDICAL DEVICE PERFORMANCE MANAGEMENT (report based) | CS | CS | 1 | 84959.9744 | 75857.12 | 84960 | 75860 | IC | N/A | Post | N/A | 2015-12-01 | N/A | 2015-12-01 | 2015-12-01 | 2019-09-01
136 | TKHK | N.3.1.3 | 2015 | 9 | TKHK/2015/CS/N.3.1.3/IC/9 | ACADEMICIAN - CLINICAL ENGINEERING (report based) | CS | CS | 1 | 84959.9744 | 75857.12 | 84960 | 75860 | IC | N/A | Post | N/A | 2015-12-01 | N/A | 2015-12-01 | 2015-12-01 | 2019-09-01
137 | TKHK | N.3.1.3 | 2015 | 10 | TKHK/2015/CS/N.3.1.3/IC/10 | EXPERT - TECHNICAL SERVICE MANAGEMENT (report based) | CS | CS | 2 | 169919.9488 | 151714.24 | 169920 | 151720 | IC | N/A | Post | N/A | 2015-12-01 | N/A | 2015-12-01 | 2015-12-01 | 2019-09-01
138 | TKHK | N.3.1.2 | 2015 | 1 | TKHK/2015/CS/N.3.1.2/IC/1 | EXPERT - MEDICAL SUPPLIES | CS | CS | 1 | 254879.9232 | 227571.36 | 254880 | 227580 | IC | N/A | Prior | N/A | 2015-10-01 | N/A | 2015-10-01 | 2015-10-01 | 2019-09-01
139 | TKHK | N.3.1.2 | 2015 | 2 | TKHK/2015/CS/N.3.1.2/IC/2 | EXPERT - CLINICAL ENGINEERING (report based) | CS | CS | 1 | 84959.9744 | 75857.12 | 84960 | 75860 | IC | N/A | Post | N/A | 2015-12-01 | N/A | 2015-12-01 | 2015-12-01 | 2019-09-01
140 | TKHK | N.3.1.2 | 2015 | 3 | TKHK/2015/CS/N.3.1.2/IC/3 | EXPERT - CLASSIFICATION- BIOMEDICAL (report based) | CS | CS | 3 | 169919.7696 | 151714.08 | 169920 | 151720 | IC | N/A | Post | N/A | 2015-12-01 | N/A | 2015-12-01 | 2015-12-01 | 2019-09-01
141 | TKHK | N.3.1.2 | 2015 | 4 | TKHK/2015/CS/N.3.1.2/IC/4 | EXPERT - CLASSIFICATION -MEDICAL (report based) | CS | CS | 5 | 424799.872 | 379285.6 | 424800 | 379290 | IC | N/A | Post | N/A | 2015-12-01 | N/A | 2015-12-01 | 2015-12-01 | 2019-09-01
142 | TKHK | N.3.1.6 | 2015 | 1 | TKHK/2015/CS/N.3.1.6/IC/1 | EXPERT - LEAN MANAGEMENT (report based) | CS | CS | 1 | 84959.9744 | 75857.12 | 84960 | 75860 | IC | N/A | Post | N/A | 2015-12-01 | N/A | 2015-12-01 | 2015-12-01 | 2019-09-01
143 | TKHK | N.3.1.6 | 2015 | 2 | TKHK/2015/CS/N.3.1.6/IC/2 | ACADEMICIAN - LEAN MANAGEMENT report based) | CS | CS | 2 | 148679.9552 | 132749.96 | 148680 | 132750 | IC | N/A | Post | N/A | 2015-12-01 | N/A | 2015-12-01 | 2015-12-01 | 2019-09-01
144 | TKHK | N.3.1.7 | 2015 | 2 | TKHK/2015/CS/N.3.1.7/IC/2 | EXPERT - FINANCE | CS | CS | 1 | 169919.7696 | 151714.08 | 169920 | 151720 | IC | N/A | Post | N/A | 2015-10-01 | N/A | 2015-10-01 | 2015-10-01 | 2019-09-01
145 | TKHK | N.3.1.7 | 2015 | 3 | TKHK/2015/CS/N.3.1.7/IC/3 | EXPERT - FINANCIAL ANALYSIS | CS | CS | 1 | 254879.9232 | 227571.36 | 254880 | 227580 | IC | N/A | Prior | N/A | 2015-10-01 | N/A | 2015-10-01 | 2015-10-01 | 2019-09-01
146 | TKHK | N.3.1.8 | 2015 | 1 | TKHK/2015/CS/N.3.1.8/IC/1 | ACADEMICIAN - ACTIVITY SCORING (report based) | CS | CS | 1 | 84959.9744 | 75857.12 | 84960 | 75860 | IC | N/A | Post | N/A | 2015-12-01 | N/A | 2015-12-01 | 2015-12-01 | 2019-09-01
147 | TKHK | N.3.1.8 | 2015 | 2 | TKHK/2015/CS/N.3.1.8/IC/2 | ACADEMICIAN - PERFORMANCE MANAGEMENT (report based) | CS | CS | 1 | 84959.9744 | 75857.12 | 84960 | 75860 | IC | N/A | Post | N/A | 2015-12-01 | N/A | 2015-12-01 | 2015-12-01 | 2019-09-01
148 | TKHK | N.3.1.8 | 2015 | 3 | TKHK/2015/CS/N.3.1.8/IC/3 | ACADEMICIAN - MEDICAL PROCESS MANAGEMENT (report based) | CS | CS | 4 | 339839.8976 | 303428.48 | 339840 | 303430 | IC | N/A | Post | N/A | 2015-12-01 | N/A | 2015-12-01 | 2015-12-01 | 2019-09-01
149 | TKHK | N.3.1.8 | 2015 | 4 | TKHK/2015/CS/N.3.1.8/IC/4 | EXPERT - STATISTICAL ANALYSIS | CS | CS | 1 | 84959.9744 | 75857.12 | 84960 | 75860 | IC | N/A | Post | N/A | 2015-12-01 | N/A | 2015-12-01 | 2015-12-01 | 2019-09-01
150 | TKHK | N.3.1.8 | 2015 | 5 | TKHK/2015/CS/N.3.1.8/IC/5 | SOFTWARE SPECIALIST - MID LEVEL (Needs Management System) | CS | CS | 1 | 212399.8464 | 189642.72 | 212400 | 189650 | IC | N/A | Prior | N/A | 2015-10-01 | N/A | 2015-10-01 | 2015-10-01 | 2019-09-01
151 | TKHK | N.3.1.9 | 2015 | 1 | TKHK/2015/CS/N.3.1.9/IC/1 | ACADEMICIAN - HEALTH CARE SERVICES (report based) | CS | CS | 3 | 254879.9232 | 227571.36 | 254880 | 227580 | IC | N/A | Post | N/A | 2015-12-01 | N/A | 2015-12-01 | 2015-12-01 | 2019-09-01
152 | SYGM | F.3.1.1.3 | 2015 | 1 | SYGM/2015/CS/F.3.1.1.3/IC/1 | Supervisor Architect | CS | CS | 1 | 253903 | 226699.1071 | 253900 | 226700 | IC | N/A | Prior | N/A | 2016-01-01 | N/A | 2016-01-01 | 2016-01-01 | 2020-01-01
153 | SYGM | F.3.1.1.3 | 2015 | 2-1. | SYGM/2015/CS/F.3.1.1.3/IC/2-1. | Architect | CS | CS | 1 | 205076 | 183103.5714 | 205076 | 183110 | IC | N/A | Prior | N/A | 2016-01-01 | N/A | 2016-01-01 | 2016-01-01 | 2020-01-01
154 | SYGM | F.3.1.1.3 | 2015 | 2-2. | SYGM/2015/CS/F.3.1.1.3/IC/2-2. | Architect | CS | CS | 1 | 205076 | 183103.5714 | 205076 | 183110 | IC | N/A | Prior | N/A | 2016-01-01 | N/A | 2016-01-01 | 2016-01-01 | 2020-01-01
155 | SYGM | F.3.1.1.3 | 2015 | 2-3. | SYGM/2015/CS/F.3.1.1.3/IC/2-3. | Architect | CS | CS | 1 | 166014 | 148226.7857 | 166014 | 148230 | IC | N/A | Post | N/A | 2016-01-01 | N/A | 2016-01-01 | 2016-01-01 | 2020-01-01
156 | SYGM | F.3.1.1.3 | 2015 | 2-4. | SYGM/2015/CS/F.3.1.1.3/IC/2-4. | Architect | CS | CS | 1 | 166014 | 148226.7857 | 166014 | 148230 | IC | N/A | Post | N/A | 2016-01-01 | N/A | 2016-01-01 | 2016-01-01 | 2020-01-01
157 | SYGM | F.3.1.1.3 | 2015 | 3-1. | SYGM/2015/CS/F.3.1.1.3/IC/3-1. | Civil Engineer | CS | CS | 1 | 205076 | 183103.5714 | 205076 | 183110 | IC | N/A | Prior | N/A | 2016-01-01 | N/A | 2016-01-01 | 2016-01-01 | 2020-01-01
158 | SYGM | F.3.1.1.3 | 2015 | 3-2. | SYGM/2015/CS/F.3.1.1.3/IC/3-2. | Civil Engineer | CS | CS | 1 | 205076 | 183103.5714 | 205076 | 183110 | IC | N/A | Prior | N/A | 2016-01-01 | N/A | 2016-01-01 | 2016-01-01 | 2020-01-01
159 | SYGM | F.3.1.1.3 | 2015 | 4-1. | SYGM/2015/CS/F.3.1.1.3/IC/4-1. | Mechanical Engineer | CS | CS | 1 | 205076 | 183103.5714 | 205076 | 183110 | IC | N/A | Prior | N/A | 2016-01-01 | N/A | 2016-01-01 | 2016-01-01 | 2020-01-01
160 | SYGM | F.3.1.1.3 | 2015 | 4-2. | SYGM/2015/CS/F.3.1.1.3/IC/4-2. | Mechanical Engineer | CS | CS | 1 | 205076 | 183103.5714 | 205076 | 183110 | IC | N/A | Prior | N/A | 2016-01-01 | N/A | 2016-01-01 | 2016-01-01 | 2020-01-01
161 | SYGM | F.3.1.1.3 | 2015 | 5 | SYGM/2015/CS/F.3.1.1.3/IC/5 | Electrical and Electronic Engineer | CS | CS | 1 | 205076 | 183103.5714 | 205070 | 183110 | IC | N/A | Prior | N/A | 2016-01-01 | N/A | 2016-01-01 | 2016-01-01 | 2020-01-01
162 | SYGM | F.3.1.1.3 | 2015 | 6 | SYGM/2015/CS/F.3.1.1.3/IC/6 | Information Technologies Engineer | CS | CS | 1 | 205076 | 183103.5714 | 205000 | 183110 | IC | N/A | Prior | N/A | 2016-01-01 | N/A | 2016-01-01 | 2016-01-01 | 2020-01-01
163 | SYGM | F.3.1.1.3 | 2015 | 7 | SYGM/2015/CS/F.3.1.1.3/IC/7 | Medical Equipment Specialist | CS | CS | 1 | 205076 | 183103.5714 | 205070 | 183110 | IC | N/A | Prior | N/A | 2016-01-01 | N/A | 2016-01-01 | 2016-01-01 | 2020-01-01
164 | SYGM | F.3.1.1.3 | 2015 | 8 | SYGM/2015/CS/F.3.1.1.3/IC/8 | Biomedical Engineer | CS | CS | 1 | 205076 | 183103.5714 | 205070 | 183110 | IC | N/A | Prior | N/A | 2016-01-01 | N/A | 2016-01-01 | 2016-01-01 | 2020-01-01
165 | SYGM | F.3.1.1.3 | 2015 | 9-1. | SYGM/2015/CS/F.3.1.1.3/IC/9-1. | Finance Specialist | CS | CS | 1 | 205076 | 183103.5714 | 205076 | 183110 | IC | N/A | Prior | N/A | 2016-01-01 | N/A | 2016-01-01 | 2016-01-01 | 2020-01-01
166 | SYGM | F.3.1.1.3 | 2015 | 9-2. | SYGM/2015/CS/F.3.1.1.3/IC/9-2. | Finance Specialist | CS | CS | 1 | 205076 | 183103.5714 | 205076 | 183110 | IC | N/A | Prior | N/A | 2016-01-01 | N/A | 2016-01-01 | 2016-01-01 | 2020-01-01
167 | SYGM | F.3.1.1.3 | 2015 | 10-1. | SYGM/2015/CS/F.3.1.1.3/IC/10-1. | Legal Expert | CS | CS | 1 | 205076 | 183103.5714 | 205076 | 183110 | IC | N/A | Prior | N/A | 2016-01-15 | N/A | 2016-01-15 | 2016-01-15 | 2020-01-01
168 | SYGM | F.3.1.1.3 | 2015 | 10-2. | SYGM/2015/CS/F.3.1.1.3/IC/10-2. | Legal Expert | CS | CS | 1 | 205076 | 183103.5714 | 205076 | 183110 | IC | N/A | Prior | N/A | 2016-01-15 | N/A | 2016-01-15 | 2016-01-15 | 2020-01-01
169 | SYGM | F.3.1.1.3 | 2015 | 11-1. | SYGM/2015/CS/F.3.1.1.3/IC/11-1. | Medical Business Expert | CS | CS | 1 | 205076 | 183103.5714 | 205076 | 183110 | IC | N/A | Prior | N/A | 2016-01-01 | N/A | 2016-01-01 | 2016-01-01 | 2020-01-01
170 | SYGM | F.3.1.1.3 | 2015 | 11-2. | SYGM/2015/CS/F.3.1.1.3/IC/11-2. | Medical Business Expert | CS | CS | 1 | 205076 | 183103.5714 | 205076 | 183110 | IC | N/A | Prior | N/A | 2016-01-01 | N/A | 2016-01-01 | 2016-01-01 | 2020-01-01
171 | SYGM | F.3.1.1.3 | 2015 | 12 | SYGM/2015/CS/F.3.1.1.3/IC/12 | Urban and Regional Planner | CS | CS | 1 | 205076 | 183103.5714 | 205000 | 183110 | IC | N/A | Prior | N/A | 2016-01-01 | N/A | 2016-01-01 | 2016-01-01 | 2020-01-01
172 | SYGM | F.3.1.1.3 | 2015 | 1 | SYGM/2015/CS/F.3.1.1.3/QCBS/1 | Institutional Law and Finance Consultancy | CS | CS | 1 | 5040000 | 4500000 | 5040000 | 4500000 | QCBS | N/A | Prior | N/A | 2015-10-31 | 2015-12-15 | 2016-02-13 | 2016-04-13 | 2017-12-01
173 | SYGM | F.3.1.1.3 | 2015 | 2 | SYGM/2015/CS/F.3.1.1.3/QCBS/2 | Engineering and Architecture Consultancy | CS | CS | 1 | 3334007.04 | 2976792 | 3334000 | 2976800 | QCBS | N/A | Post | N/A | 2015-10-31 | 2015-12-30 | 2016-02-28 | 2016-04-28 | 2017-12-01
174 | SYGM | F.3.1.1.3 | 2015 | 1 | SYGM/2015/CS/F.3.1.1.3/QCBS/1 | Medical Business and Equipment Consultancy | CS | CS | 1 | 1000016.64 | 892872 | 1000000 | 892880 | QCBS | N/A | Post | N/A | 2015-10-31 | 2016-01-14 | 2016-03-14 | 2016-05-13 | 2017-12-01
175 | SYGM | F.2.1.1.1 | 2015 | 1-1. | SYGM/2015/CS/F.2.1.1.1/IC/1-1. | Architect | CS | CS | 1 | 180127 | 160827.6786 | 180130 | 160830 | IC | N/A | Post | N/A | 2016-01-01 | N/A | 2016-01-01 | 2016-01-01 | 2018-12-01
176 | SYGM | F.2.1.1.1 | 2015 | 1-2. | SYGM/2015/CS/F.2.1.1.1/IC/1-2. | Architect | CS | CS | 1 | 120084 | 107217.8571 | 120090 | 107220 | IC | N/A | Post | N/A | 2016-01-01 | N/A | 2016-01-01 | 2016-01-01 | 2018-12-01
177 | SYGM | F.2.1.1.1 | 2015 | 2 | SYGM/2015/CS/F.2.1.1.1/IC/2 | Mechanical Engineer | CS | CS | 1 | 150106 | 134023.2143 | 150110 | 134030 | IC | N/A | Post | N/A | 2016-01-01 | N/A | 2016-01-01 | 2016-01-01 | 2018-12-01
178 | SYGM | F.2.1.1.1 | 2015 | 3 | SYGM/2015/CS/F.2.1.1.1/IC/3 | Electrical and Electronic Engineer | CS | CS | 1 | 180127 | 160827.6786 | 180130 | 160830 | IC | N/A | Post | N/A | 2016-01-01 | N/A | 2016-01-01 | 2016-01-01 | 2018-12-01
179 | SYGM | F.1.2.1.1 | 2015 | 1 | SYGM/2015/CS/F.1.2.1.1/IC/1 | Architect | CS | CS | 1 | 150106 | 134023.2143 | 150110 | 134030 | IC | N/A | Post | N/A | 2016-01-01 | N/A | 2016-01-01 | 2016-01-01 | 2018-12-01
180 | SYGM | F.1.2.1.1 | 2015 | 2 | SYGM/2015/CS/F.1.2.1.1/IC/2 | Mechanical Engineer | CS | CS | 1 | 180127 | 160827.6786 | 180130 | 160830 | IC | N/A | Post | N/A | 2016-01-01 | N/A | 2016-01-01 | 2016-01-01 | 2018-12-01
181 | SYGM | F.1.2.1.1 | 2015 | 3 | SYGM/2015/CS/F.1.2.1.1/IC/3 | Electrical and Electronic Engineer | CS | CS | 1 | 150106 | 134023.2143 | 150110 | 134030 | IC | N/A | Post | N/A | 2016-01-01 | N/A | 2016-01-01 | 2016-01-01 | 2018-12-01
182 | SYGM | F.1.2.1.1 | 2015 | 4 | SYGM/2015/CS/F.1.2.1.1/IC/4 | Environmental Engineer | CS | CS | 1 | 150106 | 134023.2143 | 150110 | 134030 | IC | N/A | Post | N/A | 2016-01-01 | N/A | 2016-01-01 | 2016-01-01 | 2018-12-01
183 | SHGM | A.1.1.2.2 | 2015 | 1 | SHGM/2015/CS/A.1.1.2.2/IC/1 | Report-based expertise support for determining the risk areas | CS | CS | 1 | 21428.568 | 19132.65 | 21429 | 19140 | IC | N/A | Post | N/A | 2015-10-01 | N/A | 2015-10-01 | 2015-10-01 | 2015-12-01
184 | SHGM | A.1.1.3.2 | 2015 | 1 | SHGM/2015/CS/A.1.1.3.2/IC/1 | Expertise support for determining the risk criteria | CS | CS | 1 | 62499.976 | 55803.55 | 62500 | 55810 | IC | N/A | Post | N/A | 2015-12-02 | N/A | 2015-12-02 | 2016-01-01 | 2017-03-01
185 | SHGM | A.1.1.4.1 | 2015 | 1 | SHGM/2015/CS/A.1.1.4.1/IC/1 | Software Specialist | CS | CS | 1 | 142000.1856 | 126785.88 | 142000 | 126790 | IC | N/A | Post | N/A | 2015-12-02 | N/A | 2015-12-02 | 2016-01-01 | 2019-09-01
186 | SHGM | A.1.1.4.3 | 2015 | 1 | SHGM/2015/CS/A.1.1.4.3/IC/1 | Data Mining Specialist | CS | CS | 1 | 70999.8912 | 63392.76 | 71000 | 63400 | IC | N/A | Post | N/A | 2015-12-02 | N/A | 2015-12-02 | 2016-01-01 | 2019-09-01
187 | SHGM | A.1.1.6.5 | 2016 | 1 | SHGM/2016/CS/A.1.1.6.5/IC/1 | Technical Service Procurement for detecting medical procedures applied inappropriately and without indication | CS | CS | Multiple | 500000 | 446428.5714 | 500000 | 446430 | IC | N/A | Post | N/A | 2016-10-02 | N/A | 2016-10-02 | 2016-11-01 | 2016-11-01
188 | SHGM | A.1.1.6.6 | 2016 | 1 | SHGM/2016/CS/A.1.1.6.6/IC/1 | Biostatistician | CS | CS | 1 | 105000.0448 | 93750.04 | 105000 | 93760 | IC | N/A | Post | N/A | 2016-07-02 | N/A | 2016-07-02 | 2016-08-01 | 2018-06-01
189 | SHGM | A.1.2.5.1 | 2016 | 1 | SHGM/2016/CS/A.1.2.5.1/IC/1 | Statistics, Analysis and Reporting Specialist | CS | CS | 1 | 20000 | 17857.1429 | 20000 | 17860 | IC | N/A | Post | N/A | 2016-09-01 | N/A | 2016-09-01 | 2016-10-01 | 2016-10-01
190 | SHGM | A.3.1.2.1 | 2015 | 1 | SHGM/2015/CS/A.3.1.2.1/IC/1 | Mental Health Specialist | CS | CS | 1 | 59996.16 | 53568 | 60000 | 53570 | IC | N/A | Post | N/A | 2015-12-31 | N/A | 2015-12-31 | 2016-02-01 | 2017-03-01
191 | SHGM | A.1.3.3.1 | 2016 | 1 | SHGM/2016/CS/A.1.3.3.1/IC/1 | Software Specialist | CS | CS | 1 | 30000 | 26785.7143 | 30000 | 26790 | IC | N/A | Post | N/A | 2016-01-02 | N/A | 2016-01-02 | 2016-02-01 | 2016-07-01
192 | ASHGM | B.1.1.1.2 | 2015 | 1 | ASHGM/2015/CS/B.1.1.1.2/IC/1 | Procurement of Statistical Consultancy Service | CS | CS | 1 | 59208.0048 | 52864.29 | 59209 | 52870 | IC | N/A | Post | N/A | 2015-10-01 | N/A | 2015-10-01 | 2015-10-01 | 2017-03-24
193 | DISAB | G.1.1.1.1 | 2015 | 1 | DISAB/2015/CS/G.1.1.1.1/IC/1 | Organization Consultant | CS | CS | 1 | 103900.0032 | 92767.86 | 103900 | 92770 | IC | N/A | Post | N/A | 2015-10-01 | N/A | 2015-10-01 | 2015-10-01 | 2019-09-01
194 | DISAB | G.1.1.2.1 | 2016 | 1 | DISAB/2016/CS/G.1.1.2.1/IC/1 | Healthcare System Analysis Consultant 1 | CS | CS | 1 | 7000 | 6250 | 7000 | 6250 | IC | N/A | Post | N/A | 2016-05-02 | N/A | 2016-05-02 | 2016-06-01 | 2016-06-01
195 | DISAB | G.1.1.2.1 | 2016 | 2 | DISAB/2016/CS/G.1.1.2.1/IC/2 | Healthcare System Analysis Consultant 2 | CS | CS | 1 | 7000 | 6250 | 7000 | 6250 | IC | N/A | Post | N/A | 2016-06-01 | N/A | 2016-06-01 | 2016-07-01 | 2016-07-01
196 | DISAB | G.1.1.2.1 | 2016 | 3 | DISAB/2016/CS/G.1.1.2.1/IC/3 | Healthcare System Analysis Consultant 3 | CS | CS | 1 | 7000 | 6250 | 7000 | 6250 | IC | N/A | Post | N/A | 2016-07-02 | N/A | 2016-07-02 | 2016-08-01 | 2016-08-01
197 | DISAB | G.1.1.2.1 | 2016 | 4 | DISAB/2016/CS/G.1.1.2.1/IC/4 | Healthcare System Analysis Consultant 4 | CS | CS | 1 | 7000 | 6250 | 7000 | 6250 | IC | N/A | Post | N/A | 2016-08-02 | N/A | 2016-08-02 | 2016-09-01 | 2016-09-01
198 | DISAB | G.1.1.2.3 | 2016 | 1 | DISAB/2016/CS/G.1.1.2.3/IC/1 | Graphics and Editorial Consultancy 1 | CS | CS | 1 | 24999.52 | 22321 | 25000 | 22330 | IC | N/A | Post | N/A | 2016-07-02 | N/A | 2016-07-02 | 2016-08-01 | 2016-08-01
199 | DISAB | G.1.1.2.3 | 2016 | 2 | DISAB/2016/CS/G.1.1.2.3/IC/2 | Graphics and Editorial Consultancy 2 | CS | CS | 1 | 24999.52 | 22321 | 25000 | 22330 | IC | N/A | Post | N/A | 2016-11-01 | N/A | 2016-11-01 | 2016-12-01 | 2016-12-01
200 | DISAB | G.1.1.5.2 | 2016 | 1 | DISAB/2016/CS/G.1.1.5.2/IC/1 | Graphics and Editorial consultancy service procurement | CS | CS | 1 | 79569.448 | 71044.15 | 79570 | 71050 | IC | N/A | Post | N/A | 2016-01-31 | N/A | 2016-01-31 | 2016-03-01 | 2016-06-01
201 | SAGEM | E.1.1.1.3 | 2015 | 1 | SAGEM/2015/CS/E.1.1.1.3/IC/1 | Software Consultant | CS | CS | 1 | 173407.696 | 154828.3 | 173408 | 154830 | IC | N/A | Post | N/A | 2015-10-01 | N/A | 2015-10-01 | 2015-10-01 | 2019-09-01
202 | SAGEM | E.1.1.1.3 | 2015 | 2 | SAGEM/2015/CS/E.1.1.1.3/IC/2 | Consultant for Project and International Health Statistics | CS | CS | 1 | 165409.664 | 147687.2 | 165410 | 147690 | IC | N/A | Post | N/A | 2015-10-01 | N/A | 2015-10-01 | 2015-10-01 | 2019-09-01
203 | SAGEM | E.1.1.1.3 | 2015 | 3 | SAGEM/2015/CS/E.1.1.1.3/IC/3 | Biostatistics Consultant | CS | CS | 1 | 149492.112 | 133475.1 | 149493 | 133480 | IC | N/A | Post | N/A | 2015-10-01 | N/A | 2015-10-01 | 2015-10-01 | 2019-09-01
204 | SAGEM | E.1.1.4.1 | 2016 | 1 | SAGEM/2016/CS/E.1.1.4.1/IC/1 | Miscellaneous International Individual Consultants | CS | CS | 6 | 503690.5216 | 449723.68 | 503700 | 449730 | IC | N/A | Post | N/A | 2016-08-02 | N/A | 2016-08-02 | 2016-09-01 | 2018-12-01
205 | SAGEM | E.6.1.1.1 | 2015 | 1 | SAGEM/2015/CS/E.6.1.1.1/IC/1 | Project Assistant | CS | CS | 1 | 158400.0768 | 141428.64 | 158400 | 141430 | IC | N/A | Post | N/A | 2015-10-01 | N/A | 2015-10-01 | 2015-10-01 | 2019-09-01
206 | SAGEM | E.6.1.1.1 | 2015 | 2 | SAGEM/2015/CS/E.6.1.1.1/IC/2 | Health Economist | CS | CS | 1 | 148799.9968 | 132857.14 | 148800 | 132860 | IC | N/A | Post | N/A | 2015-10-01 | N/A | 2015-10-01 | 2015-10-01 | 2019-09-01
207 | SAGEM | E.6.1.2.2 | 2015 | 1 | SAGEM/2015/CS/E.6.1.2.2/CQS/1 | Procurement of Consultancy Service for First Subject-Oriented HTA Work | CS | CS | 1 | 169949.9984 | 151741.07 | 169950 | 151750 | CQS | N/A | Prior | N/A | 2015-12-02 | 2016-01-01 | 2016-02-01 | 2016-03-01 | 2016-10-01
208 | SAGEM | E.6.1.2.2 | 2016 | 1 | SAGEM/2016/CS/E.6.1.2.2/CQS/1 | Procurement of Consultancy Service for Second Subject-Oriented HTA Work | CS | CS | 1 | 169949.9984 | 151741.07 | 169950 | 151750 | CQS | N/A | Post | N/A | 2016-01-02 | 2016-02-01 | 2016-03-03 | 2016-04-01 | 2016-11-01
209 | SAGEM | E.6.1.2.2 | 2016 | 2 | SAGEM/2016/CS/E.6.1.2.2/CQS/2 | Procurement of Consultancy Service for Third Subject-Oriented HTA Work | CS | CS | 1 | 169949.9984 | 151741.07 | 169950 | 151750 | CQS | N/A | Post | N/A | 2016-02-01 | 2016-03-02 | 2016-04-02 | 2016-05-01 | 2016-12-01
210 | SAGEM | E.6.1.2.2 | 2016 | 3 | SAGEM/2016/CS/E.6.1.2.2/CQS/3 | Procurement of Consultancy Service for Fourth Subject-Oriented HTA Work | CS | CS | 1 | 169949.9984 | 151741.07 | 169950 | 151750 | CQS | N/A | Post | N/A | 2016-12-01 | 2016-12-31 | 2017-01-31 | 2017-03-01 | 2017-03-01
211 | SAGEM | E.5.3.1.1 | 2015 | 1 | SAGEM/2015/CS/E.5.3.1.1/IC/1 | National Consultant for Instrument Development | CS | CS | 2 | 30000.0064 | 26785.72 | 30000 | 26790 | IC | N/A | Post | N/A | 2015-10-02 | N/A | 2015-10-02 | 2015-11-01 | 2015-11-01
212 | SAGEM | E.5.3.1.2 | 2015 | 1 | SAGEM/2015/CS/E.5.3.1.2/IC/1 | Consultancy Service for Basic Training for Healthcare System Evaluation -1 (National Academician) | CS | CS | 2 | 15000.0032 | 13392.86 | 15000 | 13400 | IC | N/A | Post | N/A | 2015-11-01 | N/A | 2015-11-01 | 2015-12-01 | 2015-12-01
213 | SAGEM | E.5.3.1.2 | 2015 | 2 | SAGEM/2015/CS/E.5.3.1.2/IC/2 | Consultancy Service for Basic Training for Healthcare System Evaluation -3 (International Academician) | CS | CS | 1 | 8000 | 7142.8571 | 8000 | 7150 | IC | N/A | Post | N/A | 2015-11-01 | N/A | 2015-11-01 | 2015-12-01 | 2015-12-01
214 | SAGEM | E.5.3.1.2 | 2016 | 1 | SAGEM/2016/CS/E.5.3.1.2/IC/1 | Consultancy Service for Advanced Training for Healthcare System Evaluation -2 (National Academician) | CS | CS | 2 | 10000.0096 | 8928.58 | 10000 | 8930 | IC | N/A | Post | N/A | 2016-03-02 | N/A | 2016-03-02 | 2016-04-01 | 2016-04-01
215 | SAGEM | E.5.3.1.2 | 2016 | 2 | SAGEM/2016/CS/E.5.3.1.2/IC/2 | Consultancy Service for Advanced Training for Healthcare System Evaluation -3 (International Academician) | CS | CS | 2 | 16000 | 14285.7143 | 16000 | 14290 | IC | N/A | Post | N/A | 2016-03-02 | N/A | 2016-03-02 | 2016-04-01 | 2016-04-01
216 | SAGEM | E.5.3.1.2 | 2016 | 3 | SAGEM/2016/CS/E.5.3.1.2/IC/3 | Consultancy Service for Trainers' Training for Healthcare System Evaluation -2 (National Academician) | CS | CS | 2 | 12000.0048 | 10714.29 | 12000 | 10720 | IC | N/A | Post | N/A | 2016-08-02 | N/A | 2016-08-02 | 2016-09-01 | 2016-09-01
217 | SAGEM | E.5.3.1.2 | 2016 | 4 | SAGEM/2016/CS/E.5.3.1.2/IC/4 | Consultancy Service for Trainers' Training for Healthcare System Evaluation -3 (International Academician) | CS | CS | 2 | 16000 | 14285.7143 | 16000 | 14290 | IC | N/A | Post | N/A | 2016-08-02 | N/A | 2016-08-02 | 2016-09-01 | 2016-09-01
218 | SAGEM | E.5.3.1.2 | 2015 | 5 | SAGEM/2015/CS/E.5.3.1.2/IC/5 | Training Consultancy Service for Geographic Information Systems Software Training Program | CS | CS | 1 | 6000 | 5357.1429 | 6000 | 5360 | IC | N/A | Post | N/A | 2015-12-02 | N/A | 2015-12-02 | 2016-01-01 | 2016-01-01
219 | SAGEM | E.5.3.1.2 | 2016 | 1 | SAGEM/2016/CS/E.5.3.1.2/IC/1 | Consultancy Service for Basic Training for Healthcare System Evaluation -1 (National Academician) | CS | CS | 2 | 15000.0032 | 13392.86 | 15000 | 13400 | IC | N/A | Post | N/A | 2016-12-02 | N/A | 2016-12-02 | 2017-01-01 | 2017-01-01
220 | SAGEM | E.5.3.1.2 | 2016 | 2 | SAGEM/2016/CS/E.5.3.1.2/IC/2 | Consultancy Service for Basic Training for Healthcare System Evaluation -3 (International Academician) | CS | CS | 1 | 8000 | 7142.8571 | 8000 | 7150 | IC | N/A | Post | N/A | 2016-12-02 | N/A | 2016-12-02 | 2017-01-01 | 2017-01-01
221 | SAGEM | E.5.3.1.3 | 2016 | 1 | SAGEM/2016/CS/E.5.3.1.3/IC/1 | Consultancy service for completing the healthcare system evaluation works by the end of 2019 1 (National/Int. Academician) | CS | CS | 2 | 20000 | 17857.1429 | 20000 | 17860 | IC | N/A | Post | N/A | 2016-05-02 | N/A | 2016-05-02 | 2016-06-01 | 2016-06-01
222 | SAGEM | E.5.3.1.3 | 2016 | 2 | SAGEM/2016/CS/E.5.3.1.3/IC/2 | Consultancy service for data analysis 1(National Academician) | CS | CS | 1 | 10000 | 8928.5714 | 10000 | 8930 | IC | N/A | Post | N/A | 2016-05-02 | N/A | 2016-05-02 | 2016-06-01 | 2016-06-01
223 | SAGEM | E.5.3.1.3 | 2016 | 3 | SAGEM/2016/CS/E.5.3.1.3/IC/3 | Training consultancy for stakeholder meeting on Turkish Healthcare System Performance Assessment -1 (national) | CS | CS | 1 | 3000 | 2678.5714 | 3000 | 2680 | IC | N/A | Post | N/A | 2016-01-02 | N/A | 2016-01-02 | 2016-02-01 | 2016-02-01
224 | SAGEM | E.5.3.1.3 | 2016 | 4 | SAGEM/2016/CS/E.5.3.1.3/IC/4 | Training consultancy for stakeholder meeting on Turkish Healthcare System Performance Assessment -1 (international) | CS | CS | 1 | 6000 | 5357.1429 | 6000 | 5360 | IC | N/A | Post | N/A | 2016-01-02 | N/A | 2016-01-02 | 2016-02-01 | 2016-02-01
225 | SAGEM | E.5.3.2.1 | 2015 | 1 | SAGEM/2015/CS/E.5.3.2.1/IC/1 | Training Consultant for Evaluation of HTP Policies | CS | CS | 3 | 15000 | 13392.8571 | 15000 | 13400 | IC | N/A | Post | N/A | 2015-11-01 | N/A | 2015-11-01 | 2015-12-01 | 2015-12-01
226 | SAGEM | E.5.3.2.1 | 2015 | 2 | SAGEM/2015/CS/E.5.3.2.1/IC/2 | Consultant for HTP Policies Evaluation Training Program and Content Preparation | CS | CS | 3 | 15000 | 13392.8571 | 15000 | 13400 | IC | N/A | Post | N/A | 2015-11-01 | N/A | 2015-11-01 | 2015-12-01 | 2015-12-01
227 | SAGEM | E.5.3.2.2 | 2016 | 1 | SAGEM/2016/CS/E.5.3.2.2/IC/1 | Training Consultant for Evaluation of HTP Policies | CS | CS | 3 | 60000 | 53571.4286 | 60000 | 53580 | IC | N/A | Post | N/A | 2016-05-02 | N/A | 2016-05-02 | 2016-06-01 | 2016-12-01
228 | SAGEM | E.5.3.2.2 | 2016 | 2 | SAGEM/2016/CS/E.5.3.2.2/IC/2 | Consultant for HTP Policies Evaluation Training Program and Content Preparation | CS | CS | 3 | 60000 | 53571.4286 | 60000 | 53580 | IC | N/A | Post | N/A | 2016-05-02 | N/A | 2016-05-02 | 2016-06-01 | 2016-12-01
229 | SAGEM | E.5.3.2.2 | 2016 | 3 | SAGEM/2016/CS/E.5.3.2.2/IC/3 | Consultant for Turkish Editing of Training Modules of HTP Policies Evaluation | CS | CS | 1 | 750 | 669.6429 | 750 | 670 | IC | N/A | Post | N/A | 2016-07-02 | N/A | 2016-07-02 | 2016-08-01 | 2016-08-01
230 | SAGEM | E.5.3.2.2 | 2016 | 4 | SAGEM/2016/CS/E.5.3.2.2/IC/4 | International Consultant for Healthcare Policies | CS | CS | 2 | 30000 | 26785.7143 | 30000 | 26790 | IC | N/A | Post | N/A | 2016-10-02 | N/A | 2016-10-02 | 2016-11-01 | 2016-11-01
231 | SAGEM | E.5.3.2.2 | 2017 | 1 | SAGEM/2017/CS/E.5.3.2.2/IC/1 | Consultant for Turkish Editing of Training Modules of HTP Policies Evaluation | CS | CS | 1 | 750 | 669.6429 | 750 | 670 | IC | N/A | Post | N/A | 2017-01-02 | N/A | 2017-01-02 | 2017-02-01 | 2017-02-01
232 | SAGEM | E.5.3.2.2 | 2017 | 2 | SAGEM/2017/CS/E.5.3.2.2/IC/2 | English Editing of Training Modules of HTP Policies Evaluation | CS | CS | 1 | 1500 | 1339.2857 | 1500 | 1340 | IC | N/A | Post | N/A | 2017-01-02 | N/A | 2017-01-02 | 2017-02-01 | 2017-02-01
233 | SAGEM | E.5.3.2.2 | 2017 | 3 | SAGEM/2017/CS/E.5.3.2.2/IC/3 | Consultant for Arabic Editing of Training Modules of HTP Policies Evaluation | CS | CS | 1 | 2250 | 2008.9286 | 2250 | 2010 | IC | N/A | Post | N/A | 2017-01-02 | N/A | 2017-01-02 | 2017-02-01 | 2017-02-01
234 | SAGEM | E.5.3.3.1 | 2015 | 1 | SAGEM/2015/CS/E.5.3.3.1/IC/1 | Consultant for the evaluation of healthcare system and policy applications | CS | CS | 1 | 217000 | 193750 | 217000 | 193750 | IC | N/A | Prior | N/A | 2015-10-02 | N/A | 2015-10-02 | 2015-11-01 | 2019-09-01
235 | SAGEM | E.5.3.3.1 | 2015 | 2 | SAGEM/2015/CS/E.5.3.3.1/IC/2 | International relations consultancy service | CS | CS | 1 | 168000 | 150000 | 168000 | 150000 | IC | N/A | Post | N/A | 2015-10-01 | N/A | 2015-10-01 | 2015-10-01 | 2019-09-01
236 | SAGEM | E.5.3.3.1 | 2015 | 4 | SAGEM/2015/CS/E.5.3.3.1/IC/4 | Healthcare system evaluation | CS | CS | 1 | 148800.1536 | 132857.28 | 148801 | 132860 | IC | N/A | Post | N/A | 2015-10-01 | N/A | 2015-10-01 | 2015-10-01 | 2019-09-01
237 | SAGEM | E.5.1.1.1 | 2015 | 1 | SAGEM/2015/CS/E.5.1.1.1/IC/1 | Consultancy Service for Evidence-based Healthcare Policy Development Training | CS | CS | 2 | 9999.36 | 8928 | 10000 | 8930 | IC | N/A | Post | N/A | 2015-12-02 | N/A | 2015-12-02 | 2016-01-01 | 2016-01-01
238 | SAGEM | E.5.1.1.1 | 2016 | 1 | SAGEM/2016/CS/E.5.1.1.1/IC/1 | Consultancy Service for Training on Planning and Implementing National Health Researches 1 | CS | CS | 2 | 9999.36 | 8928 | 10000 | 8930 | IC | N/A | Post | N/A | 2016-01-31 | N/A | 2016-01-31 | 2016-03-01 | 2016-03-01
239 | SAGEM | E.5.1.1.1 | 2016 | 2 | SAGEM/2016/CS/E.5.1.1.1/IC/2 | Consultancy Training for Basic Training on Using Statistical Analyses and Statistical Programs in Health Researches | CS | CS | 2 | 9999.36 | 8928 | 10000 | 8930 | IC | N/A | Post | N/A | 2016-10-02 | N/A | 2016-10-02 | 2016-11-01 | 2016-09-01
240 | SAGEM | E.5.1.1.1 | 2016 | 3 | SAGEM/2016/CS/E.5.1.1.1/IC/3 | Consultancy Training for Advanced Training on Using Statistical Analyses and Statistical Programs in Health Researches | CS | CS | 2 | 9999.36 | 8928 | 10000 | 8930 | IC | N/A | Post | N/A | 2016-11-01 | N/A | 2016-11-01 | 2016-12-01 | 2016-12-01
241 | SAGEM | E.5.1.1.1 | 2016 | 1 | SAGEM/2016/CS/E.5.1.1.1/IC/1 | Consultancy Service for Training on Reporting Health Researches and Writing Articles | CS | CS | 2 | 9999.36 | 8928 | 10000 | 8930 | IC | N/A | Post | N/A | 2016-12-02 | N/A | 2016-12-02 | 2017-01-01 | 2017-03-01
242 | SAGEM | E.5.1.2.2 | 2015 | 1 | SAGEM/2015/CS/E.5.1.2.2/IC/1 | Consultant for surveys on citizen and patient satisfaction in healthcare services | CS | CS | 1 | 172800.2304 | 154285.92 | 172800 | 154290 | IC | N/A | Post | N/A | 2015-10-01 | N/A | 2015-10-01 | 2015-10-01 | 2019-09-01
243 | SAGEM | E.5.1.2.2 | 2015 | 2 | SAGEM/2015/CS/E.5.1.2.2/IC/2 | Field research consultant (1 person) | CS | CS | 1 | 153599.8464 | 137142.72 | 153600 | 137150 | IC | N/A | Post | N/A | 2015-10-01 | N/A | 2015-10-01 | 2015-10-01 | 2019-09-01
244 | SAGEM | E.5.1.2.2 | 2015 | 1 | SAGEM/2015/CS/E.5.1.2.2/IC/1 | Neonatal consultant for researching the causes of low birth weight and premature birth in Turkey (1 person) | CS | CS | 1 | 10500 | 9375 | 10500 | 9380 | IC | N/A | Post | N/A | 2015-12-02 | N/A | 2015-12-02 | 2016-01-01 | 2016-12-01
245 | SAGEM | E.5.1.2.2 | 2015 | 2 | SAGEM/2015/CS/E.5.1.2.2/IC/2 | Gynecology and obstetrics consultant for researching the causes of low birth weight and premature birth in Turkey (1 person) | CS | CS | 1 | 10500 | 9375 | 10500 | 9380 | IC | N/A | Post | N/A | 2015-12-02 | N/A | 2015-12-02 | 2016-01-01 | 2016-12-01
246 | SAGEM | E.5.1.2.2 | 2015 | 3 | SAGEM/2015/CS/E.5.1.2.2/IC/3 | Statistics consultant for researching the causes of low birth weight and premature birth in Turkey (1 person) | CS | CS | 1 | 10500 | 9375 | 10500 | 9380 | IC | N/A | Post | N/A | 2015-12-02 | N/A | 2015-12-02 | 2016-01-01 | 2016-12-01
247 | SAGEM | E.5.1.2.2 | 2015 | 4 | SAGEM/2015/CS/E.5.1.2.2/IC/4 | Endocrinology and metabolic diseases consultant for national household health survey (1 person) | CS | CS | 1 | 10500 | 9375 | 10500 | 9380 | IC | N/A | Post | N/A | 2015-12-02 | N/A | 2015-12-02 | 2016-01-01 | 2016-12-01
248 | SAGEM | E.5.1.2.2 | 2015 | 5 | SAGEM/2015/CS/E.5.1.2.2/IC/5 | Cardiology consultant for national household health survey (1 person) | CS | CS | 1 | 10500 | 9375 | 10500 | 9380 | IC | N/A | Post | N/A | 2015-12-02 | N/A | 2015-12-02 | 2016-01-01 | 2016-12-01
249 | SAGEM | E.5.1.2.2 | 2015 | 6 | SAGEM/2015/CS/E.5.1.2.2/IC/6 | Public health consultant for national household health survey (1 person) | CS | CS | 1 | 10500 | 9375 | 10500 | 9380 | IC | N/A | Post | N/A | 2015-12-02 | N/A | 2015-12-02 | 2016-01-01 | 2016-12-01
250 | SAGEM | E.5.1.2.2 | 2015 | 7 | SAGEM/2015/CS/E.5.1.2.2/IC/7 | Statistics consultant for national household health survey (1 person) | CS | CS | 1 | 10500 | 9375 | 10500 | 9380 | IC | N/A | Post | N/A | 2015-12-02 | N/A | 2015-12-02 | 2016-01-01 | 2016-12-01
251 | SAGEM | E.5.1.2.2 | 2015 | 8 | SAGEM/2015/CS/E.5.1.2.2/IC/8 | Adult psychiatry consultant for mental health research in Turkey (1 person) | CS | CS | 1 | 10500 | 9375 | 10500 | 9380 | IC | N/A | Post | N/A | 2015-12-02 | N/A | 2015-12-02 | 2016-01-01 | 2016-12-01
252 | SAGEM | E.5.1.2.2 | 2015 | 9 | SAGEM/2015/CS/E.5.1.2.2/IC/9 | Statistics consultant for mental health research in Turkey (1 person) | CS | CS | 1 | 10500 | 9375 | 10500 | 9380 | IC | N/A | Post | N/A | 2015-12-02 | N/A | 2015-12-02 | 2016-01-01 | 2016-12-01
253 | SAGEM | E.5.1.2.2 | 2015 | 10 | SAGEM/2015/CS/E.5.1.2.2/IC/10 | Consultant for patient satisfaction survey (1 person) | CS | CS | 1 | 10500 | 9375 | 10500 | 9380 | IC | N/A | Post | N/A | 2015-12-02 | N/A | 2015-12-02 | 2016-01-01 | 2016-12-01
254 | SAGEM | E.5.1.2.2 | 2017 | 11 | SAGEM/2017/CS/E.5.1.2.2/IC/11 | Consultant for rational drug use reserach (1 person) | CS | CS | 1 | 7500.0016 | 6696.43 | 7500 | 6700 | IC | N/A | Post | N/A | 2017-01-30 | N/A | 2017-01-30 | 2017-03-01 | 2017-12-01
255 | SAGEM | E.5.1.2.2 | 2016 | 12 | SAGEM/2016/CS/E.5.1.2.2/IC/12 | Consultant for hospital readmission assessment (1 person) | CS | CS | 1 | 10500 | 9375 | 10500 | 9380 | IC | N/A | Post | N/A | 2016-01-31 | N/A | 2016-01-31 | 2016-03-01 | 2016-12-01
256 | SAGEM | E.4.1.1.1 | 2015 | 1 | SAGEM/2015/CS/E.4.1.1.1/IC/1 | Coordination team Member-1 (Epidemiology) | CS | CS | 1 | 161840 | 144500 | 161840 | 144500 | IC | N/A | Post | N/A | 2015-10-01 | N/A | 2015-10-01 | 2015-10-01 | 2019-09-09
257 | SAGEM | E.4.1.1.1 | 2015 | 2 | SAGEM/2015/CS/E.4.1.1.1/IC/2 | Coordination team Member-2 (Pharmacology) | CS | CS | 1 | 161840 | 144500 | 161840 | 144500 | IC | N/A | Post | N/A | 2015-10-01 | N/A | 2015-10-01 | 2015-10-01 | 2019-09-09
258 | SAGEM | E.4.1.1.1 | 2015 | 3 | SAGEM/2015/CS/E.4.1.1.1/IC/3 | Coordination team Member-3 (Evidence-based Medicine) | CS | CS | 1 | 140740.88 | 125661.5 | 140741 | 125670 | IC | N/A | Post | N/A | 2015-10-01 | N/A | 2015-10-01 | 2015-10-01 | 2019-09-09
259 | SAGEM | E.4.1.1.2 | 2015 | 1 | SAGEM/2015/CS/E.4.1.1.2/IC/1 | Sub-team Members | CS | CS | 20 | 230048 | 205400 | 230048 | 205400 | IC | N/A | Post | N/A | 2015-11-01 | N/A | 2015-11-01 | 2015-12-01 | 2016-12-01
260 | SAGEM | E.5.3.1.1 | 2015 | 2 | SAGEM/2015/CS/E.5.3.1.1/IC/2 | International Consultant for Instrument Development | CS | CS | 1 | 19999.9968 | 17857.14 | 20000 | 17860 | IC | N/A | Post | N/A | 2015-10-02 | N/A | 2015-10-02 | 2015-11-01 | 2015-11-01
261 | TKHK | N.3.1.6.1 | 2016 | 1 | TKHK/2016/CS/N.3.1.6.1/CQS/1 | Digital hospital management development service | CS | CS | 1 | 149999.9984 | 133928.57 | 150000 | 133930 | CQS | N/A | Prior | N/A | 2016-03-03 | 2016-04-02 | 2016-05-03 | 2016-06-01 | 2017-03-01
262 | SAGEM | E.5.1.1.1 | 2016 | 4 | SAGEM/2016/CS/E.5.1.1.1/IC/4 | Consultancy Service for Training on Sample Selection and Weightings in National Health Researches | CS | CS | 2 | 24999.52 | 22321 | 25000 | 22330 | IC | N/A | Post | N/A | 2016-04-01 | N/A | 2016-04-01 | 2016-05-01 | 2016-06-01
263 | SYGM | F.1.2.2.1 | 2015 | 1 | SYGM/2015/CS/F.1.2.2.1/CQS/1 | Energy Consumption and Cost Analysis | CS | CS | 1 | 299600 | 267500 | 299600 | 267500 | CQS | N/A | Prior | N/A | 2015-12-02 | 2016-01-01 | 2016-02-01 | 2016-03-01 | 2016-08-28
264 | THSK | L.2.20.4.4 | 2016 | 1 | THSK/2016/CS/L.2.20.4.4/CQS/1 | TV spots , billboards and preparation of visual materials | CS | CS | 1 | 105000 | 93750 | 105000 | 93750 | CQS | N/A | Post | N/A | 2016-11-03 | 2016-12-03 | 2017-01-02 | 2017-02-01 | 2017-02-01
265 | THSK | L.2.20.4.5 | 2015 | 1 | THSK/2015/CS/L.2.20.4.5/QCBS/1 | TV spots , billboards and preparation of visual materials | CS | CS | 1 | 525000 | 468750 | 525000 | 468750 | QCBS | N/A | Prior | N/A | 2015-10-05 | 2015-10-25 | 2015-12-09 | 2016-02-27 | 2016-08-27
266 | THSK | L.2.1.2.1 | 2016 | 1 | THSK/2016/CS/L.2.1.2.1/IC/1 | Nephrology Specialist 1 | CS | CS | 1 | 24998.4 | 22320 | 25000 | 22320 | IC | N/A | Post | N/A | 2016-02-02 | N/A | 2016-02-02 | 2016-03-01 | 2016-09-01
267 | THSK | L.2.1.2.1 | 2016 | 2 | THSK/2016/CS/L.2.1.2.1/IC/2 | Nephrology Specialist 2 | CS | CS | 1 | 24998.4 | 22320 | 25000 | 22320 | IC | N/A | Post | N/A | 2016-02-02 | N/A | 2016-02-02 | 2016-03-01 | 2016-09-01
268 | THSK | L.2.2.2.1 | 2017 | 1 | THSK/2017/CS/L.2.2.2.1/IC/1 | Public Health Specialist 1 | CS | CS | 1 | 20003.2 | 17860 | 20000 | 17860 | IC | N/A | Post | N/A | 2017-01-30 | N/A | 2017-02-14 | 2017-03-01 | 2017-03-01
269 | THSK | L.2.2.2.1 | 2017 | 2 | THSK/2017/CS/L.2.2.2.1/IC/2 | Public Health Specialist 2 | CS | CS | 1 | 20003.2 | 17860 | 20000 | 17860 | IC | N/A | Post | N/A | 2017-01-30 | N/A | 2017-02-14 | 2017-03-01 | 2017-03-01
270 | THSK | L.2.2.2.1 | 2016 | 1 | THSK/2016/CS/L.2.2.2.1/IC/1 | Public Health Specialist 1 | CS | CS | 1 | 20003.2 | 17860 | 20000 | 17860 | IC | N/A | Post | N/A | 2016-02-01 | N/A | 2016-02-01 | 2016-04-01 | 2016-04-01
271 | THSK | L.2.2.2.1 | 2016 | 2 | THSK/2016/CS/L.2.2.2.1/IC/2 | Public Health Specialist 2 | CS | CS | 1 | 20003.2 | 17860 | 20000 | 17860 | IC | N/A | Post | N/A | 2016-02-01 | N/A | 2016-02-01 | 2016-04-01 | 2016-04-01
272 | THSK | L.2.3.2.1 | 2016 | 1 | THSK/2016/CS/L.2.3.2.1/IC/1 | Consultant for preparing the content of training and information materials 1 | CS | CS | 1 | 16016 | 14300 | 16000 | 14300 | IC | N/A | Post | N/A | 2016-01-03 | N/A | 2016-01-03 | 2016-02-01 | 2016-06-01
273 | THSK | L.2.3.2.1 | 2016 | 2 | THSK/2016/CS/L.2.3.2.1/IC/2 | Consultant for preparing the content of training and information materials 2 | CS | CS | 1 | 16016 | 14300 | 16000 | 14300 | IC | N/A | Post | N/A | 2016-01-03 | N/A | 2016-01-03 | 2016-02-01 | 2016-06-01
274 | THSK | L.2.3.2.1 | 2016 | 3 | THSK/2016/CS/L.2.3.2.1/IC/3 | Consultant for trainers' training for healthcare professionals in 81 provinces 3 | CS | CS | 1 | 10999.52 | 9821 | 11000 | 9830 | IC | N/A | Post | N/A | 2016-05-01 | N/A | 2016-05-01 | 2016-07-01 | 2017-02-01
275 | THSK | L.2.3.2.1 | 2016 | 4 | THSK/2016/CS/L.2.3.2.1/IC/4 | Consultant for trainers' training for healthcare professionals in 81 provinces 4 | CS | CS | 1 | 10999.52 | 9821 | 11000 | 9830 | IC | N/A | Post | N/A | 2016-05-01 | N/A | 2016-05-01 | 2016-07-01 | 2017-02-01
276 | THSK | L.2.3.2.2 | 2015 | 1 | THSK/2015/CS/L.2.3.2.2/IC/1 | Statistician | CS | CS | 1 | 182246.4 | 162720 | 182247 | 162720 | IC | N/A | Post | N/A | 2015-10-01 | N/A | 2015-10-01 | 2015-11-01 | 2019-09-30
277 | THSK | L.2.3.2.2 | 2016 | 1 | THSK/2016/CS/L.2.3.2.2/IC/1 | Geriatrist 1 | CS | CS | 1 | 16016 | 14300 | 16000 | 14300 | IC | N/A | Post | N/A | 2016-02-02 | N/A | 2016-02-02 | 2016-03-01 | 2016-06-01
278 | THSK | L.2.3.2.2 | 2016 | 2 | THSK/2016/CS/L.2.3.2.2/IC/2 | Public health specialist 1 | CS | CS | 1 | 16016 | 14300 | 16000 | 14300 | IC | N/A | Post | N/A | 2016-02-02 | N/A | 2016-02-02 | 2016-03-01 | 2016-06-01
279 | THSK | L.2.3.2.2 | 2016 | 3 | THSK/2016/CS/L.2.3.2.2/IC/3 | Economist | CS | CS | 1 | 16016 | 14300 | 16000 | 14300 | IC | N/A | Post | N/A | 2016-02-02 | N/A | 2016-02-02 | 2016-03-01 | 2016-06-01
280 | THSK | L.2.3.2.2 | 2016 | 4 | THSK/2016/CS/L.2.3.2.2/IC/4 | Geriatrist 2 | CS | CS | 1 | 10024 | 8950 | 10000 | 8950 | IC | N/A | Post | N/A | 2016-09-03 | N/A | 2016-09-03 | 2016-10-01 | 2016-10-01
281 | THSK | L.2.3.2.2 | 2016 | 5 | THSK/2016/CS/L.2.3.2.2/IC/5 | Public health specialist 2 | CS | CS | 1 | 10024 | 8950 | 10000 | 8950 | IC | N/A | Post | N/A | 2016-09-03 | N/A | 2016-09-03 | 2016-10-01 | 2016-10-01
282 | THSK | L.2.4.2.3 | 2015 | 1 | THSK/2015/CS/L.2.4.2.3/IC/1 | Procurement of consultancy service for preparing national palliative care training module - 1 | CS | CS | 1 | 10001.6 | 8930 | 10000 | 8930 | IC | N/A | Post | N/A | 2015-10-01 | N/A | 2015-10-01 | 2015-10-01 | 2016-02-01
283 | THSK | L.2.4.2.3 | 2015 | 2 | THSK/2015/CS/L.2.4.2.3/IC/2 | Procurement of consultancy service for preparing national palliative care training module - 2 | CS | CS | 1 | 10001.6 | 8930 | 10000 | 8930 | IC | N/A | Post | N/A | 2015-10-01 | N/A | 2015-10-01 | 2015-10-01 | 2016-02-01
284 | THSK | L.2.4.3.2 | 2015 | 1 | THSK/2015/CS/L.2.4.3.2/CQS/1 | Firm Consultancy for Data Analysis and Quality Assessment | CS | CS | 1 | 30000.32 | 26786 | 30000 | 26790 | CQS | N/A | Post | N/A | 2015-12-26 | 2016-01-25 | 2016-02-24 | 2016-03-25 | 2016-09-01
285 | THSK | L.2.4.4.3 | 2016 | 1 | THSK/2016/CS/L.2.4.4.3/IC/1 | Training Consultancy 1 (partial time) | CS | CS | 1 | 13002.08 | 11609 | 13000 | 11610 | IC | N/A | Post | N/A | 2016-01-03 | N/A | 2016-01-17 | 2016-01-31 | 2017-03-01
286 | THSK | L.2.4.4.3 | 2016 | 2 | THSK/2016/CS/L.2.4.4.3/IC/2 | Training Consultancy 2 (partial time) | CS | CS | 1 | 13002.08 | 11609 | 13000 | 11610 | IC | N/A | Post | N/A | 2016-01-03 | N/A | 2016-01-17 | 2016-01-31 | 2017-03-01
287 | THSK | L.2.4.4.3 | 2016 | 3 | THSK/2016/CS/L.2.4.4.3/IC/3 | Training Consultancy 3 (partial time) | CS | CS | 1 | 10001.6 | 8930 | 10000 | 8930 | IC | N/A | Post | N/A | 2016-01-03 | N/A | 2016-01-17 | 2016-01-31 | 2016-12-01
288 | THSK | L.2.4.4.3 | 2016 | 4 | THSK/2016/CS/L.2.4.4.3/IC/4 | Training Consultancy 4 (partial time) | CS | CS | 1 | 10001.6 | 8930 | 10000 | 8930 | IC | N/A | Post | N/A | 2016-01-03 | N/A | 2016-01-17 | 2016-01-31 | 2016-12-01
289 | THSK | L.2.5.3.1 | 2015 | 1 | THSK/2015/CS/L.2.5.3.1/IC/1 | Consultancy for Post-Screening Diagnosis Training 1 | CS | CS | 1 | 9941.12 | 8876 | 9950 | 8880 | IC | N/A | Post | N/A | 2015-10-10 | N/A | 2015-10-10 | 2015-11-01 | 2017-03-31
290 | THSK | L.2.5.3.1 | 2015 | 2 | THSK/2015/CS/L.2.5.3.1/IC/2 | Consultancy for Post-Screening Diagnosis Training 2 | CS | CS | 1 | 9941.12 | 8876 | 9950 | 8880 | IC | N/A | Post | N/A | 2015-10-10 | N/A | 2015-10-10 | 2015-11-01 | 2017-03-31
291 | THSK | L.2.5.3.1 | 2015 | 3 | THSK/2015/CS/L.2.5.3.1/IC/3 | Consultancy for Post-Screening Diagnosis Training 3 | CS | CS | 1 | 9941.12 | 8876 | 9950 | 8880 | IC | N/A | Post | N/A | 2015-10-10 | N/A | 2015-10-10 | 2015-11-01 | 2017-03-31
292 | THSK | L.2.5.3.1 | 2015 | 4 | THSK/2015/CS/L.2.5.3.1/IC/4 | Consultancy for Post-Screening Diagnosis Training 4 | CS | CS | 1 | 9941.12 | 8876 | 9950 | 8880 | IC | N/A | Post | N/A | 2015-10-10 | N/A | 2015-10-10 | 2015-11-01 | 2017-03-31
293 | THSK | L.2.5.3.1 | 2015 | 5 | THSK/2015/CS/L.2.5.3.1/IC/5 | Consultancy for Post-Screening Diagnosis Training 5 | CS | CS | 1 | 9941.12 | 8876 | 9950 | 8880 | IC | N/A | Post | N/A | 2015-10-10 | N/A | 2015-10-10 | 2015-11-01 | 2017-03-31
294 | THSK | L.2.5.3.1 | 2015 | 6 | THSK/2015/CS/L.2.5.3.1/IC/6 | Consultancy for Post-Screening Diagnosis Training 6 | CS | CS | 1 | 9941.12 | 8876 | 9950 | 8880 | IC | N/A | Post | N/A | 2015-10-10 | N/A | 2015-10-10 | 2015-11-01 | 2017-03-31
295 | THSK | L.2.5.3.1 | 2015 | 7 | THSK/2015/CS/L.2.5.3.1/IC/7 | Consultancy for Post-Screening Diagnosis Training 7 | CS | CS | 1 | 9941.12 | 8876 | 9950 | 8880 | IC | N/A | Post | N/A | 2015-10-10 | N/A | 2015-10-10 | 2015-11-01 | 2017-03-31
296 | THSK | L.2.5.3.1 | 2015 | 8 | THSK/2015/CS/L.2.5.3.1/IC/8 | Consultancy for Post-Screening Diagnosis Training 8 | CS | CS | 1 | 9941.12 | 8876 | 9950 | 8880 | IC | N/A | Post | N/A | 2015-10-10 | N/A | 2015-10-10 | 2015-11-01 | 2017-03-31
297 | THSK | L.2.5.3.1 | 2015 | 9 | THSK/2015/CS/L.2.5.3.1/IC/9 | Consultancy for Post-Screening Diagnosis Training 9 | CS | CS | 1 | 9941.12 | 8876 | 9950 | 8880 | IC | N/A | Post | N/A | 2015-10-10 | N/A | 2015-10-10 | 2015-11-01 | 2017-03-31
298 | THSK | L.2.5.3.1 | 2015 | 10 | THSK/2015/CS/L.2.5.3.1/IC/10 | Consultancy for Post-Screening Diagnosis Training 10 | CS | CS | 1 | 9941.12 | 8876 | 9950 | 8880 | IC | N/A | Post | N/A | 2015-10-10 | N/A | 2015-10-10 | 2015-11-01 | 2017-03-31
299 | THSK | L.2.5.3.1 | 2015 | 11 | THSK/2015/CS/L.2.5.3.1/IC/11 | Consultancy for Post-Screening Diagnosis Training 11 | CS | CS | 1 | 9941.12 | 8876 | 9950 | 8880 | IC | N/A | Post | N/A | 2015-10-10 | N/A | 2015-10-10 | 2015-11-01 | 2017-03-31
300 | THSK | L.2.5.4.1 | 2015 | 1 | THSK/2015/CS/L.2.5.4.1/CQS/1 | Firm Consultancy for media activities | CS | CS | 1 | 50000.16 | 44643 | 50000 | 44650 | CQS | N/A | Post | N/A | 2015-12-02 | 2016-01-01 | 2016-01-31 | 2016-03-01 | 2016-03-30
301 | THSK | L.2.5.3.1 | 2015 | 12 | THSK/2015/CS/L.2.5.3.1/IC/12 | Consultancy for Post-Screening Diagnosis Training 12 | CS | CS | 1 | 9941.12 | 8876 | 9950 | 8880 | IC | N/A | Post | N/A | 2015-10-10 | N/A | 2015-10-10 | 2015-11-01 | 2017-03-31
302 | THSK | L.2.6.4.1 | 2016 | 1 | THSK/2016/CS/L.2.6.4.1/IC/1 | Academic Consultancy for Quality 1 (partial time) | CS | CS | 1 | 5998.72 | 5356 | 6000 | 5360 | IC | N/A | Post | N/A | 2016-02-01 | N/A | 2016-02-01 | 2016-03-01 | 2016-11-01
303 | THSK | L.2.6.4.1 | 2016 | 2 | THSK/2016/CS/L.2.6.4.1/IC/2 | Academic Consultancy for Quality 2 (partial time) | CS | CS | 1 | 5998.72 | 5356 | 6000 | 5360 | IC | N/A | Post | N/A | 2016-02-01 | N/A | 2016-02-01 | 2016-03-01 | 2016-11-01
304 | THSK | L.2.6.4.1 | 2017 | 1 | THSK/2017/CS/L.2.6.4.1/IC/1 | Academic Consultancy for Quality 1 (partial time) | CS | CS | 1 | 3999.52 | 3571 | 4000 | 3580 | IC | N/A | Post | N/A | 2017-01-05 | N/A | 2017-01-05 | 2017-02-01 | 2017-02-01
305 | THSK | L.2.6.4.1 | 2017 | 2 | THSK/2017/CS/L.2.6.4.1/IC/2 | Academic Consultancy for Quality 2 (partial time) | CS | CS | 1 | 3999.52 | 3571 | 4000 | 3580 | IC | N/A | Post | N/A | 2017-01-05 | N/A | 2017-01-05 | 2017-02-01 | 2017-02-01
306 | THSK | L.2.7.1.3 | 2016 | 1 | THSK/2016/CS/L.2.7.1.3/IC/1 | Procurement of consultancy for determining the level of legal compliance | CS | CS | 1 | 24999.52 | 22321 | 25000 | 22330 | IC | N/A | Post | N/A | 2016-05-15 | N/A | 2016-05-15 | 2016-07-01 | 2016-11-01
307 | THSK | L.2.11.2.1 | 2017 | 1 | THSK/2017/CS/L.2.11.2.1/IC/1 | Coordinator Endocrinology Consultant | CS | CS | 1 | 12500.32 | 11161 | 12500 | 11170 | IC | N/A | Post | N/A | 2017-01-05 | N/A | 2017-01-05 | 2017-02-01 | 2017-03-01
308 | THSK | L.2.11.2.1 | 2017 | 2 | THSK/2017/CS/L.2.11.2.1/IC/2 | Public Health Consultant | CS | CS | 1 | 10000.48 | 8929 | 10000 | 8930 | IC | N/A | Post | N/A | 2017-01-05 | N/A | 2017-01-05 | 2017-02-01 | 2017-03-01
309 | THSK | L.2.11.2.1 | 2017 | 3 | THSK/2017/CS/L.2.11.2.1/IC/3 | Statistics Consultant | CS | CS | 1 | 10000.48 | 8929 | 10000 | 8930 | IC | N/A | Post | N/A | 2017-01-05 | N/A | 2017-01-05 | 2017-02-01 | 2017-03-01
310 | THSK | L.2.11.2.1 | 2017 | 4 | THSK/2017/CS/L.2.11.2.1/IC/4 | Information Processing Consultant | CS | CS | 1 | 10000.48 | 8929 | 10000 | 8930 | IC | N/A | Post | N/A | 2017-01-05 | N/A | 2017-01-05 | 2017-02-01 | 2017-03-01
311 | THSK | L.2.11.1.1 | 2016 | 1 | THSK/2016/CS/L.2.11.1.1/CQS/1 | Preparation of films | CS | CS | 1 | 199999.52 | 178571 | 200000 | 178580 | CQS | N/A | Prior | N/A | 2016-02-01 | 2016-03-02 | 2016-04-01 | 2016-05-01 | 2016-05-01
312 | THSK | L.2.12.2.1 | 2016 | 1 | THSK/2016/CS/L.2.12.2.1/IC/1 | Coordinator Nutrition Consultant | CS | CS | 1 | 17500 | 15625 | 17500 | 15630 | IC | N/A | Post | N/A | 2016-04-01 | N/A | 2016-04-01 | 2016-05-01 | 2016-05-01
313 | THSK | L.2.12.2.1 | 2016 | 2 | THSK/2016/CS/L.2.12.2.1/IC/2 | Nutrition Consultant | CS | CS | 1 | 14000 | 12500 | 14000 | 12500 | IC | N/A | Post | N/A | 2016-04-01 | N/A | 2016-04-01 | 2016-05-01 | 2016-05-01
314 | THSK | L.2.12.2.1 | 2016 | 3 | THSK/2016/CS/L.2.12.2.1/IC/3 | Nutrition Consultant | CS | CS | 1 | 14000 | 12500 | 14000 | 12500 | IC | N/A | Post | N/A | 2016-04-01 | N/A | 2016-04-01 | 2016-05-01 | 2016-05-01
315 | THSK | L.2.12.2.1 | 2016 | 4 | THSK/2016/CS/L.2.12.2.1/IC/4 | Public Health Consultant | CS | CS | 1 | 14000 | 12500 | 14000 | 12500 | IC | N/A | Post | N/A | 2016-04-01 | N/A | 2016-04-01 | 2016-05-01 | 2016-05-01
316 | THSK | L.2.12.2.1 | 2016 | 5 | THSK/2016/CS/L.2.12.2.1/IC/5 | Statistics Consultant | CS | CS | 1 | 14000 | 12500 | 14000 | 12500 | IC | N/A | Post | N/A | 2016-04-01 | N/A | 2016-04-01 | 2016-05-01 | 2016-05-01
317 | THSK | L.2.12.2.1 | 2016 | 6 | THSK/2016/CS/L.2.12.2.1/IC/6 | Information Processing Consultant | CS | CS | 1 | 14000 | 12500 | 14000 | 12500 | IC | N/A | Post | N/A | 2016-04-01 | N/A | 2016-04-01 | 2016-05-01 | 2016-05-01
318 | THSK | L.2.12.2.2 | 2016 | 1 | THSK/2016/CS/L.2.12.2.2/IC/1 | Coordinator Nutrition Consultant | CS | CS | 1 | 15000.16 | 13393 | 15000 | 13400 | IC | N/A | Post | N/A | 2016-09-01 | N/A | 2016-09-01 | 2016-10-01 | 2016-11-01
319 | THSK | L.2.12.2.2 | 2016 | 2 | THSK/2016/CS/L.2.12.2.2/IC/2 | Nutrition Consultant | CS | CS | 1 | 11999.68 | 10714 | 12000 | 10720 | IC | N/A | Post | N/A | 2016-09-01 | N/A | 2016-09-01 | 2016-10-01 | 2016-11-01
320 | THSK | L.2.12.2.2 | 2016 | 3 | THSK/2016/CS/L.2.12.2.2/IC/3 | Nutrition Consultant | CS | CS | 1 | 11999.68 | 10714 | 12000 | 10720 | IC | N/A | Post | N/A | 2016-09-01 | N/A | 2016-09-01 | 2016-10-01 | 2016-11-01
321 | THSK | L.2.12.2.2 | 2016 | 4 | THSK/2016/CS/L.2.12.2.2/IC/4 | Public Health Consultant | CS | CS | 1 | 11999.68 | 10714 | 12000 | 10720 | IC | N/A | Post | N/A | 2016-09-01 | N/A | 2016-09-01 | 2016-10-01 | 2016-11-01
322 | THSK | L.2.12.2.2 | 2016 | 5 | THSK/2016/CS/L.2.12.2.2/IC/5 | Statistics Consultant | CS | CS | 1 | 11999.68 | 10714 | 12000 | 10720 | IC | N/A | Post | N/A | 2016-09-01 | N/A | 2016-09-01 | 2016-10-01 | 2016-11-01
323 | THSK | L.2.12.2.2 | 2016 | 6 | THSK/2016/CS/L.2.12.2.2/IC/6 | Information Processing Consultant | CS | CS | 1 | 11999.68 | 10714 | 12000 | 10720 | IC | N/A | Post | N/A | 2016-09-01 | N/A | 2016-09-01 | 2016-10-01 | 2016-11-01
324 | THSK | L.2.12.3.1 | 2015 | 1 | THSK/2015/CS/L.2.12.3.1/IC/1 | Physical Activity Consultant | CS | CS | 1 | 5167.68 | 4614 | 5200 | 4620 | IC | N/A | Post | N/A | 2015-10-01 | N/A | 2015-10-16 | 2015-10-01 | 2015-12-31
325 | THSK | L.2.12.3.1 | 2016 | 1 | THSK/2016/CS/L.2.12.3.1/IC/1 | Coordinator Nutrition Consultant | CS | CS | 1 | 23520 | 21000 | 23520 | 21000 | IC | N/A | Post | N/A | 2016-01-15 | N/A | 2016-01-15 | 2016-02-15 | 2016-03-01
326 | THSK | L.2.12.3.1 | 2016 | 2 | THSK/2016/CS/L.2.12.3.1/IC/2 | Public Health Consultant | CS | CS | 1 | 29120 | 26000 | 29120 | 26000 | IC | N/A | Post | N/A | 2016-01-15 | N/A | 2016-01-15 | 2016-02-15 | 2016-03-01
327 | THSK | L.2.12.3.1 | 2016 | 3 | THSK/2016/CS/L.2.12.3.1/IC/3 | Statistics Consultant | CS | CS | 1 | 23520 | 21000 | 23520 | 21000 | IC | N/A | Post | N/A | 2016-01-15 | N/A | 2016-01-15 | 2016-02-15 | 2016-03-01
328 | THSK | L.2.12.3.2 | 2016 | 1 | THSK/2016/CS/L.2.12.3.2/IC/1 | Coordinator Nutrition Consultant | CS | CS | 1 | 17500 | 15625 | 17500 | 15630 | IC | N/A | Post | N/A | 2016-09-01 | N/A | 2016-09-01 | 2016-10-01 | 2016-10-01
329 | THSK | L.2.12.3.2 | 2016 | 2 | THSK/2016/CS/L.2.12.3.2/IC/2 | Public Health Consultant | CS | CS | 1 | 14000 | 12500 | 14000 | 12500 | IC | N/A | Post | N/A | 2016-09-01 | N/A | 2016-09-01 | 2016-10-01 | 2016-10-01
330 | THSK | L.2.12.3.2 | 2016 | 3 | THSK/2016/CS/L.2.12.3.2/IC/3 | Statistics Consultant | CS | CS | 1 | 14000 | 12500 | 14000 | 12500 | IC | N/A | Post | N/A | 2016-09-01 | N/A | 2016-09-01 | 2016-10-01 | 2016-10-01
331 | THSK | L.2.12.3.1 | 2016 | 4 | THSK/2016/CS/L.2.12.3.1/IC/4 | Physical Activity Consultant | CS | CS | 1 | 5167.68 | 4614 | 5200 | 4620 | IC | N/A | Post | N/A | 2016-12-16 | N/A | 2016-12-31 | 2017-01-15 | 2017-03-30
332 | THSK | L.2.12.6.1 | 2016 | 1 | THSK/2016/CS/L.2.12.6.1/IC/1 | Coordinator Nephrology Consultant | CS | CS | 1 | 12500.32 | 11161 | 12500 | 11170 | IC | N/A | Post | N/A | 2016-01-15 | N/A | 2016-01-29 | 2016-02-01 | 2017-03-01
333 | THSK | L.2.12.6.1 | 2016 | 2 | THSK/2016/CS/L.2.12.6.1/IC/2 | Public Health Consultant | CS | CS | 1 | 10000.48 | 8929 | 10000 | 8930 | IC | N/A | Post | N/A | 2016-01-15 | N/A | 2016-01-29 | 2016-02-01 | 2017-03-01
334 | THSK | L.2.12.6.1 | 2016 | 3 | THSK/2016/CS/L.2.12.6.1/IC/3 | Statistics Consultant | CS | CS | 1 | 10000.48 | 8929 | 10000 | 8930 | IC | N/A | Post | N/A | 2016-01-15 | N/A | 2016-01-29 | 2016-02-01 | 2017-03-01
335 | THSK | L.2.12.6.1 | 2016 | 4 | THSK/2016/CS/L.2.12.6.1/IC/4 | Information Processing Consultant | CS | CS | 1 | 10000.48 | 8929 | 10000 | 8930 | IC | N/A | Post | N/A | 2016-01-15 | N/A | 2016-01-29 | 2016-02-01 | 2017-03-01
336 | THSK | L.2.16.3.1 | 2016 | 1 | THSK/2016/CS/L.2.16.3.1/CQS/1 | Patient follow-up, data management and statistical analysis services | CS | CS | 1 | 19999.84 | 17857 | 20000 | 17860 | CQS | N/A | Post | N/A | 2016-07-03 | 2016-08-02 | 2016-09-01 | 2016-10-01 | 2016-11-01
337 | THSK | L.2.16.3.1 | 2016 | 1 | THSK/2016/CS/L.2.16.3.1/CQS/1 | Patient follow-up, data management and statistical analysis services | CS | CS | 1 | 19999.84 | 17857 | 20000 | 17860 | CQS | N/A | Post | N/A | 2016-11-03 | 2016-12-03 | 2017-01-02 | 2017-02-01 | 2017-03-01
338 | THSK | L.2.20.1.3 | 2016 | 1 | THSK/2016/CS/L.2.20.1.3/IC/1 | Coordination of workshops on the preparation of training modules, preparation of the module result report, providing trainers' training and coordination of the workshops of consultancy units (Activities for Reinforcement of Substance Addiction Preventive Services) | CS | CS | 1 | 1249.92 | 1116 | 1250 | 1120 | IC | N/A | Post | N/A | 2016-03-02 | N/A | 2016-03-02 | 2016-04-01 | 2016-04-30
339 | THSK | L.2.20.1.7 | 2016 | 1 | THSK/2016/CS/L.2.20.1.7/IC/1 | Coordination of workshops on the preparation of training modules, preparation of the module result report, providing trainers' training and coordination of the workshops of consultancy units | CS | CS | 1 | 49999.04 | 44642 | 50000 | 44650 | IC | N/A | Post | N/A | 2016-01-31 | N/A | 2016-01-31 | 2016-03-01 | 2016-11-30
340 | THSK | L.2.20.4.3 | 2015 | 1 | THSK/2015/CS/L.2.20.4.3/CQS/1 | Preparation of film and animations | CS | CS | 1 | 7499.52 | 6696 | 7500 | 6700 | CQS | N/A | Post | N/A | 2015-10-27 | 2015-11-26 | 2015-12-26 | 2016-01-25 | 2017-03-30
341 | THSK | L.2.20.5.2 | 2016 | 1 | THSK/2016/CS/L.2.20.5.2/CQS/1 | Measurement of performance of information line | CS | CS | 1 | 15000.16 | 13393 | 15000 | 13400 | CQS | N/A | Post | N/A | 2016-04-02 | 2016-05-02 | 2016-06-01 | 2016-07-01 | 2016-07-01
342 | THSK | L.2.20.1.3 | 2016 | 2 | THSK/2016/CS/L.2.20.1.3/IC/2 | Coordination of workshops on the preparation of training modules, preparation of the module result report, providing trainers' training and coordination of the workshops of consultancy units (Activities for Reinforcement of Substance Addiction Preventive Services) | CS | CS | 1 | 1249.92 | 1116 | 1250 | 1120 | IC | N/A | Post | N/A | 2016-10-01 | N/A | 2016-10-01 | 2015-11-01 | 2015-11-01
343 | THSK | L.2.20.4.2 | 2016 | 1 | THSK/2016/CS/L.2.20.4.2/IC/1 | Preparation of the interactive web portal | CS | CS | 1 | 19999.84 | 17857 | 20000 | 17860 | IC | N/A | Post | N/A | 2016-03-26 | N/A | 2016-03-26 | 2016-04-25 | 2016-07-01
344 | THSK | L.4.2.1.2 | 2016 | 1 | THSK/2016/CS/L.4.2.1.2/IC/1 | Consultant for Job and Workload Analysis 1 (of Family Physicians and Family Health Professionals) | CS | CS | 1 | 10000.48 | 8929 | 10000 | 8930 | IC | N/A | Post | N/A | 2016-01-05 | N/A | 2016-01-05 | 2016-02-01 | 2016-02-01
345 | THSK | L.4.2.1.2 | 2016 | 2 | THSK/2016/CS/L.4.2.1.2/IC/2 | Consultant for Job and Workload Analysis 2 (of Family Physicians and Family Health Professionals) | CS | CS | 1 | 10000.48 | 8929 | 10000 | 8930 | IC | N/A | Post | N/A | 2016-11-01 | N/A | 2016-11-01 | 2016-12-01 | 2016-12-01
346 | THSK | L.4.2.1.2 | 2016 | 1 | THSK/2016/CS/L.4.2.1.2/CQS/1 | Firm Consultancy for Field Research (of Family Physicians and Family Health Professionals) | CS | CS | 1 | 50000.16 | 44643 | 50000 | 44650 | CQS | N/A | Post | N/A | 2016-09-02 | 2016-10-02 | 2016-11-01 | 2016-12-01 | 2016-12-01
347 | THSK | L.4.2.1.2 | 2017 | 1 | THSK/2017/CS/L.4.2.1.2/IC/1 | Consultant for Job and Workload Analysis 1 (of Family Physicians and Family Health Professionals) | CS | CS | 1 | 10000.48 | 8929 | 10000 | 8930 | IC | N/A | Post | N/A | 2017-01-15 | N/A | 2017-01-15 | 2017-02-05 | 2017-03-01
348 | THSK | L.4.6.3.4 | 2016 | 1 | THSK/2016/CS/L.4.6.3.4/CQS/1 | Service Consultants to take office in HLC (32 persons) - 4 consultants for each 8 provinces | CS | CS | Multiple | 754669.44 | 673812 | 754670 | 673820 | CQS | N/A | Post | N/A | 2016-01-02 | 2016-02-01 | 2016-03-02 | 2016-04-01 | 2017-03-30
349 | THSK | L.2.20.4.3 | 2016 | 1 | THSK/2016/CS/L.2.20.4.3/CQS/1 | Preparation of short films , animation, TV spots , billboards and other visual materials | CS | CS | 1 | 80000.48 | 71429 | 80000 | 71430 | CQS | N/A | Post | N/A | 2016-02-01 | 2016-03-02 | 2016-04-01 | 2016-05-01 | 2016-08-30
350 | THSK | L.2.20.1.2 | 2015 | 1 | THSK/2015/CS/L.2.20.1.2/IC/1 | Project Support Specialist | CS | CS | 1 | 154129.92 | 137616 | 154130 | 137620 | IC | N/A | Post | N/A | 2015-10-02 | N/A | 2015-10-02 | 2015-11-01 | 2019-09-01
351 | THSK | L.2.20.1.2 | 2015 | 3 | THSK/2015/CS/L.2.20.1.2/IC/3 | IT Coordinator | CS | CS | 1 | 194933.76 | 174048 | 194940 | 174050 | IC | N/A | Post | N/A | 2015-10-02 | N/A | 2015-10-02 | 2015-11-01 | 2019-09-01
352 | THSK | L.2.20.1.2 | 2015 | 4 | THSK/2015/CS/L.2.20.1.2/IC/4 | Database Application Specialist | CS | CS | 1 | 167731.2 | 149760 | 167740 | 149760 | IC | N/A | Post | N/A | 2015-10-02 | N/A | 2015-10-02 | 2015-11-01 | 2019-09-01
353 | THSK | L.2.20.1.2 | 2015 | 5 | THSK/2015/CS/L.2.20.1.2/IC/5 | Software Specialist | CS | CS | 1 | 167731.2 | 149760 | 167740 | 149760 | IC | N/A | Post | N/A | 2015-10-02 | N/A | 2015-10-02 | 2015-11-01 | 2019-09-01
354 | THSK | L.4.1.1.1 | 2015 | 1 | THSK/2015/CS/L.4.1.1.1/IC/1 | Monitoring and Evaluation Consultant | CS | CS | 1 | 137975.04 | 123192 | 137980 | 123200 | IC | N/A | Post | N/A | 2015-10-01 | N/A | 2015-10-01 | 2015-10-01 | 2017-09-30
355 | THSK | L.4.1.5.8 | 2016 | 1 | THSK/2016/CS/L.4.1.5.8/IC/1 | Consultancy Service for Trainer's Training (for Enhancing Knowledge and Skills of the Personnel Working in Central and Provincial Organization to Improve Monitoring and Evaluation Capacity in Family Medicine Practices) | CS | CS | 1 | 21000 | 18750 | 21000 | 18750 | IC | N/A | Post | N/A | 2016-01-31 | N/A | 2016-01-31 | 2016-03-01 | 2016-05-01
356 | THSK | L.4.1.5.6 | 2016 | 2 | THSK/2016/CS/L.4.1.5.6/IC/2 | Trainings for Monitoring and Evaluation in Family Medicine Practices | CS | CS | 1 | 35000 | 31250 | 35000 | 31250 | IC | N/A | Post | N/A | 2016-07-02 | N/A | 2016-07-02 | 2016-08-01 | 2016-12-01
357 | THSK | L.4.1.5.6 | 2016 | 1 | THSK/2016/CS/L.4.1.5.6/IC/1 | Trainings for Monitoring and Evaluation in Family Medicine Practices | CS | CS | 1 | 21000 | 18750 | 21000 | 18750 | IC | N/A | Post | N/A | 2016-12-02 | N/A | 2016-12-02 | 2017-01-01 | 2017-03-01
358 | THSK | L.4.3.2.2 | 2016 | 2 | THSK/2016/CS/L.4.3.2.2/IC/2 | Training Coordinator Consultant 2 persons | CS | CS | 2 | 29999.2 | 26785 | 30000 | 26790 | IC | N/A | Post | N/A | 2016-01-02 | N/A | 2016-01-17 | 2016-02-01 | 2016-04-30
359 | THSK | L.4.3.3.1 | 2016 | 1 | THSK/2016/CS/L.4.3.3.1/IC/1 | Training Technologist | CS | CS | 1 | 38998.4 | 34820 | 39000 | 34820 | IC | N/A | Post | N/A | 2016-01-31 | N/A | 2016-02-15 | 2016-03-01 | 2017-03-31
360 | THSK | L.4.3.3.1 | 2016 | 2 | THSK/2016/CS/L.4.3.3.1/IC/2 | Measurament and Evaluation Consultant | CS | CS | 1 | 3249.12 | 2901 | 3250 | 2910 | IC | N/A | Post | N/A | 2016-03-02 | N/A | 2016-03-17 | 2016-04-01 | 2016-04-30
361 | THSK | L.4.3.3.1 | 2016 | 3 | THSK/2016/CS/L.4.3.3.1/IC/3 | Medicine Consultant | CS | CS | 1 | 139998.88 | 124999 | 140000 | 125000 | IC | N/A | Post | N/A | 2016-04-30 | N/A | 2016-05-15 | 2016-05-30 | 2017-03-31
362 | THSK | L.4.3.3.1 | 2016 | 4 | THSK/2016/CS/L.4.3.3.1/IC/4 | Consultancy of Nursing and Midwifery | CS | CS | 1 | 71999.2 | 64285 | 72000 | 64290 | IC | N/A | Post | N/A | 2016-04-30 | N/A | 2016-05-15 | 2016-05-30 | 2017-03-31
363 | THSK | L.4.3.3.1 | 2016 | 1 | THSK/2016/CS/L.4.3.3.1/CQS/1 | Firm Consultancy of Developing e- learning materials | CS | CS | 1 | 255999.52 | 228571 | 256000 | 228580 | CQS | N/A | Post | N/A | 2016-06-03 | 2016-07-03 | 2016-08-02 | 2016-09-01 | 2016-12-31
364 | THSK | L.4.3.3.1 | 2016 | 2 | THSK/2016/CS/L.4.3.3.1/QCBS/2 | Firm Consultancy of Developing e- learning materials | CS | CS | 1 | 336000 | 300000 | 336000 | 300000 | QCBS | N/A | Prior | N/A | 2016-08-04 | 2016-08-24 | 2016-10-08 | 2017-01-01 | 2017-03-30
365 | THSK | L.4.3.2.2 | 2016 | 1 | THSK/2016/CS/L.4.3.2.2/IC/1 | Training Consultant 8 persons | CS | CS | 8 | 65999.36 | 58928 | 66000 | 58930 | IC | N/A | Post | N/A | 2016-01-02 | N/A | 2016-01-17 | 2016-02-01 | 2016-04-30
366 | SBSGM | D.1.3.1.1 | 2015 | 1 | SBSGM/2015/CS/D.1.3.1.1/IC/1 | Job Analyst | CS | CS | 4 | 719953.92 | 642816 | 719960 | 642820 | IC | N/A | Post | N/A | 2015-10-01 | N/A | 2015-10-01 | 2015-10-01 | 2019-09-01
367 | SBSGM | D.1.3.1.1 | 2015 | 2 | SBSGM/2015/CS/D.1.3.1.1/IC/2 | Data Statistics Consultant | CS | CS | 4 | 719953.92 | 642816 | 719960 | 642820 | IC | N/A | Post | N/A | 2015-10-01 | N/A | 2015-10-01 | 2015-10-01 | 2019-09-01
368 | SBSGM | D.1.3.1.1 | 2015 | 3 | SBSGM/2015/CS/D.1.3.1.1/IC/3 | IT Support Staff | CS | CS | 1 | 105584.64 | 94272 | 105590 | 94280 | IC | N/A | Post | N/A | 2015-10-01 | N/A | 2015-10-01 | 2015-10-01 | 2019-09-01
369 | SBSGM | D.1.3.1.1 | 2015 | 4 | SBSGM/2015/CS/D.1.3.1.1/IC/4 | Database Consultant | CS | CS | 2 | 479969.28 | 428544 | 479970 | 428550 | IC | N/A | Prior | N/A | 2015-10-01 | N/A | 2015-10-01 | 2015-10-01 | 2019-09-01
370 | SBSGM | D.1.3.1.8 | 2016 | 1 | SBSGM/2016/CS/D.1.3.1.8/IC/1 | Software Consultant | CS | CS | 6 | 998786.88 | 891774 | 998790 | 891780 | IC | N/A | Post | N/A | 2016-08-02 | N/A | 2016-08-02 | 2016-09-01 | 2019-09-01
371 | SBSGM | D.1.3.1.8 | 2016 | 2 | SBSGM/2016/CS/D.1.3.1.8/IC/2 | Database Consultant | CS | CS | 3 | 554964.48 | 495504 | 554970 | 495510 | IC | N/A | Post | N/A | 2016-08-02 | N/A | 2016-08-02 | 2016-09-01 | 2019-09-01
372 | SBSGM | D.2.1.1.1 | 2015 | 1 | SBSGM/2015/CS/D.2.1.1.1/IC/1 | Consultant for Developing IT Standards | CS | CS | 1 | 189611.52 | 169296 | 189620 | 169300 | IC | N/A | Post | N/A | 2015-10-01 | N/A | 2015-10-01 | 2015-10-01 | 2019-09-01
373 | SBSGM | D.2.1.1.1 | 2015 | 2 | SBSGM/2015/CS/D.2.1.1.1/IC/2 | Consultant for Developing Health Informatics Standards | CS | CS | 1 | 189611.52 | 169296 | 189620 | 169300 | IC | N/A | Post | N/A | 2015-10-01 | N/A | 2015-10-01 | 2015-10-01 | 2019-09-01
374 | SBSGM | D.2.1.1.1 | 2015 | 3 | SBSGM/2015/CS/D.2.1.1.1/IC/3 | Health Informatics Law Consultant | CS | CS | 1 | 157463.04 | 140592 | 157470 | 140600 | IC | N/A | Post | N/A | 2015-10-01 | N/A | 2015-10-01 | 2015-10-01 | 2019-09-01
375 | SBSGM | D.2.1.1.1 | 2015 | 4 | SBSGM/2015/CS/D.2.1.1.1/IC/4 | Software Development Consultant | CS | CS | 2 | 312023.04 | 278592 | 312024 | 278600 | IC | N/A | Post | N/A | 2015-10-01 | N/A | 2015-10-01 | 2015-10-01 | 2019-09-01
376 | SBSGM | D.2.1.1.1 | 2015 | 5 | SBSGM/2015/CS/D.2.1.1.1/IC/5 | Health Information Security Consultant | CS | CS | 1 | 156011.52 | 139296 | 156012 | 139300 | IC | N/A | Post | N/A | 2015-10-01 | N/A | 2015-10-01 | 2015-10-01 | 2019-09-01
377 | SBSGM | D.2.1.1.1 | 2015 | 6 | SBSGM/2015/CS/D.2.1.1.1/IC/6 | IT Support Staff | CS | CS | 4 | 527923.2 | 471360 | 527930 | 471360 | IC | N/A | Post | N/A | 2015-10-01 | N/A | 2015-10-01 | 2015-10-01 | 2019-09-01
378 | THSK | L.4.5.4.1 | 2015 | 1 | THSK/2015/CS/L.4.5.4.1/IC/1 | Training Coordinator | CS | CS | 1 | 6251.84 | 5582 | 6260 | 5590 | IC | N/A | Post | N/A | 2015-10-02 | N/A | 2015-10-17 | 2015-11-01 | 2015-11-30
379 | THSK | L.4.5.4.1 | 2015 | 2 | THSK/2015/CS/L.4.5.4.1/IC/2 | Training Consultant 1 | CS | CS | 1 | 3540.32 | 3161 | 3550 | 3170 | IC | N/A | Post | N/A | 2015-10-02 | N/A | 2015-10-17 | 2015-11-01 | 2015-11-30
380 | THSK | L.4.5.4.1 | 2015 | 3 | THSK/2015/CS/L.4.5.4.1/IC/3 | Training Consultant 2 | CS | CS | 1 | 3540.32 | 3161 | 3550 | 3170 | IC | N/A | Post | N/A | 2015-10-02 | N/A | 2015-10-17 | 2015-11-01 | 2015-11-30
381 | THSK | L.4.5.6.1 | 2016 | 1 | THSK/2016/CS/L.4.5.6.1/IC/1 | Distance Education Content Coordinator | CS | CS | 1 | 19999.84 | 17857 | 20000 | 17860 | IC | N/A | Post | N/A | 2016-05-02 | N/A | 2016-05-17 | 2016-06-01 | 2016-06-30
382 | THSK | L.4.5.6.1 | 2016 | 2 | THSK/2016/CS/L.4.5.6.1/IC/2 | Distance Education Consultant 1 | CS | CS | 1 | 7000 | 6250 | 7000 | 6250 | IC | N/A | Post | N/A | 2016-05-02 | N/A | 2016-05-17 | 2016-06-01 | 2016-06-30
383 | THSK | L.4.5.6.1 | 2016 | 3 | THSK/2016/CS/L.4.5.6.1/IC/3 | Distance Education Consultant 2 | CS | CS | 1 | 7000 | 6250 | 7000 | 6250 | IC | N/A | Post | N/A | 2016-05-02 | N/A | 2016-05-17 | 2016-06-01 | 2016-06-30
384 | THSK | L.4.5.6.1 | 2016 | 4 | THSK/2016/CS/L.4.5.6.1/IC/4 | Distance Education Consultant 3 | CS | CS | 1 | 7000 | 6250 | 7000 | 6250 | IC | N/A | Post | N/A | 2016-08-02 | N/A | 2016-08-17 | 2016-09-01 | 2016-09-30
385 | THSK | L.4.5.6.1 | 2016 | 5 | THSK/2016/CS/L.4.5.6.1/IC/5 | Distance Education Consultant 4 | CS | CS | 1 | 7000 | 6250 | 7000 | 6250 | IC | N/A | Post | N/A | 2016-08-02 | N/A | 2016-08-17 | 2016-09-01 | 2016-09-30
386 | THSK | L.4.5.6.1 | 2016 | 6 | THSK/2016/CS/L.4.5.6.1/IC/6 | Distance Education Consultant 5 | CS | CS | 1 | 7000 | 6250 | 7000 | 6250 | IC | N/A | Post | N/A | 2016-09-01 | N/A | 2016-09-16 | 2016-10-01 | 2016-10-30
387 | THSK | L.4.5.6.1 | 2016 | 7 | THSK/2016/CS/L.4.5.6.1/IC/7 | Distance Education Consultant 6 | CS | CS | 1 | 7000 | 6250 | 7000 | 6250 | IC | N/A | Post | N/A | 2016-09-01 | N/A | 2016-09-16 | 2016-10-01 | 2016-10-30
388 | THSK | L.4.5.6.1 | 2016 | 8 | THSK/2016/CS/L.4.5.6.1/IC/8 | Distance Education Consultant 7 | CS | CS | 1 | 7000 | 6250 | 7000 | 6250 | IC | N/A | Post | N/A | 2016-10-02 | N/A | 2016-10-17 | 2016-11-01 | 2016-11-30
389 | THSK | L.4.5.6.1 | 2016 | 9 | THSK/2016/CS/L.4.5.6.1/IC/9 | Distance Education Consultant 8 | CS | CS | 1 | 7000 | 6250 | 7000 | 6250 | IC | N/A | Post | N/A | 2016-10-02 | N/A | 2016-10-17 | 2016-11-01 | 2016-11-30
390 | THSK | L.4.5.6.1 | 2016 | 10 | THSK/2016/CS/L.4.5.6.1/IC/10 | Distance Education Consultant 9 | CS | CS | 1 | 7000 | 6250 | 7000 | 6250 | IC | N/A | Post | N/A | 2016-11-01 | N/A | 2016-11-16 | 2016-12-01 | 2016-12-30
391 | THSK | L.4.5.6.1 | 2016 | 11 | THSK/2016/CS/L.4.5.6.1/IC/11 | Distance Education Consultant 10 | CS | CS | 1 | 7000 | 6250 | 7000 | 6250 | IC | N/A | Post | N/A | 2016-11-01 | N/A | 2016-11-16 | 2016-12-01 | 2016-12-30
392 | THSK | L.4.5.5.2 | 2016 | 1 | THSK/2016/CS/L.4.5.5.2/IC/1 | Preparation of Field Guide | CS | CS | 1 | 19999.84 | 17857 | 20000 | 17860 | IC | N/A | Post | N/A | 2016-01-02 | N/A | 2016-01-17 | 2016-02-01 | 2016-02-27
393 | THSK | L.4.5.4.1 | 2016 | 1 | THSK/2016/CS/L.4.5.4.1/IC/1 | Training Coordinator 1 | CS | CS | 1 | 8336.16 | 7443 | 8340 | 7450 | IC | N/A | Post | N/A | 2016-03-02 | N/A | 2016-03-17 | 2016-04-01 | 2016-04-30
394 | THSK | L.4.5.4.1 | 2016 | 2 | THSK/2016/CS/L.4.5.4.1/IC/2 | Training Consultant 1 | CS | CS | 1 | 4719.68 | 4214 | 4720 | 4220 | IC | N/A | Post | N/A | 2016-03-02 | N/A | 2016-03-17 | 2016-04-01 | 2016-04-30
395 | THSK | L.4.5.4.1 | 2016 | 3 | THSK/2016/CS/L.4.5.4.1/IC/3 | Training Consultant 4 | CS | CS | 1 | 4719.68 | 4214 | 4720 | 4220 | IC | N/A | Post | N/A | 2016-03-02 | N/A | 2016-03-17 | 2016-04-01 | 2016-04-30
396 | THSK | L.4.5.4.1 | 2016 | 4 | THSK/2016/CS/L.4.5.4.1/IC/4 | Training Coordinator 2 | CS | CS | 1 | 8336.16 | 7443 | 8340 | 7450 | IC | N/A | Post | N/A | 2016-07-02 | N/A | 2016-07-17 | 2016-08-01 | 2016-08-30
397 | THSK | L.4.5.4.1 | 2016 | 5 | THSK/2016/CS/L.4.5.4.1/IC/5 | Training Consultant 2 | CS | CS | 1 | 4719.68 | 4214 | 4720 | 4220 | IC | N/A | Post | N/A | 2016-07-02 | N/A | 2016-07-17 | 2016-08-01 | 2016-08-30
398 | THSK | L.4.5.4.1 | 2016 | 6 | THSK/2016/CS/L.4.5.4.1/IC/6 | Training Consultant 5 | CS | CS | 1 | 4719.68 | 4214 | 4720 | 4220 | IC | N/A | Post | N/A | 2016-07-02 | N/A | 2016-07-17 | 2016-08-01 | 2016-08-30
399 | THSK | L.4.5.4.1 | 2016 | 7 | THSK/2016/CS/L.4.5.4.1/IC/7 | Training Coordinator 3 | CS | CS | 1 | 8336.16 | 7443 | 8340 | 7450 | IC | N/A | Post | N/A | 2016-10-02 | N/A | 2016-10-17 | 2016-11-01 | 2016-11-30
400 | THSK | L.4.5.4.1 | 2016 | 8 | THSK/2016/CS/L.4.5.4.1/IC/8 | Training Consultant 3 | CS | CS | 1 | 4719.68 | 4214 | 4720 | 4220 | IC | N/A | Post | N/A | 2016-10-02 | N/A | 2016-10-17 | 2016-11-01 | 2016-11-30
401 | THSK | L.4.5.4.1 | 2016 | 9 | THSK/2016/CS/L.4.5.4.1/IC/9 | Training Consultant 6 | CS | CS | 1 | 4719.68 | 4214 | 4720 | 4220 | IC | N/A | Post | N/A | 2016-10-02 | N/A | 2016-10-17 | 2016-11-01 | 2016-11-30
402 | THSK | L.4.5.4.1 | 2017 | 1 | THSK/2017/CS/L.4.5.4.1/IC/1 | Training Coordinator 1 | CS | CS | 1 | 6251.84 | 5582 | 6260 | 5590 | IC | N/A | Post | N/A | 2017-01-30 | N/A | 2017-02-14 | 2017-03-01 | 2017-03-30
403 | THSK | L.4.5.4.1 | 2017 | 2 | THSK/2017/CS/L.4.5.4.1/IC/2 | Training Consultant 1 | CS | CS | 1 | 3540.32 | 3161 | 3550 | 3170 | IC | N/A | Post | N/A | 2017-01-30 | N/A | 2017-02-14 | 2017-03-01 | 2017-03-30
404 | THSK | L.4.5.4.1 | 2017 | 3 | THSK/2017/CS/L.4.5.4.1/IC/3 | Training Consultant 2 | CS | CS | 1 | 3540.32 | 3161 | 3550 | 3170 | IC | N/A | Post | N/A | 2017-01-30 | N/A | 2017-02-14 | 2017-03-01 | 2017-03-30
405 | PYDB | P.2 | 2015 | 1 | SSYYDP/PYDB/2015/CS/A.7.1.1/SSS/04 (PYDB/2015/CS/P.2/IC/1) | Financial Management Specialist | CS | CS | 1 | 168000 | 150000 | 168000 | 150000 | SSS | N/A | Prior | N/A | 2015-11-01 | N/A | 2015-11-01 | 2015-12-01 | 2019-12-01
406 | PYDB | P.2 | 2015 | 2 | SSYYDP/PYDB/2015/CS/A.7.1.1/SSS/5 (PYDB/2015/CS/P.2/IC/2) | Financial Management Specialist | CS | CS | 1 | 168000 | 150000 | 168000 | 150000 | SSS | N/A | Prior | N/A | 2015-11-01 | N/A | 2015-11-01 | 2015-12-01 | 2019-12-01
407 | PYDB | P.2 | 2015 | 3 | SSYYDP/PYDB/2015/CS/A.7.1.1/SSS/23 (PYDB/2015/CS/P.2/IC/3) | Finance Assistant Consultant | CS | CS | 1 | 168000 | 150000 | 168000 | 150000 | SSS | N/A | Prior | N/A | 2015-11-01 | N/A | 2015-11-01 | 2015-12-01 | 2019-12-01
408 | PYDB | P.2 | 2015 | 4 | SSYYDP/PYDB/2015/CS/A.7.1.1/SSS/24 (PYDB/2015/CS/P.2/IC/4) | Finance Assistant Consultant | CS | CS | 1 | 168000 | 150000 | 168000 | 150000 | SSS | N/A | Prior | N/A | 2015-11-01 | N/A | 2015-11-01 | 2015-12-01 | 2019-12-01
409 | PYDB | P.2 | 2015 | 5-1. | PYDB/2015/CS/P.2/IC/5-1 | Accounting and Financial Analysis Consultant | CS | CS | 1 | 168000 | 150000 | 168000 | 150000 | IC | N/A | Post | N/A | 2015-12-01 | N/A | 2015-12-01 | 2016-02-15 | 2020-02-01
410 | PYDB | P.2 | 2015 | 5-2. | PYDB/2015/CS/P.2/IC/5-2 | Accounting Applications Consultant | CS | CS | 1 | 168000 | 150000 | 168000 | 150000 | IC | N/A | Post | N/A | 2015-12-02 | N/A | 2015-12-02 | 2016-02-16 | 2020-02-02
411 | PYDB | P.1 | 2015 | 1-1. | PYDB/2015/CS/P.1/IC/1-1 | Project Consultant | CS | CS | 1 | 168000 | 150000 | 168000 | 150000 | IC | N/A | Post | N/A | 2015-12-01 | N/A | 2015-12-01 | 2016-02-15 | 2020-02-01
412 | PYDB | P.1 | 2015 | 1-2. | PYDB/2015/CS/P.1/IC/1-2 | Project Consultant | CS | CS | 1 | 168000 | 150000 | 168000 | 150000 | IC | N/A | Post | N/A | 2015-12-01 | N/A | 2015-12-01 | 2016-02-15 | 2020-02-01
413 | PYDB | P.1 | 2015 | 1-3. | PYDB/2015/CS/P.1/IC/1-3 | Project Consultant | CS | CS | 1 | 168000 | 150000 | 168000 | 150000 | IC | N/A | Post | N/A | 2015-12-01 | N/A | 2015-12-01 | 2016-02-15 | 2020-02-01
414 | PYDB | P.1 | 2015 | 1-4. | PYDB/2015/CS/P.1/IC/1-4 | Grahic Design Consultant | CS | CS | 1 | 168000 | 150000 | 168000 | 150000 | IC | N/A | Post | N/A | 2015-12-01 | N/A | 2015-12-01 | 2016-02-15 | 2020-02-01
415 | PYDB | P.1 | 2015 | 1-5. | PYDB/2015/CS/P.1/IC/1-5 | Reporting Consultant | CS | CS | 1 | 168000 | 150000 | 168000 | 150000 | IC | N/A | Post | N/A | 2015-12-01 | N/A | 2015-12-01 | 2016-02-15 | 2020-02-01
416 | PYDB | P.5 | 2015 | 1-1. | PYDB/2015/CS/P.5/IC/1-1 | IT Support Staff | CS | CS | 1 | 168000 | 150000 | 168000 | 150000 | IC | N/A | Post | N/A | 2015-12-01 | N/A | 2015-12-01 | 2016-02-15 | 2020-02-01
417 | PYDB | P.5 | 2015 | 1-2. | PYDB/2015/CS/P.5/IC/1-2 | IT Support Staff | CS | CS | 1 | 168000 | 150000 | 168000 | 150000 | IC | N/A | Post | N/A | 2015-12-01 | N/A | 2015-12-01 | 2016-02-15 | 2020-02-01
418 | PYDB | P.4 | 2015 | 1-1. | PYDB/2015/CS/P.4/IC/1-1 | Procurement Consultant | CS | CS | 1 | 168000 | 150000 | 168000 | 150000 | IC | N/A | Prior | N/A | 2015-12-01 | N/A | 2015-12-01 | 2016-02-15 | 2020-02-01
419 | PYDB | P.4 | 2015 | 1-2. | PYDB/2015/CS/P.4/IC/1-2 | Procurement Consultant | CS | CS | 1 | 168000 | 150000 | 168000 | 150000 | IC | N/A | Prior | N/A | 2015-12-01 | N/A | 2015-12-01 | 2016-02-15 | 2020-02-01
420 | PYDB | P.4 | 2015 | 1-3. | PYDB/2015/CS/P.4/IC/1-3 | Statistics and Research Specialist | CS | CS | 1 | 168000 | 150000 | 168000 | 150000 | IC | N/A | Post | N/A | 2015-12-01 | N/A | 2015-12-01 | 2016-02-15 | 2020-02-01
421 | PYDB | P.3 | 2015 | 1-1. | PYDB/2015/CS/P.3/IC/1-1 | Technical Language Translator | CS | CS | 1 | 168000 | 150000 | 168000 | 150000 | IC | N/A | Post | N/A | 2015-12-01 | N/A | 2015-12-01 | 2016-02-15 | 2020-02-01
422 | PYDB | P.3 | 2015 | 1-2. | PYDB/2015/CS/P.3/IC/1-2 | Technical Language Translator | CS | CS | 1 | 168000 | 150000 | 168000 | 150000 | IC | N/A | Post | N/A | 2015-12-01 | N/A | 2015-12-01 | 2016-02-15 | 2020-02-01
423 | PYDB | P.3 | 2015 | 1-3. | PYDB/2015/CS/P.3/IC/1-3 | Technical Language Translator | CS | CS | 1 | 168000 | 150000 | 168000 | 150000 | IC | N/A | Post | N/A | 2015-12-01 | N/A | 2015-12-01 | 2016-02-15 | 2020-02-01
424 | PYDB | P.3 | 2015 | 1-4. | PYDB/2015/CS/P.3/IC/1-4 | Technical Language Translator | CS | CS | 1 | 168000 | 150000 | 168000 | 150000 | IC | N/A | Post | N/A | 2015-12-01 | N/A | 2015-12-01 | 2016-02-15 | 2020-02-01
425 | PYDB | P.3 | 2015 | 1-5. | PYDB/2015/CS/P.3/IC/1-5 | Accounting Applications Consultant | CS | CS | 1 | 168000 | 150000 | 168000 | 150000 | IC | N/A | Post | N/A | 2015-12-01 | N/A | 2015-12-01 | 2016-02-15 | 2020-02-01
426 | PYDB | P.3 | 2015 | 1-6. | PYDB/2015/CS/P.3/IC/1-6 | Accounting Applications Consultant | CS | CS | 1 | 168000 | 150000 | 168000 | 150000 | IC | N/A | Post | N/A | 2015-12-01 | N/A | 2015-12-01 | 2016-02-15 | 2020-02-01
427 | PYDB | P.3 | 2015 | 1-7. | PYDB/2015/CS/P.3/IC/1-7 | Accounting Applications Consultant | CS | CS | 1 | 168000 | 150000 | 168000 | 150000 | IC | N/A | Post | N/A | 2015-12-01 | N/A | 2015-12-01 | 2016-02-15 | 2020-02-01
[6 empty] | B.SUB TOTAL |  |  |  | 39111686.5456 | 34921148.7014 | 39111716 | 34922330
C. TRAINING AND WORKSHOPS | [5 empty] | C. TRAININGS AND WORKSHOPS
428 | SAGEM | E.2.1.1.2 | 2015 | 1 | SAGEM/2015/NCS-TR/E.2.1.1.2/S/1 | Workshop on Assessing Training Contents | NCS-TR | NCS-TR | 1 | 27668.1776 | 24703.73 | 27669 | 24710 | S | No | Prior | No | N/A | N/A | N/A | 2015-12-01 | 2015-12-01
429 | SAGEM | E.2.1.1.3 | 2016 | 1 | SAGEM/2016/NCS-TR/E.2.1.1.3/S/1 | Workshop on Determining the Needs of Information Database for Staff Training | NCS-TR | NCS-TR | 1 | 27668.1776 | 24703.73 | 27669 | 24710 | S | No | Post | No | N/A | 2016-01-02 | 2016-01-02 | 2016-02-01 | 2016-02-01
430 | SAGEM | E.2.1.1.4 | 2016 | 1 | SAGEM/2016/NCS-TR/E.2.1.1.4/S/1 | Distance Training and Management Workshop on Public Health and Family Practice System | NCS-TR | NCS-TR | 1 | 27668.1776 | 24703.73 | 27669 | 24710 | S | No | Post | No | N/A | 2016-04-01 | 2016-04-01 | 2016-05-01 | 2016-05-01
431 | SAGEM | E.2.1.1.5 | 2016 | 1 | SAGEM/2016/NCS-TR/E.2.1.1.5/S/1 | Research Workshop on Determining the Items and Amount of Training Costs | NCS-TR | NCS-TR | 1 | 27668.1776 | 24703.73 | 27669 | 24710 | S | No | Post | No | N/A | 2016-04-01 | 2016-04-01 | 2016-05-01 | 2016-05-01
432 | SAGEM | E.2.1.2.2 | 2016 | 1 | SAGEM/2016/NCS-TR/E.2.1.2.2/N/A/ | National trip and observation for studying good practices of countries – 1 | NCS-TR | NCS-TR | N/A | 12499.9952 | 11160.71 | 12500 | 11170 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2016-01-01 | 2016-01-01
433 | SAGEM | E.2.1.2.2 | 2016 | 2 | SAGEM/2016/NCS-TR/E.2.1.2.2/N/A/ | National trip and observation for studying good practices of countries – 2 | NCS-TR | NCS-TR | N/A | 12499.9952 | 11160.71 | 12500 | 11170 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2016-03-01 | 2016-03-01
434 | SAGEM | E.2.1.2.5 | 2016 | 1 | SAGEM/2016/NCS-TR/E.2.1.2.5/S/1 | Workshop on National and International Sector Analysis for Distance learning Accredation and Borrowing | NCS-TR | NCS-TR | 1 | 36000.0032 | 32142.86 | 36000 | 32150 | S | No | Post | No | N/A | 2016-12-02 | 2016-12-02 | 2017-01-01 | 2017-01-01
435 | SAGEM | E.2.1.2.2 | 2016 | 3 | SAGEM/2016/NCS-TR/E.2.1.2.2/N/A/ | International trip and observation for studying good practices of countries – 1 | NCS-TR | NCS-TR | N/A | 49798.392 | 44462.85 | 49800 | 44470 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2016-02-01 | 2016-02-01
436 | SAGEM | E.2.1.2.2 | 2016 | 4 | SAGEM/2016/NCS-TR/E.2.1.2.2/N/A/ | International trip and observation for studying good practices of countries – 2 | NCS-TR | NCS-TR | N/A | 49798.392 | 44462.85 | 49800 | 44470 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2016-04-01 | 2016-04-01
437 | SAGEM | E.2.1.2.2 | 2016 | 5 | SAGEM/2016/NCS-TR/E.2.1.2.2/N/A/ | National trip and observation for studying good practices of countries – 3 | NCS-TR | NCS-TR | N/A | 12499.9952 | 11160.71 | 12500 | 11170 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2016-05-01 | 2016-05-01
438 | SAGEM | E.2.1.2.2 | 2016 | 6 | SAGEM/2016/NCS-TR/E.2.1.2.2/N/A/ | National trip and observation for studying good practices of countries – 4 | NCS-TR | NCS-TR | N/A | 12499.9952 | 11160.71 | 12500 | 11170 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2016-07-01 | 2016-07-01
439 | TKHK | N.3.1.4.1 | 2016 | 1 | TKHK/2016/NCS-TR/N.3.1.4.1/S/1 | Organization for Enhancing Expertise in and Obtaining Information on Hospital Pharmacy Services | NCS-TR | NCS-TR | 1 | 42000 | 37500 | 42000 | 37500 | S | No | Post | No | N/A | 2016-05-02 | 2016-05-02 | 2016-06-01 | 2016-07-01
440 | TKHK | N.3.1.6.1 | 2016 | 1 | TKHK/2016/NCS-TR/N.3.1.6.1/S/1 | Organization for Enhancing Expertise in and Obtaining Information on Stock Management Practices | NCS-TR | NCS-TR | 1 | 42000 | 37500 | 42000 | 37500 | S | No | Post | No | N/A | 2016-05-02 | 2016-06-16 | 2016-06-01 | 2016-07-01
441 | TKHK | N.3.1.7.1 | 2016 | 1 | TKHK/2016/NCS-TR/N.3.1.7.1/S/1 | Organization for Training on Hospitals Financial Structures | NCS-TR | NCS-TR | 1 | 42000 | 37500 | 42000 | 37500 | S | No | N/A | No | N/A | 2016-05-02 | 2016-06-16 | 2016-06-01 | 2016-07-01
442 | SYGM | F.3.1.4.1 | 2015 | 1 | SYGM/2015/NCS-TR/F.3.1.4.1/S /1 | Organization of Leed, Breeam or DGNB Certification Training | NCS-TR | NCS-TR | 1 | 19999.84 | 17857 | 20000 | 17860 | S | No | Prior | No | N/A | 2015-10-02 | 2015-10-02 | 2015-11-01 | 2015-11-01
443 | SYGM | F.3.1.4.1 | 2015 | 2 | SYGM/2015/NCS-TR/F.3.1.4.1/S /2 | Organization of Project Management Training (Project Management Certification Program) | NCS-TR | NCS-TR | 1 | 19999.84 | 17857 | 20000 | 17860 | S | No | Post | No | N/A | 2015-10-02 | 2015-10-02 | 2015-11-01 | 2015-11-01
444 | SYGM | F.3.1.4.2 | 2016 | 1 | SYGM/2016/NCS-TR/F.3.1.4.2/N/A/1 | Technical business trip to study the foreign health facilities established with PPP model | NCS-TR | NCS-TR | N/A | 30000.32 | 26786 | 30000 | 26790 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2016-02-01 | 2016-02-01
445 | SYGM | F.3.1.4.3 | 2016 | 2 | SYGM/2016/NCS-TR/F.3.1.4.3/N/A/2 | Technical business trip to study the foreign health facilities established with PPP model | NCS-TR | NCS-TR | N/A | 30000.32 | 26786 | 30000 | 26790 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2016-08-01 | 2016-08-01
446 | SYGM | F.3.1.4.3 | 2016 | 1 | SYGM/2016/NCS-TR/F.3.1.4.3/S/1 | Workshop on Architectural and Structural Design and Setting the Standards for Green Hospitals | NCS-TR | NCS-TR | 1 | 30000.32 | 26786 | 30000 | 26790 | S | No | Post | No | N/A | 2016-04-01 | 2016-04-01 | 2016-05-01 | 2016-05-01
447 | SYGM | F.3.1.4.3 | 2016 | 2 | SYGM/2016/NCS-TR/F.3.1.4.3/S /2 | Workshop on Architectural and Structural Design and Setting the Standards for Green Hospitals | NCS-TR | NCS-TR | 1 | 30000.32 | 26786 | 30000 | 26790 | S | No | Post | No | N/A | 2016-08-02 | 2016-08-02 | 2016-09-01 | 2016-09-01
448 | SYGM | F.3.1.4.3 | 2017 | 1 | SYGM/2017/NCS-TR/F.3.1.4.3/N/A/1 | Technical business trip to study the foreign health facilities established with PPP model | NCS-TR | NCS-TR | N/A | 30000.32 | 26786 | 30000 | 26790 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2017-01-01 | 2017-01-01
449 | SYGM | F.3.1.4.4 | 2016 | 1 | SYGM/2016/NCS-TR/F.3.1.4.4/S /1 | Organization of Training on Architectural and Engineering Design | NCS-TR | NCS-TR | 1 | 15000.16 | 13393 | 15000 | 13400 | S | No | Post | No | N/A | 2016-09-01 | 2016-09-01 | 2016-10-01 | 2016-10-01
450 | SYGM | F.3.1.4.4 | 2016 | 2 | SYGM/2016/NCS-TR/F.3.1.4.4/S /2 | PPP Congress | NCS-TR | NCS-TR | 1 | 80000.48 | 71429 | 80000 | 71430 | S | No | Post | No | N/A | 2016-11-01 | 2016-11-01 | 2016-12-01 | 2016-12-01
451 | SYGM | F.3.1.4.4 | 2017 | 1 | SYGM/2017/NCS-TR/F.3.1.4.4/S /1 | Organization of Training on Architectural and Engineering Design | NCS-TR | NCS-TR | 1 | 15000.16 | 13393 | 15000 | 13400 | S | No | Post | No | N/A | 2017-09-01 | 2017-09-01 | 2017-10-01 | 2017-10-01
452 | SHGM | A.1.1.1.5 | 2015 | 1 | SHGM/2015/NCS-TR/A.1.1.1.5/N/A/1 | Studying on foreign examples about risks (3 persons, European countries) | NCS-TR | NCS-TR | N/A | 22500.0048 | 20089.29 | 22500 | 20090 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2015-10-01 | 2016-02-01
453 | SHGM | A.1.1.5.4 | 2016 | 1 | SHGM/2016/NCS-TR/A.1.1.5.4/S/1 | Organization of Training Activities for Coordinators | NCS-TR | NCS-TR | 1 | 37500 | 33482.1429 | 37500 | 33490 | S | No | Post | No | N/A | 2016-06-01 | 2016-06-01 | 2016-07-01 | 2016-07-01
454 | SHGM | A.1.2.1.3 | 2015 | 1 | SHGM/2015/NCS-TR/A.1.2.1.3/S/1 | Organization of Receiving English language training 1 | NCS-TR | NCS-TR | 1 | 18749.9984 | 16741.07 | 18750 | 16750 | S | No | Prior | No | N/A | 2015-10-02 | 2015-10-02 | 2015-11-01 | 2016-02-01
455 | SHGM | A.1.2.2.3 | 2016 | 1 | SHGM/2016/NCS-TR/A.1.2.2.3/S/1 | Workshop for determining the criteria | NCS-TR | NCS-TR | 1 | 44999.9984 | 40178.57 | 45000 | 40180 | S | No | Post | No | N/A | 2016-04-01 | 2016-04-01 | 2016-05-01 | 2016-11-01
456 | SHGM | A.1.2.4.3 | 2016 | 1 | SHGM/2016/NCS-TR/A.1.2.4.3/S/1 | Organization of Information and training for stakeholders supporting the institutional healthcare service indicator studies | NCS-TR | NCS-TR | 1 | 37499.9968 | 33482.14 | 37500 | 33490 | S | No | Post | No | N/A | 2016-09-01 | 2016-09-01 | 2016-10-01 | 2016-10-01
457 | SHGM | A.1.2.6.2 | 2016 | 1 | SHGM/2016/NCS-TR/A.1.2.6.2/S/1 | Workshop on Institutional Indicator Assessment | NCS-TR | NCS-TR | 1 | 15000.0032 | 13392.86 | 15000 | 13400 | S | No | Post | No | N/A | 2016-09-01 | 2016-09-01 | 2016-10-01 | 2016-10-01
458 | SHGM | A.1.3.4.4 | 2016 | 1 | SHGM/2016/NCS-TR/A.1.3.4.4/S/1 | Workshop on auditing health institutions and organisations for Provincial Health Directorates | NCS-TR | NCS-TR | 1 | 39732.504 | 35475.45 | 39740 | 35480 | S | No | Post | No | N/A | 2016-09-01 | 2016-09-01 | 2016-10-01 | 2016-10-01
459 | SHGM | A.1.3.4.8 | 2016 | 1 | SHGM/2016/NCS-TR/A.1.3.4.8/N/A/1 | Participation in Training (3 persons) | NCS-TR | NCS-TR | N/A | 1500 | 1339.2857 | 1500 | 1340 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2016-08-01 | 2016-08-01
460 | ASHGM | B.1.1.1.3 | 2016 | 1 | ASHGM/2016/NCS-TR/B.1.1.1.3/S/1 | Preliminary Workshop | NCS-TR | NCS-TR | 1 | 5999.9968 | 5357.14 | 6000 | 5360 | S | No | Prior | No | N/A | 2016-01-02 | 2016-01-02 | 2016-02-01 | 2016-02-01
461 | ASHGM | B.1.1.2.1 | 2016 | 1 | ASHGM/2016/NCS-TR/B.1.1.2.1/N/A/1 | On-site study and evaluation of the international examples | NCS-TR | NCS-TR | N/A | 50000.0032 | 44642.86 | 50000 | 44650 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2016-04-01 | 2016-04-01
462 | ASHGM | B.1.1.2.2 | 2016 | 1 | ASHGM/2016/NCS-TR/B.1.1.2.2/S/1 | Workshop for establishing the system in the light of foreign evaluation reports | NCS-TR | NCS-TR | 1 | 5999.9968 | 5357.14 | 6000 | 5360 | S | No | Post | No | N/A | 2016-04-01 | 2016-04-01 | 2016-05-01 | 2016-05-01
463 | ASHGM | B.1.1.2.5 | 2016 | 1 | ASHGM/2016/NCS-TR/B.1.1.2.5/S/1 | Workshop with stakeholders and experts invited from abroad for the system to be used in the patient transport | NCS-TR | NCS-TR | 1 | 26355 | 23531.25 | 26360 | 23540 | S | No | Post | No | N/A | 2016-08-02 | 2016-08-02 | 2016-09-01 | 2016-09-01
464 | ASHGM | B.1.1.2.6 | 2016 | 1 | ASHGM/2016/NCS-TR/ B.1.1.2.6/N/A/1 | Sending two paramedics for training to the University of Washington in the USA | NCS-TR | NCS-TR | N/A | 50000.0032 | 44642.86 | 50000 | 44650 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2016-11-01 | 2016-11-01
465 | ASHGM | B.1.1.2.8 | 2016 | 1 | ASHGM/2016/NCS-TR/B.1.1.2.8/S/1 | Organization of preparation of the draft program for the training of the healthcare professionals who will be transported | NCS-TR | NCS-TR | 1 | 9999.9984 | 8928.57 | 10000 | 8930 | S | No | Post | No | N/A | 2016-10-02 | 2016-10-02 | 2016-11-01 | 2016-11-01
466 | ASHGM | B.1.1.2.9 | 2016 | 1 | ASHGM/2016/NCS-TR/ B.1.1.2.9/S/1 | Organization of Implementation of the pilot trauma training | NCS-TR | NCS-TR | 1 | 15000.0032 | 13392.86 | 15000 | 13400 | S | No | Post | No | N/A | 2016-11-01 | 2016-11-01 | 2016-12-01 | 2016-12-01
467 | DISAB | G.1.1.1.1 | 2016 | 1 | DISAB/2016/NCS-TR/G.1.1.1.1/S/1 | Coordination Workshop | NCS-TR | NCS-TR | 1 | 15008 | 13400 | 15000 | 13400 | S | No | Prior | No | N/A | 2016-10-02 | 2016-10-02 | 2016-11-01 | 2016-11-01
468 | DISAB | G.1.1.1.1 | 2016 | 2 | DISAB/2016/NCS-TR/G.1.1.1.1/S/2 | Organization of Information Experience and Sharing | NCS-TR | NCS-TR | 1 | 15008 | 13400 | 15000 | 13400 | S | No | Post | No | N/A | 2016-01-02 | 2016-01-02 | 2016-02-01 | 2016-02-01
469 | DISAB | G.1.1.2.2 | 2016 | 1 | DISAB/2016/NCS-TR/G.1.1.2.2/S/1 | Training organization for the experts who will study on the Healthcare System 1 | NCS-TR | NCS-TR | 1 | 11267.2 | 10060 | 11270 | 10060 | S | No | Post | No | N/A | 2016-05-02 | 2016-05-02 | 2016-06-01 | 2016-06-01
470 | DISAB | G.1.1.2.2 | 2016 | 2 | DISAB/2016/NCS-TR/G.1.1.2.2/S/2 | Training organization for the experts who will study on the Healthcare System 2 | NCS-TR | NCS-TR | 1 | 11267.2 | 10060 | 11270 | 10060 | S | No | Post | No | N/A | 2016-10-02 | 2016-10-02 | 2016-11-01 | 2016-11-01
471 | DISAB | G.1.1.2.3 | 2016 | 1 | DISAB/2016/NCS-TR/G.1.1.2.3/S/1 | Visits abroad to study on the Healthcare Systems of the Countries (Preparation of Reports) 1 | NCS-TR | NCS-TR | 1 | 75001.92 | 66966 | 75000 | 66970 | S | No | Post | No | N/A | 2016-06-01 | 2016-06-01 | 2016-07-01 | 2016-07-01
472 | DISAB | G.1.1.2.3 | 2016 | 2 | DISAB/2016/NCS-TR/G.1.1.2.3/S/2 | Visits abroad to study on the Healthcare Systems of the Countries (Preparation of Reports) 2 | NCS-TR | NCS-TR | 1 | 75001.92 | 66966 | 75000 | 66970 | S | No | Post | No | N/A | 2016-09-01 | 2016-09-01 | 2016-10-01 | 2016-10-01
473 | DISAB | G.1.1.2.5 | 2016 | 1 | DISAB/2016/NCS-TR/G.1.1.2.5/S/1 | Workshop for studying and evaluating the healthcare system reports after the visit 1 | NCS-TR | NCS-TR | 1 | 15008 | 13400 | 15000 | 13400 | S | No | Post | No | N/A | 2016-07-02 | 2016-07-02 | 2016-08-01 | 2016-08-01
474 | DISAB | G.1.1.2.5 | 2016 | 2 | DISAB/2016/NCS-TR/G.1.1.2.5/S/2 | Organization of Presentation Service 1 | NCS-TR | NCS-TR | 1 | 24999.968 | 22321.4 | 25000 | 22330 | S | No | Post | No | N/A | 2016-08-02 | 2016-08-02 | 2016-09-01 | 2016-09-01
475 | DISAB | G.1.1.2.5 | 2016 | 3 | DISAB/2016/NCS-TR/G.1.1.2.5/S/3 | Workshop for studying and evaluating the healthcare system reports after the visit 2 | NCS-TR | NCS-TR | 1 | 15008 | 13400 | 15000 | 13400 | S | No | Post | No | N/A | 2016-10-02 | 2016-10-02 | 2016-11-01 | 2016-11-01
476 | DISAB | G.1.1.2.5 | 2016 | 4 | DISAB/2016/NCS-TR/G.1.1.2.5/S/4 | Workshop for studying and evaluating the healthcare system reports after the visit 3 | NCS-TR | NCS-TR | 1 | 15008 | 13400 | 15000 | 13400 | S | No | Post | No | N/A | 2016-12-02 | 2016-12-02 | 2017-01-01 | 2017-01-01
477 | DISAB | G.1.1.2.5 | 2016 | 5 | DISAB/2016/NCS-TR/G.1.1.2.5/S/5 | Organization of Presentation Service 2 | NCS-TR | NCS-TR | 1 | 24999.968 | 22321.4 | 25000 | 22330 | S | No | Post | No | N/A | 2016-12-02 | 2016-12-02 | 2017-01-01 | 2017-01-01
478 | DISAB | G.1.1.5.1 | 2016 | 1 | DISAB/2016/NCS-TR/G.1.1.5.1/S/1 | Strategy Workshop | NCS-TR | NCS-TR | 1 | 22211.9968 | 19832.14 | 22210 | 19840 | S | No | Post | No | N/A | 2016-12-02 | 2016-12-02 | 2017-01-01 | 2017-01-01
479 | SAGEM | E.1.1.1.3 | 2015 | 1 | SAGEM/2015/NCS-TR/E.1.1.1.3/N/A/1 | International Country Visits Made to Institutions | NCS-TR | NCS-TR | N/A | 97500.032 | 87053.6 | 97500 | 87060 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2015-10-01 | 2017-03-01
480 | SAGEM | E.1.1.2.1 | 2016 | 1 | SAGEM/2016/NCS-TR/E.1.1.2.1/S/1 | Meeting on Unmet Health Indicators 1, 2 and 3 | NCS-TR | NCS-TR | 1 | 4499.9808 | 4017.84 | 4500 | 4020 | S | No | Post | No | N/A | 2016-06-01 | 2016-06-01 | 2016-07-01 | 2016-07-01
481 | SAGEM | E.1.1.4.1 | 2016 | 1 | SAGEM/2016/NCS-TR/E.1.1.4.1/NCB/1 | Workshop on Health Statistics | NCS-TR | NCS-TR | 1 | 120000.0256 | 107142.88 | 120000 | 107150 | NCB | No | Prior | No | N/A | 2016-07-03 | 2016-08-17 | 2016-09-01 | 2016-10-01
482 | SAGEM | E.1.1.5.1 | 2016 | 1 | SAGEM/2016/NCS-TR/E.1.1.5.1/S/1 | Unit Meeting | NCS-TR | NCS-TR | 1 | 25200 | 22500 | 25200 | 22500 | S | No | Post | No | N/A | 2016-12-02 | 2016-12-02 | 2017-01-01 | 2017-03-01
483 | SAGEM | E.6.1.1.2 | 2016 | 1 | SAGEM/2016/NCS-TR/E.6.1.1.2/S/1 | Workshop Meeting on Current Situation Analysis | NCS-TR | NCS-TR | 1 | 52500 | 46875 | 52500 | 46880 | S | No | Post | No | N/A | 2016-01-31 | 2016-01-31 | 2016-03-01 | 2016-03-01
484 | SAGEM | E.6.1.1.2 | 2016 | 2 | SAGEM/2016/NCS-TR/E.6.1.1.2/S/2 | Workshop Meeting for Needs Analysis | NCS-TR | NCS-TR | 1 | 52500 | 46875 | 52500 | 46880 | S | No | Post | No | N/A | 2016-08-02 | 2016-08-02 | 2016-09-01 | 2016-09-01
485 | SAGEM | E.6.1.1.3 | 2016 | 1 | SAGEM/2016/NCS-TR/E.6.1.1.3/S/1 | Workshop on formation of institutional identity during HTA | NCS-TR | NCS-TR | 1 | 26250 | 23437.5 | 26250 | 23440 | S | No | Post | No | N/A | 2016-05-02 | 2016-05-02 | 2016-06-01 | 2016-06-01
486 | SAGEM | E.6.1.1.4 | 2016 | 1 | SAGEM/2016/NCS-TR/E.6.1.1.4/N/A/1 | Study visit for first country example | NCS-TR | NCS-TR | N/A | 26250 | 23437.5 | 26250 | 23440 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2016-05-01 | 2016-05-01
487 | SAGEM | E.6.1.1.5 | 2016 | 1 | SAGEM/2016/NCS-TR/E.6.1.1.5/S/1 | First workshop for creating strategy paper | NCS-TR | NCS-TR | 1 | 52500 | 46875 | 52500 | 46880 | S | No | Post | No | N/A | 2016-06-01 | 2016-06-01 | 2016-07-01 | 2016-07-01
488 | SAGEM | E.6.1.1.6 | 2016 | 1 | SAGEM/2016/NCS-TR/E.6.1.1.6/S/1 | Organization of First Structured Course | NCS-TR | NCS-TR | 1 | 29999.9952 | 26785.71 | 30000 | 26790 | S | No | Post | No | N/A | 2016-11-01 | 2016-11-01 | 2016-12-01 | 2016-12-01
489 | SAGEM | E.6.1.1.7 | 2016 | 1 | SAGEM/2016/NCS-TR/E.6.1.1.7/N/A/1 | Participation in international meetings in 2016 1 | NCS-TR | NCS-TR | N/A | 37499.9968 | 33482.14 | 37500 | 33490 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2016-04-01 | 2016-11-01
490 | SAGEM | E.6.1.2.1 | 2016 | 1 | SAGEM/2016/NCS-TR/E.6.1.2.1/S/1 | HTA - University Cooperation Workshop | NCS-TR | NCS-TR | 1 | 52500 | 46875 | 52500 | 46880 | S | No | Post | No | N/A | 2016-10-02 | 2016-10-02 | 2016-11-01 | 2016-11-01
491 | SAGEM | E.6.1.2.4 | 2017 | 1 | SAGEM/2017/NCS-TR/E.6.1.2.4/S/1 | Workshop on Preparation of HTA Guidelines | NCS-TR | NCS-TR | 1 | 29999.9952 | 26785.71 | 30000 | 26790 | S | No | Post | No | N/A | 2017-02-01 | 2017-02-01 | 2017-03-01 | 2017-03-01
492 | SAGEM | E.6.1.2.5 | 2016 | 1 | SAGEM/2016/NCS-TR/E.6.1.2.5/NCB/1 | National HTA Meeting/Congress in 2016 | NCS-TR | NCS-TR | 1 | 89999.9968 | 80357.14 | 90000 | 80360 | NCB | No | Post | No | N/A | 2016-03-02 | 2016-04-16 | 2016-05-01 | 2016-05-31
493 | SAGEM | E.5.3.1.1 | 2015 | 1 | SAGEM/2015/NCS-TR/E.5.3.1.1/S/1 | Workshop on instrument development for healthcare system evaluation | NCS-TR | NCS-TR | 1 | 50000 | 44642.8571 | 50000 | 44650 | S | No | Post | No | N/A | N/A | N/A | 2015-10-01 | 2015-10-01
494 | SAGEM | E.5.3.1.2 | 2015 | 1 | SAGEM/2015/NCS-TR/E.5.3.1.2/S/1 | Organization of Basic Training for Healthcare System Evaluation | NCS-TR | NCS-TR | 1 | 25000 | 22321.4286 | 25000 | 22330 | S | No | Post | No | N/A | 2015-11-03 | 2015-11-03 | 2015-12-01 | 2015-12-01
495 | SAGEM | E.5.3.1.2 | 2016 | 1 | SAGEM/2016/NCS-TR/E.5.3.1.2/S/1 | Organization of Advanced Training for Healthcare System Evaluation | NCS-TR | NCS-TR | 1 | 55000 | 49107.1429 | 55000 | 49110 | S | No | Post | No | N/A | 2016-03-04 | 2016-03-04 | 2016-04-01 | 2016-04-01
496 | SAGEM | E.5.3.1.2 | 2016 | 2 | SAGEM/2016/NCS-TR/E.5.3.1.2/S/2 | Organization of Trainers' Training for Healthcare System Evaluation | NCS-TR | NCS-TR | 1 | 50000 | 44642.8571 | 50000 | 44650 | S | No | Post | No | N/A | 2016-08-04 | 2016-08-04 | 2016-09-01 | 2016-09-01
497 | SAGEM | E.5.3.1.2 | 2015 | 2 | SAGEM/2015/NCS-TR/E.5.3.1.2/S/2 | Organization of Geographic Information Systems Software Training | NCS-TR | NCS-TR | 1 | 5000 | 4464.2857 | 5000 | 4470 | S | No | Post | No | N/A | 2015-12-04 | 2015-12-04 | 2016-01-01 | 2016-01-01
498 | SAGEM | E.5.3.1.2 | 2016 | 3 | SAGEM/2016/NCS-TR/E.5.3.1.2/S/3 | Organization of Basic Training for Healthcare System Evaluation | NCS-TR | NCS-TR | 1 | 25000 | 22321.4286 | 25000 | 22330 | S | No | Post | No | N/A | 2016-12-04 | 2016-12-04 | 2017-01-01 | 2017-01-01
499 | SAGEM | E.5.3.1.3 | 2016 | 1 | SAGEM/2016/NCS-TR/E.5.3.1.3/S/1 | Organization service for Stakeholder Meeting on Turkish Healthcare System Performance Assessment | NCS-TR | NCS-TR | 1 | 50000 | 44642.8571 | 50000 | 44650 | S | No | Post | No | N/A | 2016-01-04 | 2016-01-04 | 2016-02-01 | 2016-02-01
500 | SAGEM | E.5.3.1.3 | 2016 | 2 | SAGEM/2016/NCS-TR/E.5.3.1.3/S/2 | Organization Service for technical study meeting on Healthcare System Evaluation | NCS-TR | NCS-TR | 1 | 20000 | 17857.1429 | 20000 | 17860 | S | No | Post | No | N/A | 2016-05-04 | 2016-05-04 | 2016-06-01 | 2016-06-01
501 | SAGEM | E.5.3.2.1 | 2015 | 1 | SAGEM/2015/NCS-TR/E.5.3.2.1/S/1 | Study Meeting on Training Program for Evaluation of HTP Policies | NCS-TR | NCS-TR | 1 | 45000 | 40178.5714 | 45000 | 40180 | S | No | Post | No | N/A | 2015-10-04 | 2015-10-04 | 2015-11-01 | 2015-11-01
502 | SAGEM | E.5.3.2.2 | 2016 | 1 | SAGEM/2016/NCS-TR/E.5.3.2.2/S/1 | Meeting on Healthcare Policies -1 | NCS-TR | NCS-TR | 1 | 50000 | 44642.8571 | 50000 | 44650 | S | No | Post | No | N/A | 2016-09-03 | 2016-09-03 | 2016-10-01 | 2016-10-01
503 | SAGEM | E.5.3.2.2 | 2016 | 1 | SAGEM/2016/NCS-TR/E.5.3.2.2/N/A/1 | Study Meeting on Evaluation of HTP Policies (abroad) | NCS-TR | NCS-TR | N/A | 10000 | 8928.5714 | 10000 | 8930 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2016-09-01 | 2016-09-01
504 | SAGEM | E.5.1.1.1 | 2016 | 1 | SAGEM/2016/NCS-TR/E.5.1.1.1/S/1 | Organization of Training on Planning and Implementing National Health Researches | NCS-TR | NCS-TR | 1 | 19999.84 | 17857 | 20000 | 17860 | S | No | Post | No | N/A | 2016-02-02 | 2016-02-02 | 2016-03-01 | 2016-03-01
505 | SAGEM | E.5.1.1.1 | 2016 | 2 | SAGEM/2016/NCS-TR/E.5.1.1.1/S/2 | Organization of Sample Selection in National Surveys and Weighting Training | NCS-TR | NCS-TR | 1 | 19999.84 | 17857 | 20000 | 17860 | S | No | Post | No | N/A | 2016-05-04 | 2016-05-04 | 2016-06-01 | 2016-06-01
506 | SAGEM | E.5.1.1.1 | 2016 | 3 | SAGEM/2016/NCS-TR/E.5.1.1.1/S/3 | Organization of Basic Training on Using Statistical Analyses and Statistical Programs in Health Researches | NCS-TR | NCS-TR | 1 | 19999.84 | 17857 | 20000 | 17860 | S | No | Post | No | N/A | 2016-08-04 | 2016-08-04 | 2016-09-01 | 2016-09-01
507 | SAGEM | E.5.1.1.1 | 2016 | 4 | SAGEM/2016/NCS-TR/E.5.1.1.1/S/4 | Organization of Advanced Training on Using Statistical Analyses and Statistical Programs in Health Researches | NCS-TR | NCS-TR | 1 | 50000.16 | 44643 | 50000 | 44650 | S | No | Post | No | N/A | 2016-11-03 | 2016-11-03 | 2016-12-01 | 2016-12-01
508 | SAGEM | E.5.1.1.1 | 2016 | 5 | SAGEM/2016/NCS-TR/E.5.1.1.1/S/5 | Organization of Training on Reporting Health Researches and Writing Articles | NCS-TR | NCS-TR | 1 | 50000.0032 | 44642.86 | 50000 | 44650 | S | No | Post | No | N/A | 2016-12-04 | 2016-12-04 | 2017-01-01 | 2017-03-01
509 | SAGEM | E.5.1.2.2 | 2016 | 1 | SAGEM/2016/NCS-TR/E.5.1.2.2/N/A/1 | Participation in national/international meetings on project-related topics | NCS-TR | NCS-TR | N/A | 70000 | 62500 | 70000 | 62500 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2016-03-01 | 2016-12-01
510 | PYDB | P.1 | 2015 | 1 | PYDB/2015/NCS-TR/P.1/S/1 | Organization of Trainings for strengthening Program and Project Management 1 | NCS-TR | NCS-TR | 1 | 50000.0032 | 44642.86 | 50000 | 44650 | S | No | Post | No | N/A | 2015-10-01 | 2015-10-01 | 2015-10-01 | 2015-10-01
511 | PYDB | P.1 | 2016 | 1 | PYDB/2016/NCS-TR/P.1/S/1 | PMSU Program Evaluation Workshop 2 | NCS-TR | NCS-TR | 1 | 25000.0016 | 22321.43 | 25000 | 22330 | S | No | Post | No | N/A | 2016-03-01 | 2016-03-01 | 2016-04-01 | 2016-04-01
512 | PYDB | P.1 | 2016 | 2 | PYDB/2016/NCS-TR/P.1/S/2 | Provincial Evaluation Meeting (Oganization of a Workshop for Provincial Public Health Directors) | NCS-TR | NCS-TR | 1 | 92999.9952 | 83035.71 | 93000 | 83040 | S | No | Post | No | N/A | 2016-02-04 | 2016-02-14 | 2016-02-15 | 2016-02-19
513 | PYDB | P.1 | 2016 | 3 | PYDB/2016/NCS-TR/P.1/S/3 | Ministerial upper management workshop 1 (Oganization of a Coordination Meeting for Secretary-Generals of Public Hospitals Institution of Turkey) | NCS-TR | NCS-TR | 1 | 92999.9952 | 83035.71 | 93000 | 83040 | S | No | Post | No | N/A | 2016-02-04 | 2016-02-14 | 2016-02-15 | 2016-02-19
514 | PYDB | P.1 | 2016 | 4 | PYDB/2016/NCS-TR/P.1/S/4 | Foreign Language Training Organization 2 | NCS-TR | NCS-TR | 1 | 35000 | 31250 | 35000 | 31250 | S | No | Post | No | N/A | 2016-03-01 | 2016-03-01 | 2016-04-01 | 2016-04-01
515 | PYDB | P.1 | 2016 | 5 | PYDB/2016/NCS-TR/P.1/S/5 | Organization of Trainings for strengthening Program and Project Management 3 | NCS-TR | NCS-TR | 1 | 50000.0032 | 44642.86 | 50000 | 44650 | S | No | Post | No | N/A | 2016-03-01 | 2016-03-01 | 2016-04-01 | 2016-04-01
516 | PYDB | P.1 | 2016 | 6 | PYDB/2016/NCS-TR/P.1/S/6 | PMSU Program Evaluation Workshop 3 | NCS-TR | NCS-TR | 1 | 25000.0016 | 22321.43 | 25000 | 22330 | S | No | Post | No | N/A | 2016-06-01 | 2016-06-01 | 2016-07-01 | 2016-07-01
517 | PYDB | P.1 | 2016 | 7 | PYDB/2016/NCS-TR/P.1/S/7 | Ministerial upper management workshop 2 | NCS-TR | NCS-TR | 1 | 19999.9968 | 17857.14 | 20000 | 17860 | S | No | Post | No | N/A | 2016-06-01 | 2016-06-01 | 2016-07-01 | 2016-07-01
518 | PYDB | P.1 | 2016 | 8 | PYDB/2016/NCS-TR/P.1/S/8 | Foreign Language Training Organization 3 | NCS-TR | NCS-TR | 1 | 35000 | 31250 | 35000 | 31250 | S | No | Post | No | N/A | 2016-06-01 | 2016-06-01 | 2016-07-01 | 2016-07-01
519 | PYDB | P.1 | 2015 | 2 | PYDB/2015/NCS-TR/P.1/S/2 | PMSU Program Evaluation Workshop 1 | NCS-TR | NCS-TR | 1 | 25000.0016 | 22321.43 | 25000 | 22330 | S | No | Post | No | N/A | 2015-12-01 | 2015-12-01 | 2016-01-01 | 2016-01-01
520 | PYDB | P.1 | 2016 | 9 | PYDB/2016/NCS-TR/P.1/S/9 | PMSU Program Evaluation Workshop 4 | NCS-TR | NCS-TR | 1 | 25000.0016 | 22321.43 | 25000 | 22330 | S | No | Post | No | N/A | 2016-09-01 | 2016-09-01 | 2016-10-01 | 2016-10-01
521 | PYDB | P.1 | 2016 | 10 | PYDB/2016/NCS-TR/P.1/S/10 | Provincial Evaluation Meeting Oganization of Evaluation and Coordination Meeting for Provincial Health Directors | NCS-TR | NCS-TR | 1 | 66999.9904 | 59821.42 | 67000 | 59830 | S | No | Post | No | N/A | 2016-02-04 | 2016-02-14 | 2016-02-15 | 2016-02-19
522 | PYDB | P.1 | 2016 | 11 | PYDB/2016/NCS-TR/P.1/S/11 | Ministerial upper management workshop 3 | NCS-TR | NCS-TR | 1 | 19999.9968 | 17857.14 | 20000 | 17860 | S | No | Post | No | N/A | 2016-09-01 | 2016-09-01 | 2016-10-01 | 2016-10-01
523 | PYDB | P.1 | 2015 | 3 | PYDB/2015/NCS-TR/P.1/S/3 | Foreign Language Training Organization 1 | NCS-TR | NCS-TR | 1 | 35000 | 31250 | 35000 | 31250 | S | No | Post | No | N/A | 2015-12-01 | 2015-12-01 | 2016-01-01 | 2016-01-01
524 | PYDB | P.1 | 2015 | 4 | PYDB/2015/NCS-TR/P.1/S/4 | Organization of Trainings for strengthening Program and Project Managementr 2 | NCS-TR | NCS-TR | 1 | 50000.0032 | 44642.86 | 50000 | 44650 | S | No | Post | No | N/A | 2015-12-01 | 2015-12-01 | 2016-01-01 | 2016-01-01
525 | PYDB | P.1 | 2016 | 12 | PYDB/2016/NCS-TR/P.1/S/12 | Foreign Language Training Organization 4 | NCS-TR | NCS-TR | 1 | 35000 | 31250 | 35000 | 31250 | S | No | Post | No | N/A | 2016-09-01 | 2016-09-01 | 2016-10-01 | 2016-10-01
526 | SHGM | A.3.1.6.1 | 2016 | 1 | SHGM/2016/NCS-TR/A.3.1.6.1/N/A/1 | International Study Tours | NCS-TR | NCS-TR | N/A | 74998.56 | 66963 | 75000 | 66970 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2016-05-01 | 2017-03-01
527 | SHGM | A.3.1.5.3 | 2017 | 1 | SHGM/2017/NCS-TR/A.3.1.5.3/S/1 | Organization of Training Activities | NCS-TR | NCS-TR | 1 | 28000 | 25000 | 28000 | 25000 | S | No | Post | No | N/A | 2017-01-30 | 2017-01-30 | 2017-03-01 | 2017-03-01
528 | TKHK | N.3.1.1.1 | 2016 | 1 | TKHK/2016/NCS-TR/N.3.1.1.1/S /1 | National and International Organisation, Transportation and Accommodation Services for New Health Management Models | NCS-TR | NCS-TR | 1 | 46249.9968 | 41294.64 | 46250 | 41300 | S | No | Post | No | N/A | 2016-08-02 | 2016-08-02 | 2016-09-01 | 2016-12-01
529 | TKHK | N.3.1.1.1 | 2015 | 1 | TKHK/2015/NCS-TR/N.3.1.1.1/S /1 | Foreign Language Training | NCS-TR | NCS-TR | 1 | 40000.0048 | 35714.29 | 40000 | 35720 | S | No | Post | No | N/A | 2015-12-02 | 2015-12-02 | 2016-01-01 | 2016-12-01
530 | TKHK | N.3.1.1.1 | 2016 | 2 | TKHK/2016/NCS-TR/N.3.1.1.1/S /2 | Organization of Training on Health Facilities Accreditation Training for New Health Management Models | NCS-TR | NCS-TR | 1 | 50000.0032 | 44642.86 | 50000 | 44650 | S | No | Post | No | N/A | 2016-07-02 | 2016-07-02 | 2016-08-01 | 2016-12-01
531 | TKHK | N.3.1.1.1 | 2015 | 2 | TKHK/2015/NCS-TR/N.3.1.1.1/S /2 | Training on Ms Office Applications | NCS-TR | NCS-TR | 1 | 16499.9968 | 14732.14 | 16500 | 14740 | S | No | Post | No | N/A | 2015-12-02 | 2015-12-02 | 2016-01-01 | 2016-12-01
532 | TKHK | N.3.1.2 | 2016 | 1 | TKHK/2016/NCS-TR/N.3.1.2/S /1 | Organisation of Training on Development of Classification Activities | NCS-TR | NCS-TR | 1 | 29999.9952 | 26785.71 | 30000 | 26790 | S | No | Post | No | N/A | 2016-05-02 | 2016-05-02 | 2016-06-01 | 2016-12-01
533 | TKHK | N.3.1.3.1 | 2016 | 1 | TKHK/2016/NCS-TR/N.3.1.3.1/S /1 | Organization of Training on Biomedical Technical Services Applications | NCS-TR | NCS-TR | 1 | 34090.9072 | 30438.31 | 34100 | 30440 | S | No | Post | No | N/A | 2016-01-31 | 2016-01-31 | 2016-03-01 | 2016-12-01
534 | TKHK | N.3.1.3.1 | 2017 | 1 | TKHK/2017/NCS-TR/N.3.1.3.1/S /1 | Organization of Training on Health Facilities Design and Architecture Standards | NCS-TR | NCS-TR | 1 | 61586.896 | 54988.3 | 61590 | 54990 | S | No | Post | No | N/A | 2017-01-30 | 2017-01-30 | 2017-03-01 | 2017-03-01
535 | TKHK | N.3.1.3.1 | 2016 | 2 | TKHK/2016/NCS-TR/N.3.1.3.1/S /2 | Organization of Training on Biomedical Meteorology Applications | NCS-TR | NCS-TR | 1 | 27272.728 | 24350.65 | 27280 | 24360 | S | No | Post | No | N/A | 2016-01-31 | 2016-01-31 | 2016-03-01 | 2016-12-01
536 | TKHK | N.3.1.3.1 | 2016 | 3 | TKHK/2016/NCS-TR/N.3.1.3.1/S /3 | Organization of Training on Health Facilities Design and Architecture Standards | NCS-TR | NCS-TR | 1 | 61586.896 | 54988.3 | 61590 | 54990 | S | No | Post | No | N/A | 2016-05-02 | 2016-05-02 | 2016-06-01 | 2016-12-01
537 | TKHK | N.3.1.3.1 | 2016 | 4 | TKHK/2016/NCS-TR/N.3.1.3.1/S /4 | Organization of Training on Biomedical Technical Services Applications | NCS-TR | NCS-TR | 1 | 34090.9072 | 30438.31 | 34100 | 30440 | S | No | Post | No | N/A | 2016-11-01 | 2016-11-01 | 2016-12-01 | 2016-12-01
538 | TKHK | N.3.1.3.1 | 2016 | 5 | TKHK/2016/NCS-TR/N.3.1.3.1/S /5 | Organization of Training on Biomedical Meteorology Applications | NCS-TR | NCS-TR | 1 | 27272.728 | 24350.65 | 27280 | 24360 | S | No | Post | No | N/A | 2016-11-01 | 2016-11-01 | 2016-12-01 | 2016-12-01
539 | TKHK | N.3.1.3.1 | 2017 | 2 | TKHK/2017/NCS-TR/N.3.1.3.1/S /2 | Organization of Training on Biomedical Meteorology Applications | NCS-TR | NCS-TR | 1 | 27272.728 | 24350.65 | 27280 | 24360 | S | No | Post | No | N/A | 2017-01-30 | 2017-01-30 | 2017-03-01 | 2017-03-01
540 | TKHK | N.3.1.4.1 | 2016 | 1 | TKHK/2016/NCS-TR/N.3.1.4.1/NCB/1 | Organization for Drug Preparation and Applications | NCS-TR | NCS-TR | 1 | 128571.4304 | 114795.92 | 128580 | 114800 | NCB | No | Prior | No | N/A | 2016-01-01 | 2016-01-01 | 2016-03-01 | 2016-03-31
541 | TKHK | N.3.1.4.1 | 2016 | 2 | TKHK/2016/NCS-TR/N.3.1.4.1/NCB/2 | Organization for Drug Preparation and Applications | NCS-TR | NCS-TR | 1 | 128571.4304 | 114795.92 | 128580 | 114800 | NCB | No | Post | No | N/A | 2016-07-03 | 2016-07-03 | 2016-09-01 | 2016-10-01
542 | TKHK | N.3.1.4.1 | 2016 | 3 | TKHK/2016/NCS-TR/N.3.1.4.1/NCB/3 | Organization for Drug Preparation and Applications | NCS-TR | NCS-TR | 1 | 128571.4304 | 114795.92 | 128580 | 114800 | NCB | No | Post | No | N/A | 2016-12-31 | 2016-12-31 | 2017-03-01 | 2017-03-31
543 | TKHK | N.3.1.5.1 | 2016 | 1 | TKHK/2016/NCS-TR/N.3.1.5.1/S/1 | Organization for Training on Needs Management | NCS-TR | NCS-TR | 1 | 42000 | 37500 | 42000 | 37500 | S | No | Post | No | N/A | 2016-04-02 | 2016-04-02 | 2016-06-01 | 2016-07-01
544 | TKHK | N.3.1.8 | 2016 | 1 | TKHK/2016/NCS-TR/N.3.1.8/S/1 | Organization for Enhancing Expertise in and Obtaining Information on International Productvity and Quality | NCS-TR | NCS-TR | 1 | 42000 | 37500 | 42000 | 37500 | S | No | Post | No | N/A | 2016-05-02 | 2016-06-16 | 2016-06-01 | 2016-07-01
545 | TKHK | N.3.1.8 | 2016 | 2 | TKHK/2016/NCS-TR/N.3.1.8/NCB/2 | Organization for Training on Productvity and Quality in Hospital Management | NCS-TR | NCS-TR | 1 | 299999.9968 | 267857.14 | 300000 | 267860 | NCB | No | Post | No | N/A | 2016-04-02 | 2016-05-17 | 2016-06-01 | 2016-07-01
546 | TKHK | N.3.1.9.1 | 2016 | 1 | TKHK/2016/NCS-TR/N.3.1.9.1/S/1 | Organization for Enhancing Expertise in and Obtaining Information on Healthcare Services | NCS-TR | NCS-TR | 1 | 42000 | 37500 | 42000 | 37500 | S | No | Post | No | N/A | 2016-05-02 | 2016-06-16 | 2016-06-01 | 2016-07-01
547 | SYGM | F.3.1.2.3 | 2016 | 1 | SYGM/2016/NCS-TR/F.3.1.2.3/S /1 | Organization of Training on PPP Procurement Regulations | NCS-TR | NCS-TR | 1 | 19999.84 | 17857 | 20000 | 17860 | S | No | Post | No | N/A | 2016-10-02 | 2016-10-02 | 2016-11-01 | 2016-09-01
548 | SYGM | F.3.1.3.1 | 2015 | 1 | SYGM/2015/NCS-TR/F.3.1.3.1/S /1 | Organization of Training on PPP Certification Program | NCS-TR | NCS-TR | 1 | 99904 | 89200 | 99900 | 89200 | S | No | Post | No | N/A | 2015-10-02 | 2015-10-02 | 2015-11-01 | 2016-09-01
549 | SAGEM | E.5.1.1.1 | 2015 | 6 | SAGEM/2015/NCS-TR/E.5.1.1.1/S/6 | Organization of Evidence-based Healthcare Policy Development Training | NCS-TR | NCS-TR | 1 | 19999.84 | 17857 | 20000 | 17860 | S | No | Post | No | N/A | 2015-12-04 | 2015-12-04 | 2016-01-01 | 2016-01-01
550 | SAGEM | E.5.1.1.1 | 2015 | 1 | SAGEM/2015/NCS-TR/E.5.1.1.1/N/A/1 | Participation in National and International Seminars/Symposiums etc. Related with Health Reseraches | NCS-TR | NCS-TR | N/A | 52000.1552 | 46428.71 | 52000 | 46430 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2016-09-01 | 2017-03-01
551 | SYGM | F.1.2.2.2 | 2016 | 1 | SYGM/2016/NCS-TR/F.1.2.2.2/N/A/1 | Study tours on PPP related purposes | NCS-TR | NCS-TR | N/A | 60000.64 | 53572 | 60000 | 53580 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2016-09-01 | 2017-01-01
552 | SYGM | F.1.2.2.3 | 2017 | 1 | SYGM/2017/NCS-TR/F.1.2.2.3/S/1 | Workshop on Standards Indentification | NCS-TR | NCS-TR | 1 | 19999.84 | 17857 | 20000 | 17860 | S | No | Post | No | N/A | 2017-06-01 | 2017-06-01 | 2017-07-01 | 2017-08-15
553 | SYGM | F.2.1.2.2 | 2016 | 1 | SYGM/2016/NCS-TR/F.2.1.2.2/N/A/1 | Study tours on PPP related purposes | NCS-TR | NCS-TR | N/A | 150000.48 | 133929 | 150000 | 133930 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2016-07-01 | 2017-03-01
554 | THSK | L.2.1.2.1 | 2016 | 1 | THSK/2016/NCS-TR/L.2.1.2.1/S/1 | Workshop on preparing training materials for all health professionals | NCS-TR | NCS-TR | 1 | 22512 | 20100 | 22520 | 20100 | S | No | Post | No | N/A | 2016-06-01 | 2016-06-01 | 2016-07-01 | 2016-07-01
555 | THSK | L.2.1.2.2 | 2016 | 1 | THSK/2016/NCS-TR/L.2.1.2.2/S/1 | Meeting on preparing the content of Distance Training Module for Family Physicians | NCS-TR | NCS-TR | 1 | 30004.8 | 26790 | 30000 | 26790 | S | No | Post | No | N/A | 2016-09-01 | 2016-09-01 | 2016-10-01 | 2016-10-01
556 | THSK | L.2.2.2.1 | 2016 | 1 | THSK/2016/NCS-TR/L.2.2.2.1/S/1 | Workshop on Data Collection Training | NCS-TR | NCS-TR | 1 | 37497.6 | 33480 | 37500 | 33480 | S | No | Post | No | N/A | 2016-04-01 | 2016-04-01 | 2016-05-01 | 2016-05-01
557 | THSK | L.2.3.2.1 | 2015 | 1 | THSK/2015/NCS-TR/L.2.3.2.1/S/1 | Workshop on Preparing Training and Information Materials for the Community | NCS-TR | NCS-TR | 1 | 13048 | 11650 | 13050 | 11650 | S | No | Prior | No | N/A | 2015-10-15 | 2015-10-22 | 2015-11-01 | 2015-11-01
558 | THSK | L.2.3.2.1 | 2015 | 2 | THSK/2015/NCS-TR/L.2.3.2.1/S/2 | Workshop on Preparing Training and Information Materials for Healthcare Professionals | NCS-TR | NCS-TR | 1 | 13048 | 11650 | 13050 | 11650 | S | No | Post | No | N/A | 2015-10-15 | 2015-10-22 | 2015-11-01 | 2015-11-01
559 | THSK | L.2.3.2.1 | 2015 | 3 | THSK/2015/NCS-TR/L.2.3.2.1/S/3 | Workshop on Preparing Training and Information Materials for the Disabled and the Elderly | NCS-TR | NCS-TR | 1 | 13048 | 11650 | 13050 | 11650 | S | No | Post | No | N/A | 2015-10-15 | 2015-10-22 | 2015-11-01 | 2015-11-01
560 | THSK | L.2.3.2.1 | 2016 | 1 | THSK/2016/NCS-TR/L.2.3.2.1/S/1 | Organization of Trainers' training for healthcare professionals - 3 rounds | NCS-TR | NCS-TR | 1 | 74928 | 66900 | 74930 | 66900 | S | No | Post | No | N/A | 2016-06-01 | 2016-06-01 | 2016-07-01 | 2016-12-30
561 | THSK | L.2.3.2.1 | 2017 | 1 | THSK/2017/NCS-TR/L.2.3.2.1/S/1 | Organization of Trainers' training for healthcare professionals | NCS-TR | NCS-TR | 1 | 24976 | 22300 | 24980 | 22300 | S | No | Post | No | N/A | 2017-01-02 | 2017-01-02 | 2017-02-01 | 2017-02-01
562 | THSK | L.2.3.2.2 | 2016 | 1 | THSK/2016/NCS-TR/L.2.3.2.2/S/1 | Preliminary workshop on detecting medical elderly care | NCS-TR | NCS-TR | 1 | 20048 | 17900 | 20050 | 17900 | S | No | Post | No | N/A | 2016-01-10 | 2016-01-17 | 2016-01-24 | 2016-02-15
563 | THSK | L.2.3.2.2 | 2016 | 2 | THSK/2016/NCS-TR/L.2.3.2.2/S/2 | Organization of Standardization training of field research 1 | NCS-TR | NCS-TR | 1 | 50120 | 44750 | 50120 | 44750 | S | No | Post | No | N/A | 2016-08-20 | 2016-08-28 | 2016-09-03 | 2016-10-05
564 | THSK | L.2.3.2.2 | 2016 | 3 | THSK/2016/NCS-TR/L.2.3.2.2/S/3 | Organization of Standardization training of field research 2 | NCS-TR | NCS-TR | 1 | 50120 | 44750 | 50120 | 44750 | S | No | Post | No | N/A | 2016-09-12 | 2016-09-20 | 2016-10-01 | 2016-10-12
565 | THSK | L.2.4.4.3 | 2016 | 1 | THSK/2016/NCS-TR/L.2.4.4.3/S/1 | Organization of Palliative care training - 1st, 2nd and 3rd rounds | NCS-TR | NCS-TR | 1 | 89999.84 | 80357 | 90000 | 80360 | S | No | Post | No | N/A | 2016-01-15 | 2016-01-23 | 2016-02-01 | 2016-03-01
566 | THSK | L.2.4.4.3 | 2016 | 2 | THSK/2016/NCS-TR/L.2.4.4.3/S/2 | Organization of Palliative care training - 4th, 5th and 6th rounds | NCS-TR | NCS-TR | 1 | 90000.96 | 80358 | 90000 | 80360 | S | No | Post | No | N/A | 2016-03-01 | 2016-03-08 | 2016-04-01 | 2016-09-01
567 | THSK | L.2.4.4.3 | 2016 | 3 | THSK/2016/NCS-TR/L.2.4.4.3/S/3 | Organization of Palliative care training - 7th and 8th rounds | NCS-TR | NCS-TR | 1 | 60000.64 | 53572 | 60000 | 53580 | S | No | Post | No | N/A | 2016-09-01 | 2016-09-08 | 2016-10-01 | 2016-11-01
568 | THSK | L.2.4.4.3 | 2016 | 4 | THSK/2016/NCS-TR/L.2.4.4.3/S/4 | Organization of Palliative care training (2 rounds) 9-10 | NCS-TR | NCS-TR | 1 | 59999.52 | 53571 | 60000 | 53580 | S | No | Post | No | N/A | 2016-10-01 | 2016-10-08 | 2016-11-01 | 2016-11-01
569 | THSK | L.2.4.4.3 | 2017 | 1 | THSK/2017/NCS-TR/L.2.4.4.3/S/1 | Organization of Palliative care training - 1st, 2nd and 3rd rounds | NCS-TR | NCS-TR | 1 | 89999.84 | 80357 | 90000 | 80360 | S | No | Post | No | N/A | 2017-01-15 | 2017-01-23 | 2017-02-01 | 2017-03-01
570 | THSK | L.2.4.5.2 | 2016 | 1 | THSK/2016/NCS-TR/L.2.4.5.2/S/1 | Evaluation workshop | NCS-TR | NCS-TR | 1 | 37499.84 | 33482 | 37500 | 33490 | S | No | Post | No | N/A | 2016-11-01 | 2016-11-08 | 2016-12-01 | 2016-12-01
571 | THSK | L.2.5.3.4 | 2016 | 1 | THSK/2016/NCS-TR/L.2.5.3.4/S/1 | Organization of Post-Screening Diagnosis Training - 1st, 2nd and 3rd rounds | NCS-TR | NCS-TR | 1 | 89999.84 | 80357 | 90000 | 80360 | S | No | Post | No | N/A | 2016-01-15 | 2016-01-22 | 2016-02-01 | 2016-03-01
572 | THSK | L.2.5.3.4 | 2016 | 2 | THSK/2016/NCS-TR/L.2.5.3.4/S/2 | Organization of Post-Screening Diagnosis Training - 4th, 5th and 6th rounds | NCS-TR | NCS-TR | 1 | 90000.96 | 80358 | 90000 | 80360 | S | No | Post | No | N/A | 2016-03-01 | 2016-03-08 | 2016-04-01 | 2016-06-01
573 | THSK | L.2.5.3.4 | 2016 | 3 | THSK/2016/NCS-TR/L.2.5.3.4/S/3 | Organization of Post-Screening Diagnosis Training - 7th and 8th rounds | NCS-TR | NCS-TR | 1 | 60000.64 | 53572 | 60000 | 53580 | S | No | Post | No | N/A | 2016-08-01 | 2016-08-08 | 2016-09-01 | 2016-09-01
574 | THSK | L.2.5.3.4 | 2016 | 4 | THSK/2016/NCS-TR/L.2.5.3.4/S/4 | Organization of Post-Screening Diagnosis Training (2 rounds) 9-10 | NCS-TR | NCS-TR | 1 | 59999.52 | 53571 | 60000 | 53580 | S | No | Post | No | N/A | 2016-10-01 | 2016-10-08 | 2016-11-01 | 2016-11-01
575 | THSK | L.2.5.3.4 | 2017 | 1 | THSK/2017/NCS-TR/L.2.5.3.4/S/1 | Organization of Post-Screening Diagnosis Training - 1st, 2nd and 3rd rounds | NCS-TR | NCS-TR | 1 | 89999.84 | 80357 | 90000 | 80360 | S | No | Post | No | N/A | 2017-01-15 | 2017-01-22 | 2017-02-01 | 2017-03-01
576 | THSK | L.2.5.4.2 | 2016 | 1 | THSK/2016/NCS-TR/L.2.5.4.2/S/1 | Awareness Activity Organization | NCS-TR | NCS-TR | 1 | 70000 | 62500 | 70000 | 62500 | S | No | Post | No | N/A | 2016-02-01 | 2016-02-08 | 2016-03-01 | 2016-04-01
577 | THSK | L.2.5.4.2 | 2016 | 2 | THSK/2016/NCS-TR/L.2.5.4.2/S/2 | Awareness Activity Organization | NCS-TR | NCS-TR | 1 | 70000 | 62500 | 70000 | 62500 | S | No | Post | No | N/A | 2016-04-01 | 2016-04-08 | 2016-05-01 | 2016-10-01
578 | THSK | L.2.5.4.2 | 2016 | 3 | THSK/2016/NCS-TR/L.2.5.4.2/S/3 | Awareness Activity Organization | NCS-TR | NCS-TR | 1 | 35000 | 31250 | 35000 | 31250 | S | No | Post | No | N/A | 2016-10-01 | 2016-10-08 | 2016-11-01 | 2016-11-01
579 | THSK | L.2.5.4.2 | 2017 | 1 | THSK/2017/NCS-TR/L.2.5.4.2/S/1 | Awareness Activity Organization | NCS-TR | NCS-TR | 1 | 35000 | 31250 | 35000 | 31250 | S | No | Post | No | N/A | 2017-01-15 | 2017-01-22 | 2017-02-01 | 2017-02-01
580 | THSK | L.2.6.3.1 | 2016 | 1 | THSK/2016/NCS-TR/L.2.6.3.1/S/1 | Organization of Cancer Registry Training 1,2 | NCS-TR | NCS-TR | 1 | 70000 | 62500 | 70000 | 62500 | S | No | Post | No | N/A | 2016-01-22 | 2016-02-01 | 2016-03-01 | 2016-02-01
581 | THSK | L.2.6.3.1 | 2016 | 2 | THSK/2016/NCS-TR/L.2.6.3.1/S/2 | Organization of Cancer Registry Training 3,4 | NCS-TR | NCS-TR | 1 | 70000 | 62500 | 70000 | 62500 | S | No | Post | No | N/A | 2016-03-08 | 2016-04-01 | 2016-05-01 | 2016-03-01
582 | THSK | L.2.6.3.1 | 2016 | 3 | THSK/2016/NCS-TR/L.2.6.3.1/S/3 | Organization of Cancer Registry Training 5,6 | NCS-TR | NCS-TR | 1 | 70000 | 62500 | 70000 | 62500 | S | No | Post | No | N/A | 2016-06-08 | 2016-07-01 | 2016-08-01 | 2016-04-01
583 | THSK | L.2.6.3.1 | 2016 | 4 | THSK/2016/NCS-TR/L.2.6.3.1/S/4 | Organization of Cancer Registry Training 7 | NCS-TR | NCS-TR | 1 | 35000 | 31250 | 35000 | 31250 | S | No | Post | No | N/A | 2016-08-08 | 2016-09-01 | 2016-09-01 | 2016-05-01
584 | THSK | L.2.6.3.1 | 2016 | 1 | THSK/2016/NCS-TR/L.2.6.3.1/S/1 | Organization of Cancer Registry Training 1,2 | NCS-TR | NCS-TR | 1 | 70000 | 62500 | 70000 | 62500 | S | No | Post | No | N/A | 2016-01-22 | 2017-02-01 | 2017-03-01 | 2017-02-01
585 | THSK | L.2.6.4.1 | 2016 | 1 | THSK/2016/NCS-TR/L.2.6.4.1/S/1 | Workshop on Data Analysis and Quality Control - 1, 2 | NCS-TR | NCS-TR | 1 | 22629.6 | 20205 | 22630 | 20210 | S | No | Post | No | N/A | 2016-02-01 | 2016-02-08 | 2016-03-01 | 2016-11-01
586 | THSK | L.2.6.4.1 | 2017 | 1 | THSK/2017/NCS-TR/L.2.6.4.1/S/1 | Workshop on Data Analysis and Quality Control -1 | NCS-TR | NCS-TR | 1 | 33000.8 | 29465 | 33000 | 29470 | S | No | Post | No | N/A | 2017-01-05 | 2017-01-12 | 2017-02-01 | 2017-02-01
587 | THSK | L.2.7.1.1 | 2015 | 1 | THSK/2015/NCS-TR/L.2.7.1.1/S/1 | Meeting on determining and reporting the current situation in tobacco control | NCS-TR | NCS-TR | 1 | 56249.76 | 50223 | 56250 | 50230 | S | No | Post | No | N/A | 2015-10-10 | 2015-10-22 | 2015-11-01 | 2015-11-01
588 | THSK | L.2.7.1.1 | 2016 | 1 | THSK/2016/NCS-TR/L.2.7.1.1/S/1 | Meeting on determining and reporting the current situation in tobacco control | NCS-TR | NCS-TR | 1 | 56249.76 | 50223 | 56250 | 50230 | S | No | Post | No | N/A | 2016-10-01 | 2016-10-08 | 2016-11-01 | 2016-11-01
589 | THSK | L.2.7.1.2 | 2015 | 1 | THSK/2015/NCS-TR/L.2.7.1.2/S/1 | Meeting on determining and reporting the current situation in tobacco control | NCS-TR | NCS-TR | 1 | 37499.84 | 33482 | 37500 | 33490 | S | No | Post | No | N/A | 2015-11-01 | 2015-11-08 | 2015-12-01 | 2015-12-01
590 | THSK | L.2.7.2.1 | 2016 | 1 | THSK/2016/NCS-TR/L.2.7.2.1/S/1 | Workshop on preparing training modules and guidelines 1 (within the scope of tobacco control activities) | NCS-TR | NCS-TR | 1 | 56249.76 | 50223 | 56250 | 50230 | S | No | Post | No | N/A | 2016-03-01 | 2016-03-08 | 2016-04-01 | 2016-04-01
591 | THSK | L.2.7.2.1 | 2016 | 2 | THSK/2016/NCS-TR/L.2.7.2.1/S/2 | Workshop on preparing training modules and guidelines 2 (within the scope of tobacco control activities) | NCS-TR | NCS-TR | 1 | 56249.76 | 50223 | 56250 | 50230 | S | No | Post | No | N/A | 2016-06-01 | 2016-06-08 | 2016-07-01 | 2016-07-01
592 | THSK | L.2.7.2.3 | 2016 | 1 | THSK/2016/NCS-TR/L.2.7.2.3/S/1 | Workshop on preparing training modules and guidelines (within the scope of tobacco control activities) | NCS-TR | NCS-TR | 1 | 37499.84 | 33482 | 37500 | 33490 | S | No | Post | No | N/A | 2016-05-01 | 2016-05-08 | 2016-06-01 | 2016-06-01
593 | THSK | L.2.7.3.1 | 2016 | 1 | THSK/2016/NCS-TR/L.2.7.3.1/S/1 | Workshop on preparing training modules and guidelines 1 (within the scope of tobacco control activities) | NCS-TR | NCS-TR | 1 | 56249.76 | 50223 | 56250 | 50230 | S | No | Post | No | N/A | 2016-02-01 | 2016-02-08 | 2016-03-01 | 2016-03-01
594 | THSK | L.2.7.3.1 | 2016 | 2 | THSK/2016/NCS-TR/L.2.7.3.1/S/2 | Workshop on preparing training modules and guidelines 2 (within the scope of tobacco control activities) | NCS-TR | NCS-TR | 1 | 56249.76 | 50223 | 56250 | 50230 | S | No | Post | No | N/A | 2016-09-01 | 2016-09-08 | 2016-10-01 | 2016-10-01
595 | THSK | L.2.7.3.1 | 2017 | 1 | THSK/2017/NCS-TR/L.2.7.3.1/S/1 | Workshop on preparing training modules and guidelines (within the scope of tobacco control activities) | NCS-TR | NCS-TR | 1 | 56249.76 | 50223 | 56250 | 50230 | S | No | Post | No | N/A | 2017-02-01 | 2017-02-08 | 2017-03-01 | 2017-03-01
596 | THSK | L.2.7.4.2 | 2016 | 1 | THSK/2016/NCS-TR/L.2.7.4.2/S/1 | Meeting for providing active participation of NGOs and media in the process | NCS-TR | NCS-TR | 1 | 37499.84 | 33482 | 37500 | 33490 | S | No | Post | No | N/A | 2016-05-01 | 2016-05-08 | 2016-06-01 | 2016-06-01
597 | THSK | L.2.7.4.3 | 2016 | 1 | THSK/2016/NCS-TR/L.2.7.4.3/S/1 | Meeting for establishing advocacy groups in social media and target population | NCS-TR | NCS-TR | 1 | 37500.96 | 33483 | 37500 | 33490 | S | No | Post | No | N/A | 2016-10-01 | 2016-10-08 | 2016-11-01 | 2016-11-01
598 | THSK | L.2.11.1.1 | 2015 | 1 | THSK/2015/NCS-TR/L.2.11.1.1/S/1 | Organization of Trainers' Trainings on Counteracting Diabetes in Primary Healthcare Facilities | NCS-TR | NCS-TR | 1 | 31250.24 | 27902 | 31250 | 27910 | S | No | Post | No | N/A | 2015-10-02 | 2015-10-02 | 2015-11-01 | 2015-11-01
599 | THSK | L.2.11.1.1 | 2015 | 2 | THSK/2015/NCS-TR/L.2.11.1.1/S/2 | Organization of Training of Trainers in Combat Against Diabet at Secondary Healthcare Facilities | NCS-TR | NCS-TR | 1 | 31250.24 | 27902 | 31250 | 27910 | S | No | Post | No | N/A | 2015-10-02 | 2015-10-02 | 2015-11-01 | 2015-11-01
600 | THSK | L.2.11.1.1 | 2015 | 3 | THSK/2015/NCS-TR/L.2.11.1.1/S/3 | Provincial Evaluation Meetings on Counteracting Diabetes | NCS-TR | NCS-TR | 1 | 18124.96 | 16183 | 18125 | 16190 | S | No | Post | No | N/A | 2015-11-01 | 2015-11-01 | 2015-12-01 | 2015-12-01
601 | THSK | L.2.11.1.1 | 2016 | 1 | THSK/2016/NCS-TR/L.2.11.1.1/S/1 | Organization of Trainers' Trainings on Counteracting Diabetes in Primary Healthcare Facilities 1 | NCS-TR | NCS-TR | 1 | 31250.24 | 27902 | 31250 | 27910 | S | No | Post | No | N/A | 2016-02-01 | 2016-02-08 | 2016-03-01 | 2016-03-01
602 | THSK | L.2.11.1.1 | 2016 | 2 | THSK/2016/NCS-TR/L.2.11.1.1/S/2 | Organization of Trainers' Trainings on Counteracting Diabetes in Primary Healthcare Facilities 2 | NCS-TR | NCS-TR | 1 | 31250.24 | 27902 | 31250 | 27910 | S | No | Post | No | N/A | 2016-08-01 | 2016-08-08 | 2016-09-01 | 2016-09-01
603 | THSK | L.2.11.1.1 | 2016 | 3 | THSK/2016/NCS-TR/L.2.11.1.1/S/3 | Organization of Trainers' Trainings on Counteracting Diabetes in Secondary Healthcare Facilities 1 | NCS-TR | NCS-TR | 1 | 31250.24 | 27902 | 31250 | 27910 | S | No | Post | No | N/A | 2016-03-01 | 2016-03-08 | 2016-04-01 | 2016-04-01
604 | THSK | L.2.11.1.1 | 2016 | 4 | THSK/2016/NCS-TR/L.2.11.1.1/S/4 | Organization of Trainers' Trainings on Counteracting Diabetes in Secondary Healthcare Facilities 2 | NCS-TR | NCS-TR | 1 | 31250.24 | 27902 | 31250 | 27910 | S | No | Post | No | N/A | 2016-09-01 | 2016-09-08 | 2016-10-01 | 2016-10-01
605 | THSK | L.2.11.1.1 | 2016 | 5 | THSK/2016/NCS-TR/L.2.11.1.1/S/5 | Organization of Trainings on Diabetes Type-1 | NCS-TR | NCS-TR | 1 | 74999.68 | 66964 | 75000 | 66970 | S | No | Post | No | N/A | 2016-05-01 | 2016-05-08 | 2016-06-01 | 2016-06-01
606 | THSK | L.2.11.1.1 | 2016 | 6 | THSK/2016/NCS-TR/L.2.11.1.1/S/6 | Organization of 14th of November Diabetes Day Meeting | NCS-TR | NCS-TR | 1 | 19999.84 | 17857 | 20000 | 17860 | S | No | Post | No | N/A | 2016-10-01 | 2016-10-08 | 2016-11-01 | 2016-11-01
607 | THSK | L.2.11.1.1 | 2016 | 7 | THSK/2016/NCS-TR/L.2.11.1.1/S/7 | Provincial Evaluation Meetings on Counteracting Diabetes | NCS-TR | NCS-TR | 1 | 18124.96 | 16183 | 18125 | 16190 | S | No | Post | No | N/A | 2016-10-01 | 2016-10-08 | 2016-11-01 | 2016-11-01
608 | THSK | L.2.11.1.1 | 2016 | 8 | THSK/2016/NCS-TR/L.2.11.1.1/S/8 | Workshop on Evaluating Screening Programs in Primary Healthcare Facilities | NCS-TR | NCS-TR | 1 | 24999.52 | 22321 | 25000 | 22330 | S | No | Post | No | N/A | 2016-04-01 | 2016-04-01 | 2016-05-01 | 2016-05-01
609 | THSK | L.2.11.1.1 | 2016 | 9 | THSK/2016/NCS-TR/L.2.11.1.1/S/9 | Workshop on Updating Materials within the scope of the Diabetes Program for Schools | NCS-TR | NCS-TR | 1 | 24999.52 | 22321 | 25000 | 22330 | S | No | Post | No | N/A | 2016-04-01 | 2016-04-01 | 2016-05-01 | 2016-05-01
610 | THSK | L.2.11.1.1 | 2017 | 1 | THSK/2017/NCS-TR/L.2.11.1.1/S/1 | Inter-sectoral Cooperation Workshop for HbA1c and Glucometer Standardization | NCS-TR | NCS-TR | 1 | 24999.52 | 22321 | 25000 | 22330 | S | No | Post | No | N/A | 2017-01-05 | 2017-01-12 | 2017-01-01 | 2017-01-01
611 | THSK | L.2.11.1.1 | 2016 | 2 | THSK/2016/NCS-TR/L.2.11.1.1/S/2 | Organization of Trainers' Trainings on Counteracting Diabetes in Primary Healthcare Facilities | NCS-TR | NCS-TR | 1 | 31250.24 | 27902 | 31250 | 27910 | S | No | Post | No | N/A | 2016-02-01 | 2016-08-08 | 2017-03-01 | 2017-03-01
612 | THSK | L.2.11.2.1 | 2017 | 1 | THSK/2017/NCS-TR/L.2.11.2.1/S/1 | Organization of Training of research teams | NCS-TR | NCS-TR | 1 | 39999.68 | 35714 | 40000 | 35720 | S | No | Post | No | N/A | 2017-01-05 | 2017-01-12 | 2017-01-17 | 2017-03-01
613 | THSK | L.2.12.1.1 | 2015 | 1 | THSK/2015/NCS-TR/L.2.12.1.1/S/1 | Organization of Trainers' Trainings on Healthy Nutrition and Physical Activity | NCS-TR | NCS-TR | 1 | 33744.48 | 30129 | 33745 | 30130 | S | No | Post | No | N/A | 2015-10-05 | 2015-10-12 | 2015-11-01 | 2015-11-01
614 | THSK | L.2.12.1.1 | 2015 | 2 | THSK/2015/NCS-TR/L.2.12.1.1/S/2 | Provincial Evaluation Meetings on Counteracting Obesity | NCS-TR | NCS-TR | 1 | 30000.32 | 26786 | 30000 | 26790 | S | No | Post | No | N/A | 2015-10-05 | 2015-10-12 | 2015-11-01 | 2015-11-01
615 | THSK | L.2.12.1.1 | 2015 | 3 | THSK/2015/NCS-TR/L.2.12.1.1/S/3 | Training Meeting for Deputy Governors | NCS-TR | NCS-TR | 1 | 50000.16 | 44643 | 50000 | 44650 | S | No | Post | No | N/A | 2015-10-05 | 2015-10-12 | 2015-11-01 | 2015-11-01
616 | THSK | L.2.12.1.1 | 2015 | 4 | THSK/2015/NCS-TR/L.2.12.1.1/S/4 | Workshop on Updating the Guidebook on Counteracting Obesity for Primary Care Physicians | NCS-TR | NCS-TR | 1 | 24999.52 | 22321 | 25000 | 22330 | S | No | Post | No | N/A | 2015-10-05 | 2015-10-12 | 2015-11-01 | 2015-11-01
617 | THSK | L.2.12.1.1 | 2015 | 5 | THSK/2015/NCS-TR/L.2.12.1.1/S/5 | Workshop on National Salt Consumption Guidelines | NCS-TR | NCS-TR | 1 | 50000.16 | 44643 | 50000 | 44650 | S | No | Post | No | N/A | 2015-10-05 | 2015-10-12 | 2015-11-01 | 2015-11-01
618 | THSK | L.2.12.1.1 | 2016 | 1 | THSK/2016/NCS-TR/L.2.12.1.1/S/1 | Organization of Trainers' Trainings on Healthy Nutrition and Physical Activity 1 | NCS-TR | NCS-TR | 1 | 33744.48 | 30129 | 33745 | 30130 | S | No | Post | No | N/A | 2016-02-01 | 2016-02-08 | 2016-03-01 | 2016-03-01
619 | THSK | L.2.12.1.1 | 2016 | 2 | THSK/2016/NCS-TR/L.2.12.1.1/S/2 | Organization of Trainers' Trainings on Healthy Nutrition and Physical Activity 2 | NCS-TR | NCS-TR | 1 | 33744.48 | 30129 | 33745 | 30130 | S | No | Post | No | N/A | 2016-09-01 | 2016-09-08 | 2016-10-01 | 2016-10-01
620 | THSK | L.2.12.1.1 | 2016 | 3 | THSK/2016/NCS-TR/L.2.12.1.1/S/3 | Organization of Nutrition Friendly School Trainings 1 | NCS-TR | NCS-TR | 1 | 37499.84 | 33482 | 37500 | 33490 | S | No | Post | No | N/A | 2016-02-01 | 2016-02-08 | 2016-03-01 | 2016-03-01
621 | THSK | L.2.12.1.1 | 2016 | 4 | THSK/2016/NCS-TR/L.2.12.1.1/S/4 | Organization of Nutrition Friendly School Trainings 2 | NCS-TR | NCS-TR | 1 | 37499.84 | 33482 | 37500 | 33490 | S | No | Post | No | N/A | 2016-08-01 | 2016-08-08 | 2016-09-01 | 2016-09-01
622 | THSK | L.2.12.1.1 | 2016 | 5 | THSK/2016/NCS-TR/L.2.12.1.1/S/5 | Provincial Evaluation Meetings on Counteracting Obesity | NCS-TR | NCS-TR | 1 | 30000.32 | 26786 | 30000 | 26790 | S | No | Post | No | N/A | 2016-10-01 | 2016-10-08 | 2016-11-01 | 2016-11-01
623 | THSK | L.2.12.1.1 | 2016 | 6 | THSK/2016/NCS-TR/L.2.12.1.1/S/6 | Inter-sectoral Cooperation Meeting | NCS-TR | NCS-TR | 1 | 12500.32 | 11161 | 12500 | 11170 | S | No | Post | No | N/A | 2016-05-01 | 2016-05-08 | 2016-06-01 | 2016-06-01
624 | THSK | L.2.12.1.1 | 2016 | 7 | THSK/2016/NCS-TR/L.2.12.1.1/S/7 | Workshop on preparing Primary Care Individual and Group Consultancy Weight Management Programs | NCS-TR | NCS-TR | 1 | 50000.16 | 44643 | 50000 | 44650 | S | No | Post | No | N/A | 2016-02-01 | 2016-02-08 | 2016-03-01 | 2016-03-01
625 | THSK | L.2.12.1.1 | 2016 | 8 | THSK/2016/NCS-TR/L.2.12.1.1/S/8 | Workshop on preparing Weight Management Programs for Children | NCS-TR | NCS-TR | 1 | 50000.16 | 44643 | 50000 | 44650 | S | No | Post | No | N/A | 2016-03-01 | 2016-03-08 | 2016-04-01 | 2016-04-01
626 | THSK | L.2.12.1.1 | 2016 | 9 | THSK/2016/NCS-TR/L.2.12.1.1/S/9 | Workshop on the Role of Social Determinants in Counteracting Obesity | NCS-TR | NCS-TR | 1 | 50000.16 | 44643 | 50000 | 44650 | S | No | Post | No | N/A | 2016-03-01 | 2016-03-08 | 2016-04-01 | 2016-04-01
627 | THSK | L.2.12.1.1 | 2017 | 1 | THSK/2017/NCS-TR/L.2.12.1.1/S/1 | Organization of Trainers' Trainings on Healthy Nutrition and Physical Activity | NCS-TR | NCS-TR | 1 | 33744.48 | 30129 | 33745 | 30130 | S | No | Post | No | N/A | 2017-02-01 | 2017-02-08 | 2017-03-01 | 2017-03-01
628 | THSK | L.2.12.1.1 | 2017 | 2 | THSK/2017/NCS-TR/L.2.12.1.1/S/2 | Organization of Nutrition Friendly School Trainings | NCS-TR | NCS-TR | 1 | 39739.84 | 35482 | 39740 | 35490 | S | No | Post | No | N/A | 2017-02-01 | 2017-02-08 | 2017-03-01 | 2017-03-01
629 | THSK | L.2.12.1.1 | 2017 | 3 | THSK/2017/NCS-TR/L.2.12.1.1/S/3 | Organization of Trainers' Training on Implementing Weight Management Program in Primary Healthcare | NCS-TR | NCS-TR | 1 | 33333.44 | 29762 | 33340 | 29770 | S | No | Post | No | N/A | 2017-01-05 | 2017-01-12 | 2017-02-01 | 2017-02-01
630 | THSK | L.2.12.2.1 | 2016 | 1 | THSK/2016/NCS-TR/L.2.12.2.1/S/1 | Organization of training of research teams | NCS-TR | NCS-TR | 1 | 50000.16 | 44643 | 50000 | 44650 | S | No | Post | No | N/A | 2016-04-01 | 2016-05-16 | 2016-05-01 | 2016-05-31
631 | THSK | L.2.12.2.2 | 2016 | 1 | THSK/2016/NCS-TR/L.2.12.2.2/S/1 | Meeting on the Announcement of Results | NCS-TR | NCS-TR | 1 | 24999.52 | 22321 | 25000 | 22330 | S | No | Post | No | N/A | 2016-11-01 | 2016-11-08 | 2016-12-01 | 2016-12-01
632 | THSK | L.2.12.3.1 | 2016 | 1 | THSK/2016/NCS-TR/L.2.12.3.1/S/1 | Organization of training of research teams | NCS-TR | NCS-TR | 1 | 70000 | 62500 | 70000 | 62500 | S | No | Post | No | N/A | 2016-01-15 | 2016-01-22 | 2016-01-30 | 2016-03-01
633 | THSK | L.2.12.3.2 | 2016 | 1 | THSK/2016/NCS-TR/L.2.12.3.2/S/1 | Organization of Announcement of results | NCS-TR | NCS-TR | 1 | 24999.52 | 22321 | 25000 | 22330 | S | No | Post | No | N/A | 2016-11-01 | 2016-11-08 | 2016-12-01 | 2016-12-01
634 | THSK | L.2.12.6.1 | 2016 | 1 | THSK/2016/NCS-TR/L.2.12.6.1/S/1 | Organization of training of research teams | NCS-TR | NCS-TR | 1 | 74999.68 | 66964 | 75000 | 66970 | S | No | Post | No | N/A | 2016-01-15 | 2016-01-22 | 2016-01-29 | 2017-03-01
635 | THSK | L.2.16.1.1 | 2016 | 1 | THSK/2016/NCS-TR/L.2.16.1.1/S/1 | Information meeting 2 tour | NCS-TR | NCS-TR | 1 | 2999.36 | 2678 | 3000 | 2680 | S | No | Post | No | N/A |  |  | 2016-03-01 | 2016-04-01
636 | THSK | L.2.16.2.2 | 2016 | 1 | THSK/2016/NCS-TR/L.2.16.2.2/S/1 | Evaluation meeting | NCS-TR | NCS-TR | 1 | 3062.08 | 2734 | 3070 | 2740 | S | No | Post | No | N/A | 2016-09-01 | 2016-09-01 | 2016-10-01 | 2016-10-01
637 | THSK | L.2.16.2.2 | 2016 | 2 | THSK/2016/NCS-TR/L.2.16.2.2/S/2 | Project team meeting | NCS-TR | NCS-TR | 1 | 1499.68 | 1339 | 1500 | 1340 | S | No | Post | No | N/A | 2016-09-01 | 2016-09-08 | 2016-10-01 | 2016-11-01
638 | THSK | L.2.16.2.2 | 2016 | 1 | THSK/2016/NCS-TR/L.2.16.2.2/S/1 | Evaluation meeting | NCS-TR | NCS-TR | 1 | 3062.08 | 2734 | 3070 | 2740 | S | No | Post | No | N/A | 2016-01-08 | 2016-01-15 | 2017-02-01 | 2017-03-01
639 | THSK | L.2.16.2.2 | 2016 | 2 | THSK/2016/NCS-TR/L.2.16.2.2/S/2 | Project team meeting | NCS-TR | NCS-TR | 1 | 1499.68 | 1339 | 1500 | 1340 | S | No | Post | No | N/A | 2016-01-08 | 2016-01-15 | 2017-02-01 | 2017-03-01
640 | THSK | L.2.18.1.1 | 2015 | 1 | THSK/2015/NCS-TR/L.2.18.1.1/S/1 | Workshop on preparation of the training module | NCS-TR | NCS-TR | 1 | 13124.16 | 11718 | 13125 | 11720 | S | No | Post | No | N/A | 2015-10-01 | 2015-10-08 | 2015-10-01 | 2015-11-01
641 | THSK | L.2.18.1.2 | 2015 | 1 | THSK/2015/NCS-TR/L.2.18.1.2/S/1 | Organization of Pre-Pilot Implementer Training | NCS-TR | NCS-TR | 1 | 13124.16 | 11718 | 13125 | 11720 | S | No | Post | No | N/A | 2015-10-01 | 2015-10-08 | 2015-11-01 | 2015-12-01
642 | THSK | L.2.20.3.7 | 2016 | 1 | THSK/2016/NCS-TR/L.2.20.3.7/S/1 | Workshop for Creating Algorithm | NCS-TR | NCS-TR | 1 | 40000.8 | 35715 | 40000 | 35720 | S | No | Post | No | N/A | 2016-08-16 | 2016-08-16 | 2016-09-15 | 2016-09-15
643 | THSK | L.2.20.1.3 | 2017 | 1 | THSK/2017/NCS-TR/L.2.20.1.3/S/1 | Organization of Providing refreshing trainings (6 rounds) | NCS-TR | NCS-TR | 1 | 1249.92 | 1116 | 1250 | 1120 | S | No | Post | No | N/A | 2017-01-15 | 2017-01-22 | 2017-03-01 | 2017-03-01
644 | THSK | L.2.20.1.5 | 2015 | 1 | THSK/2015/NCS-TR/L.2.20.1.5/NCB/1 | Organization of trainers' trainings (8 rounds) | NCS-TR | NCS-TR | 1 | 120000.16 | 107143 | 120000 | 107150 | NCB | No | Post | No | N/A | 2015-12-27 | 2016-02-10 | 2016-02-25 | 2016-12-01
645 | THSK | L.2.20.1.5 | 2017 | 1 | THSK/2017/NCS-TR/L.2.20.1.5/S/1 | Organization of trainers' trainings (4 rounds) | NCS-TR | NCS-TR | 1 | 30000.32 | 26786 | 30000 | 26790 | S | No | Post | No | N/A | 2017-01-05 | 2017-01-12 | 2017-02-17 | 2017-03-01
646 | THSK | L.2.20.3.7 | 2017 | 1 | THSK/2017/NCS-TR/L.2.20.3.7/S/1 | Workshops for Creating Algorithm 3 tour | NCS-TR | NCS-TR | 1 | 39999.68 | 35714 | 40000 | 35720 | S | No | Post | No | N/A | 2017-01-30 | 2017-01-30 | 2017-03-01 | 2017-03-01
647 | THSK | L.2.20.2.2 | 2017 | 1 | THSK/2017/NCS-TR/L.2.20.2.2/S/1 | Meeting of benchmarking | NCS-TR | NCS-TR | 1 | 59999.52 | 53571 | 60000 | 53580 | S | No | Post | No | N/A | 2017-01-30 | 2017-01-30 | 2017-03-01 | 2017-03-01
648 | THSK | L.2.20.2.1 | 2017 | 1 | THSK/2017/NCS-TR/L.2.20.2.1/N/A/1 | International field trip | NCS-TR | NCS-TR | N/A | 9167.2 | 8185 | 9170 | 8190 | N/A | No | Post | N/A | N/A | N/A | N/A | 2017-01-19 | 2017-01-19
649 | THSK | L.2.20.4.1 | 2017 | 1 | THSK/2017/NCS-TR/L.2.20.4.1/S/1 | Meetings with media professionals , NGO representatives, social media phenomenons | NCS-TR | NCS-TR | 1 | 33333.44 | 29762 | 33340 | 29770 | S | No | Post | No | N/A |  |  | 2017-03-19 | 2017-03-01
650 | THSK | L.2.20.2.1 | 2016 | 1 | THSK/2016/NCS-TR/L.2.20.2.1/N/A/1 | International field trip 2 tour | NCS-TR | NCS-TR | N/A | 18333.28 | 16369 | 18340 | 16370 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2016-01-15 | 2016-03-15
651 | THSK | L.2.20.2.2 | 2016 | 1 | THSK/2016/NCS-TR/L.2.20.2.2/NCB/1 | Benchmarking meeting (2 round) (Substance Addiction) | NCS-TR | NCS-TR | 1 | 120000.16 | 107143 | 120000 | 107150 | NCB | No | Post | No | N/A | 2016-02-15 | 2016-03-16 | 2016-04-15 | 2016-11-01
652 | THSK | L.2.20.4.1 | 2016 | 1 | THSK/2016/NCS-TR/L.2.20.4.1/S/1 | Meetings with media professionals , NGO representatives, social media phenomenons | NCS-TR | NCS-TR | 1 | 33333.44 | 29762 | 33340 | 29770 | S | No | Post | No | N/A | 2016-08-01 | 2016-08-08 | 2016-03-17 | 2016-03-01
653 | THSK | L.2.20.5.3 | 2016 | 1 | THSK/2016/NCS-TR/L.2.20.5.3/S/1 | Motivation Meetings 3 tours | NCS-TR | NCS-TR | 1 | 85001.28 | 75894 | 85000 | 75900 | S | No | Post | No | N/A | 2016-08-01 | 2016-08-08 | 2016-11-01 | 2016-12-30
654 | THSK | L.2.20.5.1 | 2016 | 1 | THSK/2016/NCS-TR/L.2.20.5.1/S/1 | Organization of Operator Trainings | NCS-TR | NCS-TR | 1 | 19999.84 | 17857 | 20000 | 17860 | S | No | Post | No | N/A | 2016-08-01 | 2016-08-08 | 2016-02-17 | 2016-03-08
655 | THSK | L.2.20.3.4 | 2016 | 1 | THSK/2016/NCS-TR/L.2.20.3.4/S/1 | Standard and refreshing trainings 4 rounds | NCS-TR | NCS-TR | 1 | 49999.04 | 44642 | 50000 | 44650 | S | No | Post | No | N/A | 2016-08-01 | 2016-08-08 | 2016-03-08 | 2016-09-01
656 | THSK | L.2.20.3.2 | 2017 | 1 | THSK/2017/NCS-TR/L.2.20.3.2/S/1 | Organization of Operator Trainings | NCS-TR | NCS-TR | 1 | 18749.92 | 16741 | 18750 | 16750 | S | No | Post | No | N/A |  |  | 2017-03-01 | 2017-03-01
657 | THSK | L.2.20.3.2 | 2016 | 1 | THSK/2016/NCS-TR/L.2.20.3.2/S/1 | Organization of Operator Trainings (4 rounds) (Substance Addiction) | NCS-TR | NCS-TR | 1 | 37499.84 | 33482 | 37500 | 33490 | S | No | Post | No | N/A | 2016-08-01 | 2016-08-08 | 2016-06-01 | 2016-04-01
658 | THSK | L.4.6.2.1 | 2015 | 1 | THSK/2015/NCS-TR/L.4.6.2.1/S/1 | HLC Workshop | NCS-TR | NCS-TR | 1 | 15000.16 | 13393 | 15000 | 13400 | S | No | Post | No | N/A | 2015-10-15 | 2015-10-22 | 2015-11-01 | 2015-11-01
659 | THSK | L.4.6.2.1 | 2016 | 1 | THSK/2016/NCS-TR/L.4.6.2.1/S/1 | HLC Workshop | NCS-TR | NCS-TR | 1 | 15000.16 | 13393 | 15000 | 13400 | S | No | Post | No | N/A | 2016-03-01 | 2016-03-08 | 2016-03-20 | 2016-04-01
660 | THSK | L.4.6.2.1 | 2016 | 1 | THSK/2016/NCS-TR/L.4.6.2.1/N/A/1 | Study visits at home (4 times) | NCS-TR | NCS-TR | N/A | 37499.84 | 33482 | 37500 | 33490 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2016-01-01 | 2016-04-01
661 | THSK | L.4.6.2.1 | 2016 | 2 | THSK/2016/NCS-TR/L.4.6.2.1/N/A/2 | Study visits abroad (1 time) | NCS-TR | NCS-TR | N/A | 37499.84 | 33482 | 37500 | 33490 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2016-03-01 | 2016-03-01
662 | THSK | L.4.6.4.2 | 2016 | 1 | THSK/2016/NCS-TR/L.4.6.4.2/S/1 | Workshop on preparing HLC training documents (2 times) | NCS-TR | NCS-TR | 1 | 29999.2 | 26785 | 30000 | 26790 | S | No | Post | No | N/A | 2016-01-05 | 2016-01-12 | 2016-01-20 | 2016-04-01
663 | THSK | L.4.6.5.1 | 2016 | 1 | THSK/2016/NCS-TR/L.4.6.5.1/S/1 | Organization of Social activities for public participation in HLC | NCS-TR | NCS-TR | 1 | 93749.6 | 83705 | 93750 | 83710 | S | No | Post | No | N/A | 2016-03-16 | 2016-04-30 | 2016-04-15 | 2016-06-01
664 | THSK | L.4.6.6.2 | 2016 | 1 | THSK/2016/NCS-TR/L.4.6.6.2/S/1 | Organization of HLC Monitoring and Evaluation Workshop (3 times) | NCS-TR | NCS-TR | 1 | 14999.04 | 13392 | 15000 | 13400 | S | No | Post | No | N/A | 2016-08-01 | 2016-08-08 | 2016-08-15 | 2016-09-01
665 | THSK | L.4.6.6.2 | 2016 | 1 | THSK/2016/NCS-TR/L.4.6.6.2/N/A/1 | Study visits at home (10 times) | NCS-TR | NCS-TR | N/A | 28126.56 | 25113 | 28130 | 25120 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2016-06-01 | 2016-11-01
666 | THSK | L.4.6.6.2 | 2017 | 1 | THSK/2017/NCS-TR/L.4.6.6.2/S/1 | Organization of HLC Monitoring and Evaluation Workshop (3 times) | NCS-TR | NCS-TR | 1 | 14999.04 | 13392 | 15000 | 13400 | S | No | Post | No | N/A | 2017-01-10 | 2017-01-17 | 2017-02-25 | 2017-03-01
667 | THSK | L.4.6.6.2 | 2017 | 2 | THSK/2017/NCS-TR/L.4.6.6.2/N/A/2 | Study visits at home (10 times) | NCS-TR | NCS-TR | N/A | 9374.4 | 8370 | 9375 | 8370 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2017-02-01 | 2017-03-01
668 | THSK | L.4.1.2.5 | 2015 | 1 | THSK/2015/NCS-TR/L.4.1.2.5/N/A/1 | Study visits abroad | NCS-TR | NCS-TR | N/A | 19999.84 | 17857 | 20000 | 17860 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2015-11-01 | 2015-11-01
669 | THSK | L.4.1.3.2 | 2016 | 1 | THSK/2016/NCS-TR/L.4.1.3.2/S/1 | Preparatory workshop on monitoring and evaluation trainings | NCS-TR | NCS-TR | 1 | 12000.8 | 10715 | 12000 | 10720 | S | No | Prior | No | N/A | 2016-06-01 | 2016-06-01 | 2016-07-01 | 2016-07-01
670 | THSK | L.4.1.5.6 | 2016 | 1 | THSK/2016/NCS-TR/L.4.1.5.6/NCB/1 | Organization of Monitoring and Evaluation Trainings | NCS-TR | NCS-TR | 1 | 111624.8 | 99665 | 111625 | 99670 | NCB | No | Post | No | N/A | 2016-06-02 | 2016-07-02 | 2016-08-01 | 2016-12-30
671 | THSK | L.4.1.5.7 | 2016 | 1 | THSK/2016/NCS-TR/L.4.1.5.7/S/1 | Preparatory Workshop for Trainers' Training | NCS-TR | NCS-TR | 1 | 15008 | 13400 | 15000 | 13400 | S | No | Post | No | N/A | 2016-01-04 | 2016-01-04 | 2016-02-01 | 2016-02-27
672 | THSK | L.4.1.5.8 | 2016 | 2 | THSK/2016/NCS-TR/L.4.1.5.8/S/2 | Organization of Trainers' Training | NCS-TR | NCS-TR | 1 | 26000.8 | 23215 | 26000 | 23220 | S | No | Post | No | N/A | 2016-02-02 | 2016-02-02 | 2016-03-01 | 2016-05-01
673 | THSK | L.4.1.5.5 | 2016 | 2 | THSK/2016/NCS-TR/L.4.1.5.5/S/2 | Organization of Briefing Meeting | NCS-TR | NCS-TR | 1 | 93000.32 | 83036 | 93000 | 83040 | S | No | Post | No | N/A | 2016-06-01 | 2016-07-16 | 2016-07-01 | 2016-07-31
674 | THSK | L.4.1.5.6 | 2016 | 1 | THSK/2016/NCS-TR/L.4.1.5.6/S/1 | Organization of Monitoring and Evaluation Trainings | NCS-TR | NCS-TR | 1 | 66974.88 | 59799 | 66975 | 59800 | S | No | Post | No | N/A | 2016-12-04 | 2016-12-04 | 2017-01-01 | 2017-03-01
675 | THSK | L.4.3.3.1 | 2016 | 1 | THSK/2016/NCS-TR/L.4.3.3.1/N/A/1 | Participation in national congresses | NCS-TR | NCS-TR | N/A | 999.04 | 892 | 1000 | 900 | N/A | No | Post | N/A | N/A | N/A | N/A | 2016-05-01 | 2016-05-30
676 | THSK | L.4.3.3.1 | 2016 | 2 | THSK/2016/NCS-TR/L.4.3.3.1/N/A/2 | USA University Visit | NCS-TR | NCS-TR | N/A | 29999.2 | 26785 | 30000 | 26790 | N/A | No | Post | N/A | N/A | N/A | N/A | 2016-10-01 | 2016-10-30
677 | THSK | L.4.3.2.2 | 2016 | 1 | THSK/2016/NCS-TR/L.4.3.2.2/NCB/1 | Training Organization 3 tours | NCS-TR | NCS-TR | 1 | 207499.04 | 185267 | 207500 | 185270 | NCB | No | Post | No | N/A | 2016-03-02 | 2016-03-02 | 2016-05-01 | 2016-12-31
678 | THSK | L.4.5.3.2 | 2016 | 1 | THSK/2016/NCS-TR/L.4.5.3.2/S/1 | Training Organization 1-2 | NCS-TR | NCS-TR | 1 | 83200.32 | 74286 | 83200 | 74290 | S | No | Post | No | N/A | 2016-01-02 | 2016-01-02 | 2016-02-01 | 2016-02-27
679 | THSK | L.4.5.3.2 | 2016 | 2 | THSK/2016/NCS-TR/L.4.5.3.2/S/2 | Training Organization 3-4 | NCS-TR | NCS-TR | 1 | 83200.32 | 74286 | 83200 | 74290 | S | No | Post | No | N/A | 2016-03-02 | 2016-03-02 | 2016-04-01 | 2016-04-30
680 | THSK | L.4.5.3.2 | 2016 | 3 | THSK/2016/NCS-TR/L.4.5.3.2/S/3 | Training Organization 5-6 | NCS-TR | NCS-TR | 1 | 83200.32 | 74286 | 83200 | 74290 | S | No | Post | No | N/A | 2016-05-02 | 2016-05-02 | 2016-06-01 | 2016-06-30
681 | THSK | L.4.5.3.2 | 2016 | 4 | THSK/2016/NCS-TR/L.4.5.3.2/S/4 | Training Organization 7-8 | NCS-TR | NCS-TR | 1 | 83200.32 | 74286 | 83200 | 74290 | S | No | Post | No | N/A | 2016-07-02 | 2016-07-02 | 2016-08-01 | 2016-08-30
682 | THSK | L.4.5.3.2 | 2016 | 5 | THSK/2016/NCS-TR/L.4.5.3.2/S/5 | Training Organization 9-10 | NCS-TR | NCS-TR | 1 | 83200.32 | 74286 | 83200 | 74290 | S | No | Post | No | N/A | 2016-09-01 | 2016-09-01 | 2016-10-01 | 2016-10-30
683 | THSK | L.4.5.3.2 | 2016 | 6 | THSK/2016/NCS-TR/L.4.5.3.2/S/6 | Training Organization 11-12 | NCS-TR | NCS-TR | 1 | 83200.32 | 74286 | 83200 | 74290 | S | No | Post | No | N/A | 2016-10-02 | 2016-10-02 | 2016-11-01 | 2016-11-30
684 | THSK | L.4.5.3.2 | 2017 | 1 | THSK/2017/NCS-TR/L.4.5.3.2/S/1 | Training Organization 1 | NCS-TR | NCS-TR | 1 | 41599.04 | 37142 | 41600 | 37150 | S | No | Post | No | N/A | 2017-01-02 | 2017-01-02 | 2017-02-01 | 2017-02-27
685 | THSK | L.4.5.3.2 | 2017 | 2 | THSK/2017/NCS-TR/L.4.5.3.2/S/2 | Training Organization 2-3 | NCS-TR | NCS-TR | 1 | 83200.32 | 74286 | 83200 | 74290 | S | No | Post | No | N/A | 2017-01-30 | 2017-01-30 | 2017-03-01 | 2017-03-30
686 | THSK | L.4.5.3.2 | 2015 | 1 | THSK/2015/NCS-TR/L.4.5.3.2/S/1 | Training Organization | NCS-TR | NCS-TR | 1 | 41599.04 | 37142 | 41600 | 37150 | S | No | Post | No | N/A | 2015-10-01 | 2015-10-01 | 2015-10-30 | 2015-10-30
687 | THSK | L.4.5.3.2 | 2015 | 2 | THSK/2015/NCS-TR/L.4.5.3.2/S/2 | Training Organization 2 tours | NCS-TR | NCS-TR | 1 | 83199.2 | 74285 | 83200 | 74290 | S | No | Post | No | N/A | 2015-10-02 | 2015-10-02 | 2015-11-01 | 2015-11-30
688 | THSK | L.4.5.2.3 | 2017 | 1 | THSK/2017/NCS-TR/L.4.5.2.3/S/1 | Curriculum development and update workshop | NCS-TR | NCS-TR | 1 | 16649.92 | 14866 | 16650 | 14870 | S | No | Post | No | N/A | 2017-01-02 | 2017-01-02 | 2017-02-01 | 2017-02-27
689 | THSK | L.4.5.2.3 | 2016 | 1 | THSK/2016/NCS-TR/L.4.5.2.3/S/1 | Curriculum development and update workshop | NCS-TR | NCS-TR | 1 | 16649.92 | 14866 | 16650 | 14870 | S | No | Post | No | N/A | 2016-01-02 | 2016-01-02 | 2016-02-01 | 2016-02-27
690 | SBSGM | D.2.1.1.1 | 2015 | 1 | SBSGM/2015/NCS-TR/D.2.1.1.1/N/A/1 | Participation in Trainings and Conferences at Home and Abroad | NCS-TR | NCS-TR | N/A | 78400 | 70000 | 78400 | 70000 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2015-10-01 | 2015-12-01
691 | SBSGM | D.2.1.2.4 | 2016 | 1 | SBSGM/2016/NCS-TR/D.2.1.2.4/N/A/1 | Participation in Trainings and Conferences at Home and Abroad | NCS-TR | NCS-TR | N/A | 100800 | 90000 | 100800 | 90000 | N/A | N/A | N/A | N/A | N/A | N/A |  | 2016-06-01 | 2016-10-30
692 | SBSGM | D.2.1.2.3 | 2016 | 1 | SBSGM/2016/NCS-TR/D.2.1.2.3/N/A/1 | Participation in Trainings and Conferences at Home and Abroad | NCS-TR | NCS-TR | N/A | 156800 | 140000 | 156800 | 140000 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2016-08-01 | 2016-11-30
693 | SBSGM | D.2.1.1.2 | 2016 | 1 | SBSGM/2016/NCS-TR/D.2.1.1.2/N/A/1 | Participation in Trainings at Home and Abroad (16) and Conferences (12) Abroad | NCS-TR | NCS-TR | N/A | 156800 | 140000 | 156800 | 140000 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2016-02-01 | 2016-02-01
[6 empty] | C.SUB TOTAL |  |  |  | 11751714.7648 | 10492602.4686 | 11751831 | 10493830
D. OPERATING COSTS | [5 empty] | OPERATIONAL COSTS
694 | TKHK | N.3.1.1.1 | 2016 | 1 | TKHK/2016/OC/N.3.1.1.1/N/A/1 | International Standards Subscription | OC | OC | N/A | 50000.0032 | 44642.86 | 50000 | 44650 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2016-01-01 | 2016-12-01
695 | SHGM | A.3.1.3.1 | 2016 | 1 | SHGM/2016/OC/A.3.1.3.1/N/A/1 | Renting Office Buildings for Five Rehabilitation Centers | OC | OC | N/A | 1597874.88 | 1426674 | 1597875 | 1426680 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2017-03-01 | 2019-09-01
696 | SHGM | A.1.3.5.1 | 2016 | 1 | SHGM/2016/OC/A.1.3.5.1/N/A/1 | National field visits (7 Regions 3 persons) | OC | OC | N/A | 8162.8736 | 7288.28 | 8170 | 7290 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2016-12-01 | 2017-03-01
697 | SAGEM | E.6.1.1.3 | 2016 | 1 | SAGEM/2016/OC/E.6.1.1.3/N/A/1 | Subscription to EUnetHTA, HTAi, INAHTA, ISPOR etc. | OC | OC | N/A | 17249.9992 | 15401.785 | 17250 | 15410 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2016-04-01 | 2016-04-01
698 | SAGEM | E.6.1.1.3 | 2016 | 2 | SAGEM/2016/OC/E.6.1.1.3/N/A/2 | Subscription to Embase, Scopus, Cochrane databases etc. | OC | OC | N/A | 17249.9992 | 15401.785 | 17250 | 15410 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2016-10-01 | 2016-10-01
699 | SAGEM | E.5.1.1.1 | 2016 | 1 | SAGEM/2016/OC/E.5.1.1.1/N/A/1 | Database membership and renewal | OC | OC | N/A | 95000.64 | 84822 | 95000 | 84830 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2016-01-01 | 2017-03-01
700 | SAGEM | E.5.1.2.2 | 2016 | 1 | SAGEM/2016/OC/E.5.1.2.2/N/A/1 | Publication fee for research articles about the causes of low birth weight and premature birth in Turkey | OC | OC | N/A | 5000.0048 | 4464.29 | 5000 | 4470 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2016-01-01 | 2016-12-01
701 | SAGEM | E.5.1.2.2 | 2016 | 2 | SAGEM/2016/OC/E.5.1.2.2/N/A/2 | Publication fee for articles on patient satisfaction survey | OC | OC | N/A | 5000.0048 | 4464.29 | 5000 | 4470 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2016-01-01 | 2016-12-01
702 | SAGEM | E.5.1.2.2 | 2017 | 1 | SAGEM/2017/OC/E.5.1.2.2/N/A/1 | Publication fee for articles about national household health survey | OC | OC | N/A | 5000.0048 | 4464.29 | 5000 | 4470 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2017-01-01 | 2017-03-01
703 | SAGEM | E.5.1.2.2 | 2017 | 2 | SAGEM/2017/OC/E.5.1.2.2/N/A/2 | Publication fee for articles on mental health research in Turkey | OC | OC | N/A | 5000.0048 | 4464.29 | 5000 | 4470 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2017-01-01 | 2017-03-01
704 | SAGEM | E.4.1.2.2 | 2016 | 1 | SAGEM/2016/OC/E.4.1.2.2/N/A/1 | DUODECIM Evidence-based Medicine Guidelines | OC | OC | N/A | 700000 | 625000 | 700000 | 625000 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2016-04-01 | 2016-09-01
705 | PYDB | P.5 | 2016 | 1 | PYDB/2016/OC/P.5/N/A/1 | Maintenance and Repair Costs | OC | OC | N/A | 5000.0048 | 4464.29 | 5000 | 4470 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2015-11-01 | 2015-12-01
706 | PYDB | P.2 | 2016 | 1 | PYDB/2016/OC/P.2/N/A/1 | Daily subsistence of personnel being employed/to be employed in PMSU. | OC | OC | N/A | 71999.9952 | 64285.71 | 72000 | 64290 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2016-01-01 | 2016-01-01
707 | PYDB | P.2 | 2016 | 2 | PYDB/2016/OC/P.2/N/A/2 | Costs foreseen for monitoring and evaluation activities | OC | OC | N/A | 29999.9952 | 26785.71 | 30000 | 26790 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2016-02-01 | 2016-02-01
708 | PYDB | P.2 | 2016 | 3 | PYDB/2016/OC/P.2/N/A/3 | Costs incurred due to publication of contract announcements. | OC | OC | N/A | 5999.9968 | 5357.14 | 6000 | 5360 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2016-04-01 | 2016-04-01
709 | PYDB | P.2 | 2016 | 4 | PYDB/2016/OC/P.2/N/A/4 | Expenditures that are foreseen for replication, storage and classification and Program/Project documents | OC | OC | N/A | 15000.0032 | 13392.86 | 15000 | 13400 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2016-04-01 | 2016-04-01
710 | PYDB | P.2 | 2016 | 5 | PYDB/2016/OC/P.2/N/A/5 | Logistical costs of meetings to be held in PMSU within the scope of the program . | OC | OC | N/A | 8999.9952 | 8035.71 | 9000 | 8040 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2016-06-01 | 2016-06-01
711 | TKHK | N.3.1.1.1 | 2016 | 2 | TKHK/2016/OC/N.3.1.1.1/N/A/2 | Acquisition of Intellectual Property Rights (Patents Rights) | OC | OC | N/A | 25000.0016 | 22321.43 | 25000 | 22330 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2016-01-01 | 2016-12-01
712 | SYGM | F.3.1.3.1 | 2015 | 2 | SYGM/2015/OC/F.3.1.3.1/N/A/2 | Procurement advertisements, maintenance and repair | OC | OC | N/A | 35840 | 32000 | 35840 | 32000 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2015-10-01 | 2017-03-01
713 | SBSGM | D.2.1.2.3 | 2016 | 1 | SBSGM/2016/OC/D.2.1.2.3/N/A/1 | Purchasing International Standards | OC | OC | N/A | 299999.84 | 267857 | 300000 | 267860 | N/A | N/A | N/A | No | N/A | N/A | N/A | 2016-12-01 | 2016-12-31
[6 empty] | OC SUB TOTAL |  |  |  | 3003378.2464 | 2681587.72 | 3003385 | 2681690
[6 empty] | PROJECT TOTAL |  |  |  | 80506000.9072 | 71880357.9529 | 80506120 | 71883310
Formulas:
Expected (BD/SPN/RFP) Issue Date = +[Expected Contract Signing Date]-60
Expected (BD/SPN/RFP) Issue Date = +[Expected Contract Signing Date]
Expected Bid/Proposal Opening Date = +[Expected (BD/SPN/RFP) Issue Date]+45
Expected Bid/Proposal Opening Date = +[Expected (BD/SPN/RFP) Issue Date]
Expected Contract Signing Date = +[Expected Bid/Proposal Opening Date]+60
Expected Contract Signing Date = +[Expected Bid/Proposal Opening Date]
RfEOI and Shortlisting = +[Expected Contract Signing Date]
RfEOI and Shortlisting = +[Expected Contract Signing Date]-30